## Notes for use
Scroll down for more information
Scroll down for more information
Scroll down for more information
Last slide
Balancing Mechanism SORT Checker Tool: Version 1 June 2026
Balancing Mechanism SORT Checker Tool: Version 1 June 2026
Balancing Mechanism SORT Checker Tool: Version 1 June 2026
Balancing Mechanism SORT Checker Tool: Version 1 June 2026

## BCA Target SORT
Bilateral Connection Agreement (BCA) - Key dates to meet your target SORT
Select your target SORT Upload | September 2026 | SORT dates for 2028 are indicative only and subject to change when the SORT Schedule is confirmed
Transmission Owner Timeline | Final date to confirm Network Change Date | Final date to submit complete and correct ICCP data |  |  |  | latest Network Change Date
2026-08-18
| 2026-06-16 | 2026-07-07 |  |  |  | HVSCC
Developer Timeline |  | Final date to submit single line diagram | [5 empty] | Earliest possible EON/Energisation | Remaining Complicance actions
|  | 2026-07-07 | [5 empty] | 2026-08-19
NESO SCADA Database and Displays |  |  | Building, checking and testing SCADA database and displays |  |  |  | Operational Metering Signals Testing
|  |  | Start date |  | Final date | SCADA Upload | Earliest Testing Date |  | Minimum two weeks to allow for retesting if necessary, |  | Final testing Date
|  |  | 2026-07-08 |  | 2026-08-17 | 2026-08-18 | 2026-08-19 |  |  |  | 2026-08-31
NESO Registration Team | Support Lead party and representative to complete Registration process and complete requirements including creating records in Single Markets Platform (SMP) | [9 empty] | Verification of Unit details and Approval in SMP |  | Implementation Date
[12 empty] | Cutoff Date |  | Back-Up Date
[12 empty] | 2026-09-01 | 2026-09-23 | 2026-09-30
SORT Upload
Lead Party or Representative (SORT) Timeline |  |  |  | Notify which Units expect to enter SORT | Complete BM Registration in SMP and fulfil requirements |  |  |  |  | Last date to submit Units in SMP
|  |  |  | 2026-08-04 | [5 empty] | 2026-08-25
Formulas:
Final date = [SCADA Upload]-1
Earliest Testing Date = [SCADA Upload]+1

## BCA Energisation Date
Bilateral Connection Agreement (BCA) - Key dates to meet your target SORT
Input your Energisation/EON date |  | 2027-05-22 | SORT dates for 2028 are indicative only and subject to change when the SORT Schedule is confirmed
Please enter a date before 18/10/2028
Transmission Owner Timeline |  | Final date to confirm Network Change Date | Final date to submit complete and correct ICCP/DSS data |  |  |  | Latest possible Network Change Date
2027-05-21
|  | 2027-03-19 | 2027-04-09 |  |  |  | HVSCC
Developer Timeline |  |  | Final date to submit single line diagram | [5 empty] | EON / Energisation | Remaining Complicance actions | [5 empty] | è ION
|  |  | 2027-04-09 | [5 empty] | 2027-05-22
NESO SCADA Database and Displays |  |  |  | Building, checking and testing SCADA database and displays |  |  |  | Operational Metering Signals Testing
|  |  |  | Start date |  | Final date | SCADA Upload | Earliest Testing Date |  |  |  | Final testing Date
|  |  |  | 2027-04-10 |  | 2027-05-20 | 2027-05-21 | 2027-05-22 |  |  |  | 2027-06-29
NESO Registration Team |  | Support Lead party and representative to complete Registration process and complete requirements including creating records in Single Markets Platform (SMP) | [9 empty] | Verification of Unit details and Approval in SMP |  | Implementation Date
[13 empty] | Cutoff Date |  | Back-Up Date
[13 empty] | 2027-06-30 | 2027-07-21 | 2027-07-28
SORT Upload
Lead Party or Representative (SORT) Timeline |  |  |  |  | Notify which Units expect to enter SORT | Complete BM Registration in SMP and fulfil requirements |  |  |  |  | Last date to submit Units in SMP
[5 empty] | 2027-06-02 | [5 empty] | 2027-06-23
Formulas:
Final date = [SCADA Upload]-1
Earliest Testing Date = [SCADA Upload]+1

## non-BCA Target SORT
Key dates to meet your target SORT for units registering under BEGA, BELLA, Supplier and VLP agreements
Select your target SORT Upload | July 2027 | SORT dates for 2028 are indicative only and subject to change when the SORT Schedule is confirmed
Operational Meter Signals Testing
Final testing Date
2027-06-28
NESO Registration Team | Support Lead party and representative to complete Registration process and complete requirements including creating records in Single Markets Platform (SMP) |  |  |  |  | Verification of Unit details and Approval in SMP |  | Implementation Date
[7 empty] | Cutoff Date |  | Back-Up Date
[7 empty] | 2027-06-29 | 2027-07-21 | 2026-09-30
SORT Upload
Lead Party or Representative (SORT) Timeline |  |  | Notify which Units expect to enter SORT | Complete BM Registration in SMP and fulfil requirements | Last date to submit Units in SMP
|  |  | 2027-06-01 |  | 2027-06-22

## Reference
Sort Upload Dates | SORT dates for 2028 are indicative only and subject to change when the SORT Schedule is confirmed
Energisation dates (allowing 2 weeks for Op Meter Signals testing)
Month | Notify us before | Submit in SMP before | Cutoff date | Implementation date | Backup date | 2 Weeks before Cutoff date
May 2026 | 2026-03-31 | 2026-04-21 | 2026-04-28 | 2026-05-20 | 2026-05-27 | 2026-04-15
July 2026 | 2026-05-26 | 2026-06-16 | 2026-06-23 | 2026-07-15 | 2026-07-22 | 2026-06-10
September 2026 | 2026-08-04 | 2026-08-25 | 2026-09-01 | 2026-09-23 | 2026-09-30 | 2026-08-19
November 2026 | 2026-10-06 | 2026-10-27 | 2026-11-03 | 2026-11-25 | 2026-12-02 | 2026-10-21
January 2027 | 2026-12-08 | 2026-12-29 | 2027-01-05 | 2027-01-27 | 2027-02-03 | 2026-12-23
March 2027 | 2027-01-26 | 2027-02-16 | 2027-02-23 | 2027-03-17 | 2027-03-31 | 2027-02-10
May 2027 | 2027-03-30 | 2027-04-20 | 2027-04-27 | 2027-05-19 | 2027-05-26 | 2027-04-14
July 2027 | 2027-06-01 | 2027-06-22 | 2027-06-29 | 2027-07-21 | 2027-07-28 | 2027-06-16
September 2027 | 2027-08-10 | 2027-08-31 | 2027-09-07 | 2027-09-29 | 2027-10-06 | 2027-08-25
November 2027 | 2027-10-05 | 2027-10-26 | 2027-11-02 | 2027-11-24 | 2027-12-01 | 2027-10-20
January 2028 | 2027-12-07 | 2027-12-28 | 2028-01-04 | 2028-01-26 | 2028-02-02 | 2027-12-22
March 2028 | 2028-01-25 | 2028-02-15 | 2028-02-22 | 2028-03-15 | 2028-03-29 | 2028-02-09
May 2028 | 2028-03-28 | 2028-04-18 | 2028-04-25 | 2028-05-17 | 2028-05-24 | 2028-04-12
July 2028 | 2028-05-30 | 2028-06-20 | 2028-06-27 | 2028-07-19 | 2028-07-26 | 2028-06-14
September 2028 | 2028-08-08 | 2028-08-29 | 2028-09-05 | 2028-09-27 | 2028-10-04 | 2028-08-23
November 2028 | 2028-10-03 | 2028-10-24 | 2028-10-31 | 2028-11-22 | 2028-11-29 | 2028-10-18
Formulas:
Notify us before = [Cutoff date]-28
Submit in SMP before = [Cutoff date]-7
Cutoff date = [Implementation date]-22