## Sheet1
GC0079 Timeline
Task | Resource | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | Comments
1. RoCoF Case for Change:
1.1 Finalise and Document RoCoF proposals; | WG | [9 empty] | Refresh of existing work | bar: 2017-02-01 to 2017-03-01
1.2 Finalise RoCoF Benefits assessment | WG | [9 empty] | Workgroup actions to be addressed | bar: 2017-01-01 to 2017-02-01
1.3 Finalise RoCoF Implementation costs assessment | WG | [9 empty] | Update with wk24 data | bar: 2017-01-01 to 2017-02-01
2. Vector Shift Case For Change:
2.1 Develop and Document Vector Shift proposals; | WG | [9 empty] | A: timeline for a "non-vector shift" proposal B: Timeline for new vector shift setting | bar: 2017-01-01 to 2017-08-01
2.1.1 a) Incident History | bar: 2017-01-01
2.1.1 b) Model the effect of disturbances | WG | bar: 2017-01-01 to 2017-02-01
2.1.1 c) Assess impact on VS relay | Islanding Specialist | bar: 2017-03-01 to 2017-06-01
2.1.1 d) Establish feasible settings | WG | bar: 2017-03-01 to 2017-06-01
2.1.1 e) ER G83 Withstand Capability | Islanding Specialist | bar: 2017-03-01 to 2017-06-01
2.1.3 a) Assessment of relative risk - VS vs RoCoF | Islanding Specialist | bar: 2017-01-01 to 2017-04-01
2.1.3 b) Assessment of Islanding Risk | Islanding Specialist | bar: 2017-03-01 to 2017-08-01
2.1.3 c) Islanding Risk for RoCoF based proposal | Islanding Specialist | bar: 2017-05-01
2.1.2 Agree proposal | WG | [9 empty] | A: timeline for a "non-vector shift" proposal B: Timeline for new vector shift setting | bar: 2017-03-01 to 2017-08-01
2.2 Develop Vector Shift Benefits case; and | WG | [9 empty] | Update with wk24 data and revise assumptions as proposals are developed | bar: 2017-03-01 to 2017-04-01
2.3 Develop Vector Shift Implementation Cost assessment. | WG | bar: 2017-01-01 to 2017-04-01
3. Implementation:
3.1 Develop plan for combined RoCoF and Vector Shift change and compliance assurance; | WG & Regulatory specialist | bar: 2017-03-01 to 2017-04-01
3.2 Develop combined Benefits assessment; and | WG | bar: 2017-01-01 to 2017-04-01
3. 3 Develop combined implementation Costs assessment. | WG | bar: 2017-01-01 to 2017-04-01
4. Develop charging and incentive arrangements to facilitate efficient implementation. | Regulatory Specialist | bar: 2017-02-01 to 2017-04-01
5. Complete Workgroup reports and present to DCRP | WG | [9 empty] | A: timeline for a "non-vector shift" proposal B: Timeline for new vector shift setting | bar: 2017-05-01 to 2017-09-01