## All Actions
Action Log: Meeting 6
Meeting Name: GC0048: Joint GCRP/DCRP Workgroup on National Application of RfG
| Action | Owner | Progress | Status
1 | Investigate whether BELLAs/BEGAs will still exist in the future | RW | Update 24/9/14: RW advised they will still exist and noted that RfG doesn’t change the contractual relationships between parties. | Closed
2 | Workgroup to provide comments on Terms of Reference before finalising at the next GCRP/DCRP | ALL | Action complete. Noting that as with any Terms of Reference, they are ‘live’ working documents and therefore may be subject to change in the future. | Closed
5a | Requirements for GB parties (Generators, Network Operators etc.) to ensure compliance with the European Network Codes once they enter into force. An non-compliance consequences. (Monitoring of this compliance is actioned by DECC and Ofgem) | Ofgem and DECC | Update 20.10.14 - Action 5 split into two sections based on workgroup feedback. This action is for more clarity on the requirements as and when available from Ofgem/DECC. Updated 20.11.14 - Taken forward with action 5b and action 9 into new action 25. | Closed
5b | Requirements for Member State Compliance with the European Network Codes once they enter into force/implementation monitoring. (Monitoring of this would be actioned by ACER and ENTSO-E). | Ofgem and DECC | Update 20.10.14 - Action 5 split into two sections based on workgroup feedback. This action is for more clarity on the requirements as and when available from Ofgem/DECC. Updated 20.11.14 - Taken forward with action 5a and action 9 into new action 25. | Closed
6 | Update the comparison table between RfG and the existing GB Codes | AJ | To confirm timescales - could draft based on 'non-yellow' articles in the January 2014 RfG code, or could wait for next RfG Commission draft. Update 20.10.14 - Updated version discussed by AJ (Agenda item 5) | Closed
8 | Set out the process for making future changes to European Network Codes. | RM | There is a draft process set out by ACER. But in effect it requires the code to go back through Comitology which is therefore not quick. More clarity on this would be useful. Update 24.09.14 - Noted that this is a process to be defined and set by the Commission. RM to confirm if the 5 year period of changes to ENC once in force has a timetable, process or breakdown of what is covered. Update 20.10.14 - RM directed workgroup to the document published by ACER for how amendments can be made once an ENC becomes law. SLK circulated the link to the workgroup and included in the Meeting 4 minutes. | Closed
9 | Enforcement of G83 and G59 | RM | Check with DECC with regards to the enforcement of G83 and G59 and report back to RfG workgroup. Update 20.10.14 - RM advised that DECC and Ofgem are liaising on this and RM will report back to the workgroup on the outcome of these discussions. Updated 20.11.14 - Taken forward with action 5a and 5b into new action 25. | Closed
10 | FRT Requirements | AJ | Discuss at the FRT Workgroup the FRT requirements for Type B and how this fits in with ongoing GB work. Update 20.10.14 - Covered in presentation by AJ. | Closed
11 | Treatment of User’s under the GB Code framework | AJ | Provide an update slide on the treatment of User’s under the GB Code framework including BCA’s, BELLA’s, BEGA’s and LEEMPS. Update 20.10.14 - Covered in presentation by AJ. | Closed
12 | Examples of definition conflicts between ENC and GB codes | AF/All | Provide RM with examples of where definitions between ENC and GB codes conflict. In particular, the example given in the meeting of Power Stations and Units where the definitions will have to apply to existing plants. Update 20.10.14 - Examples provided and discussed by the workgroup. Update 20.11.14 - Taken forward within action 19. | Closed
13 | RfG timescales within connection offer documentation | AJ | Speak to legal to consider including a note within the informal offer letter or in the offer appendices referencing RfG and the likely timescales. Update 20.10.14 - Update provided by AJ of suggested options, AJ to consider and develop further with NGET Lawyers. Update 20.11.14 - Discussion ongoing within NGET. | Ongoing
14 | Draft task list/project plan | CG and RW | Draft a timeline/project plan, tasks and prioritise and to send to the RfG workgroup ahead of the next meeting. Update 20.10.14 - Presentation covered by RW (Agenda item 7). Next steps; 1. RW and CG to produce task list which will be used to develop an RfG project plan. 2. Project plan lead by CG based on assumption of Entry into Force Q1 next year with an implementation of 2 years. This is to be included on the agenda for the next meeting. Updated 20.11.14 - Work ongoing, presentations covered under this months meeting agenda. Update 16/12/14 - Ongoing To be covered in Meeting 6 presentation material (Agenda Item 8). | Ongoing
15 | National Parameters Table | RM & AJ | Prepare a table outlining the national parameters to be selected following receipt of the list of actions under Articles 8 to 23 of the RfG code (January 2014 draft) from RM. This will incorporate the draft implementation plan presented to the ECCAF Code Mapping Working Group in April 2014. Update 20.10.14 - Presentation covered by RW (Agenda item 6) | Closed
16 | Assumptions Log to capture assumptions made to date in terms of implementation of RfG and to facilitate project plan. | CG | Covered in Meeting 5 presentation material. | Closed
17 | Insights from Commercial Frameworks-Gas rep from NGET on approach adopted on the Gas ENCs | RW | Covered in Meeting 5 presentation material. | Closed
18 | Ofgem/DECC Steering Group clarification. (Terms of Reference and the reporting lines requirement for the RfG workgroup) | RM | RM covered under A.O.B of Meeting 5. Specifics around how and what the RfG workgroup should report into the Steering Group still to be defined. RM to provide further update at December RfG workgroup meeting. As this item will now be covered as a standing agenda item, the action has been closed and covered as an agenda item going forward. | Closed
19 | Raise with ACER the definitions across ENCS and flag the codes which do not apply retrospectively | RM | Work is ongoing RM to report back to the workgroup the progress made on this. | Ongoing
20 | RW to prepare material for the three priority items to work through for the next workgroup meeting; Retrospectivity process (3.a.3) TSO setting of banding thresholds (3.b.2-4) Process for consideration of plant as new/existing (3.a.4) | RW | Covered in Meeting 5 presentation material. | Closed
21 | Website documentation and publishing format – can the documents run in chronological order or be split by meeting date? | SLK | SLK advised the current functionality of the website and workgroup pages does not permit this request however there is a review of National Grid's website being undertaken and these comments have been fed into this review. | Closed
22 | ‘Stakeholder Representation’ added as a standing agenda item for this workgroup | SLK | Complete. | Closed
23 | Corrections to Meeting 4 Presentations, publishing to website and notification to membership. | AJ and SLK | Complete. | Closed
24 | Additional post meeting action request from Mike Kay: Meeting invites to be sent for all forthcoming RfG workgroup meetings. | SLK | Complete. | Closed
25 | Future Compliance Regime Update | RM/JR | Taken forward from Action 5a, 5b and 9. There is the requirement for DECC and Ofgem to provide an update on the future compliance regime. For example, enforcement of G59 and G83, decommissioning, impact on domestic customers. | Ongoing
26 | Develop Risk Register draft for the RfG Workgroup | RW/AJ | To be covered in Meeting 6 presentation material (Agenda Item 9). | Ongoing
27 | Project Plan Progression | Chair and Workgroup | To be covered in Meeting 6 presentation material (Agenda Item 8). | Ongoing
28 | Banding Presentation Corrections/Updates | RW and RJW | Update banding presentation wording from ‘compromise’ to recommendation/proposal and include the suggestion from MB of clear splits between bands. Complete | Closed
29 | Costs to Generators. | CW and RW | Determine the cost to generators of complying with the cumulative requirements of bands A-C in particular and therefore the impact that would be felt in moving the thresholds. CW to progress this action for synchronous plant and RW to speak to Zoltan Zavody of Renewable UK for non-synchronous plant. To be covered in Meeting 6 presentation material (Agenda Item 6). | Ongoing
30 | Consideration of Operational costs to NGET | RW | To consider how to assess operational costs for NGET. To be covered in Meeting 6 presentation material (Agenda Item 7). | Ongoing
31 | Frequency Response Services | RW and MK | to consider how NGET will use frequency response services for Type B and C generators. MK will also look at type B/C costs. To be covered in Meeting 6 presentation material (Agenda items 7and 8). | Ongoing
32 | Preliminary banding assessment data source/s | RW and RJW | To provide more information on what data was used as part of the preliminary banding assessment including that from the GC0035 Workgroup and what the issues with this or necessary assumptions had been, and liaise with MK, AC and SM on any further information required from the DNOs. To be covered in Meeting 6 presentation material (Agenda Item 5). | Ongoing
33 | Presentation Correction | AJ and SLK | To update Timeline slide error – ‘general’ repeated twice and SLK to re-publish to the website (and advice the workgroup). Complete | Closed
34 | New Standing Agenda Item ' DECC/Ofgem Steering Group Reporting' | SLK | To add ‘DECC/Ofgem Steering Group Reporting’ as a standing agenda item. Complete | Closed
35 | DECC/Ofgem Steering Group Terms of Reference for workgroup circulation | JW |  | NEW
36 | ‘RfG Banding Threshold Setting Considerations’ RW to circulate to the workgroup; assumptions and further details behind this presentations findings. | RW |  | NEW
37 | RW and AJ to look into AF's query on what is the current maximum amount available of Frequency Response and also where possible add this to the graph slide 9 Projection of Generation Types by 2020 (Slow Progression model) detailed within the ‘RfG Banding Threshold Setting Considerations’ presentation. | RW and AJ |  | NEW
38 | RW to liaise with NGET System Operability Framework representatives and the potential for them to give a presentation at a future RfG workgroup meeting. JW to speak to SO Ofgem colleagues for thoughts. | JW and RW |  | NEW
39 | RW/AJ and AF to look internally into the rationale behind the current GB banding (but noted they may not be able to confirm an answer on this). | AF, RW and AJ |  | NEW
40 | RW and RJW to chase up non-synchronous banding date/costs from Renewable UK. | RW and RJW |  | NEW
41 | National Parameters Selection Presentation - AJ to provide workgroup with reasoning/values behind each parameter, any associated Grid Code modification names, confirmation of any impacts to the Project Plan timescale of 1 year and to review the TSO/DNO interactions. | AJ |  | NEW
42 | SLK to look into the possibility of circulating to the workgroup an organogram depicting the DECC/Ofgem Steering group placement in the ENC governance structure. | SLK |  | NEW
43 | AJ/CR/All to work towards a detailed project plan by February 2015 ahead of the March Steering Group meeting. | AJ/CR/All |  | NEW
44 | SLK to look to plan in future workgroup meetings from June 2015 onwards. | SLK |  | NEW