## Timeline for approval
Section 8: 8.19.1.(e) makes the following provision for the Panel and states “Having regard to the complexity, importance and urgency of particular CUSC Modification Proposals, the CUSC Modifications Panel may determine the priority of CUSC Modification Proposals and may (subject to any objection from the Authority taking into account all those issues) adjust the priority of the relevant CUSC Modification Proposal accordingly”
Complexity | The modification is viewed as being resource intensive and will most likely require a higher than average number of workgroups to conclude the process. Additionally the modification defect is viewed to have implications for many different areas of the energy market which need to be taken into consideration throughout the process.
Importance | The perceived value & risk associated with the proposed modification. The value / risk could be considered from a number of different perspectives i.e. financial / regulatory / licence obligations both directly for customer and end consumers more generally.
Urgency | A modification which requires speedy consideration within the code governance process, both complexity and importance should be factors considered in evaluating urgency as well as the timescales for implementation within the respective code.
Modifications at Workgroup Stage
Movement | Date Modification Raised | Modifications at WG Stage | Panel Justification on Prioritisation | Cross Code Impacts | Date of First WG | WG Development [WG already held] | WG Report submission | Expected FMR Date to Authority | Anticipated frequency of meetings*
GC0104: EU Connection Codes GB Implementation – Demand Connection Code
Same position | 2018-07-19 | CMP303 - Improving local circuit charge cost-reflectivity | Required ahead of the completion of the CfD Auctions |  | 25 September 2018 | 7 up to July 2019 | n/a | September 2019 | TBC
Up one place (as CMP295 removed from stack) | 2019-05-22 | CMP317 Identification and exclusion of Assets Required for Connection when setting Generator Transmission Network Use of System (TNUoS) charges | Based on current assumption on timing with 2020 deadline*; if it is assessed that the timing is not so critical the modification will be reviewed and may be reassessed on the prioritisation stack. *Note deadline now 2021, reassessed and still considered by July Panel to still be high priority |  | 27 June 2019 | 2 up to July 2019 | Timeline agreed: January 2020 | March 2020 | TBC
Up one place (as CMP295 removed from stack) | 2019-04-16 | CMP315 - TNUoS: Review of the expansion constant and the elements of the transmission system charged for | Scale and complexity; no requirement with compliance. Unlikely to be implemented ahead of Tariff setting for 2020. To be reviewed following first workgroup |  | TBC | TBC | TBC | TBC | TBC
Up one place (as CMP295 removed from stack) | 2019-02-15 | CMP311 'Reassessment of CUSC credit requirements for Suppliers, specifically for “User Allowed Credit” as defined in Section 3, Part III section 3.27 of the CUSC' | Priority based on substantial changes for Suppliers and Consumers. Early conculsion will help parties to understand any requirements on them |  | 9 April 2019 | 3 up to July 2019 | Timeline agreed: September 2019 | November 2019 | TBC
Up two places | 2018-09-20 | CMP306 - Align annual connection charge rate of return at CUSC 14.3.21 to price control cost of capital | Materiality, Clear solution, Link to having a decision by Autumn 2019 to give time for consideration in regards to publication of charging statement. |  | 31 January 2019 | 2 up to July 2019 | Timeline agreed: August 2019 | October 2019 | TBC
Up three places | 2018-10-19 | CMP308 Removal of BSUoS charges from Generation | High impact of BSUoS Payers, Impact on BSUoS recovery, Consumer Impacts |  | 18 December 2018 | 4 up to July 2019 | Timeline agreed: Agred at July Panel to delay to October 2019 as next Workgroup meeting won't be until September 2019 | December 2019 | TBC
Up three places | 2019-04-16 | CMP316 - TNUoS Arrangements for Co-located Generation Sites | Scale and complexity; no requirement with compliance. Unlikely to be implemented ahead of Tariff setting for 2020. To be reviewed following September workgroup |  | 20 June 2019 | 1 up to July 2019 | TBC | TBC | TBC
New entry | 2018-07-18 | CMP320 'Island MITS Radial Link Security Factor' | Material cost to island generators. Proposed application April 2024. |  | TBC | TBC | TBC | TBC | TBC
Moved down one | 15/02/2018 | CMP291 ‘The open, transparent, non-discriminatory and timely publication of the harmonised rules for grid connection (in accordance with the RfG, DCC and HVDC) and the harmonised rules on system operation (in accordance with the SOGL) set out within the Bilateral Agreement(s) exhibited in the CUSC.’ | Prioritisation based on alignment to European Law changes/timetables July Panel: Moved down reflecting quoracy issues |  | 12 July 2018 | 2 up to July 2019 | Timeline of August 2019 forWorkgroup Report to be presented for Panel Approval previously agreed: this won't be possible so need to request extension at August Panel once extension period established) | TBC | TBC
Up one place (as CMP280/281 removed from stack) | 2017-10-10 | CMP287 ‘Improving TNUoS Predictability through Increased Notice of Inputs Used in the TNUoS Tariff Setting Process’ | Priority based on a need for a quick decision date to have an effect on tariff setting timetables |  | 18 January 2018 | 5 up to July 2019 | Timeline agreed: October 2019 | December 2019 | TBC
Up one place (as CMP280/281 removed from stack) | 2017-10-10 | CMP286 ‘Improving TNUoS Predictability through Increased Notice of the Target Revenue used in the TNUoS Tariff Setting Process’ | Priority based on a need for a quick decision date to have an effect on tariff setting timetables |  | 18 January 2018 | 5 up to July 2019 | Timeline agreed at July Panel: January 2020 | March 2020 | TBC
Up one place (as CMP280/281 removed from stack) | 2018-02-12 | CMP288’ Explicit Charging Arrangements for Customer Delays’ and CMP289’ Consequential change to support the introduction of explicit charging arrangements for customer delays and backfeeds via CMP288’ | Priority based on Consumer benefits. Quite a degree of complexity involved, extended timeline to December2018. |  | 16 May 2018 | 6 up to July 2019 | Timeline agreed at July Panel: October 2019 | December 2019 | TBC
Up one place (as CMP280/281 removed from stack) | 2018-08-23 | CMP304 'Improving the Enhanced Reactive Power Service by making it fit for purpose' | High Materiality July Panel majority view is to leave where it is currently sat within the stack |  | TBC | 3 up to July 2019 | TBC | TBC | TBC
Up one place (as CMP280/281 removed from stack) | 2018-04-23 | CMP298 - Updating the Statement of Works process to facilitate aggregated assessment of relevant and collectively relevant embedded generation | Priority based on assessment against other modifications. A SOW process is also already in place, so there is no immediate need for any urgency. |  | 02 October 2018 | 5 up to July 2019 | Agreed at July Panel to extend timeline from October 2019 to December 2019 as Workgroup Consultation not to be issued until w/c 28 October 2019. | TBC | TBC
Up two places (as CMP280/281 and CMP292 removed from stack) | 2018-06-27 | CMP300 'Cost reflective Response Energy Payment for Generators with low or negative marginal costs' | Low materiality |  | 15 February 2019 | 1 up to July 2019 | Timeline agreed at July Panel: August 2019 | October 2019 | TBC
Modifications on hold
CMP271 - Improving the cost reflectivity of demand tx charges (RWE) CMP274 - Winter TNUoS Time of Use Tariff for Demand TNUoS (UK Power Reserve) CMP276 – Socialising T costs associated with “green policies” (Alkane) CMP307 - Expanding the BSUoS charging base to include embedded generation (Engie)
Modifications not at workgroup
Modification number |  | Next Stage Gate | Comments
CMP280/281 - Removal of UoS charges from Storage |  | Code Admin Consultation | To be submitted w/c 29 July 2019; plan to present DFMR at Special Panel in September 2019
CMP285 CUSC Governance Reform – Levelling the Playing Field |  | Implementation | Implemented 5 July 2019
CMP292 - Introducing a Section 8 cut-off date for changes to the Charging Methodologies |  | DFMR | DFMR approved at July Panel. FMR to be submitted.
CMP295 - Contractual Arrangements for Virtual Lead Parties (Project TERRE) |  | Code Admin Consultation | To be submitted w/c 29 July 2019; plan to present DFMR at Special Panel in September 2019
CMP301 - Clarification on the treatment of project costs associated with HVDC and subsea circuits |  | Implementation | Authority Decision received 11 June 2019; Implementation Date 1 April 2020
CMP305 - Removal of the Enhanced Reactive Power Service (ERPS) |  | Code Admin Consultation | Date TBC - to be submitted at same time as CMP304
CMP309 - CUSC changes in the event the UK leaves the EU without an agreement |  | DFMR | Date TBC
CMP310- CUSC section 14 changes in the event the UK leaves the EU without an agreement |  | DFMR | Date TBC
CMP313 - Critical Friend review period for submission of new modifications |  | Implementation | To be implemented 1 August 2019
CMP314- Updating the CUSC to align Power Available with the Grid Code definition for Power Park Modules |  | Code Admin Consultation | Issued 15 July 2019, open until 5 August 2019
CMP319- Consequential changes to Section 11 of the CUSC as a result of CMP280 and/or CMP281 |  | Code Admin Consultation | To be submitted w/c 29 July 2019; plan to present DFMR at Special Panel in September 2019
*Frequency of meetings is dependent on consultation phases, workgroup availability, CA availability
Down 3

## Sheet2
July |  |  | Suggestions to add onto Prioritisation stack next time:
| WG Meetings | CMP293/94 WebEx 09/07/2018 | * Plan on a page
|  | CMP291/95 12/07/2018 | * Add CMP300
CMP288/89 16/07/2018
CMP285 17/07/2018
CMP280/81 26/07/2018
CMP286/87 - Planned for 6th July, postponed to carry out analysis to the 31st July
| CAC | CMP301 sent out 02/07/2018
| WG Consultation | CMP280 closed 10/07/2018
| Panel Recommendation Vote | DFMR CMP301
DFMR CMP275/CMP296/CMP297/CMP299
| Sent FMR's to Authority | 4 =CMP275, CMP296, CMP297 & CMP299
Aug | WG Meetings | CMP288/89 6/08/2018
CMP291/95 TBC
CMP280/81 TBC - Last week of August
| WG Consultation (hoping to send out) | CMP285 and CMP281
Sep | WG Meetings | CMP291/95 TBC
CMP292 TBC
CMP298 TBC
CMP300 TBC