## Timeline for approval
Section 8: 8.19.1.(e) makes the following provision for the Panel and states “Having regard to the complexity, importance and urgency of particular CUSC Modification Proposals, the CUSC Modifications Panel may determine the priority of CUSC Modification Proposals and may (subject to any objection from the Authority taking into account all those issues) adjust the priority of the relevant CUSC Modification Proposal accordingly”
Complexity | The modification is viewed as being resource intensive and will most likely require a higher than average number of workgroups to conclude the process. Additionally the modification defect is viewed to have implications for many different areas of the energy market which need to be taken into consideration throughout the process.
Importance | The perceived value & risk associated with the proposed modification. The value / risk could be considered from a number of different perspectives i.e. financial / regulatory / licence obligations both directly for customer and end consumers more generally.
Urgency | A modification which requires speedy consideration within the code governance process, both complexity and importance should be factors considered in evaluating urgency as well as the timescales for implementation within the respective code.
Modifications at Workgroup Stage
Movement | Date Modification Raised | Modifications at WG Stage | Panel Justification on Prioritisation | Cross Code Impacts | Date of First WG | WG Development [WG already held] | WG Report submission | Expected FMR Date to Authority | Anticipated frequency of meetings*
GC0104: EU Connection Codes GB Implementation – Demand Connection Code
| 2018-07-19 | CMP303 - Improving local circuit charge cost-reflectivity | Required ahead of the completion of the CfD Auctions |  | 25 September 2018 | 8 up to 27 September 2019 | n/a | October 2019 | TBC
| 2019-05-22 | CMP317 Identification and exclusion of Assets Required for Connection when setting Generator Transmission Network Use of System (TNUoS) charges | Based on current assumption on timing with 2020 deadline*; if it is assessed that the timing is not so critical the modification will be reviewed and may be reassessed on the prioritisation stack. *Note deadline now 2021, reassessed and still considered by July Panel to still be high priority |  | 27 June 2019 | 3 up to 27 September 2019 | Timeline agreed: January 2020 | March 2020 | TBC
New | 2019-09-27 | CMP324: Generation Zones – changes for RIIO-T2 | Connection to RIIO timeline, implementation required before October 2020. |  |  | #VALUE! | Timeline to be agree | To be agree
| 2019-04-16 | CMP315 - TNUoS: Review of the expansion constant and the elements of the transmission system charged for | Scale and complexity; no requirement with compliance. Unlikely to be implemented ahead of Tariff setting for 2020. To be reviewed following first workgroup Decision from Ofgem needed by September 2020 |  | TBC | 1 up to 27 September 2019 | TBC | TBC | TBC
| 2019-02-15 | CMP311 'Reassessment of CUSC credit requirements for Suppliers, specifically for “User Allowed Credit” as defined in Section 3, Part III section 3.27 of the CUSC' | Priority based on substantial changes for Suppliers and Consumers. Early conculsion will help parties to understand any requirements on them |  | 9 April 2019 | 5 up to 27 September 2019 | Timeline agreed at August Panel: November 2019 | January 2020 | TBC
| 2018-10-19 | CMP308 Removal of BSUoS charges from Generation | High impact of BSUoS Payers, Impact on BSUoS recovery, Consumer Impacts |  | 18 December 2018 | 5 up to 27 September 2019 | Timeline agreed: Agred at July Panel to delay to October 2019 as next Workgroup meeting won't be until 9 September 2019 | December 2019 | TBC
| 2019-04-16 | CMP316 - TNUoS Arrangements for Co-located Generation Sites | Scale and complexity; no requirement with compliance. Unlikely to be implemented ahead of Tariff setting for 2020. To be reviewed following September workgroup |  | 20 June 2019 | 2 up to 27 September 2019 | TBC | TBC | TBC
| 2018-07-18 | CMP320 'Island MITS Radial Link Security Factor' | Material cost to island generators. Proposed application April 2024. |  | TBC | 1 up to 30 August 2019 | TBC | TBC | TBC
| 2018-08-23 | CMP304 'Improving the Enhanced Reactive Power Service by making it fit for purpose' | High Materiality August Panel agreed to move CMP304 up the Prioritisation Stack as National Grid ESO are no longer producing a product road map. In addition, Ofgem will only make their decision on CMP305 at the same time as CMP304. |  | TBC | 3 up to 27 September 2019 | TBC | TBC | TBC
| 15/02/2018 | CMP291 ‘The open, transparent, non-discriminatory and timely publication of the harmonised rules for grid connection (in accordance with the RfG, DCC and HVDC) and the harmonised rules on system operation (in accordance with the SOGL) set out within the Bilateral Agreement(s) exhibited in the CUSC.’ | Prioritisation based on alignment to European Law changes/timetables July Panel: Moved down reflecting quoracy issues |  | 12 July 2018 | 2 up to 27 September 2019 | Timeline of August 2019 forWorkgroup Report to be presented for Panel Approval previously agreed: this won't be possible so need to request extension at August Panel once extension period established) | TBC | TBC
| 2017-10-10 | CMP287 ‘Improving TNUoS Predictability through Increased Notice of Inputs Used in the TNUoS Tariff Setting Process’ | Priority based on a need for a quick decision date to have an effect on tariff setting timetables |  | 18 January 2018 | 5 up to 27 September 2019 | Timeline agreed: October 2019 | December 2019 | TBC
| 2017-10-10 | CMP286 ‘Improving TNUoS Predictability through Increased Notice of the Target Revenue used in the TNUoS Tariff Setting Process’ | Priority based on a need for a quick decision date to have an effect on tariff setting timetables |  | 18 January 2018 | 5 up to 27 September 2019 | Timeline agreed at July Panel: January 2020 | March 2020 | TBC
| 2018-02-12 | CMP288’ Explicit Charging Arrangements for Customer Delays’ and CMP289’ Consequential change to support the introduction of explicit charging arrangements for customer delays and backfeeds via CMP288’ | Priority based on Consumer benefits. Quite a degree of complexity involved, extended timeline to December2018. |  | 16 May 2018 | 6 up to 27 September 2019 | Timeline agreed at July Panel: October 2019 | December 2019 | TBC
| 2018-04-23 | CMP298 - Updating the Statement of Works process to facilitate aggregated assessment of relevant and collectively relevant embedded generation | Priority based on assessment against other modifications. A SOW process is also already in place, so there is no immediate need for any urgency. |  | 02 October 2018 | 5 up to 27 September 2019 | Agreed at July Panel to extend timeline from October 2019 to December 2019 as Workgroup Consultation not to be issued until w/c 28 October 2019. | TBC | TBC
| 2018-06-27 | CMP300 'Cost reflective Response Energy Payment for Generators with low or negative marginal costs' | Low materiality |  | 15 February 2019 | 1 up to 27 September 2019 | Timeline agreed at July Panel: August 2019 | October 2019 | TBC
New Modifications
n/a | 2019-09-12 | CMP321: Housekeeping Modification to clarify the definition of Affiliate as a result of CMP285 | TBC | TBC | TBC | n/a | n/a | TBC | TBC
n/a | 2019-09-12 | CMP322: Updating the CUSC section 4 “Balancing Services” to ensure Ofgem have the appropriate authority to approve Ts and Cs, relevant to EBGL Article 18, held within the SCTs | TBC | TBC | TBC | [0] up to 27 September 2019 | Timeline to be agreed once 1st WG meeting has occurred (if WG needed) | TBC | TBC
n/a | 2019-09-12 | CMP323: Updating the CUSC governance process to ensure we capture the EBGL change process for Article 18 T and Cs | TBC | TBC | TBC | [0] up to 27 September 2019 | Timeline to be agreed once 1st WG meeting has occurred (if WG needed) | TBC | TBC
n/a | 2019-09-12 | CMP324: Generation Zones – changes for RIIO-T2 | TBC | TBC | TBC | [0] up to 27 September 2019 | Timeline to be agreed once 1st WG meeting has occurred | TBC | TBC

## Sheet2
July |  |  | Suggestions to add onto Prioritisation stack next time:
| WG Meetings | CMP293/94 WebEx 09/07/2018 | * Plan on a page
|  | CMP291/95 12/07/2018 | * Add CMP300
CMP288/89 16/07/2018
CMP285 17/07/2018
CMP280/81 26/07/2018
CMP286/87 - Planned for 6th July, postponed to carry out analysis to the 31st July
| CAC | CMP301 sent out 02/07/2018
| WG Consultation | CMP280 closed 10/07/2018
| Panel Recommendation Vote | DFMR CMP301
DFMR CMP275/CMP296/CMP297/CMP299
| Sent FMR's to Authority | 4 =CMP275, CMP296, CMP297 & CMP299
Aug | WG Meetings | CMP288/89 6/08/2018
CMP291/95 TBC
CMP280/81 TBC - Last week of August
| WG Consultation (hoping to send out) | CMP285 and CMP281
Sep | WG Meetings | CMP291/95 TBC
CMP292 TBC
CMP298 TBC
CMP300 TBC