## Open
CACoP Actions Log - 2019
Action Ref. | Action | Owner | Notes | Update
037 - 2019 | All representatives to approach their panels and obtain their views on a central CACoP website. | All | New
038 - 2019 | FM to obtain quotes for website. | SPAA | New | FM - Progress, havent had responses from all codes.

## Closed
CACoP Actions Log - 2019
Action Ref. | Action | Owner | Notes | Update
01/02 | Dcode administrator to update the CACoP document to reflect the discussions held and to obtain background information where requested. | DCode | Closed
01/03 | CUSC to chase a query dating back to October on DCP 295 | Mike Oxenham | Closed
01/04 | SEC to share information on SECMP 0041 to all Code Administrators | Talia Addy | Closed
01/05 | All CACoP members to disseminate the information on SECMP 0041 to contract managers | All CACoP members | Closed
01/06 | National Grid to update the horizon scanning document once it has been reviewed by CACoP members | National Grid | Closed
01/08 | DCUSA to produce a proposal for a centralised CACoP website and present it at the next CACoP meeting | Dan Fittock | Closed
01/09 | The BSC representative to contact the Chair if they would like further information on the MAMCoP Change Process under SPAA | Chris Wood | Closed
01/01 | All CACoP members to review the contacts section of the CACoP and provide feedback to DCode for them to update | All CACoP members | Closed
02/01 | Ofgem to update the cover note and draft Principle to reflect the discussions at the meeting. | Ofgem | Closed
02/02 | All Code Administrators to present the draft Principle to their respective Code Panels for comment | All CACoP members | Closed
02/03 | UNC to lead on the CACoP sub-group to review the reporting template | UNC | Closed
02/04 | All CACoP members to present the updated CACoP document to their Code Panels following revisions to Principle 12. | All CACoP members | Closed
02/05 | DCUSA to consider the development of a wider communication plan, potentially to include a website | DCUSA | Closed
02/06 | CUSC/Grid Code to review the structure and layout of the horizon scan document in advance of the next meeting | CUSC/Grid Code | Closed
02/07 | All CACoP members to send any relevant information regarding Panel governance procedures to the UNC | All CACoP members | Closed
02/08 | The Secretariat to circulate a work plan for the group | Secretariat | Closed
02/09 | Ofgem to obtain timescales from Future Thinking and let MRA know the final date to submit their contacts for the Customer Survey | Ofgem | Closed
01/07 | All CACoP members to review the Central Modification Register and ensure that the most recent information has been included. Any amendments should be sent to MRASCo | All CACoP members | Closed
02C/01 | SPAA to speak with all CACoP members to compile a list of questions that need answers from the Ofgem EU Exit Group | SPAA | Closed
03/01 | The Secretariat to obtain feedback from the DCode Code Administrator about their position on Ofgem's proposed innovation principle | Secretariat | Closed
03/02 | All CACoP members to share what work they are conducting in regards to the National Grid seperation | All CACoP members | Closed
03/04 | MRA to speak to individual Codes regarding the central modifications register and update them on the information that is missing from the document | MRA | Closed
03/05 | All CACoP members to update their CACoP pages on their webistes and ensure that there is a link to the DCUSA website for any meeting documentation | All CACoP members | Closed
03/07 | All CACoP members to get a GDPR steer on whether contact details of a Change Proposer should be included on the CP form | All CACoP members | Closed
02/10 | All CACoP members to feedback their scheduled Release dates and times to allow a common picture to be formed by the MRA. | All CACoP members | Closed
03/03 | All CACoP members to update the new version of the horizon scanning document | All CACoP members | Closed
04/01 | GS to circulate examples of scenarios when contact details would need to be shared and circualte the webinar that was discussed at the Joint MIS Development Group | Glenn Sheern | Closed
04/02 | SPAA representative to ensure that a questions is sent to the EU exit group regarding what the plan would be if there was no deal | SPAA | Closed
04/03 | Ofgem to inform the group when they will be receiving their cross-code survey reports and when Future Thinking would be willing to attend each Panel | Ofgem | Closed
04/04 | BSC representative to circulate examples of when data would need to be shared for change process purposes | BSC | Closed
05/01 | Ofgem to provide a list of questions for Code Administrators in regards to Brexit and to provide tag lines for use in published material and to present to the Code Panels | Heather Stewart - Ofgem | Closed
05/02 | Ofgem to review the results of the cross-code survey and inform the secretariat of any key areas that the CACoP group should focus on in regards to their 2018 review of the CACoP document | Colin Down - Ofgem | Closed
05/03 | All Code Administrators to confirm to the Ofgem representative that they have a deorgation process in place for any instances where an innovation is being tested (principle 14) | All Code Administrators | Closed
05/04 | CW agreed to finalise the horizon scanning document and circulate to members by close of play on 25 September 2018 | Chris Wood | Closed
05/06 | The BSC representatives to draft wording for a joint CACoP Brexit publication | Chris Wood | Closed
05/08 | BSC representative to draft wording for a joint CACoP Horizon Scanning publication | Chris Wood | Closed
03/06 | SPAA representative to review the joint working practice document and feedback any recommended changes for discussion at the communication strategy workshop | SPAA | Closed
05/07 | MRA & SPAA reps to draft wording for a joint CACoP Faster Switiching and REC publication | Simon Fox-Mella and Fraser Mathieson | Closed | Draft wording for Joint CACoP Faster Switiching and REC Publication has been produced and this action is now closed.
06/02 | The SPAA representative agreed to review the Faster Switching and REC CACoP Lines and amend to ensure that they are more CACoP specific. | SPAA | Closed | Draft wording for Joint CACoP Faster Switiching and REC Publication has been reviewed lines amened to ensure that they are more CACoP specific and this action is now closed.
001 - 2019 | Ofgem to respond to questions from (FM) and to consider how CACoP can help support in this area. | Ofgem | Closed | Lesley Nugent dialled into the meeting on 19 March 2019 detailing how CACoP can feed into the Energy Codes Review. The Code Manager role could empower CACoP to respond to industry change.
003 - 2019 | All Code Administrators to seek feedback from their stakeholders through panels or any other stakeholder interaction points on: • How well they understand what CACoP is • What value they think CACoP can add to industry • How they would like to be communicated and engaged going forwards | All | Closed | This action was scoped out at the March 2019 meeting.
004 - 2019 | National Grid ESO (RH) to circulate key messages from the CACoP meeting to industry by end of the week | National Grid ESO | Closed | National Grid ESO (RH) to circulated key messages on 27 March 2019
005 - 2019 | National Grid ESO (RGA) to upload onto the CACoP Website | National Grid ESO | Closed | National Grid ESO (RGA) has uploaded "Highlights -CACoP Meeting 19 March 2019" onto the Website.
05/05 | The Chair to liaise with Jon Dixon to establish what role the CACoP group can play in regards to the REC being established | National Grid ESO | Closed | This action is no longer relevant - no further comments from the group members and is therefore closed.
06/03 | National Grid ESO to circulate the feedback received regarding the CP Prioritisation work | National Grid ESO | Closed | This action is ongoing, National Grid ESO will provide update at next meeting.
06/04 | The DCUSA representative to look at the options for the aligining all Code CACoP website papges and provide a paper for the next CACoP meeting | DCUSA | Closed | Draft paper has been produced inviting comments/thoughts from the group to refine and finalise the paper and give scope for the CACoP website. This will be revisited as a part of developing an engagement strategy for CACoP. This action is closed and may be reviewed at the end of the year.
002 - 2019 | Lines to Take to be proposed by (FM) for adoption by CACoP. To be revisited in the March 2019 meeting | SPAA | Closed | This action is closed and if necessary will be revisoted later on in the year.
006 - 2019 | National Grid ESO to review and add more detail to actions and to establish if they are still valid | National Grid ESO | Closed | More details added to actions log and this action can now be closed
009 - 2019 | MRA (EA) to share updated Central Modification Register with the CACoP community by next in person meeting in May 2019 | MRA (EA) | Closed | Central Modification Register was circulated on 4 April 2019 with request to all update/amend any inaccuracies
013 - 2019 | National Grid ESO to write the CACoP engagement approach plan (RH), circulate to the CACoP community for discussion at the April 2019 WebEx | National Grid ESO | Closed | National Grid ESO (RH) has produced the CACoP Engagement Approach Plan, circulated it to the CACoP members. Discussions followed in the 24 April 2019 Webex meeting. Amendments were made accordingly in tack changes for all group member to agree/supply further comments by next meeting in May 2019. This has been circulated to the group members following the 24 April 2019 WebEx meeting
014 - 2019 | National Grid ESO to set up WebEx meetings inbetween the regular in person scheduled meetings. | National Grid ESO | Closed | National Grid ESO (RGA) set up first WebEx meeting for the CACoP group to meet bi-monthly which took place on 24 April 2019
015 - 2019 | National Grid ESO to provide Ofgem (LN) the CACoP work plan by 31 May 2019 | National Grid ESO | Closed | Once ageement has been reached by the group members, the CACoP Work Plan will be submited to Ofgem by National Grid ESO (RH)
016 - 2019 | UNC (EA) to investigate into why no cross code inpacts were showing on the Central Modification Register whilst approximately 40% were identified as having an impact on the iGT, UNC or SPAA or both. Results to be shared at next CACoP meeting. | UNC | Closed | Central Modification Register was circulated on 4 April 2019 with request to all update/amend any inaccuracies. (EA) encouraged all to complete and bring up to date. Questions/queries were invited by (EA) in this regard.
05/09 | DCUSA to draft wording for a joint CACoP publication regarding their achievements for 2018 and their aims for 2019. This will be completed by the end of the year. | DCUSA | Closed | This action is ongoing and and update will be provided in the May 2019 meeting
008 -2019 | Gemserve to share flow diagram of the pre-mod process used by Gemserve to assess modifications to identify root cause of the problem before starting to examine solutions by next in person meeting in May 2019 | Genserv | Closed | No progress on this action yet, update to be provided at the May 2019 meeting (Gemserv provided this on 7 May)
007 - 2019 | National Grid ESO to request industry cross-code updates from the group ahead of the bi-monthly in person meeting. | National Grid ESO | Closed | National Grid ESO to get industry updates from the various codes prior/immediately after the meetings to ensure information is accurately recorded. All group members agreed to provide this information ahead/immediately after the meeting.
010 - 2019 | National Grid ESO to invite Ofgem to July 2019 CACoP meeting for update on Energy Codes Review | National Grid ESO | Closed | Ofgem presented at the event
011 - 2019 | Elexon to circulate the link to Horizon Scan/Plan and also circulate the Horizon Scan to to CACoP community by next meeting in person meeting in May 2019 | Elexon | Closed | On going, update will be provided in the May 2019 meeting - update provided in May meeting and action is now closed
06/01 | Future Thinking to provide the tiers used to determine that participants of the survey are engaged with the Code enough to take part | Future Thinking | Closed | Ofgem updated CACop at the may meeting on the methodology used.
012 - 2019 | After review of the Horizon Scan all feedback comments to be sent to Elexon | All | Closed | Update will be provided in the May 2019 meeting - All CACoP group members agreed to send feed back to Elexon - action is now closed
017 - 2019 | National Grid ESO (Chair) to speak to Elexon to request them to host an agenda item on the July engagement event, with draft agenda to discuss to be discussed at May 2019 meeting | National Grid ESO (Chair) | Closed | Elexon provided a draft agenda to the CACoP group members. This was discussed in some detail as to what he CACoP group members would like the Agenda to look like and the actioon can now be closed.
018 - 2019 | First Newsletter to be published in May 2019 by Gemserv (MRA) - all group members to supply any items they wish to be included/considered therein | All | Closed | Gemserv circulated the draft Newsletter and requested input from all the codes. All CACoP group members have committed to let Gemserve have any items they wish to be included in the newsletter by close of business 24 May 2019 to enable the first publication to industry by the end of May 2019.
019 - 2019 | All to independently review the "CACoP Principles Self Audit" spreadsheet, establish how we meet these principles and share any areas that are identified as learnings at the next meeting in May 2019. | All | Closed | All CACoP group members indpendently reviewed the CACoP Principles Self Audit and discussed their findings in the 21 May meeting - this action can now be closed.
020 - 2019 | National Grid ESO to re-circulate the CACoP Forward Work Plan 2019 comprising the amendments made and clarity given where required, requesting the group members to review and provide further comments if/where appropriate. | National Grid ESO | Closed | The CACoP Forward Work Plan 2019 was circulated by NGESO on 24 April 2019 inviting further comments if appropriate. This document will be discussed at the next CACoP meeting in May 2019. This document was discussed at the May meeting and the action can now be closed
021 - 2019 | All CACoP group member to review and update as necessary the Forward Work Plan 2019 - Appendix 1: List of Code Administrators by next meeting in May 2019 | All | Closed | All CACoP group members indpendently reviewed the Forward Work Plan and updated it where necessary. This was discussed in detail at the 21 May meeting. The document has been finalised and uploaded onto the CACoP Website - this action can now be closed.
023 - 2019 | All CACoP group member to send to Gemserv items they would like to be added to the first Newsletter to be produced by Gemserv by the end of May 2019 | All | Closed | Newsletter items were sent and first newsletter has been issued.
025 - 2019 | National Grid ESO Chair to speak to Ofgem regarding feedback received from CACoP group members, in relation to information requested in the template forwarded to all to assist with the CACoP Annual Review | National Grid ESO Chair | Closed | CACoP annual survey now under way.
022 - 2019 | National Grid ESO to ensure slidepack is issued and up loaded onto the website ahead of the meeting. | National Grid ESO | Closed
024 - 2019 | Elexon to supply Gemserv with any further material they may have in relation to Brexit to be included in the first Newsletter due to be published in May 2019 | Elexon | Closed
026 - 2019 | All Code Administrators to nominate an individual who will be able to support some work over the next month or so in connection SoLR. Provide any high-level thoughts e.g. major impediments to fast-tracking a CoS for a subset of customers and initial thoughts on impacts. | All | Closed
027 - 2019 | All to look at and feed back to Gemserv possible solutions which including speeding up the SoLR process to minimise time taken for the SoLR Supplier to be able to service all the customers of the failed supplier; and determining the feasibility of fast-tracking a standard Change of Supplier for only the customers of a failed Supplier who have smart meters in the prepayment mode. | All | Closed