## Tracker 20-21
Information correct as of |  | 2021-05-07
Role | Title | Deliverable | Description | Planned Delivery Date | Commentary
1 | Upgrade of information systems | Widen access to API (Application Programming Interface) system | We have reviewed our approach and we are going to widen access to the API. This is going to be done in two ways: - We are reviewing the applicable communication standard and will relax the size threshold (currently 100MW) for use of the API. This document, which requires Grid Code Panel approval, will be completed in September 2020. - We will allow use of the API across all market participant routes subject to the communication standards. API Go-Live is expected in July 2020. | Q1-Q2 2020-21 | API Go-Live occurred on 17 September 2020 Additional capability was added into existing systems in Q1 2021-22 to deal with an increased number of market participants. There will also be continuing scaling requirements - as and when required - which form an ongoing process to allow a wider range of connections for market participants. Communication Standard which defines the capacity limits was approved at December Grid Code panel and has now been issued.
1 | Transparency of data used by our ENCC in our close-to-real-time decision making | Publishing the BMU ID for trades | We will take forward the recommendations of the P399 industry working group modification and publish information to the market about the trades we carry out. We will proactively work with our stakeholders to publish data in an accessible format using the API technology. It is an enabler for our trusted partner ambition. | Dependent on P399 code change | This is being covered by the P399 mod, and impacts all cash out files (Trading, N-BM STOR, N-BM FR etc). Completed: The modification went back out for consultation on 8 December 2020, responses were due by 22 December. Responses were collated and presented to the Panel at its meeting on 14 January 2021 and the Modification Report was subsequently sent to Ofgem on 19 January with a recommendation for approval. Ongoing: An Ofgem decision is expected shortly, and the deadline to have the change implemented is November 2021. The recommendation from the BSC panel is that the party IDs are not published prior to the BSC change which is likely to be in November 2021.
1 | Support access for Intermittent Generation | Deliver second phase of Power Available integration | Phase 2b of Power Available (PA) is a continuation of the existing PA project to integrate the PA signal into the Control Room to enable greater use of wind for Mandatory Frequency Response (MFR). This will improve wind forecasting and response optimisation by blending PA with weather forecasts to provide a real time measure of output for wind units. | Q3 2020-21 | Power Available phase 2 was delivered on 30 March 2021.
1 | Support access for Intermittent Generation | Implement State of Energy signal | Define and implement a state of energy signal from limited-energy assets into the Control Room to give visibility of the remaining energy in limited-duration assets, such as batteries. | Q2 2020-21 (Publish outcome of operational trial) Q3 2021-22 (define and implement signal) | Three phases of BM Reserve from Storage trial were undertaken and reviews published. Project will build upon Power Available, and the impact analysis has been delayed as a result of COVID-19 (reference FP addendum). Impact Assessment has now commenced in Q4 2020-21 with planned go-live in Q3 2021-22.
1 | Support access for Intermittent Generation | Deliver Power Available integration phase 1 (priority rolled from 2019-2020) | Integration of Power Available into energy calculations to improve ENCC visibility of Power Park Modules returning from BOAs and high-wind shutdown. | Q1 2020-21 | Power Available (PA) phase 1 has now been completed. There is a case study in our mid-year report to demonstrate the consumer benefits we have achieved.
1 | Whole system operability | Inertia measurement | Implement novel tools to measure system inertia in real-time which will significantly improve the accuracy of measurement and optimise the ESO’s real-time operation, service procurement and network development with the increasing number of embedded generators. It is essential to measure the full system inertia from both the transmission and distribution sides. To increase inertia management accuracy, two suppliers are currently working on different methods to provide the first operational installations. We have experienced programme delays due to issues with integration with existing systems, resulting in an anticipated delivery date of Q2 2020-21 for the first solution. It is estimated that the projects will provide up to 15 percent improvement in the accuracy of the rate of change of frequency measurement. This is based on the limited results from the Samuel Inertia Measurement project (SIM) final report. | Q2 2020-21 (first supplier Q1 2021-22 (second supplier) | The first supplier GE’s inertia metering system is live, PMU data has been provided for the Scottish region and a demo for initial key users has been delivered in March, enabling initial assessment of the results data to now take place across the summer. NGET are continuing to roll out PMUs which will enable additional regions to be added to the Inertia metering system over 2021. The GE Inertia forecasting testing is ongoing. Model training is planned from May with the aim of going live in summer 2021. Second supplier, Reactive Technologies' system is planned to go live in August 2021 (Q2 2021-22) following an extended tender process for the modulator. Work started on the modulator design and build. Initial site works are complete ahead of modulator delivery in May 2021. As the new tools are embedded, we will evaluate them against our existing techniques: this will allow us to assess the benefit of the new tools.
1 | Product Roadmap for Restoration implementation | Deliver competitively tendered black start contracts | Award contracts to successful parties for South West/Midlands tender Award contracts to successful parties for Northern tender Carry out preparatory work for future tender opportunities in South East, in preparation for tender event in Q1 2022/23. | Q1-Q2 2021-22 | South West/Midlands tender: On Monday 9 November 2020 we announced contracts with six providers for Black Start services. The six contracts, five of which are new, total £84 million with each bid offering commercial benefits compared to other bidders and Black Start options. Historically - dates for tender reviewed with participants in light of COVID-19, amendments made to procurement timelines and service commencement date. Early delivery has been incentivised. Northern: Procurement timeline amended following consultation with providers – may impact on commencement dates for contracts. Current/revised contract award date (delayed due to COVID-19 and following a consultation with all Tender Participants) was 30 April 2021. South East: We have reviewed our strategic approach for the South East, and shared our plans in the Black Start Strategy and Procurement Methodology 2021-22 which was published for consultation on 5 Feb 2021 and submitted for Ofgem’s approval in early April 2021.
1 | Electricity Operational Forum and stakeholder engagement | Electricity Operational Forum | This stakeholder event that aims to provide operational information is currently on hold following UK government’s advice on COVID-19. We are holding weekly ENCC webinars instead as an enabler for our trusted partner ambition. | Changed format and delivered throughout the year. | Weekly ENCC webinars have been held to maintain stakeholder engagement while social distancing measures are in place and have been well received by industry. An online version of the Operational Forum was held in November.
1 | Electricity Operational Forum and stakeholder engagement | ENCC visit days | This stakeholder event aims to monthly open door to market participants to the ENCC to learn about system operation. We are holding weekly ENCC webinars instead as an enabler for our trusted partner ambition. | Changed format and delivered throughout the year. | Complete: Weekly ENCC webinars have been held to maintain stakeholder engagement while social distancing measures are in place.
1 | Upgrade of information systems | Expand dispatch facility to handle a large number of small Balancing Mechanism Units, subject to market take-up | We will continually monitor and report on the number of Virtual Lead Parties (VLPs) entering the BM and will forecast the future volumes of number of market participants, prioritising and delivering the backlog of system changes and identifying system upgrades that are required to ensure the existing systems are capable of handling the increasing number of participants. Currently, our dispatch system can accommodate up to 100 small units. We plan to scale this, such that by the end of September it can accommodate a larger number of units. We will keep the scale of this expansion under review, depending on how many market participants come forward to participate. Creation of additional data storage capability for existing BM dispatch system. Complete the design stage for re-platforming our existing multi-dispatch tool. Replacement of existing dispatch optimiser with modern optimiser with capability to solve for more complex scenarios, including a larger number of small BM units. Commence re-platforming our existing multi-dispatch tool delivery. This will fully integrate the current interim process for bulk dispatch of Balancing Mechanism Units (BMUs) into control room systems. This will reduce our manual processes, and make it easier for the Electricity National Control Centre (ENCC) to dispatch a large number of small BMUs at once. | Q1-Q4 2020-21 | We have increased data storage capability in 31 March 2021 onwards, from 600 to 2000 BM Units. We will continue to ensure the systems are able to handle the future pipeline of new participants. The programme is moving into the foundation stage which starts in May 2021 for six months. The phase takes the high-level requirements and will produce a prioritised roadmap. In the meantime, we are continuing to ensure our existing systems are able to handle the future pipeline of new participants. As part of the activities building towards RIIO-2 we are gaining an in depth understanding of the requirements to replace our existing systems to ensure these are adaptable and compatible with the transformation for carbon free operation in 2025. This will ensure efficient IT CAPEX spend across the portfolio of IT work and avoid regret spend. An extensive planning exercise to deliver this transformation is currently underway. In the meantime, we will continue with incremental development, in line with operational requirements.
1 | Upgrade of information systems | Interconnector programmes | Continued integration of interconnectors into operational systems. Before an interconnector begins commercial operation, there are a range of IT systems which need to be updated, and for each system there are milestones which need to be completed: requirements, design, development and testing, implementation, and closure. During 2020-21, we will work on IT changes for Eleclink, IFA2, and NSL - but the precise timing of the commissioning dates for each of these interconnectors has been pushed back by the interconnector owner. IFA2 is expected to commission on 31 October 2020. Both Eleclink and NSL have been delayed to July 2021. We will hold regular meetings to collect customer feedback and carry out satisfaction surveys to measure our performance. Compliance with European Codes continues, with new European methodology due to go live this summer which will increase our ability to participate in real time European markets. We are aiming to introduce efficiencies by aligning processes, enabling new commercial services, and streamlining our IT systems. It is also recognised that with the development of each additional cross border project, the role and significance of interconnectors evolves. In order to better understand the future operational impact of interconnectors we will engage further with the industry in Q2 2020 to gather views and work collaboratively to develop a target post-2025 interconnector model. This year we will deliver IT changes to accommodate the new interconnector, IFA2, commissioning in Q3, increasing the amount of clean energy the UK can exchange with Europe. We will update the interconnector management tool to enable the additional interconnectors going live throughout the year and introduce Balancing Mechanism system updates. We will also introduce updates to aid intraday market changes for one existing interconnector and to set up intraday markets for two new interconnectors; this will increase flexibility for market participants. The commissioning of each new interconnector is the culmination of several years of work to agree operating processes with the interconnector and connecting TSO, and to deliver the necessary IT systems. There is an IT programme that manages all the interconnector changes, both for new interconnectors and developments to existing ones, such as the introduction of increased intraday gates on Nemo and BritNed last year. Each project in the programme has its own plan and progress is regularly reviewed at programme board meetings. Changes to plans are also managed through these board meetings. | Ongoing | Completed: Industry stakeholder engagement has been completed. In Q3 2020-21 six bilateral onboarding sessions were held, covering all current and imminent interconnector parties. Additional sessions were held with both Ofgem and BEIS. During Q4 2020-21, four interconnector workshops were held to assess, confirm and prioritise ESO's initial Road to 2025 work packages. A workshop was held for Operability, Trusted Partnerships, Cross border markets and Frameworks. Ongoing: IT programmes for new interconnectors continue to progress in line with interconnectors’ expectations. Net Transfer Capacity (NTC) work has been impacted by both EU Exit (Trade and Cooperation Agreement) and retained elements from the Clean Energy Package. Final regulatory route being currently agreed with Ofgem - current expectation is that NTC will be implemented by the end of Q2 2021-22.
1 | Upgrade of information systems | Frequency and Time Equipment version 3 (FATE-3) Project | We will improve our frequency monitoring tool and update our current information system to FATE-3. | Q4 2020-21 | Upgrade was completed on 1 April 2021.
1 | Upgrade of information systems | PI gateway refresh | Upgrading of systems to transfer data from Scottish TOs. | Q2 2021-22 | The existing PI link is being maintained until we further upgrade our systems. Activity will resume in 2021-22.
1 | Upgrade of information systems | Platform for Energy Forecasting (PEF) (Priority) | We will be publishing a new version of the Energy Forecasting Strategic Project Roadmap by 30 June 2020. The previous version, from June 2019, is published on our website . We will publish additional energy forecasts to the market: 2-14 days ahead national demand forecast 2-52 weeks ahead national demand forecasts Within day-14 days wind power forecasts. | Q1-Q4 2020-21 | New version of Strategic Roadmap published on 25 June. • 2 - 14 Day Ahead Demand Forecast being published on the Data Portal as of 23 September. • 2-52 weeks ahead national demand forecasts were delivered in Q3. • Within day-14 Day Ahead Wind Forecasts were delivered in Q4.
1 | Upgrade of information systems | Technology Advisory Council (formerly Design Authority) | We will launch the Technology Advisory Council (DA) in Q3 2020-21, in preparation for RIIO-2. This is a key enabler for our zero-carbon and trusted partner ambitions. | Q3 2020-21 | We launched the Technology Advisory Council in December 2020. This includes representatives from energy networks, market participants and service providers, technology and transformation experts and academia. Agendas, minutes and slides from all meetings published on website. The group met for a second time in March 2021 and will now meet on a quarterly basis. We will also set up working groups to discuss specific elements in more detail. During the first meetings, we have shared the early transformation visions and roadmaps for our Balancing, Network Control, open data and digital market enablement, with positive feedback received.
1 | Upgrade of information systems | Improving information access: Data platform Strategy Data portal expansion Data platform foundation implementation Data platform expansion Master data management implementation | Foundation work for data analysis platform, involving auditing current data flows and designing new platform for RIIO-2 and making all published ESO data available via the ESO data portal. | Q4 2020-21 - Q4 2025-26 | Completed: The Data and Analytics Platform project was mobilised in September 2020 and has completed scoping works in March 2021. A strategy paper has been completed, which includes: • Data Roadmap / Investment Plan • High Level information regarding options for the Data and Analytics Systems Architecture • Overall requirements of the new platform, as determined by workshops with subject matter experts. A Digital and Data Strategy was delivered in December 2020 . Foundational requirements of the Data and Analytics platform have been reviewed and prioritised ready for deployment from Q1 2021-22.
1 | Transparency of data used by our ENCC in our close-to-real-time decision making | More clarity of operational decision making | We will continue to engage with stakeholders through our Operational Forums and webinars to find out what data is valuable to them and how we could best provide this. Based on the feedback from our stakeholders, we will share complementary analysis and insight of how we make decisions where required. It is an enabler for our trusted partner ambition. We will continue engaging with stakeholders and industry throughout the year and we will be expanding the data portal offering based on stakeholders’ feedback, to ensure we keep delivering the most beneficial data: Machine readable version of the System Operation Plan (SOP). Improving the transparency of our trading decisions. Data to support better understanding our dispatch decisions. | Q2-Q4 2020-21 | Machine readable version of the System Operating Plan (SOP) went live on 30 September The Super Stable Export Limit (SEL) tool has been created and publication has gone live. A Trading transparency webinar was held and feedback from this has been reviewed. Industry were updated as to plans and progress at the Ops Forum in November and a further update was provided at the Operational Transparency Forum on 9 December 2020. We have now started to publish our historic trades between 2015 and November 2020, IC requirements and auction results, and balancing services contract enactment data. Also GALLEX contract enactments, voltage requirements and any addition system reasons for trades are all being published via the Data Portal. We are currently in the process of reviewing the information for thermal and ROCOF requirements to be able to publish these also. We have started publishing skip rate (now referred to as Dispatch Transparency) data and a supporting methodology under our Forward Plan deliverable “Data to support better understanding our dispatch decisions” on 31 March 2021. The methodology was shared with Ofgem on 28 January. The Dispatch Transparency publication provides details on the reasons actions were taken out of price merit, which therefore supports understanding system needs and how the market operates.
1 | Enhanced customer experience | TOGA replacement | Following stakeholder engagement to understand user requirements, we will be developing the TOGA system replacement. This is the tool that customers and TOs use to request system access | Q3 2020-21 | Completed: Our original proposal was to replace TOGA (Transmission Outage and Generator Availability) with two new systems by w/c 30 Nov 2020: electricity Network Access Management System (eNAMS) and electricity Generator Availability Margin Analysis (eGAMA). eGAMA was successfully delivered and went live on 18 March 2021 as agreed with Elexon, BSC Panel and Grid Code Panel. Ongoing: eNAMS has experienced further delays during User Acceptance Testing (UAT), leading to ESO revising its timeline. Throughout February and March 2021, the Agile project has carried out further project sprints and concluded that go-live with full eNAMS functionality requires further time for the following reasons: • User Acceptance Testing had taken longer than planned due to availability of internal and external users' and time taken to implement corrections to critical functions identified during UAT • Data validation and migration had taken longer than planned due to the need to review and align existing data structures The project has undertaken a re-planning exercise and streamlined delivery to minimise risk of further delays to go-live. The pilot release of some eNAMS functions went live on 9 December, and the final release of eNAMS and Go-Live is planned for week commencing 31 May 2021. Lessons learned sessions have been undertaken for both eNAMS and eGAMA and actions implemented to minimise any further delays.
1 | Upgrade of information systems | Significant upgrading of IT systems to prepare for European Network Codes (priority) | Significant upgrading of IT systems to prepare for European Network Codes | Q3 2020-21 | Completed: We continued to work with industry through the GB TERRE Implementation Group to consider the next steps on TERRE Implementation. The Trade and Cooperation Agreement (TCA) indicates that GB will not have access to EU balancing platforms. This was supplemented in January by guidance from BEIS that, while not ruling out the potential for cross-border balancing in the future, indicated that progressing day ahead agreements was the priority. We have engaged the group on the potential for the ESO leading a cost-benefit analysis on a GB-only Replacement Reserve (RR) product, in line with our previously published scenarios. Feedback from the group is that it may be better to wait until the priority items in the TCA are progressed to avoid any duplication or overlap, and that work on TERRE should be paused. Ongoing: We have discussed the group recommendations with Ofgem and agreed to carry out, via a third party, a CBA on a GB only replacement reserve product. The outcome of the CBA will be used to inform the frequency reform programme and can also be used should future technical agreements with the EU afford. No further work with industry will continue at this stage
2 | Product Roadmaps for Response and Reserve implementation | Implement the first new frequency response product (priority) | Buy Dynamic Containment. | Date is being revised (at the time of publishing the Addendum) | We launched Dynamic Containment (DC) on 1 October 2020 after months of industry engagement, and introduced daily procurement, which is a significant development in our market reform activities under Role 2 within the ESO Forward Plan. Our initial intention of trialling day ahead procurement in the Response and Reserve Roadmap was for early summer 2021, which brings us ahead of schedule in our market reform. Further developments to DC (e.g. procuring high frequency) will be delivered under response reform as communicated in the Markets Roadmap to 2025 document published in March during Markets Week.
2 | Improving the way we facilitate code change | Onboarding process for new industry parties (priority) | Feedback told us that new parties often struggle to understand our processes and find it confusing to know where to look for information. We will deliver the following: • Updating all our documentation and advice on the website for both new and current industry parties, consolidating this information on the website for ease of access and use. This will include different media such as podcasts • Offering in-house training; launching a new induction day for our stakeholders where they can learn more and meet the team. Once established these will be held on a regular basis based on industry need | Q2–Q3 2020-21 | The ESO Code Administration team has now created a comprehensive onboarding page on the ESO website. This was created in direct response to feedback that told us that new industry parties often found it hard to navigate the complexities of the code change process. We have provided simple, easy to read information and clearly signposted where stakeholders can find more information. In addition to this, we wanted to give new parties additional help. We have also conducted two successful onboarding webinars and will look to continue to offer more support to new parties across the next year.
2 | Improving the way we facilitate code change | Improving industry confidence in ESO Code Governance (priority) | Feedback told us that stakeholders lacked confidence in the ESO Code Governance team, with the main issue being that our documentation (that forms the basis of our modification process), was often inaccurate and complex. As a result, we are changing our internal processes, making us more efficient and helping us to write in Plain English. We believe this will help create more confidence in our output and role. We will deliver the following incremental improvements to our service: • Better articulating ESO’s role as Code Administrator in facilitating the change process, enabling all parties to contribute to change and maximizing the delivery of consumer benefit Improvements in how our reports are written, with an ambition to adopt Plain English principles. Reaching a wider audience and better informing them of the changes being developed. A number of deliverables are scheduled: • Skills and capabilities assessed within the team complimented by external Plain English training. All documentation (proposal form, workgroup report, workgroup consultation) updated to simplify the process. • The whole team capable of writing our documents in Plain English reinforced though documented feedback from industry • All web pages refreshed to reflect Plain English style • Conduct proactive engagement with industry to reassess all of our changes to seek further feedback and evaluate the next level of change | Q1-Q4 2020-21 | The ESO Code Administration team has taken on feedback from industry that told us it needed more confidence in us. Since then, we have made our critical friend process more robust. We have undertaken many other improvement activities to help us better facilitate the code change process to be more transparent. Most recently, we created a new process for Panel to prioritise modifications. We feel examples like this where we can provide the right tools and guidance, truly demonstrate one of the ways we are improving industry confidence.
2 | Facilitate electricity network charging reform through Charging Futures | Facilitate electricity network charging reform through Charging Futures | Facilitate electricity network charging reform through Charging Futures 1. Targeted Charging Review (TCR) 2. Access and Forward Looking Charges Significant Code Review (SCR) 3. Reform of Balancing Services Charges | Q1-Q4 2020-21 | We continue to offer a programme of accessible events for parties to learn and contribute to electricity charging reform that our stakeholders have come to expect. Despite COVID-19 we hosted our second virtual forum via webinars in July and the second Balancing Services Charges Task Force published its final report in September 2020. Most recently, we hosted two Charging Futures webinars that received high stakeholder satisfaction scores. Average secretariat score of 9.05 and average event score of 8.4. The speed of delivery is dependent on Ofgem’s decisions so point 2 and 3 will continue to be discussed in Charging Future Forums in 2021.
2 | Transform the customer experience for network charging | Publications and guidance of the impact of charging reform to our customers | Significant reforms to charging arrangements are expected over the 2019–21 timeframe. The Charging Futures project helps to facilitate industry input and guide users through reform. Complementary to Charging Futures, we will provide extra guidance on how this will affect users’ charges in understandable, real terms. Provide industry with regular updates on the changes and impact that TCR will have to processes and deliverables, and ensure that guidance and publications fall in line by Q3 2020-21 | Q3-Q4 2020-21 | There were a number of uncertainties underlying the charging regime, such as RIIO-2 parameter resets and Targeted Charging Review (TCR) implementation. The TNUoS five-year view (21-22 to 25-26) was published on 31 August 2020, which has implemented the TCR changes. To help the industry understand the potential impact from some of the uncertainties, we have also provided sensitivity analyses to help provide a range of outcomes and views on tariffs. The Final Tariffs for 2021-22 were published at the end of January 2021 and the impact of TCR on the 2021-22 tariffs have been outlined in the report. We have published guidance on CMP281 (BSUoS charges for storage), TNUoS modelling for 3-ended HVDC circuits, and the TNUoS onshore locational security factor. We hosted a successful charging forum where we provided some clarity on the significant regulatory changes such as TCR for TNUoS and BSUoS charges. Going forward, guidance documents will be published on the TNUoS generation residual (TGR) and Transmission Demand Residual (TDR) following the related CMA appeal and Ofgem's further decision.
2 | Transform the customer experience for network charging | Introduce new ‘new entrant’ e-learning on charging | Developing and roll-out further training such as webinars and workshops, in addition to publishing guidance documents to help all parties understand charging methodologies, in particular the new TNUoS methodologies introduced through TCR. We aim to complete the following milestones: • Q1: Publish an updated webinar for connection charges • Q2: Publish an updated webinar for BSUoS charges • Q3: Develop workshops on the topics selected by the customers as part of the Charging Forum event • Q4: Publish an updated webinar for TNUoS charges with a focus on new charging methodologies introduced by TCR. | Q1-Q4 2020-21 | We delivered the following milestones as set out in the Forward Plan Addendum: • Q1: Publish an updated webinar for connection charges • Q2: Publish an updated webinar for BSUoS charges • Q3: Develop workshops on the topics selected by the customers as part of the Charging Forum event • Q4: Publish an updated webinar for TNUoS charges with a focus on new charging methodologies introduced by TCR. Q1: We provided industry with a first look of the confirmed/potential impacts of the TCR. In addition to this we have also provided insight into the generation re-zoning which forms part of CUSC modification proposal (CMP324/325). In conjunction with the 2021-22 Forecast TNUoS Tariffs report, we produced a pre-recorded webinar providing further insight into upcoming changes. The recorded webinars for connection charges were rescheduled for Q4. Q2: After the publication of the TNUoS five year view, we hosted a webinar in September 2020 to go through the report and analysis with a focus on the new charging methodologies. Recorded webinars for BSUoS were rescheduled for Q4: this covered the TCR BSUoS changes taking effect in April 2021. Q4: Following the successful Transmission Charging Forum, we have published recorded webinars on connection charging, BSUoS, TNUoS tariff setting and billing on our website.
2 | Transform the customer experience for network charging | Improve the digital customer experience for TNUoS, BSUoS and Connection Charging Data; including improvements to existing NGESO billing system to improve user experience | We are investigating options for updating our systems, and have a clear drive to put customer functionality at the heart of any new products. Our intent is to deliver the following milestones: • Q1: We will complete the review of the current systems, data requirements and the information we currently provide externally, taking into account the TCR decisions. • Q2-Q3: A scope and plan will be outlined, we will look to develop the required changes throughout, by revisiting our scope and seeking feedback to ensure delivery is fit for purpose and meets expectations, both internally and externally. • Q4: We will be looking to enter the implementation phase | Q1-Q4 2020-21 | Completed: With the implementation of the new ESO data portal for the wider ESO, key data and information related to BSUoS, TNUoS and Connection charging have been reworked and improvements to accessibility/ functionality have been made. With these changes, industry and interested parties now have the ability to create direct connections to published TNUoS tariff data through the data portal API function, allowing for real-time data updates. We delivered the following milestones as set out in the Forward Plan Addendum: • Q1: We completed the review of the current systems, data requirements and the information we currently provide externally, taking into account the TCR decisions. • Q2-Q3: A scope and plan was outlined, we looked to develop the required changes throughout, by revisiting our scope and seeking feedback to ensure delivery is fit for purpose and meets expectations, both internally and externally. Due to COVID-19, the priorities have been to assist the industry via two support schemes - TNUoS scheme and BSUoS scheme (CMP345/350). As such, we have experienced delays in the optioneering work. To ensure the timely delivery of the regulatory changes, it was decided to implement the TCR changes in the existing Charging and Billing System. Ongoing: We will be looking to enter the implementation phase. The optioneering work has been completed and the sanction paper is due to be submitted for internal approval.
2 | Transform the customer experience for network charging | Establish a ‘cross party’ approach to onboarding, mapping out whole industry requirements | Work with other industry stakeholders, such as ELEXON and Ofgem, to provide a joint-up onboarding guidance document, mapping out the industry requirements and obligations. • Q1: Agree the approach and scope for the joint-up onboarding guidance with ELEXON • Q2: Engage with customers, seeking their feedback and suggestions on the onboarding process. • Q3: Begin drafting the guidance documents. • Q4: Finalise and publish the guidance, incorporating the finalised new TNUoS and BSUoS charging methodologies. | Q1-Q4 2020-21 | Completed: The key milestones we set out in the Forward Plan Addendum were: • Q1: Agree the approach and scope for the joint-up onboarding guidance with ELEXON • Q2: Engage with customers, seeking their feedback and suggestions on the onboarding process. • Q3: Begin drafting the guidance documents. • Q4: Finalise and publish the guidance, incorporating the finalised new TNUoS and BSUoS charging methodologies. Having engaged and discussed with Elexon, there were several issues highlighted such as who is responsible for the accuracy of the pack and how we can keep the information updated given the amount of frequent changes. It was therefore agreed that the first step is to develop a customer onboarding package from an ESO charging perspective. The Q2 and Q3 milestones were delayed due to lockdown and challenges on industry party resource. However, customer feedback was sought on onboarding guidance through the 2021 Transmission Charging Forum. Ongoing: The initial onboarding pack has been drafted for suppliers (the largest customer category) and is due for new supplier testing by the end of May. The onboarding pack for other customer types will be completed by September 2021. In the pack we signpost the information customers may want to find from Elexon or Ofgem.
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Implement Targeted Charging Review (TCR) decision in conjunction with DNOs | Raise and implement Connection and Use of System Code (CUSC) modifications to support the TCR. The key milestones for delivering the TCR are: • Q1: Working groups complete development of modifications and submit to Ofgem • Q1: ESO to produce preliminary cut of bands • Q1: CUSC and DCUSA modifications approved by Ofgem • Q2: Designated party set final bands • Q4: TNUoS go-live | Q1-4 2020-21 | The key milestones as set out in the Forward Plan Addendum for delivering the Targeted Charging Review (TCR) were: • Q1: Working groups complete development of modifications and submit to Ofgem • Q1: ESO to produce preliminary cut of bands • Q1: CUSC and DCUSA modifications approved by Ofgem • Q2: Designated party set final bands • Q4: TNUoS go-live There were three different sets of TCR modifications: BSUoS, Transmission Demand Residual (TDR) and Transmission Generation Residual (TGR). For BSUoS, we have completed all of the milestones. For TDR, we have completed the development of modifications and submitted them to Ofgem. We have also raised subsequent follow on modifications as requested by Ofgem. We are awaiting a decision from Ofgem to progress the subsequent milestones for transmission band setting. For TGR, we had completed all milestones. The ESO has now prepared follow on modifications as outlined in Ofgem's decision letters. Due to feedback received via TCMF, CMP368/369 modifications were raised in April 2021 following the outcome of the CMA appeal on CMP317/327
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Supporting the Access SCR | Supporting the Access SCR by: • Q1-Q2: Providing modelling for TNUoS related reforms • Q1-Q2: Providing data to feed into Ofgem’s consumer benefit analysis • Q1-Q3: Leading on various elements of the Access SCR subgroups • Ongoing: Supporting Ofgem in their policy development. | Q1 - Q3 2020-2021 Ongoing | We have provided Ofgem with all of the necessary modelling and information for their cost benefit analysis to be undertaken. We will continue to support the Access Subgroup through the creation of papers on focus areas for Ofgem, once work on the Access SCR resumes.
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Lead code modifications | Leading and implementing code modifications on key areas, such as: • Removing distortions between co-located and single technology sites; • Re-design Transmission Network Use of System (TNUoS) generation zones • BSUoS changes, subject to the second balancing services taskforce outcome. The target delivery date for these modifications refers to when the modifications are expected to conclude, including the relevant regulatory decisions. | Q3-Q4 2020-21 | Completed: The codes team have progressed all code modifications relating to the Targeted Charging Review (TCR) and Significant Code Review (SCR). Changes relating to BSUoS charges and TNUoS generation charges as a result of the TCR, have also been approved, although we await Ofgem's decisions on the remaining demand changes. The zoning modification has recently been approved by Ofgem. Ofgem have published their BSUoS taskforce response and as a result we will work with industry to raise changes to develop the arrangements in this space. Ongoing: In terms of other code changes, due to the TCR and other industry congestion, these have moved into RIIO-2 and will be concluded within 2021-22.
2 | Product Roadmaps for Response and Reserve implementation | Consult on future frequency response products (priority) | Consult with the industry on the design of future frequency response products beyond Dynamic Containment. | Date is being revised (at the time of publishing the Addendum) | The delivery dates for Dynamic Moderation (DM) & Dynamic Regulation (DR) were amended to accommodate changes to the Forward Plan in 2020. We intend to develop the new response services in 2021 and launch them by March 2022. We have communicated a delivery plan in the Markets Roadmap to 2025 document, which was published in March, this contains milestones for new product development. We hosted a response reform webinar in April where we discussed DC procurement and development, DM and DR development, the weekly auction trial and key milestones in the delivery plan.
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Balancing Services Charges Task Force | Publication of the second ESO-led balancing services charges task force final report | Q2 2020-21 | The BSUoS taskforce has now concluded and the report published and sent to Ofgem. The taskforce's conclusions support removing BSUoS charges from generators to be paid 100% by final demand and recommend that the charge is fixed in advance by the ESO to remove risk premia from consumer bills. Ofgem have now published their response and we are working closely with them and industry on the next steps. We have raised the required modifications to CUSC as part of this work.
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Capacity Market Modelling - Cross-border participation in capacity markets | Development of a modelling methodology to calculate available capacity for cross-border participation in capacity markets on a consistent basis across Europe. We will be demonstrating our progress with the following milestones: • ENTSO-E (European Network of Transmission System Operators) Task Force begins • Draft methodology will be developed • ENTSO-E consultation. • Methodology will be finalised | Q1-Q4 2020-21 | ENTSO-E have a mandate to develop the methodology under Regulation (EU) 2019/943 as part of the Clean Energy Package, which will help facilitate direct participation of cross-border capacity in the capacity market. ACER published their decision on the cross-border participation in capacity markets on 22 December. We have now reviewed the details of this methodology. We believe that the changes we made to our modelling in 2020 mean we are already consistent with the ENTSO-E methodology, for example the definition of a stress period, modelling European countries in line with their reliability standards (stress periods are defined in the Capacity Market rules as periods when GB experiences loss of load). We also note the positive feedback from BEIS' Panel of Technical Experts in their 2020 PTE Report on the changes we made in 2020. As such, we do not envisage any significant modelling changes are needed to facilitate direct participation of cross-border in the GB capacity market, whenever a decision is taken to implement it.
2 | Making Electricity Market Reform (EMR) easier for participants | Capacity Market (CM) Modelling – facilitating broader participation in the CM to provide security of supply at best value for consumers | Investigate the various sources of technology type and capacity data that would enable a robust method to be developed and implemented into the future. Dependent on the investigation, improved methodology may be developed. DCUSA approve DCP350 and recommend it is approved by the Authority. Expect the Authority to approve the modification. Expect data to be published. We will then need to assess, process and analyse the data to determine potential options for evaluating embedded generation de-rating factors directly from embedded data. Agree with BEIS, Ofgem and the Panel of Technical Experts (PTE) on whether it is appropriate to change how we determine de-rating factors for embedded generation using this data. Consult on potential changes with industry as required in the Capacity Market rules. Implement for the 2021 Electricity Capacity Report. Note – The indicative timeline may be revised when we develop and agree project scopes with BEIS, Ofgem and the PTE as part of the EMR development project process. We will provide updates to the industry via the Forward Plan tracker. | Q1-Q4 2020-21 | ESO have been supporting a DCUSA Change Proposal referred to as DCP350 to create a register of embedded assets. This was approved by DCUSA in May 2020 and by the Authority on 1 July 2020. The first version of the data was published in July 2020. We intended to use this data to improve our modelling of embedded generation for the capacity market, which may lead to a change in how we determine de-rating factors. We assessed the data in the Electricity Capacity Registers in conjunction with metred hourly output data that we had already acquired from Electralink. This assessment was discussed and scrutinised by BEIS, Ofgem and BEIS Panel of Technical Experts within the capacity market modelling process. The outcome of the assessment concluded that the data quality was not good enough to be able to develop an alternative, robust de-rating factor method. We are continuing to work closely with the DNOs to improve data quality and we are intending to publish the analysis to-date in Q1 2021-22.
2 | Delivery of the Power Responsive initiative | Support coordination of Distributed Energy Resource (DER) engagement on flexibility developments | Facilitate constructive dialogue between the demand side community and ESO subject matter experts in the development of flexibility products and markets. | Q1-Q4 2020-21 | We worded with Everoze to deliver the Annual Report for 2020 , which was published on 1 April 2021. We are also continuing to work with Piclo and Electron local market trials. At the Steering Group in January we brought experts from Market Change Delivery and Grid Code teams to discuss their work on reforming reserve products and delivering code changes on emergency disconnection.
2 | Delivery of the Power Responsive initiative | Power Responsive Stakeholder Engagement | Promote industry developments for demand side flexibility and facilitate feedback to shape ESO deliverables through a range of engagement activities. These will include conferences, working groups, webinars, consultations, editorials, training sessions and reports. | Q1-Q4 2020-22 | We have progressed with virtual events such as the Major Energy Users’ Council (MEUC) webinar session on 14 October 2020, and the Energyst Event in November.
2 | Product Roadmaps for Response and Reserve implementation | Report on auction trial (priority) | Status update on the success of trial, learnings from the first six months and how these are informing future developments. Trial separate procurement of low frequency (LF) and high frequency response (HF) services. Publish plan for day ahead procurement and consult on enduring auction design. | Q1-Q3 2020-21 | Complete with changed format: we have published the status update, implemented separate procurement of Low Frequency (LF) and High Frequency (HF) as part of Dynamic Containment (DC), and have begun day-ahead procurement as part of DC. In Q3 2020-21 we hosted 1:1s with auction trial participants to seek feedback on the trial. Using that feedback, and analysis of the trial to date, we published a report reviewing progress and learnings from the auction trial. In addition, we launched multiple user functionality, published a user guide for active participants, shared a unit ID mapping table for industry to have visibility of units taking part in the trial and the monthly FFR tender. In response to stakeholder feedback we also published a document explaining merit orders. We have removed the separation of LF/HF from the trial and instead implemented it in the delivery of DC. DC LF was delivered in October 2020 and plans are in place to deliver DC HF in autumn 2021. We previously committed to planning for and trialling day ahead procurement and running residual auctions under the auction trial. DC took on day ahead procurement, and we no longer see benefit in the residual auction, which was supported in the independent review of the trial, which we published in September. The feedback from providers, learnings from the trial to date, coupled with our experience of day ahead procurement of DC will shape the development of the enduring auction platform. For more information please listen to the auction platform podcast recorded in March 2021 for Markets Week.
2 | Product Roadmaps for Reactive implementation | Publish our strategy for the future of reactive power (priority) | Strategy outlining how we will look to integrate learnings from all reactive power projects (pathfinders, Power Potential, DNO boundary investigations) to create a coherent plan for the development for the future of reactive power. Procurement publication, communicating the next steps on reactive procurement. | Q3 2020-21 - Q2 2021-22 | We have introduced the 6-step approach that is being used to review and develop 'Future of Reactive Power', the first round of industry engagement was completed, which included meetings with some individual stakeholders and a webinar in December 2020, to share what the reactive power issues are and the current observations/learnings from existing projects (Pathfinder, Power Potential, network boundary transfer etc). The second Industry webinar was held on 31 March, introducing the plan and scope of work, and our intention to start designing and analysing the reactive power market next. A Market survey was launched on 2 April 2021 to help us understand the potential size of the market and the general interest from industry.
2 | Product Roadmaps for Response and Reserve implementation | Market design and implementation plan for reformed reserve products (priority) | Deliver a proposal for reformed reserve products, including detail of how they will interact with both new frequency response products and pan-European Standard products (Trans European Replacement Reserve Exchange (TERRE) and Manually Activated Reserves Initiative (MARI), as well as other elements of Electricity Balancing Guideline (EBGL) and the recast Electricity Regulation, and a plan for implementation. Increase competition and transparency in the procurement of fast reserve. Consult on strategy for more competitive procurement of optional fast reserve. Study impact of completed reforms and consult on further development of reserve services. | Date is being revised (at the time of publishing the Addendum) | The reserve product reform consultation was published on 4 March 2021, with responses requested by 2 April 2021. We are now engaging with industry groups such as ADE, Energy UK and the FGG.
2 | Product Roadmaps for Response and Reserve implementation | Support development and implementation of Pan-European replacement reserve standard products (priority) | Support development and implementation of Pan European standard products TERRE and MARI to allow Great Britain parties to participate. TERRE go live. MARI external milestones we are following: • Grid Code and Balancing and Settlement Code changes • Start of parallel run • Go live | Q1-4 2020-21 | Completed: After leaving the European Union we now have a Trade and Cooperation Agreement (TCA) with our EU partners. BEIS have written two letters to NGESO. Unfortunately, in the area of balancing, these do not add further detail to what we have in the TCA. As a result, after consultation with Ofgem and the wider industry, we have put TERRE on hold, and we have withdrawn our Grid Code and BSC mods on MARI. We have also informed the central European projects that we are changing our status on TERRE and MARI from Member to Observer. Ongoing: On TERRE we have committed, via the TERRE Implementation Group, to a cost-benefit analysis looking at a GB only standalone version.
2 | Product Roadmap for Reactive implementation | Power Potential trial with UKPN (priority) | Innovation project in partnership with UKPN aiming to create a new reactive power market for Distributed Energy Resources (DER) and generate additional capacity on the network. | Q3-Q4 2020-21 | All Power Potential trials, Technical and Markets have now been completed with the latter closing out on 28 March 2021. The project team is currently compiling the learning from the project within a number of SRDC (Successful Delivery Reward Criteria) reports focusing on Cost Benefit Analysis, Technical and Commercial Trial Results, and DSO Risk / Reward. These will be submitted to Ofgem through April and May in advance of a project closure report and a final stakeholder meeting (RMAP).
2 | Product Roadmap for Reactive implementation | Review learning from Power Potential (priority) | Learnings to inform whether to procure reactive power services from DER and if so, how to do so in partnership with DNOs. | Q3-Q4 2020-21 | As part of the project closure processes the project team shared key learnings from Power Potential with key inter-related projects. These include both the RDP programme, that is working directly with DSO / DNOs, and the "Future of Reactive" project that is considering the development of wider reactive power and voltage control markets.
2 | Improving the way we facilitate code change | Customer focussed communications (priority) | Feedback from stakeholders has clearly stated that communications from the ESO Code Administration team could be improved upon. In a dynamic and resource stretched landscape, it is essential that people who want to engage with the modification process gain clarity on our role, as well as find accurate and updated information. We will progress the following deliverables: • Launching easier to read industry emails with a subscription tool that enables users to quickly manage their communication preferences • Publish a Code Administrator annual report; a report for our stakeholders providing more detail on how we’re performing, our improvements and what changes mean for them | Q1 2020-21 | An email subscription tool has now been implemented alongside easy to read emails. The first Code Administrator Annual report has also been published on our website in direct response to stakeholder feedback asking us for more transparency.
2 | Power Responsive | Deliver innovation projects to unlock demand flexibility | Work with industry stakeholders through collaborative projects to understand the role of smaller scale assets and technology innovation in unlocking greater flexibility, to identify and unlock barriers to entry and maximise opportunities for accessible, competitive markets | Q2 2020-21 | The Residential Response Network Innovation Allowance (NIA) Project has now concluded, as has the United Utilities project Enhancing Flexibility from Wastewater Catchment Areas.
2 | Improving the way we facilitate code change | Incorporation of all 14 Code Administrator Code of Practice (CACoP) Principles | Adoption of all 14 CACoP principles in a robust manner whilst supporting the development of modifications. | Ongoing | Two modifications were raised in March 2020 to facilitate the 14th CACoP principle; sandboxing. Due to congestion from high priority modifications, they were given a low priority. The modifications will proceed in line with Panel’s decision on where they sit in terms of a priority against other modifications. We anticipate that this will not be progressed with any urgency at this stage. We therefore do not have any control over the speed in which it progresses. An email subscription tool has now been implemented alongside easy to read emails. The first Code Administrator Annual report has also been published on our website in direct response to stakeholder feedback asking us for more transparency.
3 | Whole system operability | Accelerated Loss of Main | Lead the Accelerated Loss of Mains programme and provide assurance of value for money via quarterly performance reporting in June, September and in subsequent quarters subject to the need for programme continuation. Review and update the methodology for how we intend to procure balancing services from Distribution Network Owners (DNOs) to enable RoCoF and vector shift changes. | Q2 2020-21 and ongoing | Over 12.9GW of generation at 6,709 sites have now applied to the programme, with changes already made at sites with a combined capacity of over 9.2GW. The addition of generators contacted and known to have achieved compliance takes the total engaged to 16.3GW, or 61% of total generation capacity within scope. The programme is on track to address risks associated with Vector Shift (VS) protection in line with expectations and our forecast expenditure on Vector Shift Risks for 2021-22 is now zero. The benefits associated with Rate of Change Frequency (RoCoF) risk reduction are expected to be seen progressively over 2021 and we have taken action to bring this forward as much as possible, with enhanced payment arrangements in place, increased engagement and enhanced risk assessment. Programme priorities have been agreed for the next 18 months and efforts continue to bring more distributed generators into the programme. Applications rates picked up as a result of increased engagement activity with 1.7GW of applications approved in Window 6 compared to 1GW in the previous window.
3 | Regional Development Programmes (RDPs) | Development of commercial arrangements for Transmission Constraint Management (TCM) service from DER | Commercial arrangements for DER TCM scoped with UKPN Delivery plan for DER TCM within UKPN RDP area published Commercial arrangements for DER TCM scoped with WPD Delivery plan for DER TCM within WPD RDP area published | Q2-Q4 2020-21 | Initial design workshops, held with both UKPN and WPD, have been successful in defining the project phases and overall scope. These workshops have also focused in on the core elements of the commercial arrangement that will now be further informed by stakeholder feedback. Learning from these workshops will continue to be disseminated through our monthly Joint DNO Forum. We have now also published our updated RDP Fact Sheet on the NGESO website, which has been endorsed by all GB DNOs and the ENA. In addition, the '2025 - Road to Net Zero' publication contains information on our delivery plan for both the DER TCM projects with respective DNOs. IT development of TCM services in UKPN and WPD areas has now commenced and is progressing as planned to delivery in 2022-23: see RIIO-2 Delivery Schedule D15.5.1 and D15.5.2.
3 | Regional Development Programmes (RDPs) | Co-ordinated DER inter-tripping functionality for transmission fault management. Including completion of work with WPD and UKPN | Delivery of N-3 inter-tripping of DER with UKPN Delivery of N-3 inter-tripping of DER with WPD Delivery of communication link between NGESO and SSE-N | Q2-Q4 2020-21 | Completed: Co-ordinated DER intertripping functionality is now in service in the UKPN south coast area. Ongoing: Due to the volume of remaining NGET transmission outages required to complete the N-3 work with WPD and SSEN, we have not been able to deliver this capability during the 2020-21 financial year. We explored alternative methods of delivery with NGET earlier in the year, however, due to the additional complexities of an incremental delivery, it was unlikely to deliver any benefits over the original approach. NGESO is now focussing on progressing the elements of delivery that can proceed with both SSEN and WPD, in lieu of the completion of the outstanding transmission outages. We are aiming to begin exchanging data via the ICCP links in July 2021, with completion of the remaining outages by November 2021 and full end-to-end commissioning by January 2022.
3 | Regional Development Programmes (RDPs) | Develop the Generation Export Management Scheme (GEMS) in South West Scotland to manage transmission constraints | Integrate SPEN ANM management of local constraints with NGESO management of wider transmission constraints. High level design of NGESO commercial systems to interface with GEMS Detailed design of NGESO commercial systems to interface with GEMS Commercial contract structure for DER TCM scoped with SPEN | Q2-Q4 2020-21 | Completed: NGESO has completed significant design work over the course of the last year to ensure the required documentation is ready for the procurement of the GEMS technical solution with SPT. In addition, good progress has been made across all GB DNOs to ensure a consistent approach is derived for the commercial contract structure for DER, in line with the ongoing RDP Design Workshops and the latest ENA Open Networks work in this area. The majority of the work to integrate the SPD ANM into business-as-usual processes has been completed. Ongoing: GEMS development work will continue as planned through to commissioning in 2022-23, There are some areas of the Active Network Management (ANM) integration that require finalisation. This is not currently delaying the deployment of the ANM solution across SPD's network although we are striving to resolve these areas during April.
3 | Whole System thought leadership | Support BEIS and industry in developing a strategy for clean heat | Hold meetings at least quarterly to advise BEIS on the implications of clean heat pathways for the operation of the Whole Energy System. Develop a fuller understanding of how the Whole Energy System might be operated under different clean heat pathways; working with the Gas System Operator. Share and test thinking on Clean Heat pathways with networks and industry. | Q1-Q4 2020-21 and Ongoing | We met with BEIS at least quarterly throughout the year. We continue to discuss whole energy system matters with the system operation teams in National Grid Gas Transmission (GSO) in the context of our ongoing stakeholder engagement on energy policy. No formal project was taken forward in 2020-21 as our teams are focused on understanding the longer-term direction of the ESO in the context of the Ofgem review of system operation and the Energy White Paper. We published a thought piece about the implications for system operation of clean heat pathways on 16 November 2020 and held a webinar on 8 December 2020 to get industry feedback on the thought piece.
3 | Whole System thought leadership | Active engagement in the development of DSO and co-ordinated flexibility markets including cross-sector considerations | Active input into the Open Networks 2020 project including leading the Whole Energy System workstream and associated CBA product. In this workstream will continue to ensure a cross-sector representation including non-network stakeholders. Active engagement with Ofgem’s work on DSO and the development of a DSO framework for RIIO-ED2 | Q3 2020-21 | The ESO has been actively involved in all ENA Open Networks workstreams and at the Steering Group meeting. We have led the project's Whole Energy System workstream and the associated whole system CBA deliverable. We have also led on the procurement processes deliverable in the project's flexibility workstream. We have been involved in the development of the DSO framework for RIIO-ED2 and have begun to engage with DNOs to ensure our activities align with their proposed works. We have also engaged with broader DSO policy developments such as responding to Ofgem's call for evidence on the visibility of distributed generation connected to the GB distribution networks.
3 | Network value assessment tools | Voltage needs identification tools/ processes | Document and test voltage needs identification tools / processes for inclusion in the NOA methodology. Identify up to three areas for further evaluation. | Q4 2020-21 and ongoing | Developed Historical Data Mining Tool and completed initial view on potential next priority regions for high voltage assessment. Initial outcome of voltage needs identification process was published at the end of June 2020. Additional tools developed: • Power Uncertainty Year-round Analyzer (POUYA) - A tool to do year-round probabilistic assessment of the GB network to cope with the increasing uncertainties arising from renewables. • An additional module in Python for POUYA to assess year-round losses and CO2 calculation for Ten Year Development Plan (TYNDP) projects. • Voltage optimization - Python based tool to assess future reactive power requirements. • Voltage pathfinder option testing - A DIgSILENT Programming Language (DPL) script to test high number of voltage solution options combinations and flag any compliance issues • Stability Pathfinder option testing - A DPL script to calculate the fault infeed for different options and topologies submitted to the Stability Pathfinder • Voltage screening tool - allows us to visualise the recent frequency of use of voltage control equipment and cost of actions taken to resolve voltage issues on the system in operational timescales.
3 | Enhanced customer experience | Continue to work with Customers and Network Owners to understand requirements and scope of system wide single platform to provide online account management and connection application functionality | Detailed scoping of tool to provide a visual and live update for customers on the progress of their connection application. | Ongoing, due to be completed in 2022 | Discussions with Customers and Stakeholders regarding scope of Portal completed in January 2020. We did intend to engage on further discussions to identify functionality, but the TOs have accelerated their portals and have now physically launched them. From the products the TOs have launched, and the work we did with industry last year, we now know what is required from the ESO portal. Work on the ESO portal has now commenced with project planning and scoping activities being progressed.
3 | Insight documents | Operability Strategy Report | Provide a view of current and future operability challenges, to help inform stakeholders’ investment strategies, and commercial and operational plans. | Q3 2020-21 | The frequency of this report has changed to annual (rather than every 6 months) to align with our other publications. The report was published in December 2020.
3 | Insight documents | FES: Bridging the gap to net zero | Taking the key messages from the 2020 Future Energy Scenarios, identify and progress the actions that need to happen to meet the net zero target. This work will be informed by feedback from the 2019-20 performance year of our FES: Bridging the gap to net zero project. | Q3-Q4 2020-21 | Starting in September 2020, we engaged with a wide range of external stakeholders about how markets, technology and data and digitalisation can help the energy industry manage the challenges of increasing numbers of peaks and troughs due to greater decarbonisation. We held four webinars and ran three working groups, which resulted in a set of key recommendations and actions for the ESO, industry and policy makers. The final report was launched on 4 March to an external audience via a webinar. It was also published on our website.
3 | Whole system operability | Address actions raised in the E3C report into the GB Power Disruption Event of 9 August 2019 | The E3C report into the GB Power Disruption event of 9 August 2019 identified a number of actions to be addressed by the industry. These are delivered through the Electricity Task Group. | Q1 2020-21 | We progressed and completed NGESO actions identified by the Ofgem and E3C reports following the power outage of 9 August 2019, including completing an internal audit, conducting a review of the current Limited Operational Notification (LON) and Grid Code derogation processes, and implementing the improvements identified by these reviews. As agreed we have raised Grid Code modification GC0141 which is now under industry process, and SQSS modification GSR027 on frequency standards which has been approved by the Authority and is now awaiting final approval from Ofgem for implementation of the new SQSS requirements.
3 | Insight documents | Summer Outlook | We will publish this in conjunction with the corresponding National Grid Gas Transmission publication, providing our data and analysis for the upcoming summer. | Q1 2020-21 | Complete: Published April 2020: https://www.nationalgrideso.com/document/167541/download
3 | Insight documents | Winter Outlook | We will publish this in conjunction with the corresponding National Grid Gas Transmission publication, providing our data and analysis for the upcoming winter. | Q3 2020-21 | Complete: Published October 2020: https://www.nationalgrideso.com/document/178126/download
3 | Insight documents | Winter Review and consultation | We will publish this in conjunction with the corresponding National Grid Gas Transmission publication, providing data and analysis relating to the previous winter | Q1 2020-21 | Complete: Published 24 June 2020: https://www.nationalgrideso.com/document/171986/download
3 | Insight documents | Future Energy Scenarios (FES) | Provides our range of credible scenarios for the future of energy to support the planning of the Great Britain transmission system supported by continued, varied and wide stakeholder engagement and research. In Q2 we will produce the FES publication with the supporting data workbook, hold the FES conference and executive briefing, and publish a call for evidence. Stakeholder engagement will happen throughout the year in the form of bilaterals, workshops, webinars, videos and thought pieces. We are also planning on delivering more information on the costing of each scenario pathway following the FES publication. | Q2-Q3 2020-21 | Complete: Report published July 2020. https://www.nationalgrideso.com/document/173821/download The Launch conference for stakeholders was shifted to a virtual event online. This year we have designed the FES report to be digital first, reducing our environmental footprint and making the overall length of the document 25% shorter, whilst including broader analysis and new sections on whole system flexibility not previously covered by FES.
3 | Whole system operability | Implement approach for efficient reactive power flows between networks | Having worked with network owners to design a whole system approach to managing reactive power flows between networks, implement that approach. | Q4 2020-21 | Conclusion of this work was indirectly impacted by changes in working arrangements brought about by COVID-19 related restrictions and was de-prioritised relative to other deliverables where workload had ramped up. Our analysis has indicated that it is unlikely that a generic conclusion on an optimal exchange of reactive power can be drawn, and therefore we are focusing instead on market-based solutions using cost-benefit analysis, such as the ongoing voltage Pathfinder projects and wider reactive power market reforms to explore a better way of managing future voltage issues. This year, we focussed instead on refining the Pennine reactive power requirements, where there was an opportunity to benefit consumers, as outlined in our role 3 case study. Future work on the choice of reactive power solutions will concentrate on wider reactive power market reforms.
3 | Pathfinder Projects | Stability pathfinder (priority) | Assessing a range of commercial and network solutions to meet system stability needs. When we refer to stability in this context we are talking about the stability of frequency, voltage and the ability of a network user to remain connected to the system during normal operation, during and after a fault. We will develop and test processes to define requirements of transmission system stability needs, focussing on dynamic volts, inertia and fault levels as an indication of system stability requirements. Working with other network organisations we will develop and test processes to obtain and evaluate options to meet the requirements set out through technical and economic assessment. | Q2 2021-2022 | Completed: We launched the Stability Pathfinder Phase 2 RFI on 17 June 2020. We held an RFI webinar on 25 June 2020. Webinar recording and FAQ document is available on our website. We published RFI summary feedback and next steps on 19 August 2020 which included a timeline for Phase 2 tender process. Expression of Interest was published on 30 September 2020 seeking short circuit level and inertia services up to 2030. We have run a series of webinars in October & November. Milestones for phase 2 of the Stability Pathfinder are as follows: • Q2 Invitation for Expressions of Interest which was published in September • Q3 Publish draft commercial terms which was published in October • Q4 Commence technical feasibility studies published in March 2021 following EOI outcome • Q4 Publish final commercial terms (will be published end of May 2021) The NOA methodology was updated in July 2020, in line with our licence obligation which incorporated any lessons learnt from Phase 1 which was completed in January 2020. Ongoing: We will publish a further update to the NOA methodology next year, incorporating learnings from the Stability Pathfinder phase 2.
3 | Pathfinder Projects | Mersey Voltage pathfinder: Project recommendations (priority) | Working with other network organisations we will conduct post tender evaluation through NOA based criteria and assessment to determine the best combination of asset and commercial solutions for meeting the regional high voltage needs. This will develop the necessary contract arrangements to facilitate participation by new and existing providers. | Q1 2020-21 | On 22 May 2020 the ESO awarded 9-year contracts for static voltage support in the Mersey region to PeakGen (200 MVAr Reactor) and Zenobe (40 MVAr of reactive capability from battery storage). These contracts are worth a total of £8.67m and are due to commence from April 2022. This Pathfinder is the first time that we have directly compared market solutions to a TO network asset build approach for a long-term transmission level requirement. An update to the tender results and lessons learnt report was published on 11 December 2020. We have also confirmed the contracts signed to address the short-term Mersey voltage needs on 19 March 2021. This confirmed that the contract strategy was informed by the results of EOI that highlighted that other parties were unable to meet the technical requirements or timescales.
3 | Pathfinder Projects | Pennines Voltage pathfinder (priority) | Subject to reviewing whether it is in the interest of consumers to progress the Pennines Voltage Pathfinder at this time, we will publish the invitation to tender and award contracts to successful parties. We will continue the high voltage project in the Pennine region to also consider market based solutions, include commercial solutions and further develop the necessary funding mechanisms to facilitate the participation of DNO solutions. | Q2-Q4 2020-21 | An update on the Pennine tender was published on our website on 29 January 2021. We published an invitation to tender on 26 March 2021. The tender is expected to last up to 40 weeks with an outcome no later than January 2022 for contract start in 2024. Over the last two months we have been able to simplify and reduce levels of interactivity across the Pennine and North of England region such that we can tender for two distinct sub-regions. We are tendering for a minimum of 700MVAr across the 2 regions, and the tender is open to both new and existing connections at transmission and distribution levels, including aggregators. We have been working with the transmission owner (TO) NGET to identify site-specific information; this is available to industry on request. We have also defined and agreed the scope of studies with the DNOs who will assess any solutions that fall within their areas as part of the tender.
3 | Pathfinder Projects | Constraint Management Pathfinder (priority) | The aim of this project will be to provide a commercial product based around constraint management. We will analyse the impact of constraint services in an attempt to alleviate network congestion, reduce balancing costs, and deliver greater value to Great Britain consumers as the electricity network evolves. | Q1 - Q2 2020-21 | We delivered on our target we set in the Forward Plan of providing a response to the market of a tender for an intertrip service. From then, we provided the market more information on the service on the service design, how participants will be able to take part and a timeline of the overall process. The Constraint Management Pathfinder has now progressed to running an Expression of Interest (EOI) as per the timeline and is inviting already connected generation to participate in the service we announced further details in December 2020. During the six-week window we are hoping for generation connected to the Scottish transmission network to enter a feasibility assessment to be pre-qualified and entered into a commercial tender. Successful tenders will be able to deliver the service from as early as 1 October 2022 onwards. The ESO is also working with the TO to build intertrip channels to connect the providers so effectively, the generator would declare an interest and the ESO would work with the TO to facilitate the rest. This is the first time the ESO will be running a commercial tender to procure intertrip volume.
3 | Early Competition | Early Competition plan setting out implementation for models (priority) | Consult with industry on detailed models for Early Competition Provide written update to Ofgem on progress to date Consult with industry on Early Competition Plan (including models, roles and implementation) Provide written update to Ofgem on progress to date Submission of final Early Competition Plan to Ofgem | Q1-Q4 2020-21 | Throughout the year we have been working closely with stakeholders to develop a model for early competition. We have had to adapt our approach to engagement due to the COVID-19 pandemic, moving to virtual workshops rather than face to face. We have developed our proposals iteratively using two formal consultations to seek views in addition to targeted workshops. We have also established robust governance for the project including setting up our ESO Networks Stakeholder Group (ENSG) to provide challenge on our approach to stakeholder engagement and how we have taken the feedback received on board in developing our proposals. There are also areas where we have had constructive feedback and have responded to this by extending our second consultation window to 10 weeks (first one being 6 weeks) and held an additional workshop with industry stakeholders on the approach of a TO counterfactual in March. We submitted our final plan to Ofgem at the end of April. This includes some modifications to our proposals following responses to our Phase 3 consultation. This was accompanied by a report from the ENSG on our stakeholder engagement. Feedback from the ENSG has been positive on our engagement approach and our willingness to take on board and act on feedback. We will also be holding a webinar on our final plan for stakeholders in May.
3 | NOA: Enhanced communication | Improve accessibility of ETYS and NOA publications (priority) | We will enhance the information that is provided on system needs to allow a wider audience to better understand needs and propose solutions to meet them. We will continue to engage with stakeholders on the development of capabilities and implementation of the Network Development Roadmap. Publication of needs to the market through RFI packs, which are supported by webinars. Enhancements to information in ETYS, to include requirements for a wider set of system needs and more detail on existing system needs. Provide regular updates to stakeholders on the progress of pathfinding projects and continue engagement with impacted stakeholders through mechanisms such as the ENA Open Networks project. | Ongoing | As a result of feedback we have received, this year we intend to make it clearer how the content for both of these publications applies to our stakeholders. We are also intending to reach new stakeholders and make the publications accessible and relevant to them by trying to answer the "so what?" question. We have published ETYS online and have replaced the single document with an interactive web version. Our stakeholders can provide feedback directly to us via the website which means we can seek to respond quickly. We can also learn from what interests our stakeholders using this approach and provide them with more relevant information in future publications.
3 | Whole System Operability | Defining roles and responsibility for voltage management across the transmission distribution interface (priority) | Working with DNOs to optimise voltage on a whole system basis: • Short-term operational solutions • Transmission – distribution reactive power performance measures | Q3 2020-21 | This deliverable was being progressed alongside the development of the approach for efficient reactive power flows between networks. Conclusion of this work was indirectly impacted by changes in working arrangements brought about by COVID-19 related restrictions and was de-prioritised relative to other deliverables where workload had ramped up. Any necessary planning process changes relating to voltage management across the transmission-distribution interface will be taken forward by extension of the business as usual process.