## Tracker 20-21
This information is correct as of |  | 2020-06-19
Role | Title | Deliverable | Description | Baseline Delivery Date | Commentary
1 | Upgrade of information systems | Produce plan for widening access to API (Application Programming Interface) system (Priority) | Review the scaling requirement for the API system based on current and forecasted volumes in the market. If required, we will produce a plan which sets out proposals and timescales for widening access to the web based API and any associated code and policy modifications which will be required to facilitate this. | Q1 2020-21 | Scaling requirement is an ongoing process in terms of volumes. Codes changes being progressed for implementation of greater MW volume per units register ( Q3 2020-21 Grid Code Change)
1 | Upgrade of information systems | Expand dispatch facility to handle a large number of small Balancing Mechanism Units, subject to market take-up | Currently, our dispatch system can accommodate up to 100 small units. We plan to scale this, such that by the end of September it can accommodate a larger number of units. We will keep the scale of this expansion under review, depending on how many Virtual Lead Parties (VLPs) come forward to participate. Creation of additional data storage capability for existing BM dispatch system Complete the design stage for re-platforming our existing multi-dispatch tool Replacement of existing dispatch optimiser with modern optimiser with capability to solve for more complex scenarios, including a larger number of small BM units Re-platforming our existing multi-dispatch tool delivery. This will fully integrate the current interim process for bulk dispatch of Balancing Mechanism Units (BMUs) into control room systems. This will reduce our manual processes, and make it easier for the ENCC to dispatch a large number of small BMUs at once. | Q1-Q4 2020-21 | On track.
1 | Upgrade of information systems | Interconnector programmes | Continued integration of interconnectors into operational systems. Before an interconnector begins commercial operation, there are a range of IT systems which need to be updated, and for each system there are milestones which need to be completed: requirements, design, development and testing, implementation, and closure. During 2020-21, we will work on IT changes for Eleclink, IFA2, and NSL- but the precise timing of the phases will depend on the go-live date for each interconnector, which can be changed by the interconnector owner. We will hold regular meetings to collect customer feedback and carry out satisfaction surveys to measure our performance. | Ongoing | On track.
1 | Upgrade of information systems | Platform for Energy Forecasting (PEF) (Priority) | Produce updated version of Energy Forecasting Strategic roadmap. The previous version, from June 2019, is published on our website . We will publish additional energy forecasts to the market: 2-14 days ahead national demand forecast 2-52 weeks ahead national demand forecasts Within day-14 days wind power forecasts | Q1-Q4 2020-21 | On track.
1 | Upgrade of information systems | Design Authority | We will launch the Design Authority (DA) in Q3 2020-21, in preparation for RIIO-2. | Q3 2020-21 | On track.
1 | Upgrade of information systems | Improving information access (Priority) | Foundation work for data analysis platform, involving auditing current data flows and designing new platform for RIIO-2. Make all published ESO data available via the ESO data portal | Ongoing | On track.
1 | Transparency of data used by our ENCC in our close-to-real-time decision making | More clarity of operational decision making | We will continue to engage with stakeholders through our Operational Forums and webinars to find out what data is valuable to them and how we could best provide this. Based on the feedback from our stakeholders, we will share complementary analysis and insight of how we make decisions where required. We will continue engaging with stakeholders and industry throughout the year and we will be expanding the data portal offering based on stakeholders’ feedback, to ensure we keep delivering the most beneficial data. | Q2 – Q4 2020-21 | Stakeholder engagement at Ops Forum on hold due to COVID outbreak. Otherwise on track.
1 | Transparency of data used by our ENCC in our close-to-real-time decision making | Publishing the BMU ID for trades | We will take forward the recommendations of the P399 industry working group modification and publish information to the market about the trades we carry out. We will proactively work with our stakeholders to publish data in an accessible format using the API technology. | Dependent on P399 code change | No working group meeting scheduled due to current conditions.
1 | Support access for Intermittent Generation | Deliver second phase of Power Available integration | Phase 2b of Power Available (PA) is a continuation of the existing PA project to integrate the PA signal into the Control Room to enable greater use of wind for Mandatory Frequency Response (MFR). This will improve wind forecasting and response optimisation by blending PA with weather forecasts to provide a real time measure of output for wind units. | Q3 2020-21 | First phase roll-out having difficulties, meaning phase 2 of PA will be pushed to Q4
1 | Support access for Intermittent Generation | Implement State of Energy signal | Define and implement a state of energy signal from limited-energy assets into the Control Room to give visibility of the remaining energy in limited-duration assets, such as batteries. | Q4 2020-21 | Builds on the work of PA, so delays in that project cascade into the state of energy signal project. To be updated in the Forward Plan addendum.
1 | Whole system operability | Inertia measurement | Implement novel tools to measure system inertia in real-time which will significantly improve the accuracy and optimise the ESO’s real-time operation, service procurement and network development with the increasing number of embedded generators. It is essential to measure the full system inertia from both the transmission and distribution sides. | Q2 2020-21 and ongoing | On track.
1 | Product Roadmap for Restoration implementation | Deliver competitively tendered black start contracts | Award contracts to successful parties for South West/Midlands tender Award contracts to successful parties for Northern tender Carry out preparatory work for future tender opportunities in South East, in preparation for tender event in Q1 2021-22. | Q2–Q4 2020-21 | The tenders are running as expected.
1 | Electricity Operational Forum and stakeholder engagement | Electricity Operational Forum | This stakeholder event takes place three times a year to provide operational information. | Q2, Q3 and Q4 2020-21 | On hold during lockdown
1 | Electricity Operational Forum and stakeholder engagement | ENCC visit days | Monthly open door to market participants to the ENCC to learn about system operation. | Q1-Q4 2020-21 | On hold during lockdown
2 | Product Roadmaps for Response and Reserve implementation | Implement the first new frequency response product (priority) | Buy Dynamic Containment. | Q1 2020-21 | ESO experts working on Dynamic Containment have been redeployed to solve short-term operability challenges caused by low demand. We intend to engage further on DC when the project team reconvenes and we will continue to share updates via the Future of Balancing Services newsletter and our website.
2 | Product Roadmaps for Response and Reserve implementation | Consult on future frequency response products (priority) | Consult with the industry on the design of future frequency response products beyond Dynamic Containment. | Q1 2020-21 | We assume that disruption will continue during the months ahead and as we aren’t quite clear on the impact on the full breadth of our activities and the energy industry just yet, we haven’t currently changed the delivery dates of the roadmap. However, we will be constantly reviewing our project plans taking into account changing priorities for the ESO and the time our stakeholders need to engage and take part in new services
2 | Product Roadmaps for Response and Reserve implementation | Report on auction trial (priority) | Status update on the success of trial, learnings from the first six months and how these are informing future developments. | Q2 2020-21 | We are on track to share our learnings with industry in Q2 2020-21.
2 | Product Roadmaps for Response and Reserve implementation | Publish our strategy for the future of reactive power (priority) | Strategy outlining how we will look to integrate learnings from all reactive power projects (pathfinders, Power Potential, DNO boundary investigations) to create a coherent plan for the development for the future of reactive power. | Q3 2020-21 | We are on track to share a high level strategy on reactive power with industry in Q3.
2 | Product Roadmaps for Response and Reserve implementation | Market design and implementation plan for reformed reserve products (priority) | Deliver a proposal for reformed reserve products, including detail of how they will interact with both new frequency response products and pan-European Standard products (Trans European Replacement Reserve Exchange (TERRE) and Manually Activated Reserves Initiative (MARI), as well as other elements of Electricity Balancing Guideline (EBGL) and the recast Electricity Regulation, and a plan for implementation. Increase competition and transparency in the procurement of fast reserve. | Q4 2020-21 | We will recommence engagement on the design of the new suite of response products when the DC project reconvenes. We are considering the reserve design in light of how the new pan-European Standard product TERRE will be used, and what the impact of wider access will be on the makeup of the Balancing Mechanism. We will be progressing reformed reserve products once we have more clarity on these areas
2 | Product Roadmaps for Response and Reserve implementation | Support development and implementation of Pan-European replacement reserve standard products (priority) | Support development and implementation of Pan-European replacement reserve standard products (priority) | Q1-Q4 2020-21 | We have advised the general industry that because of the COVID19 pandemic we cannot go-live with TERRE in June 2020 but will have to delay until Oct 2020 For MARI we are starting the process of code mods and fully participating in the central project
2 | Product Roadmap for Reactive implementation | Power Potential trial with UKPN (priority) | Innovation project in partnership with UKPN aiming to create a new reactive power market for DER and generate additional capacity on the network. | Q1-Q4 2020-21 | NGESO and UKPN have confirmed to the project participants that the Power Potential trail calendar has been delayed to a September start date. This reflects the need to replan site visits for installation and commissioning of DER equipment in light of COVID priorities.
2 | Product Roadmap for Reactive implementation | Review learning from Power Potential (priority) | Learnings to inform whether to procure reactive power services from DER and if so, how to do so in partnership with DNOs. | Q3-Q4 2020-21 | This will be aligned with the delivery of the core Power Potential project that is subject to some delays
2 | Improving the way we facilitate code change | Improving the way we facilitate code change: Customer focussed communications (priority) | Feedback from stakeholders has clearly stated that communications from the ESO Code Administration team could be improved upon. In a dynamic and resource stretched landscape, it is essential that people who want to engage with the modification process gain clarity on our role, as well as find accurate and updated information. We will progress the following deliverables: • Launching easier to read industry emails with a subscription tool that enables users to quickly manage their communication preferences • Publish a Code Administrator annual report; a report for our stakeholders providing more detail on how we’re performing, our improvements and what changes mean for them | Q1 2020-21 | The email subscription tool has now been implemented.
2 | Improving the way we facilitate code change | Improving the way we facilitate code change: Onboarding process for new industry parties (priority) | Feedback told us that new parties often struggle to understand our processes and find it confusing to know where to look for information. We will deliver the following: • Updating all our documentation and advice on the website for both new and current industry parties, consolidating this information on the website for ease of access and use. This will include different media such as podcasts • Offering in-house training; launching a new induction day for our stakeholders where they can learn more and meet the team. Once established these will be held on a regular basis based on industry need. | Q2–Q3 2020-21 | On track
2 | Improving the way we facilitate code change | Improving the way we facilitate code change: Improving industry confidence in ESO Code Governance (priority) | Feedback told us that stakeholders lacked confidence in the ESO Code Governance team, with the main issue being that our documentation (that forms the basis of our modification process), was often inaccurate and complex. As a result, we are changing our internal processes, making us more efficient and helping us to write in Plain English. We believe this will help create more confidence in our output and role. We will deliver the following incremental improvements to our service: • Better articulating ESO’s role as Code Administrator in facilitating the change process, enabling all parties to contribute to change and maximizing the delivery of consumer benefit Improvements in how our reports are written, with an ambition to adopt Plain English principles. Reaching a wider audience and better informing them of the changes being developed. A number of deliverables are scheduled: • Skills and capabilities assessed within the team complimented by external Plain English training. All documentation (proposal form, workgroup report, workgroup consultation) updated to simplify the process. • The whole team capable of writing our documents in Plain English reinforced though documented feedback from industry • All web pages refreshed to reflect Plain English style • Conduct proactive engagement with industry to reassess all of our changes to seek further feedback and evaluate the next level of change | Q1-Q4 2020-21 | On track
2 | Facilitate electricity network charging reform through Charging Futures | Facilitate electricity network charging reform through Charging Futures | Facilitate reform of arrangements across the whole electricity system by communicating with all users of the electricity system and creating opportunities for all users to learn, ask and contribute to reform. This will include: • Regular Forums • Webinars • Podcasts • Summary notes • Charging Futures website. | Q1-Q4 2020-21 | Due to Covid-19 the usual programme of Forums may be altered until Government advice changes. We will continue to update industry on electricity charging reforms via webinars, newsletters and other regular communications.
2 | Transform the customer experience for network charging | Publications and guidance of the impact of charging reform to our customers | Significant reforms to charging arrangements are expected over the 2019–21 timeframe. The Charging Futures project helps to facilitate industry input and guide users through reform. Complementary to Charging Futures, we will provide extra guidance on how this will affect users’ charges in understandable, real terms. Provide industry with regular updates on the changes and impact that TCR will have to processes and deliverables, and ensure that guidance and publications fall in line. | Q3-Q4 2020-21 | See comment for 2.14
2 | Transform the customer experience for network charging | Introduce new ‘new entrant’ e-learning on charging | Developing and roll-out further training such as webinars and workshops, in addition to publishing guidance documents to help all parties understand charging methodologies, in particular the new TNUoS methodologies introduced through TCR. We aim to complete the following milestones: • Publish an updated webinar for connection charges • Publish an updated webinar for BSUoS charges • Develop workshops on the topics selected by the customers as part of the Charging Forum event Publish an updated webinar for TNUoS charges with a focus on new charging methodologies introduced by TCR. | Q1-Q4 2020-21 | In our recent publication of the 21-22 Forecast TNUoS Tariffs report, we provied industry with a first look of the confirmed/potential impacts of the TCR. In addition to this we have also provided insight into the generation re-zoning which falls part of CUSC modification proposal (CMP324/325). In conjuction with this report, we produced a pre-recorded webinar providing further insight into upcomming changes. Work will continue through out the year to provide industry with updates and clarification to these changes through our Qaurterly updates and 5 year forecast.
2 | Transform the customer experience for network charging | Improve the digital customer experience for TNUoS, BSUoS and Connection Charging Data; including improvements to existing NGESO billing system to improve user experience | We are investigating options for updating our systems, and have a clear drive to put customer functionality at the heart of any new products. Our intent is to deliver the following milestones: • We will complete the review of the current systems, data requirements and the information we currently provide externally, taking into account the TCR decisions. • A scope and plan will be outlined, we will look to develop the required changes throughout, by revisiting our scope and seeking feedback to ensure delivery is fit for purpose and meets expectations, both internally and externally. • We will be looking to enter the implementation phase | Q1-Q4 2020-21 | Work is in progress and will fall in line with the TCR timetable
2 | Transform the customer experience for network charging | Establish a ‘cross party’ approach to onboarding, mapping out whole industry requirements | Work with other industry stakeholders such as ELEXON and Ofgem to provide a joint-up onboarding guidance document, mapping out the industry requirements and obligations. In Q1 2020-21 we plan to agree the approach and scope for the joint-up onboarding guidance with ELEXON By Q2 2020-21 we aim to engage with customers seeking their feedback and suggestions on the onboarding process In Q3 2020-21 we intend to begin drafting the guidance documents During Q4 2020-21 we will finalise and publish the guidance, incorporating the finalised new TNUoS and BSUoS charging methodologies. | Q1-Q4 2020-21 | We had an initial discussion with Elexon to align the objectives early this year. Following lockdown and challenges on industry party resource, its anticipated that it will take longer to complete the exercise. But we are still aiming to deliver by Q4 2020/21
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Implement Targeted Charging Review (TCR) decision in conjunction with DNOs | Raise and implement Connection and Use of System Code (CUSC) modifications to support the TCR. The key milestones for delivering the TCR are: • Working groups complete development of modifications and submit to Ofgem • ESO to produce preliminary cut of bands • CUSC and DCUSA modifications approved by Ofgem • Designated party set final bands • TNUoS go-live | Q4 2020-21 | We continue to progress the modifications to deliver the Targeted Charging Review: - The Code Administrator Consultation on the definitions required for the demand residual has just opened. - A second Code Administrator Consultation on the BSUoS embedded benefits is due soon, we are consulting again due to Ofgem's approval of CMP281 (storage) which needs to be incorporated into the legal text.
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Lead code modifications | Leading and implementing code modifications on key areas, such as: • Removing distortions between co-located and single technology sites; • Re-design Transmission Network Use of System (TNUoS) generation zones • BSUoS changes, subject to the second balancing services taskforce outcome. The target delivery date for these modifications refers to when the modifications are expected to conclude, including the relevant regulatory decisions. | Q4 2020-21 | The deivery date is at risk but we have not amended as yet. It will be influenced by CUSC panel prioritisation planning over the next few months.
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Balancing Services Charges Task Force | Publication of the second ESO-led balancing services charges task force final report | Q3 2020-21 | Following lockdown and challenges on industry party resource we have agreed with Ofgem to pause the taskforce for 3 months. The taskforce will recommence in July with the aim of delivering its report to Ofgem at the end of September.
2 | Transform industry frameworks to enable decentralised, decarbonised and digitised energy markets | Capacity Market Modelling - Cross-border participation in capacity markets | Development of a modelling methodology to calculate available capacity for cross-border participation in capacity markets on a consistent basis across Europe. We will be demonstrating our progress with the following milestones: • ENTSO-E (European Network of Transmission System Operators) Task Force begins • Draft methodology will be developed • ENTSO-E consultation. • Methodology will be finalised | Q4 2020-21 | ENTSO-E have a mandate to develop the methodology under Regulation (EU) 2019/943 as part of the Clean Energy Package, which will help facilitate direct participation of cross-border capacity in the capacity market. National Grid ESO are participating in the ENTSO-E Task Force to play a leading role in developing the methodology. The impact of COVID-19 presents a risk that could lead to National Grid ESO needing to commit resources to other work priroities that would reduce our involvement in the ENTSO-E work.
2 | Making Electricity Market Reform (EMR) easier for participants | Capacity Market (CM) Modelling – facilitating broader participation in the CM to provide security of supply at best value for consumers | Investigate the various sources of technology type and capacity data that would enable a robust method to be developed and implemented into the future. Dependent on the investigation, improved methodology may be developed. | Q1-Q4 2020-21 | National Grid ESO have been supporting a DCUSA Change Proposal referred to as DCP350 to create a register of embedded assets. DCUSA approved it in May and recommended the Authority now approve it for implementation. It’s currently with Ofgem and we expect approval June / July. We intend to use this data to improve our modelling of embedded generation for the capacity market, which may lead to a change in how we determine de-rating factors.. The impact of COVID-19 presents a risk that could lead to National Grid ESO needing to commit resources to other work priroities that could lead to this work being delayed. As the capacity market modelling follows an annual process, any delay would be 12 months to coincide with the next annual cycle..
2 | Delivery of the Power Responsive initiative | Support coordination of Distributed Energy Resource (DER) engagement on flexibility developments | Facilitate constructive dialogue between the demand side community and ESO subject matter experts in the development of flexibility products and markets. | Q1-Q4 2020-21 | Covid-19 has delayed a lot of development work and made workshops more challenging, which has delayed some of the work. However, we will be going ahead with the first engagement session on 5th June at the Steering Group with the RDP team.
2 | Delivery of the Power Responsive initiative | Power Responsive Stakeholder Engagement | Promote industry developments for demand side flexibility and facilitate feedback to shape ESO deliverables through a range of engagement activities. These will include conferences, working groups, webinars, consultations, editorials, training sessions and reports. | Q1-Q4 2020-21 | Develop and run alternative virtual content in the absence of physical events.
3 | Whole system operability | Lead the of Loss of Mains programme Protection setting (priority) | Lead the Accelerated Loss of Mains programme and provide assurance of value for money via quarterly performance reporting in June, September and in subsequent quarters subject to the need for programme continuation. Review and update the methodology for how we intend to procure balancing services from Distribution Network Owners (DNOs) to enable RoCoF and vector shift changes. | Q2 2020-21 and ongoing | COVID-19 has impacted on the programme's delivery assurance process. Activity has resumed with new safe working practices which means that programme milestones can now be met but with a risk to programme performance in 2021-22
3 | Whole system operability | Address actions raised in the E3C report into the GB Power Disruption Event of 9 August 2019 | The E3C report into the GB Power Disruption event of 9 August 2019 identified a number of actions to be addressed by the industry. These are delivered through the Electricity Task Group. | Q1 2020-21 | On track to complete in Q1
3 | Whole system operability | Implement approach for efficient reactive power flows between networks | Having worked with network owners to design a whole system approach to managing reactive power flows between networks, implement that approach. | Q1 2020-21 | Indirectly impacted by COVID-19 and likely to be de-prioritised
3 | Pathfinder Projects | Stability pathfinder (priority) | Assessing a range of commercial and network solutions to meet system stability needs. When we refer to stability in this context we are talking about the stability of frequency, voltage and the ability of a network user to remain connected to the system during normal operation, during and after a fault. We will develop and test processes to define requirements of transmission system stability needs, focussing on dynamic volts, inertia and fault levels as an indication of system stability requirements. Working with other network organisations we will develop and test processes to obtain and evaluate options to meet the requirements set out through technical and economic assessment. | Q4 2020-21 | On track.
3 | Pathfinder Projects | Mersey Voltage pathfinder: Project recommendations (priority) | Working with other network organisations we will conduct post tender evaluation through NOA based criteria and assessment to determine the best combination of asset and commercial solutions for meeting the regional high voltage needs. This will develop the necessary contract arrangements to facilitate participation by new and existing providers. | Q1 2020-21 | 22nd May - NG ESO have awarded 9 year contracts for static voltage support in the Mersey region to PeakGen (200 MVAr Reactor) and Zenobe (40 MVAr of reactive capability from battery storage). These contracts are worth a total of £8.67m and are due to commence from April 2022. This pathfinder is the first time that we have directly compared market solutions to a TO network asset build approach for a long term transmission level requirement.
3 | Pathfinder Projects | Pennines Voltage pathfinder (priority) | Subject to reviewing whether it is in the interest of consumers to progress the Pennines Voltage Pathfinder at this time, we will publish the invitation to tender and award contracts to successful parties. We will continue the high voltage project in the Pennine region to also consider market based solutions, include commercial solutions and further develop the necessary funding mechanisms to facilitate the participation of DNO solutions. | Q2-Q4 2020-21 | On track.
3 | Pathfinder Projects | Constraint Management Pathfinder (priority) | The aim of this project will be to provide a commercial product based around constraint management. We will analyse the impact of constraint services in an attempt to alleviate network congestion, reduce balancing costs, and deliver greater value to Great Britain consumers as the electricity network evolves. | Q1-Q2 2020-21 | On track.
3 | Early Competition | Early Competition plan setting out implementation for models (priority) | Consult with industry on detailed models for Early Competition Provide written update to Ofgem on progress to date Consult with industry on Early Competition Plan (including models, roles and implementation) Provide written update to Ofgem on progress to date Submission of final Early Competition Plan to Ofgem | Q1-Q4 2020-21 | On track.
3 | NOA: Enhanced communication | Improve accessibility of ETYS and NOA publications (priority) | We will enhance the information that is provided on system needs to allow a wider audience to better understand needs and propose solutions to meet them. We will continue to engage with stakeholders on the development of capabilities and implementation of the Network Development Roadmap. Publication of needs to the market through RFI packs, which are supported by webinars. Enhancements to information in ETYS, to include requirements for a wider set of system needs and more detail on existing system needs. Provide regular updates to stakeholders on the progress of pathfinding projects and continue engagement with impacted stakeholders through mechanisms such as the ENA Open Networks project. | Ongoing | Ongoing
3 | Regional Development Programmes (RDPs) | RDPs: Development of commercial arrangements for Transmission Constraint Management (TCM) service from DER | Commercial arrangements for DER TCM scoped with UKPN Delivery plan for DER TCM within UKPN RDP area published Commercial arrangements for DER TCM scoped with WPD Delivery plan for DER TCM within WPD RDP area published | Q2-Q4 2020-21 | Active engagement with WPD through this month and external engagement through Power Responsive Steering Group.
3 | Regional Development Programmes (RDPs) | RDPs: Co-ordinated DER inter-tripping functionality for transmission fault management. | Delivery of N-3 inter-tripping of DER with UKPN Delivery of N-3 inter-tripping of DER with WPD Delivery of communication link between NGESO and SSE-N | Q2-Q4 2020-21 | Programme remains on track at this time. Some risks associated with project partner delivery that are being monitored.
3 | Regional Development Programmes (RDPs) | RDPs: Develop and implement the Generation Export Management Scheme (GEMS) in South West Scotland to manage transmission constraints | Integrate SPEN ANM management of local constraints with NGESO management of wider transmission constraints. High level design of NGESO commercial systems to interface with GEMS Detailed design of NGESO commercial systems to interface with GEMS Commercial contract structure for DER TCM scoped with SPEN | Q2-Q4 2020-21 | Programme remains on track at this sime subject to further discussion with SPEN following publication of their revised DSO strategy.
3 | Regional Development Programmes (RDPs) | Regional Development Programmes: Identification of future RDPs | Roadmap describing the need and timescale for future RDPs during RIIO-2. | Q4 2020-21 | Following discussion at Open Networks this work will be progressed within the project as part of workstream 1B. This will ensure it aligns with the development of DSO processes for identification of future distirbution system needs.
3 | Whole System thought leadership | Support BEIS and industry in developing a strategy for clean heat | Hold meetings at least quarterly to advise BEIS on the implications of clean heat pathways for the operation of the Whole Energy System. Develop a fuller understanding of how the Whole Energy System might be operated under different clean heat pathways; working with the Gas System Operator. Share and test thinking on Clean Heat pathways with networks and industry. | Q1-Q4 2020-21 | Regular discussions with BEIS, CCC, and network companies on future heat pathways in Q1 have focussed on the modelling and analysis work for FES 2020.
3 | Whole System thought leadership | Active engagement in the development of DSO and co-ordinated flexibility markets including cross-sector considerations | Active input into the Open Networks 2020 project including leading the Whole Energy System workstream and associated CBA product. In this workstream will continue to ensure a cross-sector representation including non-network stakeholders. Active engagement with Ofgem’s work on DSO and the development of a DSO framework for RIIO-ED2 | Q3 2020-21 | On track. Following external feedback we've reviewed our representatives in workstream 1A to ensure we can provide valued input into its 2020 products.
3 | Network value assessment tools | Voltage needs identification tools/ processes | Document and test voltage needs identification tools / processes for inclusion in the NOA methodology. Identify up to three areas for further evaluation. | Q4 2020-21 & ongoing | On track
3 | Enhanced customer experience | Continue to work with Customers and Network Owners to understand requirements and scope of system wide single platform to provide online account management and connection application functionality | Detailed scoping of tool to provide a visual and live update for customers on the progress of their connection application. | Ongoing, due to be completed in 2022 | On Track.
3 | Insight documents | Operability Strategy Report | Provide a view of current and future operability challenges, to help inform stakeholders’ investment strategies, and commercial and operational plans. | Q3 2020-21 | On track
3 | Insight documents | FES: Bridging the gap to net zero | Taking the key messages from the 2020 Future Energy Scenarios, identify and progress the actions that need to happen to meet the net zero target. This work will be informed by feedback from the 2019-20 performance year of our FES: Bridging the gap to net zero project. | Q3-Q4 2020-21 | On track
3 | Insight documents | Summer Outlook | We will publish this in conjunction with the corresponding National Grid Gas Transmission publication, providing our data and analysis for the upcoming summer. | Q1 2020-21 | On track
3 | Insight documents | Winter Outlook | We will publish this in conjunction with the corresponding National Grid Gas Transmission publication, providing our data and analysis for the upcoming winter. | Q3 2020-21 | On track
3 | Insight documents | Winter Review and consultation | We will publish this in conjunction with the corresponding National Grid Gas Transmission publication, providing data and analysis relating to the previous winter | Q1 2020-21 | On track
3 | Insight documents | Future Energy Scenarios (FES) | Provides our range of credible scenarios for the future of energy to support the planning of the Great Britain transmission system supported by continued, varied and wide stakeholder engagement and research. In Q2 we will produce the FES publication with the supporting data workbook, hold the FES conference and executive briefing, and publish a call for evidence. Stakeholder engagement will happen throughout the year in the form of bilaterals, workshops, webinars, videos and thought pieces. We are also planning on delivering more information on the costing of each scenario pathway following the FES publication. | Q2-Q3 2020-21 | Launch conference for stakeholders to be shifted to a virtual event online. Slimmed down version of FES document.