## Sheet1
GC0145 / P407 Action Log
Action Number | Raised | Owner | Action | Comment | Due by | Status
3 | WG1 | LT / MR | Confirm the files/format in which the data will be sent to Elexon and NGESO | LIBRA is platform to share files | Ongoing | Closed
6 | WG1 | LT | Agree the scope for a separate issue group for interconnectors – with aim to prevent discussions had on MARI being duplicated in bilateral agreements | Review this after WG4 to see if a separate workshop is required. | TBC | Open
8 | WG1 | JG | Circulate updated Terms of Reference to Workgroup to Review – aim to get them to July Panel | ToR reviewed. Submitted for July Panel | 2020-07-30 | Closed
9 | WG2 | LT | ‘How the platform works’ – slide Update to include interconnectors | Data flow diagram for TERRE provided. MARI data flow diagram will not be available until summer 2021. | WG3 | Closed
11 | WG2 | LT | Confirm which documents can be shared with the workgroup in addition to the legal text. I.e. dispatch guide | Detailed dispatch instructions will not be included in the MARI workgroup. | WG3 | Closed
12 | WG2 | MR | Update diagram from P344 to include MARI – how it interacts with the settlement periods | TE has provided this and it was covered in WG3. | 2020-07-22 | Closed
13 | WG2 | MR / LT | ‘Accepting the bids’ – slide. Interconnectors and NGESO’s ramping restrictions. Update slide which was previously shared for TERRE |  | WG4 | Open
14 | WG2 | LT | Confirm the degree of flexibility in ramping (timings etc) | Covered in WG3 | WG3 | Closed
15 | WG2 | LT | Confirm detail on Direct and Scheduled Activation (including interconnector communications) including when instructions will be received and where from. | Covered in WG3 | WG3 | Closed
16 | WG2 | LT | Check the overlap between MARI and other Ancillary Services. I.e. which are mutually exclusive. (Including the services which I/Cs deliver) | Covered in WG3 | WG3 | Closed
18 | WG2 | JG/NF | Revisit workgroup planning | Will revisit after workgroup 4 | WG3 | Closed
19 | 44033 | Workgroup | WG to consider slide 6 on I/Cs slide before I/Cs workshop |  | TBC | Closed
20 | 44033 | JG/NF | Include a standing item on Brexit negotiations to Workgroup agendas | Included | WG3 | Closed
10 | WG2 | LT | ‘Submission of bids’ – slide Confirm if 1MW is the step increment for bids or whether 0.1MW is possible | Remains 1MW at this point but there are meetings outside of this workgroup where this is being discussed. | Ongoing | Open
17 | WG2 | LT | Share any updates from NGESO internal IT working group |  | Ongoing | Open
7 | WG1 | JG | Appeal for more representation on the workgroup – service providers, smaller players, aggregators, DSR | Further appeals to member organisations were made however no new members gained. CA to contact interested parties from ADE meeting | WG2 | Closed
1 | WG1 | JG | Arrange code modification process walk through session JM, CA & MJ. | Meeting held | WG2 | Closed
2 | WG1 | LT | Share Excel spreadsheet showing timelines for Scheduled and Direct Activation | Document not shareable externally | WG2 | Closed
4 | WG1 | LT/AJ/SM | Confirm whether Interconnector BM Units can participate in MARI | IC BM units cannot participate in MARI | Ongoing | Closed
5 | WG1 | JG | Schedule time for the workgroup to consider existing interconnector settlement processes and how project MARI will interact with them | WG3 / WG4 | TBC | Closed
18 | 44033 | SA/JG | Send doodle poll for WG4 |  | 2020-07-21 | Closed
21 | WG3 | LT / KP / JG | Create a table to capture the discussion on the points raised on slide 6 of the interconnector settlement processes slides - share with workgroup |  | WG4 | Open
22 | WG3 | JG | Circulate LIBRA data flow diagram for TERRE |  | 2020-08-21 | Closed
23 | WG3 | JG | Schedule time for further discussion on dispatch principles | To cover in WG4 | WG4 | Open
24 | WG3 | JG | Circulate Elexon slides |  | 2020-08-21 | Closed
25 | WG3 | LT | Confirm whether it is OK to ramp for less than 10 minutes (including interconnectors) |  | WG4 | Open
26 | WG3 | JG | Send out doodle poll for alternative date for the 1 September workgroup |  | 2020-08-21 | Open
27 | WG3 | MR | Clarify how the auction results impact subsequent auctions |  | WG4 | Open
28 | WG3 | LT | Clarify question 3 on slide 10 |  | WG4 | Open