## Sheet1
GC0145 / P407 Action Log
Action Number | Raised | Owner | Action | Comment | Due by | Status
3 | WG1 | LT / MR | Confirm the files/format in which the data will be sent to Elexon and NGESO | LIBRA is platform to share files | Ongoing | Closed
6 | WG1 | LT | Agree the scope for a separate issue group for interconnectors – with aim to prevent discussions had on MARI being duplicated in bilateral agreements | Review this after WG4 to see if a separate workshop is required. | TBC | Open
8 | WG1 | JG | Circulate updated Terms of Reference to Workgroup to Review – aim to get them to July Panel | ToR reviewed. Submitted for July Panel | 2020-07-30 | Closed
9 | WG2 | LT | ‘How the platform works’ – slide Update to include interconnectors | Data flow diagram for TERRE provided. MARI data flow diagram will not be available until summer 2021. | WG3 | Closed
11 | WG2 | LT | Confirm which documents can be shared with the workgroup in addition to the legal text. I.e. dispatch guide | Detailed dispatch instructions will not be included in the MARI workgroup. | WG3 | Closed
12 | WG2 | MR | Update diagram from P344 to include MARI – how it interacts with the settlement periods | TE has provided this and it was covered in WG3. | 2020-07-22 | Closed
13 | WG2 | MR / LT | ‘Accepting the bids’ – slide. Interconnectors and NGESO’s ramping restrictions. Update slide which was previously shared for TERRE |  | WG4 | Open
14 | WG2 | LT | Confirm the degree of flexibility in ramping (timings etc) | Covered in WG3 | WG3 | Closed
15 | WG2 | LT | Confirm detail on Direct and Scheduled Activation (including interconnector communications) including when instructions will be received and where from. | Covered in WG3 | WG3 | Closed
16 | WG2 | LT | Check the overlap between MARI and other Ancillary Services. I.e. which are mutually exclusive. (Including the services which I/Cs deliver) | Covered in WG3 | WG3 | Closed
18 | WG2 | JG/NF | Revisit workgroup planning | Will revisit after workgroup 4 | WG3 | Closed
19 | 44033 | Workgroup | WG to consider slide 6 on I/Cs slide before I/Cs workshop |  | TBC | Closed
20 | 44033 | JG/NF | Include a standing item on Brexit negotiations to Workgroup agendas | Included | WG3 | Closed
10 | WG2 | LT | ‘Submission of bids’ – slide Confirm if 1MW is the step increment for bids or whether 0.1MW is possible | Remains 1MW at this point but there are meetings outside of this workgroup where this is being discussed. | Ongoing | Open
17 | WG2 | LT | Share any updates from NGESO internal IT working group |  | Ongoing | Open
7 | WG1 | JG | Appeal for more representation on the workgroup – service providers, smaller players, aggregators, DSR | Further appeals to member organisations were made however no new members gained. CA to contact interested parties from ADE meeting | WG2 | Closed
1 | WG1 | JG | Arrange code modification process walk through session JM, CA & MJ. | Meeting held | WG2 | Closed
2 | WG1 | LT | Share Excel spreadsheet showing timelines for Scheduled and Direct Activation | Document not shareable externally | WG2 | Closed
4 | WG1 | LT/AJ/SM | Confirm whether Interconnector BM Units can participate in MARI | IC BM units cannot participate in MARI | Ongoing | Closed
5 | WG1 | JG | Schedule time for the workgroup to consider existing interconnector settlement processes and how project MARI will interact with them | WG3 / WG4 | TBC | Closed
18 | 44033 | SA/JG | Send doodle poll for WG4 |  | 2020-07-21 | Closed
21 | WG3 | LT / KP / JG | Create a table to capture the discussion on the points raised on slide 6 of the interconnector settlement processes slides - share with workgroup |  | WG5 | Open
22 | WG3 | JG | Circulate LIBRA data flow diagram for TERRE |  | 2020-08-21 | Closed
23 | WG3 | JG | Schedule time for further discussion on dispatch principles | To cover in WG5. If the data is going to be cleaned before it goes into the platform - how this interacts with the dispatch principles | WG5 | Open
24 | WG3 | JG | Circulate Elexon slides |  | 2020-08-21 | Closed
25 | WG3 | LT | Confirm whether it is OK to ramp for less than 10 minutes (including interconnectors) | Examples / more info to be shared with WG | WG4 | Open
26 | WG3 | NF | Send out doodle poll for alternative date for the 1 September workgroup |  | 2020-08-21 | Closed
27 | WG3 | MR | Clarify how the auction results impact subsequent auctions | Nothing in the legal text to stop users from participating in subsequent auctions | WG4 | Open
28 | WG3 | LT | Clarify question 3 on slide 10 - re: transfer capacity calculation | LT to liaise with Neil from ESO to confirm | WG4 | Open
29 | WG4 | JG | Get a DNO to participate in the WG to get a DNO view on Term L of the ToR | Re: constraints | WG5 | Open
30 | WG4 | TJ | Raise ToR change with GC0144 workgroup to cover MARI re: market suspension |  | WG5 | Open
31 | WG4 | LT | Share defined terms with workgroup |  | WG5 | Open
32 | WG4 | LT | Re-share Legal text following amendments |  | WG5 | Open
33 | WG4 | LT | Provide more clarity on feasability bids and filtering - how interconnectors are treated and whether this is included in the Grid Code |  | WG5 | Open
34 | WG4 | Workgroup | Workgroup to consider whether the mFRR Standard Product Shape should be incentivised, and if so whether it should be harmonised with RR. And, to consider whether separate instruction deviation cashflows are required for Scheduled and Direct Activiations |  | WG5 | Open
35 | WG4 | LT / MR | Provide clarifty on deviation volumes for Interconnectors |  | WG5 | Open
36 | WG4 | MR | Consider the benefits of profiled settlement |  |  | Open