## Sheet1
GC0145 / P407 Action Log
Action Number | Raised | Owner | Action | Comment | Due by | Status
3 | WG1 | LT / MR | Confirm the files/format in which the data will be sent to Elexon and NGESO | LIBRA is platform to share files | Ongoing | Closed
6 | WG1 | LT | Agree the scope for a separate issue group for interconnectors – with aim to prevent discussions had on MARI being duplicated in bilateral agreements | Workgroup to review and confirm whether they're happy to close this item | TBC | Closed
8 | WG1 | JG | Circulate updated Terms of Reference to Workgroup to Review – aim to get them to July Panel | ToR reviewed. Submitted for July Panel | 2020-07-30 | Closed
9 | WG2 | LT | ‘How the platform works’ – slide Update to include interconnectors | Data flow diagram for TERRE provided. MARI data flow diagram will not be available until summer 2021. | WG3 | Closed
11 | WG2 | LT | Confirm which documents can be shared with the workgroup in addition to the legal text. I.e. dispatch guide | Detailed dispatch instructions will not be included in the MARI workgroup. | WG3 | Closed
12 | WG2 | MR | Update diagram from P344 to include MARI – how it interacts with the settlement periods | TE has provided this and it was covered in WG3. | 2020-07-22 | Closed
13 | WG2 | MR / LT | ‘Accepting the bids’ – slide. Interconnectors and NGESO’s ramping restrictions. Update slide which was previously shared for TERRE | The original slide is not available. The current slide that was previously shared should be sufficient while we're working on further detail. | WG4 | Closed
14 | WG2 | LT | Confirm the degree of flexibility in ramping (timings etc) | Covered in WG3 | WG3 | Closed
15 | WG2 | LT | Confirm detail on Direct and Scheduled Activation (including interconnector communications) including when instructions will be received and where from. | Covered in WG3 | WG3 | Closed
16 | WG2 | LT | Check the overlap between MARI and other Ancillary Services. I.e. which are mutually exclusive. (Including the services which I/Cs deliver) | Covered in WG3 | WG3 | Closed
18 | WG2 | JG/NF | Revisit workgroup planning | Will revisit after workgroup 4 | WG3 | Closed
19 | 44033 | Workgroup | WG to consider slide 6 on I/Cs slide before I/Cs workshop |  | TBC | Closed
20 | 44033 | JG/NF | Include a standing item on Brexit negotiations to Workgroup agendas | Included | WG3 | Closed
10 | WG2 | LT | ‘Submission of bids’ – slide Confirm if 1MW is the step increment for bids or whether 0.1MW is possible | Remains 1MW at this point but there are meetings outside of this workgroup where the possibility of smaller increments is being discussed (however that would be covered in a separate modification) | Ongoing | Closed
17 | WG2 | LT | Share any updates from NGESO internal IT working group | Implementation guidelines document due to be published in near future | Ongoing | Open
7 | WG1 | JG | Appeal for more representation on the workgroup – service providers, smaller players, aggregators, DSR | Further appeals to member organisations were made however no new members gained. CA to contact interested parties from ADE meeting | WG2 | Closed
1 | WG1 | JG | Arrange code modification process walk through session JM, CA & MJ. | Meeting held | WG2 | Closed
2 | WG1 | LT | Share Excel spreadsheet showing timelines for Scheduled and Direct Activation | Document not shareable externally | WG2 | Closed
4 | WG1 | LT/AJ/SM | Confirm whether Interconnector BM Units can participate in MARI | IC BM units cannot participate in MARI | Ongoing | Closed
5 | WG1 | JG | Schedule time for the workgroup to consider existing interconnector settlement processes and how project MARI will interact with them | WG3 / WG4 | TBC | Closed
18 | 44033 | SA/JG | Send doodle poll for WG4 |  | 2020-07-21 | Closed
21 | WG3 | LT / KP / JG | Create a table to capture the discussion on the points raised on slide 6 of the interconnector settlement processes slides - share with workgroup | Remains open | WG6 | Closed
22 | WG3 | JG | Circulate LIBRA data flow diagram for TERRE |  | 2020-08-21 | Closed
23 | WG3 | JG | Schedule time for further discussion on dispatch principles | Further discussion needed in order to enable BSC solution | WG7 | Closed
24 | WG3 | JG | Circulate Elexon slides |  | 2020-08-21 | Closed
25 | WG3 | LT | Confirm whether it is possible to ramp for more or less than 10 minutes (including interconnectors) | Ramping will be 10 minutes up and down. WG are asked to look at dispatch principles document and feedback. | WG6 | Open
26 | WG3 | NF | Send out doodle poll for alternative date for the 1 September workgroup |  | 2020-08-21 | Closed
27 | WG3 | MR | Clarify how the auction results impact subsequent auctions | Closed but raised new action 37 with ESO ownership | WG4 | Closed
28 | WG3 | LT | Clarify question 3 on slide 10 - re: transfer capacity calculation | Available transfer capacity methodology. This methodology will not be published (as has been agreed for TERRE) but will look to amend the legal text accordingly based on the same principles already agreed for TERRE. | WG5 | Closed
29 | WG4 | JG | Get a DNO to participate in the WG to get a DNO view on Term L of the ToR | DNO now in attendance | WG5 | Closed
30 | WG4 | TJ | Raise ToR change with GC0144 workgroup to cover MARI re: market suspension | Will be discussed 04/11 | WG6 | Open
31 | WG4 | LT | Share defined terms with workgroup | Awaiting sign-off | WG6 | Open
32 | WG4 | LT | Re-share Legal text following amendments | Remains open | WG5 | Open
33 | WG4 | LT | Provide more clarity on feasability bids and filtering - how interconnectors are treated and whether this is included in the Grid Code | NGESO are in the process of setting up an internal group to discuss | WG6 | Closed
34 | WG4 | Workgroup | Workgroup to consider whether the mFRR Standard Product Shape should be incentivised, and if so whether it should be harmonised with RR. And, to consider whether separate instruction deviation cashflows are required for Scheduled and Direct Activiations |  | WG6 | Closed
35 | WG4 | LT / MR | Provide clarifty on deviation volumes for Interconnectors. Confirm in which document the interconnector deviations on the MARI profile sit. | Need to continue looking at deviation volumes and will bring back to a future Workgroup | WG6 | Open
36 | WG4 | MR | Consider the benefits of profiled settlement | Discussed at WG5 but further thought is needed by WG members | WG6 | Closed
37 | WG5 | LT | Elexon needs to know the TSO defined variable characteristics of the mFRR Standard Product Shape | Agreed to pick this up at a later point and note in report. | WG7 | Closed
38 | WG5 | LT | Confirm whether settlement is block or profiled for interconnectors |  | WG6 | Open
39 | WG5 | LT | Confirm ESO view on incentivisation of mFRR Standard Product Shape |  | WG7 | Closed
40 | WG5 | LT | DNO-ESO catch up to discuss DNO considerations for MARI |  | WG6 | Closed
41 | WG5 | LT | Confirm how products will interact |  | WG7 | Closed
42 | WG5 | MR | Elexon to cover any P375 interaction | No interaction. BSC legal text will need to consider. | WG6 | Closed
43 | WG6 | Workgroup | Interconnector Workgroup members to consider what concerns they have around the stacking of cross border activations. ESO to set up meeting to discuss. |  | WG7 | Open
44 | WG6 | Workgroup | Workgroup to feedback on dispatch principles draft document |  | WG7 | Open
45 | WG6 | Workgroup | Workgroup to consider deviation cashflow options A, B and C presented |  | WG7 | Open
46 | WG6 | LT | DNO and ESO to catch up regards legal text |  | WG7 | Open