## Milestones
Milestones
A project milestone schedule should be provided incorporating but not limited to the below steps.
Where the conditions precedent have not yet been met, dates should be provided estimating when these will be in place from.
Unique Tender number:
Milestone | Date | Comments
1.Financial means
2.Planning permission & necessary permits
3.Technical solution model / analysis |  | Do you currently have a model that allows the solution to be assessed?
4.Proof of land ownership / control |  | Freehold/Leasehold rights?
5.Construction & procurement plans
6.Provision of technical requirements tables (from schedule E) |  | See schedule E of contract
7.Building / engineering contracts
8.Certification |  | Who will provide?
9.Pre-commissioning testing, connection & proving tests (& outages where existing generation asset) |  | EDL comms established? Connection agreement in place?
10.Conditions precedent obtained in full |  | BCA/BEGA in place?, MSA in place?
Unique Tender number:
Milestone | Date | Comments
1.Financial means
2.Planning permission & necessary permits
3.Technical solution model / analysis |  | Do you currently have a model that allows the solution to be assessed?
4.Proof of land ownership / control |  | Freehold/Leasehold rights?
5.Construction & procurement plans
6.Provision of technical requirements tables (from schedule E) |  | See schedule E of contract
7.Building / engineering contracts
8.Certification |  | Who will provide?
9.Pre-commissioning testing, connection & proving tests (& outages where existing generation asset) |  | EDL comms established? Connection agreement in place?
10.Conditions precedent obtained in full |  | BCA/BEGA in place?, MSA in place?
Further tables can be added as required.

## Contact Details
Contact Details
Contact Details | Contact Name
Company Name
Address Line 1
Address Line 2
Address Line 3
Address Line 4
Address Line 5
Post Code
Email Address
Phone Number

## Tender Submissions
Identifier |  |  |  |  | Location | [5 empty] | Capability | [6 empty] | Dispatch |  |  | Commercial
Company Name | Unique tender number (e.g. 1, 2, ...) | BMU ID | Mutually exclusive grouping (e.g. 1, 2, ...) | All or nothing grouping (e.g. A, B, ...) | Are you already connected (Y/N) | When do you expect to connect (DD/MM/YYYY) | Connection Agreement type (BCA, BEGA) | Connection Voltage Level (132 kV / 275 kV / 400 kV) | Onshore and A/C connection (Y/N) | Connection Point | Rating (MVA) | H (s) | Inertia (MVA.s) | Absorption (Mvar) | Injection (Mvar) | Power consumption (MW) | Power Oscillation Damping capability (Y/N) | Start date (DD/MM/YYYY) | Time to Synchronise (minutes) | EDL and EDT installed (Y/N) | Cost - FY20/21 (£/SP) | MSA (Y/N) | Contract End Date (2023 or 2026) | Post-Tender Milestones provided? (Y/N)
1
2
3
4
5

## Reference
Tender submission reference
This sheet outlines the data required to be completed in the tender submission.
Please input your tender submission data into the contact details, tender submissions and milestones sheets.
Identifier | Company Name | This must match the company name
| Unique tender number (e.g. 1, 2, ...) | Tender ID for tenders, start at 1 (e.g. 1, 2, 3, 4 - )
| BMU ID | Enter the existing BMU ID if applicable, or "XXXX" where an ID would need to be created. If the submission needs to refer to more than one new ID, enter "XXXX-N", where 'N' is a unique number (e.g. XXXX-1, XXXX-2, ...)
| Mutually exclusive grouping (e.g. 1, 2, ...) | All tenders or all-or-nothing groups that should be considered to be mutually exclusive give the same number. Mutually exclusive means that we can accept only one of the tenders or all-or-nothing groups.
| All or nothing grouping (e.g. A, B, ...) | All tenders that should be considered part of an all or nothing group give the same letter. All or nothing means that if we want to accept one of the tenders, we have to accept all of them. If there are more than 26 groups, continue the sequence with two letters (e.g. A, B, C, ..., Z, AA, AB, ...) All tender lines within an all-or-nothing group must share the same mutually exclusive number.
Location | Are you already connected (Y/N) | Y/N
| When do you expect to connect (DD/MM/YYYY) | DD/MM/YYYY
Connection Agreement type (BCA/BEGA)
| Connection Voltage Level (132 kV / 275 kV / 400 kV) | Providers must be connected between 132kV and 400kV inclusive
| Onshore and A/C connection (Y/N) | Y/N are you connected to an onshore A/C substation
| Connection Point | Please specify the name of the substation that you are connected to. Please contact DNO or TO if unsure.
Capability | Rating (MVA) | The rating of the asset
| H (s) | The H constant of the asset
| Inertia (MVA.s) | The inertia provided by the asset, created by multiplying the rating and H value
| Absorption (Mvar) | The absorption of Mvar provided by the asset
| Injection (Mvar) | The injection of Mvar provided by the asset
| Power consumption (MW) | The power consumed by asset in steady state
| Power Oscillation Damping capability (Y/N) | Y/N
Dispatch | Start date (DD/MM/YYYY) | Needs to be 01/04/2021 or earlier
| Time to Synchronise (minutes) | Time to synchronise following instruction. Expected to be less that 15min, if longer please state.
| EDL and EDT installed (Y/N) | Y/N whether EDL and EDT are already installed
Commercial | Cost FY20/21 (£/SP) | The firm fee paid for every settlement period when available (subject to indexation)
| MSA (Y/N) | Y/N whether you already have an MSA in place
| Contract End Date (2023 / 2026) | Either "31/03/2023" or "31/03/2026" (without quotes)
| Post Tender Milestones Provided (Y/N) | See Milestones sheet
Contact Details | Contact Name | Single point of contact for tender submission
Company Name
Address Line 1
Address Line 2
Address Line 3
Address Line 4
Address Line 5
Post Code
Email Address
Phone Number

## Conditional Tenders (Example)
Conditional tender example
This sheet provides an example of how we would interpret submissions which includes conditionality. | Company Name | BMU ID | Unique ID | Mutually Exclusive | All or Nothing | MVA.s | £/SP | Weighted Avg Price (£/MVA.s/SP) | Mutually Exclusive
| Corp Ltd. | BMUID-1 | 1 | 1 | A | 100 | 10 | All or Nothing | 1 | 2 | 3 | 4 | 5 | 6
| Corp Ltd. | BMUID-1 | 2 | 1 | B | 100 | 10 | A | 0.1
| Corp Ltd. | BMUID-2 | 3 | 1 | B | 100 | 9 | B | 0.095
| Corp Ltd. | BMUID-1 | 4 | 1 | C | 100 | 9 | C | 0.08
| Corp Ltd. | BMUID-2 | 5 | 1 | C | 100 | 8 | D |  | 0.18333
| Corp Ltd. | BMUID-3 | 6 | 1 | C | 100 | 7 | E |  | 0.175
| Corp Ltd. | BMUID-4 | 7 | 2 | D | 60 | 11 | F |  | 0.15
| Corp Ltd. | BMUID-4 | 8 | 2 | E | 60 | 11 | H |  |  | 0.14
| Corp Ltd. | BMUID-5 | 9 | 2 | E | 60 | 10 | I |  |  | 0.14
| Corp Ltd. | BMUID-4 | 10 | 2 | F | 60 | 10 | J |  |  | 0.14 | 0.14
| Corp Ltd. | BMUID-5 | 11 | 2 | F | 60 | 9 | K |  |  |  | 0.14
| Corp Ltd. | BMUID-6 | 12 | 2 | F | 60 | 8 | L |  |  |  | 0.14
| Corp Ltd. | XXXX-1 | 13 | 3 | H | 50 | 7 | M |  |  |  | 0.14
| Corp Ltd. | XXXX-2 | 14 | 3 | I | 50 | 7 | N |  |  |  | 0.14
| Corp Ltd. | XXXX-3 | 15 | 3 | I | 50 | 7 | O |  |  |  | 0.14
| Corp Ltd. | XXXX-4 | 16 | 3 | I | 50 | 7 | P |  |  |  | 0.14
| Corp Ltd. | XXXX-5 | 17 | 3 | J | 50 | 7 | Q |  |  |  | 0.14
| Corp Ltd. | XXXX-6 | 18 | 3 | J | 50 | 7 | R |  |  |  |  | 0.14
| Corp Ltd. | XXXX-7 | 19 | 4 | J | 50 | 7 | S |  |  |  |  | 0.14
| Corp Ltd. | XXXX-8 | 20 | 4 | J | 50 | 7 | T |  |  |  |  | 0.14
| Corp Ltd. | XXXX-9 | 21 | 4 | K | 50 | 7 | U |  |  |  |  | 0.14
| Corp Ltd. | XXXX-10 | 22 | 4 | L | 50 | 7 | V |  |  |  |  | 0.14
| Corp Ltd. | XXXX-11 | 23 | 4 | M | 50 | 7 | W |  |  |  |  | 0.14
| Corp Ltd. | XXXX-12 | 24 | 4 | N | 50 | 7 | X |  |  |  |  | 0.14
| Corp Ltd. | XXXX-13 | 25 | 4 | O | 50 | 7 | Y |  |  |  |  | 0.14
| Corp Ltd. | XXXX-14 | 26 | 4 | P | 50 | 7 | Z | [5 empty] | 0.14
| Corp Ltd. | XXXX-15 | 27 | 4 | Q | 50 | 7 | AA | [5 empty] | 0.14
| Corp Ltd. | XXXX-16 | 28 | 5 | R | 50 | 7 | AB | [5 empty] | 0.14
| Corp Ltd. | XXXX-17 | 29 | 5 | S | 50 | 7 | AC | [5 empty] | 0.14
| Corp Ltd. | XXXX-18 | 30 | 5 | T | 50 | 7 | AD | [5 empty] | 0.14
| Corp Ltd. | XXXX-19 | 31 | 5 | U | 50 | 7
| Corp Ltd. | XXXX-20 | 32 | 5 | V | 50 | 7
| Corp Ltd. | XXXX-21 | 33 | 5 | W | 50 | 7
| Corp Ltd. | XXXX-22 | 34 | 5 | X | 50 | 7
| Corp Ltd. | XXXX-23 | 35 | 5 | Y | 50 | 7
| Corp Ltd. | XXXX-24 | 36 | 6 | Z | 50 | 7
| Corp Ltd. | XXXX-25 | 37 | 6 | AA | 50 | 7
| Corp Ltd. | XXXX-26 | 38 | 6 | AB | 50 | 7
| Corp Ltd. | XXXX-27 | 39 | 6 | AB | 50 | 7
| Corp Ltd. | XXXX-28 | 40 | 6 | AB | 50 | 7
| Corp Ltd. | XXXX-29 | 41 | 6 | AC | 50 | 7
| Corp Ltd. | XXXX-30 | 42 | 6 | AC | 50 | 7
| Corp Ltd. | XXXX-31 | 43 | 6 | AD | 50 | 7
| Corp Ltd. | XXXX-32 | 44 | 6 | AD | 50 | 7
This simplified tender submission would be interpreted as:
Within each of the Mutually Exclusive Groups (1, 2, ..., 6), accept up to one of the All-or-Nothing Groups (A, B, ..., AD). Where an All-or-Nothing Group contains one or more tender lines.
Meaning that, for example:
Within Mutually Exclusive Group 1, if All-or-Nothing Group C was accepted, only tender lines with Unique IDs 4, 5 and 6 would be accepted.
Within Mutually Exclusive Group 2, all three All-or-Nothing Groups (D, E and F) could be rejected.
Mutually Exclusive Groups 3 and 4 are rejected in their entirety because All-or-Nothing Group J contains tender lines which belong to both Mutually Exclusive Groups.
Within Mutually Exclusive Group 5, if All-or-Nothing Group R was accepted, only the tender line with Unique ID 28 would be accepted.
Within Mutually Exclusive Group 6, if All-or-Nothing Group AC was accepted, only tender lines with Unique IDs 41 and 42 would be accepted.
Please note that the prices in this example are fictitious and for the purposes of demonstration only. It is greatly simplified to demonstrate how “All-or-Nothing” and “Mutually Exclusive” groups will be used in the tender assessment. It does not include many of the factors that will be considered as part of the tender assessment.
Note on J4: Prices are fictitious and for the purposes of demonstration only.