## CUSC
Connection Use Of System Code (CUSC): is the contractual framework for connection to, and use of, the National Electricity Transmission System (NETS).
|  |  | General Modification Information | [12 empty] | Mod Development | [6 empty] | Consultation |  |  | Ofgem
Mod Number | Status | Comments | Priority: | Panel Comments on Prioritisation as at 29 January 2021 | Framework | Date raised | Proposer Name | Proposer Organisation | Title | Purpose: What is the Mod trying to deliver | Stakeholders Impacted | Change Route | Impact on - Electricity Balancing Guidelines (EBGL) Article 18 terms and conditions | Chair | Tech Sec | Proposal raised | Present to Panel | Workgroup Meetings | Workgroup Consultation | Post Workgroup Consultation | Workgroup Vote | Workgroup Alternatives raised | Report to Panel | Code Administrator Consultation | Panel Vote | Sent to Ofgem | Ofgem Decision Received | Implemented
CMP271 | On hold | Was put on hold awaiting TCR decision. Now that Ofgem have published their Direction on the Targeted Charging Review, Code Admin contacting Proposers to ascertain if Modification needs to be progressed or withdrawn. Noted to June 2020 Panel that Proposer confirmed on 22 June 2020 that this can be withdrawn and Code Admin will now start withdrawal process. | - | n/a | CUSC | 29/9/2016 | Bill Reed | RWE | Improving the cost reflectivity of demand transmission charges | Proposed that the transmission charging methodology should include a Peak Security demand tariff levied at Triad, a Year round demand tariff & revenue recovery levied on a year round supplier. | Generators, Suppliers, Embedded Generators | TBC | No | TBC | TBC
CMP274 |  | Proposer has sought withdrawal of CMP274. As no-one wished to support CMP274 in place of the original Proposer by 5pm on 24 February 2020, we sought agreement (under CUSC 8.16.10(b)) from February 2020 Panel to withdraw this Modification - Panel agreed to withdraw. A further period of 5 Business Days was given to industry for support to be indicated and as no support was received, CMP274 is now withdrawn. | - | n/a | CUSC | 29/9/2016 | Grace March | Sembcorp Energy UK | Winter TNUoS Time of Use Tariff TToUT for Demand TNUoS | Proposed to update the transmission charging methodology to include a Peak demand tariff based on current locational element of the demand TNUoS charge methodology using the existing Triad methodology for determining user charges & a Winter Weekday demand tariff based on the current Demand residual element of the demand TNUoS charge methodology. | Generators, Suppliers, Embedded Generation, Transmission Network Operators, HH Demand Customers | TBC |  | TBC | TBC
CMP276 | On hold | Was put on hold awaiting TCR decision. Now that Ofgem have published their Direction on the Targeted Charging Review, Code Admin contacting Proposers to ascertain if Modification needs to be progressed or withdrawn. | - | n/a | CUSC | 2017-06-02 | John Harmer | Alkane Energy Ltd | Socialising TO costs associated with ''green policies'' | Proposes a reduction in the demand residual element of the TNUoS £/kW (''Triad'') charge by creating 2 new charge lines for all demand offtakes. (Please also refer to CMP264 & 265). | Embedded Generators, HH metered consumers, NG, HH | TBC | No | TBC | TBC
CMP280 | Pending Authority Decision | Panel voted by majority to approve Draft Final Modification Report at Special Panel 12 September 2019. Following 27 September Panel, issued 5 day Code Admin Consultation for related Modification CMP281 on a proposed legal text change on 4 October 2019 (closed 11 October 2019). Final Modification Reports for CMP280, CMP281 and CMP319 sent to Ofgem on 15 October 2019. Ofgem decision was expected on or before 19 November 2019. At August 2020 Panel, Ofgem advised that an update on CMP280 will be published at end of September 2020 (published 2 October 2020). ESO clarified at August 2020 Panel that 1 April 2021 implementation date is no longer achievable given the delay in decision. At November 2020 Panel, Ofgem advised that they will consider whether or not CMP280 is needed after they have decided on the other Transmission Demand Residual Modifications but do not expect to make a decision on CMP280 in the near future. | - | n/a | CUSC | 22/6/2017 | Simon Lord | Engie | Creation of a New Generator TNUoS Demand Tariff which removes liability for TNUoS Demand Residual Charges from Generation & Storage Users | Aims to remove the liability to the TNUoS Demand Residual tariff element from Generation and Storage Users. | Suppliers, Generators & Storage Operators | Standard Governance Route with Workgroup | No | Ren Walker | n/a |  | 2017-06-30 | 2019-06-01 | 2018-05-14 | 2019-06-01 | 2019-06-01 | 1 | 2019-07-01 | 2019-07-01 | 2019-09-12 | 2019-10-01 | 2019-11-19 | 2021-04-01
CMP281 | Implementation | Panel voted by majority to approve Draft Final Modification Report at Special Panel 12 September 2019. Following 27 September Panel, issued 5 day Code Admin Consultation for related Modification CMP281 on a proposed legal text change on 4 October 2019 (closed 11 October 2019). Final Modification Reports for CMP280, CMP281 and CMP319 sent to Ofgem on 15 October 2019. Ofgem decision was expected on or before 19 November 2019. On 24 March 2020, Ofgem announced that they were reviewing their work plans for 2020 in light of the Coronavirus national emergency. They also announced that from Wednesday 25 March they would temporarily pause publishing new information on their website (with some specific exceptions) until this review has been completed. Ofgem completed this review on 16 April 2020. At April CUSC Panel, Ofgem advised that the publishing moratorium would be lifted on 29 April 2020 and approved CMP281 on 14 May 2020. Implementation 1 April 2021. | - | n/a | CUSC | 22/6/2017 | Simon Lord | Engie | Removal of BSUoS Charges From Energy Taken From the National Grid System by Storage Facilities | Aims to remove liability from storage facilities for the Balancing Services Use of System (BSUoS) charges on imports. | Suppliers | Standard Governance Route with Workgroup | No | Ren Walker | n/a |  | 2017-06-30 | 2019-06-01 | 2018-10-23 | 2018-11-01 | 2019-06-01 | 0 | 2019-07-01 | 2019-07-01 | 2019-09-12 | 2019-10-01 | 2020-05-14 | 2021-04-01
CMP286 | Workgroup Stage | Proposer has clarified that no further RFI would be required for CMP286/CMP287 (demand forecast fixing) and although the TCR may reduce the benefits of CMP286/CMP287, CMP286/CMP287 would not itself have any impact on the TCR. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Low so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged. | Low | • Panel recognised the work done so far but noted the interactions with TCR and the potential need for a 2nd Request for Information on CMP287. Need to understand the TCR outcome before progressing further October Panel agreed to leave priority unchanged. | CUSC | 2017-10-10 | Niall Coyle | Npower | Improving TNUoS Predictability Through Increased Notice of the Target Revenue used in the TNUoS Tariff Setting Process | Improve the predictability of TNUoS demand charges by bringing forward the date at which the target revenue used in TNUoS tariff setting is fixed to allow customer prices to more accurately reflect final TNUoS rates. | Suppliers, Generators, embedded generators and National Grid | Standard Governance Route with Workgroup | No | Joe Henry | Rob Pears |  | 2017-11-20 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP287 | Workgroup Stage | Proposer has clarified that no further RFI would be required for CMP286/CMP287 (demand forecast fixing) and although the TCR may reduce the benefits of CMP286/CMP287, CMP286/CMP287 would not itself have any impact on the TCR. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Low so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged. | Low | • Panel recognised the work done so far but noted the interactions with TCR and the potential need for a 2nd Request for Information on CMP287. Need to understand the TCR outcome before progressing further October Panel agreed to leave priority unchanged. | CUSC | 2017-10-10 | Niall Coyle | Npower | Improving TNUoS Predictability Through Increased Notice of Inputs Used in the TNUoS Tariff Setting Process. | Improve the predictability of TNUoS demand charges by bringing forward the date at which certain parameters used in TNUoS tariff setting (such as demand forecasts) are fixed to allow customer prices to more accurately reflect final TNUoS rates. | Suppliers, Generators, embedded generators and National Grid | Standard Governance Route with Workgroup | No | Joe Henry | Rob Pears |  | 2017-11-20 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP288 | Workgroup Stage | Workgroup Report was due to be presented at October 2019 Panel. The original Proposer (NGET) applied for materially impacted party status. Noted to August Panel that further extension will need to be requested but we need to get workgroup meeting in diary before we can confirm what extension will be needed. Ofgem have sent their response to NGET's request and have granted them Materially Impacted Party Status for CMP288 but not CMP289 and also not on an enduring basis. Last Workgroup held 2 December 2019. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Low to Medium so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged. | Low to Medium | • Panel recognised a lot of work done on this, but Workgroup Members on the Panel questioned whether or not 2 workgroups are sufficient to complete this • Materiality unclear as proposal seeks to add transparency to the existing arrangements October Panel agreed to leave priority unchanged. | CUSC | 15/2/2018 | Richard Woodward | NGET | Explicit charging arrangements for customer delays and backfeeds | Seeks to recover additional costs incurred by Transmission Owners and TNUoS liable parties as a result of Transmission Owners completing transmission works earlier than the contracted Completion Date or the party connecting initiating a delay to the contracted Completion Date. The changes to the non-charging element of the CUSC are covered under CMP289. | Electricity Transmission Owners; Developers requiring new generation, interconnector or demand connections | Standard Governance Route with Workgroup | No | Joe Henry | Rob Pears |  | 2018-02-23 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP289 | Workgroup Stage | Workgroup Report was due to be presented at October 2019 Panel. The original Proposer (NGET) applied for materially impacted party status. Noted to August Panel that further extension will need to be requested but we need to get workgroup meeting in diary before we can confirm what extension will be needed. Ofgem have sent their response to NGET's request and have granted them Materially Impacted Party Status for CMP288 but not CMP289 and also not on an enduring basis. Last Workgroup held 2 December 2019. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Low to Medium so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged. | Low to Medium | • Panel recognised a lot of work done on this, but Workgroup Members on the Panel questioned whether or not 2 workgroups are sufficient to complete this • Materiality unclear as proposal seeks to add transparency to the existing arrangements October Panel agreed to leave priority unchanged. | CUSC | 15/2/2018 | Jon Wisdom | ESO | Consequential change to support the introduction of explicit charging arrangements for customer delays and backfeeds via CMP288 | Seeks to recover additional costs incurred by Transmission Owners and TNUoS liable parties as a result of Transmission Owners completing transmission works earlier than the contracted Completion Date or the party connecting initiating a delay to the contracted Completion Date. The changes to the charging element of the CUSC are covered under CMP288. | Electricity Transmission Owners; Developers requiring new generation, interconnector or demand connections | Standard Governance Route with Workgroup | No | Joe Henry | Rob Pears |  | 2018-02-23 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP291 | Workgroup Stage | Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Low so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged. | Low | • Complex change • Enduring requirement but no compliance date set October Panel agreed to leave priority unchanged. | CUSC | 15/2/2018 | Garth Graham | SSE | The open, transparent, non discriminatory and timely publication of the harmonised rules for grid connection (in accordance with the RfG, DCC and HVDC) and the harmonised rules on system operation set out within the Bilateral Agreements | Aims to set out within the CUSC the obligations in the EU Connection Network Codes and System Operation Guideline as they relate to the harmonised rules for connection and system operation in GB. | Transmission Owners (including OFTOs and Interconnectors), Distribution Network Operators, Transmission System Users, System Operator, Generators, Demand customers and providers of services | Standard Governance Route with Workgroup | No | Nisar Ahmed | Rob Pears |  | 2018-02-23 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP292 | Pending Authority Decision | Draft Final Modification Report approved at July Panel. Final Modification Report submitted 16 August 2019. CMP292 decision was expected 20 September 2019; however, at August 2020 Panel, Ofgem advised that this has been further de-prioritised as they are prioritising decisions on the TCR Modifications. Ofgem re-iterated at January 2021 Panel that this remains de-prioritised. | - | n/a | CUSC | 15/2/2018 | Jon Wisdom | ESO | Introducing a Section 8 cut-off date for changes to the Charging Methodologies | Ensure that CUSC Charging Methodologies are fixed in advance of the relevant Charging Year to allow ESO to appropriately set and forecast charges with the aim of reducing the risk of charges out-turning differently to the forecasts produced by ESO and created by Users. | Chargeable Users, The Company | Standard Governance Route with Workgroup | No | Ren Walker | n/a |  | 2018-02-23 | 2018-12-05 | 2018-12-20 | 2018-12-20 | 2018-12-20 | 0 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-16 | 2019-09-20 | 2021-04-01
CMP298 | Workgroup Stage | Workgroup Report was due to be presented at December 2019 Panel. Workgroup held 4 October 2019 to review the workgroup report, legal text and product document where it was clear a number of iterations were still required. Next Workgroup Meeting was to be held 9 December 2019 with a view to issuing for workgroup consultation shortly thereafter but no comments had been received from Workgroup - they have now. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The June Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. June Panel determined that Priority of this was Low. October Panel reviewed the request from the Open Networks to re-start Workgroups and noted the increasing risk of divergence in treatment across Network Operators. Therefore, priority was raised to Medium. Workgroups proposed for 23 February 2021 and 3 March 2021 ahead of Workgroup Consultation. | Medium | • Will have long term benefits to consumers (by allowing more projects to connect and so provide more competition in the generation market • Complex change • This is a process improvement modification and is seeking to reflect current working practice. However, there is risk of inconsistency in its application by Network Operators so important that Code changes are progressed. October Panel reviewed the request from the Open Networks to re-start Workgroups and noted the increasing risk of divergence in treatment across Network Operators. Therefore, priority was raised from Low to Medium. Code Admin will liaise with Proposer and Open Networks on next steps including timing of next Workgroup. | CUSC | 17/4/2018 | Grahame Neale | ESO | Updating the Statement of Works process to facilitate aggregated assessment of relevant and collectively relevant embedded generation | Due to increasing levels of embedded generation connections the process for assessing their overall impact on the transmission system needs to be revised allowing ESO to recognise the changes caused by multiple small scale connections and plan accordingly. | DNO's, TO's, embedded generators and the System Operator | Standard Governance Route with Workgroup | No | Paul Mullen | n/a |  | 2018-04-27 | 2021-03-03 | 11/3/21 to 1/4/21 | 2021-04-12 | 2021-04-16 |  | 2021-04-30 | 7/5/21 to 28/5/21 | 2021-06-25 | 2021-07-07 | TBC | TBC
CMP300 | Pending Authority Decision | October 2020 Panel were asked to approve that the Terms of Reference have been met and agree for CMP300 to proceed to Code Administrator Consultation. More detail on the Benefits/Costs was provided within the updated Workgroup Report; however, Panel still required illustrative numbers to be added before they approve that the Terms of Reference have been met. This has now been added and on 9 November Panel agreed that the Terms of Reference had been met. Code Administrator Consultation was issued 9 November 2020 and closed 5pm on 9 December 2020 with 2 responses received. Changes were proposed to the legal text as part of the responses to the Code Administrator Consultation. The CUSC Panel considered these changes and by majority agreed that these changes were minor rather than typographical. In accordance with CUSC 8.23.4 , the CUSC Panel directed the CMP300 Workgroup to review these changes. If the CMP300 Workgroup unanimously agree that these changes are minor, then the Draft Final Modification Report will be presented for recommendation vote at a Special Panel already scheduled for 8 January 2021. The CMP300 Workgroup unanimously agreed that the changes were minor and the Draft Final Modification Report was presented for recommendation vote at 8 January 2021. Special Panel on 8 January 2021 agreed by majority that the CMP300 Original and WACM1 better facilitated the CUSC objectives than the current CUSC arrangements. Final Modification Report sent to Ofgem on 19 January 2021. Ofgem at January 2021 Panel indicated that a decision would be made ~ mid February 2021. | - | n/a | CUSC | 17/5/2018 | Paul Youngman | Drax | Cost reflective Response Energy Payment for Generators with low or negative marginal costs | To ensure that the Response Energy Payment paid to or by generators with respect to a Balancing Mechanism Unit with low or negative marginal costs is reflective of the cost or avoided cost of energy production. | Medium impact on Mandatory Frequency Response (MFR) providers and National Grid Electricity System Operator (ESO) | Standard Governance Route with Workgroup | Yes | Paul Mullen | n/a |  | 2018-05-25 | 2019-10-31 | 2019-04-01 | 2019-05-01 | 2019-10-31 | 1 | 2020-10-30 | 2020-12-09 | 2021-01-08 | 2021-01-19 | 2021-02-09 | 10 working days after Ofgem decision
CMP301 |  | Panel voted unanimously to approve CMP301 at Special Panel meeting on 4 April 2019. Authority Decision approving CMP301 received 11 June 2019. Implemented 1 April 2020. | - | n/a | CUSC | 21/6/2018 | Jon Wisdom | ESO | Clarification on the treatment of project costs associated with HVDC and subsea circuits | Building on CMP213, which introduced specific expansion factors for HVDC and subsea circuits, ensuring this is consistent with the rules for onshore circuits | CUSC Parties who are subject to TNUoS charges | Standard Governance Route, straight to Code Admin Consultation |  | Ren Walker | n/a | 2018-06-21 | 2018-06-29 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2018-07-02 | 2018-07-27 | 2018-08-01 | 2019-05-01 | 2020-04-01
CMP303 |  | Workgroup held 29 August 2019 to address Ofgem feedback. Code Administrator Consultation (running for 5 working days) issued 25 September and closed 2 October 2019. Draft Final Modification Report presented to October Panel - Panel recommended by majority that both Original and WACM3 better facilitated the CUSC Objectives than the Baseline. Final Modification Report sent to Ofgem 11 November 2019 - decision expected by 16 December 2019. Ofgem believe CMP303, CMP320 and CMP337 are all linked and proposed to decide on them together in July 2020.On 3 July 2020, Ofgem rejected CMP303 and its alternatives as given the approval of CMP337/338 (on 3 July 2020), CMP303 and its alternatives would be unnecessary and inefficient. | - | n/a | CUSC | 19/7/2018 | Paul Mott | EDF Energy | Improving local circuit charge cost-reflectivity | Seeks to remove additional costs from local circuit expansion factors that are incurred beyond the connected, or to-be-connected, generation developers’ need. | Some local circuit-connected generation connecters Other users of the transmission system (generators) who directly or indirectly pay TNUoS charge (very low) | Standard Governance Route with Workgroup |  | Ren Walker | n/a | 2018-07-19 | 2018-07-27 | 2018-12-20 | 2018-12-20 | 2018-12-20 | 2018-12-20 | 9 | 2019-02-01 | 2019-03-01 | 2019-10-25 | 2019-11-11 | 2020-07-03 | Rejected
CMP304 | Workgroup Stage | Placed 'on hold' until July 2019 at the Panel in April 2019. Proposer was awaiting the National Grid ESO product road map to be presented; however, National Grid ESO have since confirmed they are not now producing a Roadmap. It was agreed at July 2019 Panel that work on this Modification will restart. Last Workgroup Meeting was held on 16 December 2019. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Medium so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged. | Medium | • Modification seeks to apply a different timescale to the provision on reactive power – Panel divided though on whether this is a simple change as solution still needs to be clarified • Ofgem cannot make a final decision on CMP305 until CMP304 is completed • Decreased cost to consumers if more competition October Panel agreed to leave priority unchanged. | CUSC | 23/8/2018 | Garth Graham | SSE | Improving the Enhanced Reactive Power Service by making it fit for purpose | This proposal aims to ensure that the reactive power services (I) delivers transparency and clear information to the market; (ii) facilitates greater competition in the provision of services; and (iii) meets the changing needs of balancing services providers and operational requirements of the system operator. | ESO and providers of reactive power | Standard Governance Route with Workgroup | No | Kirsten Shilling | Shazia Akhtar | 2018-08-23 | 2018-08-31 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP305 | On Hold | Ofgem sent CMP305 back with a request for additional information. Ofgem have stated that they wish to make the decision on CMP305 at the same time as CMP304. | - | n/a | CUSC | 23/8/2018 | Urmi Mistry | ESO | Removal of the Enhanced Reactive Power Service (ERPS) | The aim of this modification is to remove references to the Enhanced Reactive Power Service (ERPS) from the CUSC. ERPS is an opt-in tendered commercial service for which no tenders have been submitted in seven and a half years, and no contracts have been agreed in nine years. | This proposal has low impact on industry and providers of balancing services. No tenders have been received for this service since January 2011, and there have been no new contracts signed since October 2009. | Standard Governance Route with Workgroup | No | Ren Walker | n/a | 2018-08-23 | 2018-08-31 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2018-10-05 | 2018-11-30 | 2018-12-19 | Sent back - Timeline to align to CMP304 | TBC
CMP306 | Implementation | Workgroup Report approved at August 2019 Panel. Issued for Code Administrator Consultation 11 September 2019 and closed 5pm on 2 October 2019. Draft Final Modification Report presented to October Panel - Panel recommended unanimously that Original better facilitated the CUSC Objectives than the Baseline. Final Modification Report sent to Ofgem 11 November 2019 - decision expected by 19 December 2019. Ofgem advised at February Panel that the related STC issue has been resolved and they are minded to approve this by end March 2020. On 24 March 2020, Ofgem announced that they were reviewing their work plans for 2020 in light of the Coronavirus national emergency. They also announced that from Wednesday 25 March they would temporarily pause publishing new information on their website (with some specific exceptions) until this review has been completed. Ofgem completed this review on 16 April 2020. At April CUSC Panel, Ofgem advised that the publishing moratorium would be lifted on 29 April 2020 and approved CMP306 on 21 May 2020 with Implementation Date of 1 April 2021. | - | n/a | CUSC | 20/9/2018 | Lee Wells | Northern Powergrid | Align annual connection charge rate of return at CUSC 14.3.21 to price control cost of capital | Seeks to align the rate of return applied to the net asset value of connection points in the calculation of annual connection charges (as set out at paragraph 14.3.21 of the Connection Charging Methodology) to the pre-tax cost of capital in the price control of the Relevant Transmission Licensee (plus a margin of 1.5 percentage points in the case of MEA-linked assets). This will improve the cost reflectivity of the charges, since the return on capital will equal the Authority’s most recent assessment of that cost for the Relevant Transmission Licensee. | Chargeable Users under the Connection Charging Methodology and transmission licensees | Standard Governance Route with Workgroup | No | Ren Walker | n/a |  | 2018-09-28 | 2019-08-01 | 2019-04-01 | 2019-08-01 | 2019-08-01 | 0 | 2019-08-30 | 2019-09-13 | 2019-10-25 | 2019-11-01 | 2020-05-21 | 2021-04-01
CMP307 | On Hold | Was put on hold awaiting TCR decision. Now that Ofgem have published their Direction on the Targeted Charging Review, Code Admin contacted Proposers to ascertain if Modification needs to be progressed or withdrawn. Noted to June Panel that Proposer are keen to progress this but suggested waiting for conclusion of 2nd BSUoS taskforce before proceeding. Prioritisation of this Modification will be discussed following final 2nd BSUoS final Taskforce Recommendation (end of November 2020 to mid December 2020) - October Panel agreed to leave priority unchanged. On 14 December 2020, Proposer notified their wish to withdraw CMP307 and Code Admin notified industry of this and asked that anyone who wishes to support CMP307 and become the official Proposer to notify cusc.team@nationalgrideso.com by 5pm on 21 December 2020. As no notice to support CMP307 in place of the Proposer was received, Panel were asked under 8.16.10(b) to agree to the withdrawal of CMP307 at the Special Panel on 8 January 2021 - Panel agreed to this. | - | • Supported Proposer’s view to wait first for final 2nd BSUoS final Taskforce Recommendation and confirmation of Ofgem’s planned steps thereafter October Panel agreed to leave priority unchanged. | CUSC | 20/9/2018 | Simon Lord | Engie | Expanding the BSUoS charging base to include embedded generation | Seeks to change the current collection of BSUoS from suppliers and embedded Exemptible generation to a methodology where BSUoS is charged on a gross basis to suppliers and BSUoS is charged on exports from embedded Exemptible generation. | This proposal will have a high impact on embedded generation and a moderate impact (reduction) on all others who are currently subject to BSUoS. | TBC | No | TBC | TBC |  | 2018-09-28 | n/a | n/a | n/a | n/a | 0 | n/a | n/a | n/a | n/a | n/a | n/a
CMP308 | Workgroup Stage | Workgroup Alternatives and Legal Text being finalised. December Panel confirmed this was still a high priority Modification and there was a prevailing view that the work done on CMP308 would be brought into the discussions on CMP333 - CMP308 could have even be a Workgroup Alternative to CMP333 Original Proposal. This has not happened and progress of this Modification is dependent on the outcome of the 2nd BSUoS taskforce - therefore next Workgroup will be no earlier than until outcome of the 2nd BSUoS taskforce is known. October Panel agreed to leave priority unchanged - some Panel members believed it prudent to wait until Ofgem conclusions on the 2nd BSUoS taskforce; whilst some Panel members supported the Proposer's opinion that direction of travel is known and better to get this re-started and get Workgroups in the diary. At December Panel, the Panel agreed to move CMP308 from “Low” to “High” following publication of Ofgem’s conclusions on the 2nd BSUoS Taskforce on 11 December 2020. Workgroups on CMP308 held 27 January 2021 and 16 February 2021 with next Workgroup on 10 March 2021. | High | • Panel supportive of progressing but agreed to wait first for final 2nd BSUoS final Taskforce Recommendation and confirmation of Ofgem’s planned steps thereafter October Panel agreed to leave priority unchanged - some Panel members believed it prudent to wait until Ofgem conclusions; whilst some Panel members supported the Proposer's opinion that direction of travel is known and better to get this re-started and get Workgroups in the diary. Panel noted that Ofgem's conclusions are due to be published soon (end of November 2020/mid December 2020) so by majority agreed to delay decision on priority for CMP308 until after such decision. At December Panel, the Panel agreed to move CMP308 from “Low” to “High” following publication of Ofgem’s conclusions on the 2nd BSUoS Taskforce on 11 December 2020. Workgroups on CMP308 re-started January 2021. | CUSC | 19/10/2018 | Simon Vicary | EDF | Removal of BSUoS charges from Generation | This proposal seeks to modify the CUSC to better align GB market arrangements with those prevalent within other EU member states by removing BSUoS charges from Generation. | Generators and Suppliers | Standard Governance Route with Workgroup | No | Joe Henry | Kavita Patel |  | 2018-10-26 | TBC | 2019-04-01 | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP309 |  | Modifications prepared for a 'no deal' Brexit scenario. CMP309 applies to the non charging CUSC applicable objectives, CMP310 applies to the charging CUSC objectives. A Code Administrator Consultation has already been held from 28 February 2019 to 21 March 2019 (the “First Code Administrator Consultation”) - there was 1 respondent. Since, the First Code Administrator Consultation, the legal text has changed. Given these changes and the time that has elapsed since the First Code Administrator Consultation, the CUSC Panel on 30 October 2020 agreed with the Code Administrator’s proposal to have a Second Code Administrator Consultation. The Second Code Administrator Consultation was opened on 6 November 2020 and closed 5pm on 27 November 2020 with no responses received. Timing of when the Draft Final Modification Report will be presented to Panel depends if and when a no deal scenario is confirmed. As a Deal was approved formally by Government on 30 December 2020, both CMP309 and CMP310 will be withdrawn (as they both relate to a No Deal scenario). The Proposer of CMP309 & CMP310 has withdrawn support of the modifications and no-one expressed support to become the new Proposer by 5pm on 13 January 2021. Therefore Panel, on 29 January 2021, were asked under 8.16.10(b) to agree to the withdrawal of CMP309 and CMP310 - Panel agreed to this. | - | n/a | CUSC | 15/2/2019 | Katharina Birkner | ESO | CUSC changes in the event the UK leaves the EU without an agreement | The proposed modification aims to ensure that retained EU law will function effectively in the context of the CUSC. In the event the United Kingdom leaves the European Union without an agreement, it will ensure that the CUSC takes into account the provisions in the relevant Statutory Instruments that have been prepared under the European Union (Withdrawal) Act 2018 as well as relevant consequential licence modifications. | NA | Self - Governance, straight to Code Admin Consultation | No | Paul Mullen | n/a |  | 2019-02-25 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2020-11-27 | N/A - to be withdrawn | N/A Self governance mod | N/A Self governance mod | N/A - to be withdrawn
CMP310 |  | Modifications prepared for a 'no deal' Brexit scenario. CMP309 applies to the non charging CUSC applicable objectives, CMP310 applies to the charging CUSC objectives. A Code Administrator Consultation has already been held from 28 February 2019 to 21 March 2019 (the “First Code Administrator Consultation”) - there was 1 respondent. Since, the First Code Administrator Consultation, the legal text has changed. Given these changes and the time that has elapsed since the First Code Administrator Consultation, the CUSC Panel on 30 October 2020 agreed with the Code Administrator’s proposal to have a Second Code Administrator Consultation. The Second Code Administrator Consultation was opened on 6 November 2020 and closed 5pm on 27 November 2020 with no responses received. Timing of when the Draft Final Modification Report will be presented to Panel depends if and when a no deal scenario is confirmed. As a Deal was approved formally by Government on 30 December 2020, both CMP309 and CMP310 will be withdrawn (as they both relate to a No Deal scenario). The Proposer of CMP309 & CMP310 has withdrawn support of the modifications and as no-one has expressed support to become the new Proposer by 5pm on 13 January 2021, we will seek formal withdrawal of these at the CUSC Panel on 29 January 2021. | - | n/a | CUSC | 15/2/2019 | Katharina Birkner | ESO | CUSC section 14 changes in the event the UK leaves the EU without an agreement | The proposed modification aims to ensure that retained EU law will function effectively in the context of the CUSC. In the event the United Kingdom leaves the European Union without an agreement, it will ensure that the CUSC takes into account the provisions in the relevant Statutory Instruments that have been prepared under the European Union (Withdrawal) Act 2018 as well as relevant consequential licence modifications. | NA | Self - Governance, straight to Code Admin Consultation | No | Paul Mullen | n/a |  | 2019-02-25 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2020-11-27 | N/A - to be withdrawn | N/A Self governance mod | N/A Self governance mod | N/A - to be withdrawn
CMP311 | Workgroup Stage | Workgroup Consultation issued 1 October 2019 and open until 29 October 2019. Webinar held 21 October 2019 to explain the proposed change and impacts to be held during the consultation period. Meeting held 11 November 2019 to discuss the Workgroup Consultation responses. 1 workgroup alternative raised and was discussed at meeting on 10 December 2019. May 2020 Panel noted that ESO are revising their solution so Workgroup Report was not presented to May 2020 Panel as originally anticipated. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Medium to High. Workgroups were due to commence from November 2020; however, at September Panel, ESO highlighted that the RIIO draft determinations are due to be published in December and the ESO are anticipating that this will resolve the issue that CMP311 addresses. As this won’t be confirmed until the determinations are published, October Panel agreed to de-prioritise and revisit at February 2021 Panel. | Medium to High | • Important in current Covid-19 environment to provide as much clarity for suppliers as possible • Solution already consulted on and even with revised solution anticipate 2 Workgroups to get this to Panel Workgroups were due to commence from November 2020; however, at September Panel, ESO highlighted that the RIIO draft determinations are due to be published in December and the ESO are anticipating that this will resolve the issue that CMP311 addresses. As this won’t be confirmed until the determinations are published, October Panel agreed to de-prioritise and revisit at February 2021 Panel. | CUSC | 15/2/2019 | James Stone | ESO | Reassessment of CUSC credit requirements for Suppliers, specifically for “User Allowed Credit” as defined in Section 3, Part III section 3.27 of the CUSC | CMP311 will be changing the amount of credit that is allowed to Suppliers under the User Allowed Credit requirements. | Suppliers | Standard Governance Route with Workgroup | No | Paul Mullen | Rachel Beaufoy |  | 2019-02-25 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP314 |  | Ofgem decision received 22 August 2019 approving CMP314. Implemented 1 April 2020. | - | n/a | CUSC | 15/2/2019 | Jon Wisdom | ESO | Updating the CUSC to align Power Available with the Grid Code definition for Power Park Modules | To align the CUSC with the Grid Code on the use of Power Available in ESO headroom calculations for Power Park Modules. | Positive impact for Power Park Modules – e.g. intermittent generators. It helps enable participation in MFR (Mandatory Frequency Responses) in a way that is equitable to controllable generation types | Self - Governance, straight to Code Admin Consultation |  | Ren Walker | n/a |  | 2019-04-01 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2019-05-01 | 2019-06-01 | 2019-07-12 | 2019-08-22 | 2020-04-01
CMP315 | Workgroup Stage | Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Low to Medium so there are no Workgroups expected imminently. October Panel noted that CMP315 is considering similar subject matter to CMP353 and agreed that CMP315 could be considered, alongside any further Modification Proposals if necessary, as part of an enduring solution to address the potential issues in the current calculation of the Expansion Constant and Expansion Factors. As a decision is expected by 2 December 2020 on CMP353 and this decision may comment on potential enduring solutions, Panel agreed to leave priority for CMP315 unchanged until such decision is made. However, November 2020 Panel agreed to move CMP315 from “Low to Medium” to “High” in light of recent developments re: the Expansion Constant. Workgroups on CMP315 will re-start ~March 2021. | High | • Panel recognised there is a material impact here; however, argued that need to understand the TCR outcome before progressing further October Panel noted that CMP315 is considering similar subject matter to CMP353 and agreed that CMP315 could be considered, alongside any further Modification Proposals if necessary, as part of an enduring solution to address the potential issues in the current calculation of the Expansion Constant and Expansion Factors. As a decision is expected by 2 December 2020 on CMP353 and this decision may comment on potential enduring solutions, Panel agreed to leave priority for CMP315 unchanged until such decision is made. However, November 2020 Panel agreed to move CMP315 from “Low to Medium” to “High” in light of recent developments re: the Expansion Constant. Workgroups on CMP315 will re-start March 2021. | CUSC | 16/4/2019 | Nick Sillito | PeakGen | TNUoS: Review of the expansion constant and the elements of the transmission system charged for | The expansion constant is a key input in setting the value of the locational element of transmission network use of system charges. This modification proposal would review how the expansion constant is determined such that it best reflects the costs involved. | Generators and suppliers paying locational TNUoS charges | Standard Governance Route with Workgroup | No | Paul Mullen | Kavita Patel |  | 2019-04-01 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP316 | Workgroup Stage | First workgroup held 20 June 2019. Second meeting held on 16 September 2019. Workgroup members strongly argued that an amendment to the SQSS would be required in order to amend charges for co-location. ESO representative to consider this. If ESO concur with this, the work will take a considerable amount of time. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Medium so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged. | Medium | • Although not many co-located sites currently, this complex change needs to be progressed before volumes become large and unmanageable • Clarity needed ahead of Contracts for Difference Auctions in 2021 • April 2022 Implementation October Panel agreed to leave priority unchanged. | CUSC | 16/4/2019 | Katharina Birkner | ESO | TNUoS Charging Methodology for Co-located Generation | Generation sites which comprise multiple technology types within one Power Station are termed “co-located”. This modification will develop a cost-reflective methodology to allow the CUSC charging arrangements to accommodate the growing number of such sites. | Co-located Generators, NGESO | Standard Governance Route with Workgroup | No | Shazia Akhtar | Kavita Patel |  | 2019-04-01 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP317 / CMP327 | Implementation | Following Ofgem’s TCR decision on 21 November 2019, CMP327 was raised by National Grid ESO as an Urgent proposal and given the linkages with CMP317 also requested CMP317 to be treated as Urgent and requested for CMP327 to be amalgamated with CMP317. Panel agreed to urgency and amalgamation for both CMP317 and CMP327 so this will be progressed on a Urgent timetable subject to Ofgem approval. Requests for Urgency and amalgamation issued to Ofgem 2 December 2019. On 29 January, Ofgem approved the Panel's request for amalgamation but on 10 February rejected the request for Urgency. Workgroup Consultation launched 20 February 2020 and closed 12 March 2020. June 2020 Panel unanimously agreed that Workgroup had met its Terms of Reference and this could proceed to Code Administrator Consultation. Code Administrator Consultation was issued 29 June 2020 and closed 5pm on 20 July 2020. The July 2020 CUSC Panel recommended by majority that, of the Original and WACMs 1 – 83, the following better facilitated the CUSC Objectives than the Baseline: WACMs 7, 8, 14, 15, 49, 50, 52, 53, 56, 57, 59, 60, 70, 71, 73, 74, 77, 78, 80 and 81. Final Modification Report sent to Ofgem on 13 August 2020. At November 2020 Panel, Ofgem confirmed that they expect decision to be made before Christmas 2020. Ofgem decision was received 17 December 2020 - both the CMP327/317 and CMP339 Original Proposals will be implemented on 1 April 2021 | - | n/a | CUSC | 22/5/2019 (CMP317) 28/11/2019 (CMP327) | Jon Wisdom | ESO | Identification and exclusion of Assets Required for Connection when setting Generator TNUoS charges (CMP317) Removing the Generator Residual from TNUoS Charges (TCR) (CMP327) | Ensuring that average generator transmission charges set under the CUSC methodology did not fall below the €0-2.50/MWh range stipulated in EU regulation 838/2010 (The Limiting Regulation). (CMP317) Change the TNUoS Charging Methodology such that the Residual element of Generator TNUoS is £0 (CMP327) | Generator Users liable for TNUoS (High Impact) Supplier Users liable for TNUoS (Medium Impact) | Standard Governance Route with Workgroup | No | Rob Marshall | Joe Henry |  | 2019-05-01 | 2020-02-03 | 2020-03-12 | 2020-06-09 | 2020-06-16 | 83 | 2020-06-26 | 2020-07-20 | 2020-07-31 | 2020-08-13 | 2020-12-17 | 2021-04-01
CMP318 |  | At August Panel, Panel recommended that the Final Modification Report can be issued to Authority - sent 10 October 2019. Ofgem approved Modification on 11 November 2019 - Implemented 1 April 2020. | - | n/a | CUSC | 22/5/2019 | Jon Wisdom | ESO | Maintaining Non Half- Hourly (NHH) charging arrangements for Measurement Classes F and G | To extend the period over which Meter Point Administration Numbers (MPANs) in Measurement Classes F and G are treated as Non Half Hourly for Transmission Network Use of System (TNUoS) charging purposes | Supplier Users | Standard Governance Route, straight to Code Admin Consultation |  | Ren Walker | n/a |  | 2019-05-01 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2019-08-01 | 2019-08-01 | 2019-10-10 | 2019-11-11 | 2020-04-01
CMP319 | Implementation | Panel voted by majority to approve Draft Final Modification Report at Special Panel 12 September 2019. Following 27 September Panel, issued 5 day Code Admin Consultation for related Modification CMP281 on a proposed legal text change on 4 October 2019 (closed 11 October 2019). Final Modification Reports for CMP280, CMP281 and CMP319 sent to Ofgem on 15 October 2019. Ofgem decision was expected on or before 19 November 2019. On 24 March 2020, Ofgem announced that they were reviewing their work plans for 2020 in light of the Coronavirus national emergency. They also announced that from Wednesday 25 March they would temporarily pause publishing new information on their website (with some specific exceptions) until this review has been completed. Ofgem completed this review on 16 April 2020. At April CUSC Panel, Ofgem advised that the publishing moratorium would be lifted on 29 April 2020 and approved CMP319 on 21 May 2020. Implementation Date 1 April 2021. | - | n/a | CUSC | 20/6/2019 | Simon Lord | Engie | Consequential changes to Section 11 of the CUSC as a result of CMP280 and/or CMP281 | As part of the Workgroup analysis, the Workgroup identified that CMP 280 and 281 are charging modification and as such can only change section 14 of the CUSC. If either modification is approved changes to other none charging sections of the CUSC will be required. These changes cannot be achieved with CMP280 And CMP281. The principle addition related to the definitions of storage as a class. The definitions are common to CMP 280, 281 and their alternates. | National Grid ESO: Changes will be required to the BSUoS and TNUoS billing systems to tag out the appropriate metered import volumes for the purpose of the BSUoS and TNUoS charging base. Suppliers: The reduced recovery of BSUoS and TNUoS charges from storage operators will need to be recovered from the balance of parties liable to BSUoS and TNUoS | Standard Governance Route, straight to Code Admin Consultation | No | Ren Walker | n/a |  | 2019-07-01 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2019-07-01 | 2019-09-12 | 2019-10-01 | 2020-05-21 | 2021-04-01
CMP320 | Implementation | Workgroup Report presented to December's Panel at which Panel agreed that the terms of reference have been met and this could proceed to Code Administrator Consultation. Code Administrator Consultation sent 17 December 2019 and closed 5pm on 20 January 2020. Draft Final Modification Report presented to January's Panel at which Panel recommended unanimously that the Original was better than Baseline and by majority that WACM1 and WACM2 were better than the Baseline. Final Modification Report sent to Ofgem 12 February 2020. Ofgem approved CMP320 Original 9 July 2020 - to be implemented 1 April 2021. | - | n/a | CUSC | 18/7/2019 | Jennifer Geraghty | SSE | Island MITS Radial Link Security Factor | Islands that have a MITS Node but are served by a single circuit radial link are exposed to non-cost reflective charging of a 1.8 Security Factor rather than the application of a 1.0 Security Factor. This proposal will apply a 1.0 Security Factor in that situation. | Island based Generation (High Impact) Non Island based Users (Low Impact) | Standard Governance Route with Workgroup | No | Paul Mullen | n/a |  | 2019-07-01 | 2019-08-23 | 2019-09-06 | 2019-11-08 | 2019-12-05 | 2 | 2019-12-13 | 2019-12-17 | 2020-01-31 | 2020-02-12 | 2020-07-09 | 2021-04-01
CMP322 |  | Presented at September Panel. Panel approved for this to be issued for Code Administrator Consultation, which was issued 24 October 2019 and closed 14 November 2019. November Panel carried out recommendation vote and unanimously recommended that the Original better facilitated the relevant objectives than the Baseline. Final Modification Report sent to Ofgem 24 December 2019. Ofgem decision 5 February 2020 approving CMP322. Implemented 4 April 2020. | - | n/a | CUSC | 2019-09-19 | John Welch | ESO | Updating the CUSC section 4 “Balancing Services” to ensure Ofgem have the appropriate authority to approve Ts and Cs, relevant to EBGL Article 18, held within the SCTs | Seeks to amend the CUSC to create a mechanism for Ofgem to approve changes to the ESO Standard Contract Terms when those changes include amendments to the Terms & Conditions related to balancing. | Ofgem and National Grid ESO contracts team to ensure SCT process is updated in line with CUSC requirements (Low Impact) | Standard Governance Route with Workgroup |  | Ren Walker | n/a |  | 2019-09-27 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2019-11-14 | 2019-11-29 | 2019-12-24 | 2020-02-07 | 2020-04-04
CMP323 |  | Presented at September Panel; Panel raised queries and was then re-presented to October Panel . The Panel agreed that CMP323 met the Standard Governance criteria and by majority agreed the modification should proceed to Code Administrator Consultation once the related BSC and Grid Code Modification Workgroups have been held so there is consistency across the Codes. Following approval from February Grid Code Review Panel that GC0132 had met its Terms of Reference, CMP323 Code Administrator Consultation issued 18 March and closed 5pm on 8 April 2020. Draft Final Modification Report presented to April's Panel at which Panel recommended by majority that the Original was better than Baseline. Final Modification Report sent to Ofgem 6 May 2020 and decision to implement the Original proposal was received 23 June 2020. This was implemented 25 June 2020. June Panel noted that a fast track self governance Modification will be raised in July 2020 to include a table mapping the EBGL Article 18 Terms and Conditions for Balancing Service Providers and Balancing Responsible Parties to the CUSC. This will be used to confirm if a CUSC Modification has EBGL impacts. | - | n/a | CUSC | 19/9/2019 | John Welch | ESO | Updating the CUSC governance process to ensure we capture the EBGL change process for Article 18 T and Cs | To ensure that the governance process for making future changes to the European Balancing Guidelines (EBGL) Article 18 (A18) T and Cs that are found in the CUSC incorporates the amendment process as laid out in EBGL Article 6 (A6) and Article (A10). | Code Governance team at National Grid ESO; industry parties raising Modifications (Low Impact) | Standard Governance Route, straight to Code Admin Consultation |  | Ren Walker | n/a |  | 2019-10-01 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2020-04-08 | 2020-04-24 | 2020-05-06 | 2020-06-23 | 2020-06-25
CMP324 | Implementation | CMP324 presented at September Panel and Panel approved for this to be sent to Workgroup. Recognised that defect was very tightly defined and therefore CMP325 presented at October Panel to allow alternatives to be raised. Panel agreed that CMP325 met the Standard Governance criteria and agreed the modification should proceed to workgroup. Panel also agreed that CMP324 and CMP325 will be progressed jointly with 1st workgroup held 22 November 2019 and 2nd workgroup held 19 December 2019. Panel agreed updated Terms of Reference at January 2020 Panel. Workgroup Consultation launched on 26 February 2020 and closed 18 March 2020. Meeting held 26 March 2020 to discuss responses at which Workgroup felt that there was insufficient time to develop Workgroup Alternatives to get Workgroup Report to April Panel. March Panel agreed that CMP324/325 Workgroup Report will be presented to May 2020 (rather than April 2020 Panel). May Panel agreed that Workgroup had met its Terms of Reference and this could proceed to Code Administrator Consultation - this was issued on 3 June 2020 and closed at 5pm on 24 June 2020. The July 2020 CUSC Panel recommended by majority that the Original, WACM1 and WACM3 better facilitated the CUSC Objectives than the Baseline. However, the CUSC Panel recommended by majority that WACM2 did not better facilitate the CUSC Objectives than the Baseline. Final Modification Report sent to Ofgem on 13 August 2020 - decision received 11 November 2020 approving WACM2 (use the current 27 TNUoS charging zones within the CUSC and remove the requirement of re-zoning at the start of every Transmission Price Control). Implementation Date is 1 April 2021. | - | n/a | CUSC | 19/9/2019 | Grahame Neale | ESO | Generation Zones – changes for RIIO-T2 | The CUSC requires that generation zones, used for Transmission Network Use of System (TNUoS) tariff setting, are reviewed at the start of each price control period. This CMP seeks to change the zones and the underlying methodology used to establish them. | Generator Users liable for generation TNUoS (High Impact) | Standard Governance Route with Workgroup | No | Joe Henry | Jennifer Groome |  | 2019-09-27 | 2020-02-18 | 2020-03-18 | 2020-04-22 | 2020-04-22 | 3 | 2020-05-29 | 2020-06-24 | 2020-07-31 | 2020-08-13 | 2020-11-11 | 2021-04-01
CMP325 | Implementation | CMP324 presented at September Panel and Panel approved for this to be sent to Workgroup. Recognised that defect was very tightly defined and therefore CMP325 presented at October Panel to allow alternatives to be raised. Panel agreed that CMP325 met the Standard Governance criteria and agreed the modification should proceed to workgroup. Panel also agreed that CMP324 and CMP325 will be progressed jointly with 1st workgroup held 22 November 2019 and 2nd workgroup held 19 December 2019. Panel agreed updated Terms of Reference at January 2020 Panel. Workgroup Consultation launched on 26 February 2020 and closed 18 March 2020. Meeting held 26 March 2020 to discuss responses at which Workgroup felt that there was insufficient time to develop Workgroup Alternatives to get Workgroup Report to April Panel. March Panel agreed that CMP324/325 Workgroup Report will be presented to May 2020 (rather than April 2020 Panel). May Panel agreed that Workgroup had met its Terms of Reference and this could proceed to Code Administrator Consultation - this was issued on 3 June 2020 and closed at 5pm on 24 June 2020. The July 2020 CUSC Panel recommended by majority that the Original, WACM1 and WACM3 better facilitated the CUSC Objectives than the Baseline. However, the CUSC Panel recommended by majority that WACM2 did not better facilitate the CUSC Objectives than the Baseline. Final Modification Report sent to Ofgem on 13 August 2020 - decision received 11 November 2020 approving WACM2 (use the current 27 TNUoS charging zones within the CUSC and remove the requirement of re-zoning at the start of every Transmission Price Control). Implementation Date is 1 April 2021. | - | n/a | CUSC | 2019-10-10 | Grahame Neale | ESO | Rezoning – CMP324 Expansion | The ESO has written a Cusc Modification Proposal (CMP324) to alter the manner in which rezoning is carried out within Section 14 of CUSC. This Mod proffers an alternative defect, better enabling the issue to be explored by a Workgroup | Generators liable for TNUoS (High Impact) | Standard Governance Route with Workgroup | No | Joe Henry | Jennifer Groome |  | 2019-10-25 | 2020-02-18 | 2020-03-18 | 2020-04-22 | 2020-04-22 | 3 | 2020-05-29 | 2020-06-24 | 2020-07-31 | 2020-08-13 | 2020-11-11 | 2021-04-01
CMP326 | Workgroup Consultation | The Panel agreed that CMP326 met the Standard Governance criteria and agreed the modification should proceed to workgroup. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Medium to High. Workgroups to be held 11 December 2020 (completed) and 15 January 2021 prior to Workgroup Consultation being issued on 25 January 2021. Timeline will be finalised at 1st Workgroup Meeting. October Panel noted that the Proposer is awaiting the completion of analysis from ESO Control Room to ensure maximum value at the Workgroups. October Panel agreed to leave priority unchanged. However, they did re-assess priority at November's Panel and agreed to leave the priority unchanged as the Panel were satisfied with the plan for CMP326. Workgroup meetings held 11 December 2020 and 15 January 2021 and Workgroup Consultation was issued 1 February 2021 (closing 5pm on 22 February 2021). | Medium to High | • Simple change as appears to be a binary choice between 2 options – 2 Workgroups anticipated • Needs to be progressed before volumes become larger and unmanageable – increased interest following Power Available project going live in May • There have been recent developments on Power Available October Panel noted that the Proposer is awaiting the completion of analysis from ESO Control Room to ensure maximum value at the Workgroups. October Panel agreed to leave priority unchanged. However, they did re-assess priority at November's Panel and agreed to leave the priority unchanged as the Panel were satisfied with the plan for CMP326. | CUSC | 2019-10-10 | James Stone | ESO | Introducing a 'Turbine Availability Factor' for use in Frequency Response Capacity Calculation for Power Park Modules (PPMs) | To introduce a ‘Turbine Availability Factor’ into the CUSC to enable accurate calculation by the NGESO Control Centre and consequently accurate settlement of the Frequency Response capability of PPMs when some of the turbines on site are unavailable. | National Grid Electricity System Operator (Medium Impact); Power Park Module Generators (Low Impact) | Standard Governance Route with Workgroup | Yes | Paul Mullen | Rachel Beaufoy | 2019-10-10 | 2019-10-25 | 2021-01-15 | 1/2/21 to 22/2/21 | 2021-03-02 | 2021-03-02 |  | 2021-03-26 | 2021-05-06 | 2021-05-28 | 2021-06-09 | TBC | TBC
CMP328 | Workgroup Stage | The CUSC Panel unanimously agreed that CMP328 should follow the standard governance route and proceed to a Workgroup. Code Admin and Proposer have reviewed the list of parties who have requested to join the CMP328 and Workgroup and Code Admin have sought additional DNO membership. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was High. Workgroups held on 5 August 2020 and 15 October 2020. Panel have previously expressed concern on the direction of travel; however October Panel noted recent progress made and re-assessed priority at November Panel following the Workgroup on 19 November 2020. The Panel noted the complexity of CMP328 and the need for one more Workgroup in early 2021 (was 12 January but now 10 February 2021) prior to the Workgroup Consultation being issued. The November 2020 Panel were content to defer the decision on CMP328 until January 2021 Panel with the expectation that the Workgroup Consultation had been issued by then. However, as the Workgroup has been delayed at Proposer's request to 10 February 2021, Code Admin proposed that the decision on CMP328 prioritisation was deferred until February 2021 Panel. Panel agreed to this request. Good progress was made at the meeting on 10 February and a short meeting will be held on 17 February 2021 to finalise the content of the Workgroup Consultation ahead of issuing this on 19 February 2021. | High | • Raised on behalf of all DNOs • Needs to be progressed in parallel with completion of Transmission and Distribution interactivity process (expected to be completed ~ April 2021) • Significant volumes of these Tertiary Windows connections already progressing so there is a pressing need for a solution Panel have previously expressed concern on the direction of travel; however October Panel noted recent progress made and re-assessed priority at November Panel following the Workgroup on 19 November 2020. The Panel noted the complexity of CMP328 and the need for one more Workgroup in January 2021 prior to the Workgroup Consultation being issued. The November 2020 Panel were content to defer the decision on CMP328 until January 2021 Panel with the expectation that the Workgroup Consultation had been issued by then. However, as the Workgroup has been delayed at Proposer's request to 10 February 2021, Code Admin proposed that the decision on CMP328 prioritisation was deferred until February 2021 Panel. Panel agreed to this request. | CUSC | 2019-11-28 | Joanna Knight | Scottish and Southern Energy Power Distribution Limited | Connections Triggering Distribution Impact Assessment | This modification proposes to put in place an appropriate process to be utilised when any connection triggers a Distribution impact assessment. | Distribution Network Operators (DNO) and ESO (Medium Impact) New transmission connected Users (Low Impact) | Standard Governance Route with Workgroup | No | Rob Pears | Kavita Patel | 2019-11-28 | 2019-11-29 | 2021-02-10 | 19/2/21 to 12/3/21 | w/c 22/3/21 | w/c 29/3/21 |  | 2021-04-30 | 5/5/21 to 26/5/21 | 2021-06-25 | 2021-07-06 | TBC | TBC
CMP330 | Workgroup Consultation | The CUSC Panel unanimously agreed that CMP330 should follow the standard governance route and proceed to a Workgroup. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Medium to High. Workgroup Consultation launched on 26 January 2021 and closed 5pm on 16 February 2021 with 10 responses received. Meeting to discuss Workgroup Consultation responses to be held w/c 1 March 2021. | Medium to High | • Simple change and potential for cost savings and faster connections • Clarity needed ahead of Contracts for Difference Auctions in 2021 October Panel were content with progress made and agreed to leave priority unchanged. | CUSC | 2019-11-28 | Andy Pace | Energy Potential Limited | Allowing new Transmission Connected parties to build Connection Assets greater than 2km in length | To amend the definition of Connection Assets in section 14 of the CUSC to allow cable and overhead line lengths over 2km to be contestable where agreed between the Transmission Owner and the User. | New Transmission connected sites and Transmission Owners (Medium Impact) | Standard Governance Route with Workgroup | No | Ren Walker | Rob Pears | 2019-11-28 | 2019-11-29 | 2021-01-22 | 26/1/21 to 16/2/21 | w/c 01/3/21 | w/c 01/3/21 |  | 2021-03-26 | 2021-04-27 | 2021-05-28 | 2021-06-10 | TBC | 2022-04-01
CMP331 | Workgroup Stage | The CUSC Panel unanimously agreed that CMP331 should follow the standard governance route and proceed to a Workgroup. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Low so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged but noted requested implementation date of 1 April 2022. | Low | • April 2022 Implementation at earliest • Materiality on the wider charging base not clear October Panel agreed to leave priority unchanged but noted requested implementation date of 1 April 2022. | CUSC | 2019-11-28 | Andy Pace | Energy Potential Limited | Option to replace generic Annual Load Factors (ALFs) with site specific ALFs | To provide new generators with the option to replace the generic Annual Load Factors (ALFs) used to determine their TNUoS charges with a site-specific ALF. | New Transmission connected generators (Medium Impact); Existing Transmission connected generators; National Grid Electricity System Operator (Low Impact) | Standard Governance Route with Workgroup | No | TBC | TBC | 2019-11-28 | 2019-11-29 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP332 |  | The CUSC Panel recommended that CMP332 meets the Urgency criteria and should be treated as Urgent (subject to Ofgem approval). Request for Urgency sent 19 December 2019 but on 10 February Ofgem rejected the request for Urgency. Workgroup Consultation issued 6 February and closed 5pm on 27 February. Meetings held 5 and 6 March to discuss workgroup consultation responses. Workgroup meeting on 20 March 2020 to finalise Workgroup Alternatives. On 25 March 2020, Proposer requested under 8.17A.4 to withdraw CMP332 seeking Ofgem permission under 8.17A.5. Decision received from Ofgem 31 March 2020 giving permission for NGESO to withdraw CMP332 and Direction for NGESO to raise a new modification replacing CMP332 but for implementation 1 year later (April 2022). Code Admin advised industry on 31 March 2020 and opened the 5 working day window (closing 5pm on 7 April 2020) to give another Party the opportunity to support CMP332 (in place of the original Proposer). No support from another Party received - April Panel agreed that CMP332 can be formally withdrawn. | n/a | CMP332 is a Modification that Ofgem have directed ESO to raise. Decision required by 16 March 2020 to meet implementation date of 1 April 2021. December Panel also agreed that CMP332 was Urgent (subject to Ofgem approval) | CUSC | 2019-12-12 | Grahame Neale | ESO | Transmission Demand Residual bandings and allocation (TCR) | To create a methodology by which the residual element of demand TNUoS can be apportioned to Half Hourly (HH) and Non Half-Hourly (NHH) demand, and a separate methodology to determine the ‘bands’ against which the residual element of demand TNUoS is levied | Suppliers and Demand Users connected to the Transmission Network (High Impact) | Standard Governance Route (Urgent) with Workgroup |  | Paul Mullen | Jennifer Groome | 2019-12-12 | 2019-12-12 | 2020-01-29 | 2020-02-27 | 2020-04-06 | n/a | 17 (TBC) | n/a | n/a | n/a | n/a | n/a | n/a - Withdrawn 24 April 2020
CMP333 | Implementation | 1st Code Administrator Consultation was issued 20 April 2020 for 18 Working Days and closed 15 May 2020. However, legal text needs to be revised following Ofgem's decision on CMP281. In light of this, May Special Panel unanimously agreed a) that CMP333 will proceed to a 2nd 10 working day Code Administrator Consultation once the revised legal text has been agreed by the CMP333 Workgroup and b) that Draft Final Modification Report will be presented to July Panel rather than May Panel. 2nd Code Administrator (now 15 working days as there is sufficient time) opened 17 June 2020 and closed 8 July 2020. The July CUSC Panel noted that a respondent to the Code Administrator Consultation had proposed changes to the CMP333 legal text. The CUSC Panel unanimously agreed that some of these changes were not typographical and therefore directed (under CUSC 8.23.4(ii)) the CMP333 Workgroup to assess these changes. The CUSC Panel also unanimously agreed that, once the CMP333 Workgroup have agreed the legal text (Workgroup meeting 24 August 2020), a 3rd Code Administrator Consultation would be run for 5 working days with the scope limited to the proposed changes to the CMP333 legal text. Workgroup met 24 August 2020 and legal text has been sent to Panel for final review (by 5pm on 27 August 2020). Code Administrator Consultation (with scope limited to the proposed changes to the CMP333 legal text) was issued 28 August 2020 and closed 7 September 2020 with 1 response received. The CUSC Panel on 16 September 2020 unanimously recommended that the Original facilitated the CUSC Objectives than the Baseline (the arrangements currently set out in CUSC). Final Modification Report issued to Ofgem on 18 September 2020. At November 2020 Panel, Ofgem confirmed that they expect decision to be made before Christmas 2020. Decision received 3 December 2020, which will implement the Original proposal on 1 April 2021. | - | n/a | CUSC | 2019-12-12 | Jenny Doherty | ESO | BSUoS – charging Supplier Users on gross demand (TCR) | To give effect to Ofgem's decision to levy BSUoS to Suppliers on a gross volumetric basis. | Supplier Users, Embedded Generators (High Impact) | Standard Governance Route (Urgent) with Workgroup | No | Chrissie Brown | Kavita Patel | 2019-12-12 | 2019-12-12 | 2020-02-13 | 2020-03-05 | 2020-03-10 | 2020-03-10 | 0 | 2020-03-27 | 2020-09-07 | 2020-09-16 | 2020-09-18 | 2020-12-03 | 2021-04-01
CMP334 |  | The CUSC Panel noted that CMP334 will be progressed in a joint workgroup with the equivalent DCUSA Modification (DCP359). Workgroup Consultation issued 23 March 2020 and closed 17 April 2020. - responses discussed at 20 and 21 April 2020 Workgroup meetings. There is 1 alternative solution (WACM1) to exclude those who solely provide voltage support from paying the Transmission Demand Residual. April Panel agreed to new timeline (which is not Urgent), which means Workgroup Report will now come to May’s Normal Panel (rather than a Special Panel in May) and the Draft Final Modification Report will now be re-presented to July's Panel (rather than May's Normal Panel). Panel also agreed that these Modifications no longer need to follow an Urgent timeline. May Panel agreed that Workgroup has met its Terms of Reference and this can proceed to Code Administrator Consultation - this was sent on 16 June 2020 and closed 5pm on 6 July 2020. The July CUSC Panel unanimously recommended that the Original and by majority that WACM1 better facilitated the CUSC Objectives than the Baseline. Final Modification Report sent to Ofgem on 13 August 2020. At November 2020 Panel, Ofgem confirmed that they expect decision to be made w/c 30 November 2020. Decision received 30 November 2020, which will implement WACM1. This was implemented on 14 December 2020. | - | n/a | CUSC | 2020-01-16 | Grahame Neale | ESO | Transmission Demand Residual - consequential definition changes (TCR) | CMP332 is developing a methodology for the Transmission Demand Residual to be applied only to ‘Final Demand’ on a ‘Site’ basis. This Modification creates the definitions of "Final Demand" and "Site". | National Grid Electricity System Operator, Suppliers, Demand Users (connected to the Transmission Network or Distribution network) and Distribution Network Operators | Standard Governance Route (Urgent) with Workgroup | No | Paul Mullen | Jennifer Groome | 2020-01-16 | 2020-01-31 | 2020-03-11 | 2020-04-15 | 2020-05-13 | 2020-05-13 | 1 | 2020-05-29 | 2020-07-03 | 2020-07-31 | 2020-08-13 | 2020-11-30 | 2020-12-14
CMP335 | Pending Authority Decision | The CUSC Panel recommended that CMP335 meets the Urgency criteria and should be treated as Urgent (subject to Ofgem approval) - request for Urgency sent to Ofgem 11 February 2020 and granted 20 February 2020. Panel also noted that CMP335 and 336 will be progressed in a joint workgroup. Workgroup Consultation for CMP335/336 was due to be issued on 26 March 2020. However, on 25 March 2020, Proposer requested under 8.17A.4 to withdraw related Modification CMP332 seeking Ofgem permission under 8.17A.5. Decision received from Ofgem 31 March 2020 giving permission for NGESO to withdraw CMP332 and Direction for NGESO to raise a new modification replacing CMP332 but for implementation 1 year later (April 2022). CMP335/336 will have same Implementation Date so Urgent timeline no longer required - timing and length of Workgroup Consultation is currently being agreed. April Panel noted that timeline will be aligned where possible with the new CMP332 and CMP340. Panel also agreed that these Modifications no longer need to follow an Urgent timeline. Workgroup Consultation issued 15 May 2020 for 20 working days and closing on 15 June 2020 with 7 responses received. Meeting to discuss responses was set up for 25 June 2020 but has been delayed to 6 July 2020. June Panel noted that Workgroup Report will be presented to normal August Panel (rather than special Panel in August); and that Draft Final Modification Report will be presented to a Special Panel on 1 October 2020 (rather than normal Panel in September). August Panel unanimously agreed that terms of reference have been met and this can proceed to Code Administrator Consultation - this was issued 1 September 2020 and closed 5pm on 22 September 2020 with 4 non-confidential responses received. At the Panel Vote on 1 October 2020, the CUSC Panel recommended unanimously that the Original better facilitated the CUSC Objectives than the Baseline (the arrangements currently set out in CUSC).Final Modification Report sent to Ofgem on 6 October 2020. At January 2021 Panel, Ofgem confirmed that a minded to decision is expected on CMP343 in February 2021 with the decisions on CMP340 and CMP335/CMP336 to follow this. | - | n/a | CUSC | 2020-01-16 | Eleanor Horn | ESO | Transmission Demand Residual billing and consequential changes to CUSC Section 3 and 11 (TCR) | CMP332 is developing a methodology for the Transmission Demand Residual to be applied only to ‘Final Demand’ on a ‘Site’ basis. CMP334 creates the definitions of "Final Demand" and "Site". This modification aims to revise Section 3 and 11 of the CUSC to set out how/when the Residual is recovered from parties once the Residual charges are determined. | National Grid Electricity System Operator, Distribution Network Operators, Suppliers and Demand Users connected to the Transmission Network | Standard Governance Route (Urgent) with Workgroup | No | Paul Mullen | Jennifer Groome | 2020-01-16 | 2020-01-31 | 2020-03-16 | 2020-06-15 | 2020-08-07 | 2020-08-13 | 0 | 2020-08-28 | 2020-09-22 | 2020-10-01 | 2020-10-06 | Spring 2021 | 2022-04-01
CMP336 | Pending Authority Decision | The CUSC Panel recommended that CMP336 meets the Urgency criteria and should be treated as Urgent (subject to Ofgem approval) - request for Urgency sent to Ofgem 11 February 2020 and granted 20 February 2020. Panel also noted that CMP335 and 336 will be progressed in a joint workgroup. Workgroup Consultation for CMP335/336 was due to be issued on 26 March 2020. However, on 25 March 2020, Proposer requested under 8.17A.4 to withdraw related Modification CMP332 seeking Ofgem permission under 8.17A.5. Decision received from Ofgem 31 March 2020 giving permission for NGESO to withdraw CMP332 and Direction for NGESO to raise a new modification replacing CMP332 but for implementation 1 year later (April 2022). CMP335/336 will have same Implementation Date so Urgent timeline no longer required - timing and length of Workgroup Consultation is currently being agreed. April Panel noted that timeline will be aligned where possible with the new CMP332 and CMP340. Panel also agreed that these Modifications no longer need to follow an Urgent timeline. Workgroup Consultation issued 15 May 2020 for 20 working days and closed on 15 June 2020 with 7 responses received. Meeting to discuss responses was set up for 25 June 2020 but has been delayed to 6 July 2020. June Panel noted that Workgroup Report will be presented to normal August Panel (rather than special Panel in August); and that Draft Final Modification Report will be presented to a Special Panel on 1 October 2020 (rather than normal Panel in September). August Panel unanimously agreed that terms of reference have been met and this can proceed to Code Administrator Consultation - this was issued 1 September 2020 and closed 5pm on 22 September 2020 with 4 non-confidential responses received. At the Panel Vote on 1 October 2020, the CUSC Panel recommended unanimously that the Original and WACM1 better facilitated the CUSC Objectives than the Baseline (the arrangements currently set out in CUSC. Final Modification Report sent to Ofgem on 6 October 2020. At January 2021 Panel, Ofgem confirmed that a minded to decision is expected on CMP343 in February 2021 with the decisions on CMP340 and CMP335/CMP336 to follow this. | - | n/a | CUSC | 2020-01-16 | Eleanor Horn | ESO | Transmission Demand Residual billing and consequential changes to CUSC Section 14 (TCR) | CMP332 is developing a methodology for the Transmission Demand Residual to be applied only to ‘Final Demand’ on a ‘Site’ basis. CMP334 creates the definitions of "Final Demand" and "Site". This modification aims to revise Section 14 of the CUSC to set out how/when the Residual is recovered from parties once the Residual charges are determined. | National Grid Electricity System Operator, Distribution Network Operators, Suppliers and Demand Users connected to the Transmission Network | Standard Governance Route (Urgent) with Workgroup | No | Paul Mullen | Jennifer Groome | 2020-01-16 | 2020-01-31 | 2020-03-16 | 2020-06-15 | 2020-08-07 | 2020-08-13 | 2 | 2020-08-28 | 2020-09-22 | 2020-10-01 | 2020-10-06 | Spring 2021 | 2022-04-01
CMP337 | Implementation | CUSC January 2020 Panel asked for clarity on a number of issues (notably the impact on wider TNUoS) before determining whether this should proceed to Workgroup or Code Administrator Consultation. February 2020 Panel agreed that this should proceed to Workgroup. On 9 March, Proposer requested Urgent treatment of CMP337/CMP338. The CUSC Panel on 18 March unanimously recommended that CMP337/CMP338 meets the Urgency criteria and should be treated as Urgent (subject to Ofgem approval) - request for Urgency sent to Ofgem on 23 March 2020 and granted 1 April 2020. Workgroups held 8 and 20 April 2020. Workgroup Consultation ran from 30 April 2020 to 11 May 2020 and Workgroup Vote held 13 May 2020. Special Panel on 20 May 2020 agreed that Terms of Reference have been met. Panel on 29 May 2020 recommended by majority that the Original for both CMP337 and CMP338 was better than Baseline. Final Modification Report sent to Ofgem on 3 June 2020 - Ofgem decision approving this received 3 July 2020. Implementation Date 1 April 2024. | - | n/a | CUSC | 2020-01-16 | Rachel Kettles | SSE | Impact of DNO Contributions on Actual Project Costs and Expansion Factors | To allow Distribution Network Operators to contribute to the cost of new transmission assets, and allow this contribution to be netted off from the Transmission Owner’s actual project costs in a way which maintains the exact pro-rating of costs between local and wider TNUoS charge elements as is currently in place, | National Grid Electricity System Operator, all Users who pay Generation TNUoS (Low Impact); Distribution Network Operators, Transmission Owners, Remote Island Generators (Shetland, Western Isles and Orkney) (Medium Impact) | Standard Governance Route (Urgent subject to Ofgem Approval) with Workgroup | No | Shazia Akhtar | Ren Walker | 2020-01-16 | 2020-02-28 | 2020-04-20 | 2020-05-04 | 2020-05-07 | 2020-05-07 | 0 | 2020-05-19 | 2020-05-22 | 2020-05-29 | 2020-06-03 | 2020-07-03 | 2024-04-01
CMP338 | Implementation | CUSC January 2020 Panel asked for clarity on a number of issues (notably the impact on wider TNUoS) before determining whether this should proceed to Workgroup or Code Administrator Consultation. February 2020 Panel agreed that this should proceed to Workgroup. On 9 March, Proposer requested Urgent treatment of CMP337/CMP338. The CUSC Panel on 18 March unanimously recommended that CMP337/CMP338 meets the Urgency criteria and should be treated as Urgent (subject to Ofgem approval) - request for Urgency sent to Ofgem on 23 March 2020 and granted 1 April 2020. Workgroups held 8 and 20 April 2020. Workgroup Consultation ran from 30 April 2020 to 11 May 2020 and Workgroup Vote held 13 May 2020. Special Panel on 20 May 2020 agreed that Terms of Reference have been met. Panel on 29 May 2020 recommended by majority that the Original for both CMP337 and CMP338 was better than Baseline. Final Modification Report sent to Ofgem on 3 June 2020 - Ofgem decision approving this received 3 July 2020. Implementation Date 1 April 2024. | - | n/a | CUSC | 2020-01-16 | Rachel Kettles | SSE | Impact of DNO Contributions on Actual Project Costs and Expansion Factors – New Definition of Cost Adjustment | Introduce a new definition of “Cost Adjustment” in the CUSC to give effect to CMP337 | National Grid Electricity System Operator, all Users who pay Generation TNUoS (Low Impact); Distribution Network Operators, Transmission Owners, Remote Island Generators (Shetland, Western Isles and Orkney) (Medium Impact) | Standard Governance Route (Urgent subject to Ofgem Approval) with Workgroup | No | Shazia Akhtar | Ren Walker | 2020-01-16 | 2020-02-28 | 2020-04-20 | 2020-04-29 | 2020-05-07 | 2020-05-07 | 0 | 2020-05-19 | 2020-05-22 | 2020-05-29 | 2020-06-03 | 2020-07-03 | 2024-04-01
CMP339 | Implementation | CUSC Panel on 18 March 2020 agreed that CMP339 will be progressed via the existing CMP317/327 Workgroup. April Panel agreed that CMP339 Workgroup Report will be presented to June Panel and Draft Final Modification Report will be presented to July Panel. Workgroup Consultation issued 13 May 2020 for 15 working days and closed 4 June 2020 (0 responses received). June 2020 Panel unanimously agreed that Workgroup has met its Terms of Reference and this can proceed to Code Administrator Consultation. Code Administrator Consultation was issued 29 June 2020 and closed 5pm on 20 July 2020 (1 response received). The July 2020 CUSC Panel recommended by majority that the Original and all WACMs 1- 23 better facilitated the CUSC Objectives than the Baseline. Final Modification Report sent to Ofgem on 13 August 2020. At November 2020 Panel, Ofgem confirmed that they expect decision to be made before Christmas 2020. Ofgem decision was received 17 December 2020 - both the CMP327/317 and CMP339 Original Proposals will be implemented on 1 April 2021 | - | n/a | CUSC | 2020-03-12 | Jon Wisdom | ESO | Consequential changes for CMP317/327 (TCR) | Allow the CMP317/327 Workgroup to develop the appropriate definitions needed for the Original and any alternative Proposals and any other changes outside of Section 14 as appropriate. | All CUSC Users as this will amend Sections other than Section 14 for the purposes of CMP317/327 (Low Impact) | Standard Governance Route (with Urgent timeline) with Workgroup | No | Rob Marshall | Joe Henry | 2020-03-12 | 2020-03-18 | 2020-04-30 | 2020-06-04 | 2020-06-09 | 2020-06-16 | 24 | 2020-06-26 | 2020-07-20 | 2020-07-31 | 2020-08-13 | 2020-12-17 | 2021-04-01
CMP340 | Pending Authority Decision | CUSC Panel on 18 March 2020 recommended that CMP340 meets the Urgency criteria and should be treated as Urgent (subject to Ofgem approval) - request for Urgency sent to Ofgem by on 23 March 2020. Panel also agreed that a short workgroup nominations (up to 30 March 2020) will be opened but that CMP40 will be progressed via the existing CMP332 Workgroup. Panel also recommended that no Workgroup Consultation is needed and we have also sought approval from Ofgem on this (under Governance Rule 8.24.7). Noting that the CMP332 has been Withdrawn and the replacement CMP332 (CMP343) will be presented to May's Panel, the April Panel did not raise any objections to CMP340 being revised rather than being withdrawn and re-raised. April Panel also agreed to withdraw their recommendation for Urgency and Proposer have confirmed they no longer require to follow an Urgent timeline. CMP343 was presented to May 2020 and Panel agreed that this would be worked on jointly with CMP340. 1st Workgroup was due to be held 22 June 2020 but has been delayed to 1 July 2020. June Panel noted that Workgroup Report will be presented to normal August Panel (rather than special Panel in August); and that Draft Final Modification Report will be presented to a Special Panel on 1 October 2020 (rather than normal Panel in September). Workgroup Consultation ran from 10 to 31 July 2020 with 13 responses received (1 confidential). August Panel unanimously agreed that terms of reference have been met and this can proceed to Code Administrator Consultation - this was issued 1 September 2020 and closed 5pm on 22 September 2020 with 21 non-confidential responses received. At Panel Vote on 1 October 2020, the CUSC Panel recommended unanimously that the Original, WACM1 and WACM2 better facilitated the CUSC Objectives than the Baseline (the arrangements currently set out in CUSC). Final Modification Report sent to Ofgem on 6 October 2020. At January 2021 Panel, Ofgem confirmed that a minded to decision is expected on CMP343 in February 2021 with the decisions on CMP340 and CMP335/CMP336 to follow this. | - | n/a | CUSC | 2020-03-12 | Grahame Neale | ESO | Consequential changes for CMP343 (TCR) | Allow the CMP343 Workgroup to develop the appropriate definitions needed for the Original and any alternative Proposals and any other changes outside of Section 14 as appropriate. | All CUSC Users as this will amend Sections other than Section 14 for the purposes of CMP332 (Low Impact) | Standard Governance Route (with Urgent timeline) with Workgroup | No | Paul Mullen | Jennifer Groome | 2020-03-12 | 2020-03-18 | 2020-07-07 | 2020-07-31 | 2020-08-11 | 2020-08-12 | 2 | 2020-08-28 | 2020-09-22 | 2020-10-01 | 2020-10-06 | Spring 2021 | 2022-04-01
CMP341 | Workgroup Stage | The CUSC Panel on 27 March 2020 recommended that CMP341 would follow standard governance and be progressed via a joint workgroup with the equivalent Grid Code Modification (GC0140) due to the level of crossover between the 2 Modifications. Terms of Reference were agreed for CMP341 and the Code Administrator will ensure that there is alignment (where needed) with the Terms of Reference agreed for GC0140. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was Low so there are no Workgroups expected imminently. October Panel agreed to leave priority unchanged. | Low | • Complex • Although a CACOP and Ofgem driven initiative, there does not appear to be any current industry appetite to progress October Panel agreed to leave priority unchanged. | CUSC | 2020-03-12 | Phil Smith | ESO | CUSC Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions | Enables parties to be derogated from specific CUSC obligations in order to conduct small-scale, time-limited live trials of innovative technologies, connections, products or services | CUSC Panel, National Grid ESO, Ofgem, Innovators, CUSC Parties and other Code Administrators | Standard Governance Route with Workgroup | No | TBC | TBC | 2020-03-12 | 2020-03-27 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP342 | Implementation | The CUSC Panel on 29 May 2020 unanimously agreed that CMP342 should follow the self-governance route and proceed to Code Administrator Consultation - this was sent on 19 June 2020 and closed 5pm on 10 July 2020 (1 response received). The CUSC Panel had unanimously agreed that CMP342 should follow the self-governance route and proceed to Code Administrator Consultation. Following a challenge on material impacts of the proposed change from a respondent to the Code Administrator Consultation, the Panel is still considering he appropriate governance route and will decide on the final outcome at the August Panel Panel (28 August 2020). On the 31 July 2020, Panel also raised questions as to when a party would be liable for VAT and to whom. On 6 August 2020, the ESO provided Panel with this clarification and, based on this, Panel agreed that CMP342 can proceed to a vote at the August and does not need to go to a Workgroup. August Panel agreed by majority to maintain their decision that CMP342 should follow the self-governance route. Code Admin clarified the timeline and next steps and Panel then undertook the self-governance vote. Panel, by majority, determined that the Original proposal better facilitated the CUSC objectives and CMP342 will be implemented on 9 October 2020 unless there are any Appeals received in the 15 working day Appeals Window (anticipated to be 11 September 2020 to 2 October 2020). Appeal received 2 October 2020 so implementation will not now occur on 9 October 2020. Ofgem published a letter on 2 November 2020 stating that they are satisfied that this is a valid request for appeal and set out next steps, which indicated a decision date on this Appeal by 7 December 2020. Decision received 16 December 2020, rejecting this Appeal - CMP342 was implemented 23 December 2020. | n/a | n/a | CUSC | 2020-05-13 | Nick George | ESO | Clarification of VAT for Securities in the CUSC | Seeks to clarify, and confirm the position that NGESO has always applied, that when calculating the amount Users are required to secure under the CUSC, the amount of applicable Value Added Tax is to be included. | Low impact on All Users | Standard Governance, straight to Code Admin Consultation | No | n/a | n/a | 2020-05-13 | 2020-05-29 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2020-07-10 | 2020-08-28 | N/A Self governance mod | N/A Self governance mod | 2020-12-23
CMP343 | Pending Authority Decision | The CUSC Panel on 29 May 2020 unanimously agreed that CMP343 should follow the standard governance route and proceed to a Workgroup and should be worked on jointly with CMP340. 1st Workgroup was due to be held 22 June 2020 but has been delayed to 1 July 2020. June Panel noted that Workgroup Report will be presented to normal August Panel (rather than special Panel in August); and that Draft Final Modification Report will be presented to a Special Panel on 1 October 2020 (rather than normal Panel in September). Workgroup Consultation ran from 10 to 31 July 2020 with 13 responses received (1 confidential). August Panel unanimously agreed that terms of reference have been met and this can proceed to Code Administrator Consultation - this was issued 1 September 2020 closed 5pm on 22 September 2020 with 21 non-confidential responses received. At Panel Vote on 1 October 2020, the CUSC Panel recommended unanimously that WACM2 better facilitated the CUSC Objectives than the Baseline (the arrangements currently set out in CUSC) and recommended by majority that the Original, WACM1, WACM6, WACM7, WACM8 and WACM9 better facilitated the CUSC Objectives than the Baseline. Final Modification Report sent to Ofgem on 6 October 2020. At January 2021 Panel, Ofgem confirmed that a minded to decision is expected on CMP343 in February 2021 with the decisions on CMP340 and CMP335/CMP336 to follow this. | - | n/a | CUSC | 2020-05-13 | Grahame Neale | ESO | Transmission Demand Residual bandings and allocation for 1 April 2022 implementation (TCR) | Creating a methodology by which the residual element of demand Transmission Network Use of System (TNUoS) charges can be apportioned to Half-Hourly (HH) and Non Half-Hourly (NHH) demand, and a separate methodology to determine ‘bands’ against which the residual element of demand TNUoS is levied. | High impact on National Grid ESO, Distribution Network Operators (DNO), Suppliers and Demand Users connected to the Transmission Network | Standard Governance Route with Workgroup | No | Paul Mullen | Jennifer Groome | 2020-05-13 | 2020-05-29 | 2020-07-07 | 2020-07-31 | 2020-08-11 | 2020-08-12 | 8 | 2020-08-28 | 2020-09-22 | 2020-10-01 | 2020-10-06 | 2021-02-01 | 2022-04-01
CMP344 | Pending Authority Decision | The CUSC Panel on 29 May 2020 unanimously agreed that CMP344 should follow the standard governance route and proceed to a Workgroup. Workgroup Nominations closed 15 July 2020. Since the start of 2020, the focus has been on progressing the TCR Modifications, Covid-19 related Modifications and High Priority Charging Modification. Inevitably, this meant that other lower priority Modifications would not be progressed. However, from August 2020, we are now able to progress the rest of the Modifications in the Prioritisation Stack. Between 29 May 2020 Panel and June Panel, Proposers with these Modifications had all provided updated justification against each of the Prioritisation Criteria – namely Complexity, Importance and Urgency. The Panel carefully considered the views of the Proposers. For each Modification, Panel determined if the Priority was High, Medium to High, Medium, Low to Medium or Low. Panel determined that Priority of this was High. Workgroup Consultation issued 2 November 2020 and closed 5pm on 23 November 2020 with Workgroup held on 24 November 2020 to assess the 8 Workgroup Consultation responses received and hold Workgroup Vote. November 2020 Panel agreed that the Workgroup had met its Terms of Reference and can proceed to Code Administrator Consultation once legal text changes had been agreed with the Workgroup (this was agreed with the Workgroup on 30 November 2020). Code Administrator Consultation was issued on 1 December 2020 and closed 5pm on 22 December 2020 with 4 responses received. Special Panel on 8 January 2021 carried out recommendation vote and agreed by majority that the CMP344 Original better facilitated the CUSC objectives than the current CUSC arrangements. Final Modification Report was sent to Ofgem on 12 January 2021 - decision required by 25 January 2021 to meet Implementation Date of 1 April 2021. However, Ofgem advised at the January 2021 Panel, that they do not expect to make a decision until ~ end March 2021. | - | • Must be implemented prior to the start of the next price control period from 1st April 2021 • Received stakeholder support for this to be progressed at pace given significant potential costs of any future income adjusting events October Panel were content with progress made and agreed to leave priority unchanged. | CUSC | 2020-05-13 | Bill Reed | RWE | Clarification of Transmission Licensee revenue recovery and the treatment of revenue adjustments in the Charging Methodology | Clarifies that the allowed revenue for Transmission Owners recovered from Transmission Users under the Charging Methodologies is fixed for each onshore price control period for onshore transmission licensees and at the point of asset transfer for OFTOs. | High impact on Transmission Owners, Transmission Users including Generation and Suppliers and Medium Impact on National Grid ESO | Standard Governance Route with Workgroup | No | Joe Henry | Ren Walker | 2020-05-13 | 2020-05-29 | 2020-10-22 | 2020-11-23 | 2020-11-24 | 2020-11-24 | 0 | 2020-11-27 | 1/12/20 to 22/12/20 | 2021-01-08 | 2021-01-12 | 2021-03-31 | 2021-04-01
CMP345 |  | May 2020 Special Panel unanimously recommended that CMP345 should proceed on an urgent timeline and agreed a timeline which balanced the need for pace whilst ensuring industry scrutiny. Ofgem approved Urgent treatment of this Modification on 22 May 2020. 45 responses received for Workgroup Consultation that was run from 1 June 2020 to 5pm on 3 June 2020. Special Panel on 9 June 2020 unanimously agreed that CMP345 Workgroup Report had met its Terms of Reference. 30 responses received for Code Administrator Consultation that was run from 9 June 2020 to 3pm on 12 June 2020. Special Panel on 15 June 2020 recommended by majority that none of the proposed solutions better facilitated the CUSC Objectives than the Baseline. Final Modification Report issued to Ofgem 15 June 2020, requesting decision by 22 June 2020. Decision received 23 June 2020 - Ofgem opted for WACM2 which is to apply a cap of £15/MWh to the BSUoS price in each settlement period from the implementation date to the end of August 2020. Any under recovery of revenue from the application of the cap will be recovered through BSUoS charges equally across all settlement periods in the 2021/22 Charging Year. This was implemented on 25 June 2020. | - | n/a | CUSC | 2020-05-19 | Garth Graham | SSE | Defer the additional Covid-19 BSUoS costs | To defer the additional BSUoS costs arising from Covid-19 that are incurred in 2020/21 to 2021/22. | High impact on Generators and Suppliers and Medium impact on National Grid ESO | Standard Governance Route (with Urgent timeline) with Workgroup |  | Paul Mullen | Ren Walker | 2020-05-19 | 2020-05-29 | 2020-05-29 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 8 | 2020-06-09 | 2020-06-12 | 2020-06-15 | 2020-06-15 | 2020-06-23 | 2020-06-25
CMP346 | Implementation | The CUSC Panel on 26 June 2020 agreed by majority that CMP346 should follow the self-governance route and proceed to Code Administrator Consultation once legal text has been updated following Panel comments. This was circulated to Panel on 5 August and no comments were received by the 12 August deadline. Code Admin Consultation issued 20 August 2020 and closed on 11 September 2020 - no responses received. Draft Final Modification Report was presented for Panel Vote on 25 September 2020. The CUSC Panel unanimously determined that this should be implemented. This will be implemented 1 April 2021 as there were no appeals raised in the Appeals Window 6 October 2020 to 27 October 2020. | n/a | n/a | CUSC | 2020-06-11 | Sarah Chleboun | ESO | Price Control Updates to Charging Parameters | To amend incorrect and misleading references to old charging parameters in CUSC Section 14. | High impact on Generators and Suppliers and Medium impact on National Grid ESO | Self - Governance, straight to Code Admin Consultation | No | n/a | n/a | 2020-06-11 | 2020-06-26 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2020-09-11 | 2020-09-25 | N/A Self governance mod | N/A Self governance mod | 2021-04-01
CMP347 | Implementation | The CUSC Panel on 26 June 2020 agreed unanimously that CMP347 should follow the self-governance route and proceed to Code Administrator Consultation once legal text has been updated following Panel comments. This was circulated to Panel on 5 August and no comments were received by the 12 August deadline. Code Admin Consultation issued 20 August 2020 and closed 5pm on 11 September 2020 - no responses received. Draft Final Modification Report was presented for Panel Vote on 25 September 2020. The CUSC Panel unanimously determined that this should be implemented. This will be implemented 1 April 2021 as there were no appeals raised in the Appeals Window 6 October 2020 to 27 October 2020. | n/a | n/a | CUSC | 2020-06-11 | Sarah Chleboun | ESO | Offshore Local TNUoS Tariff Clarifications | To ensure the treatment for the three offshore local tariffs are consistent with each other and amend incorrect references relating to offshore local tariffs. | High impact on Generators and Suppliers and Medium impact on National Grid ESO | Self - Governance, straight to Code Admin Consultation | No | n/a | n/a | 2020-06-11 | 2020-06-26 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2020-09-11 | 2020-09-25 | N/A Self governance mod | N/A Self governance mod | 2021-04-01
CMP348 |  | The July 2020 Panel unanimously agreed that CMP348 met the Self Governance and Fast Track criteria and agreed the modification should be implemented on 8 September 2020 subject to no appeals being raised in the Appeals Window 10 August 2020 to 1 September 2020. No appeals raised in the Appeals Window - Implementation 8 September 2020. | n/a | n/a | CUSC | 2020-07-16 | Ren Walker | ESO | Housekeeping Modification to insert Exhibit Y into the CUSC following implementation of CMP323 and amend numbering in Section 6 | To insert Exhibit Y (Electricity Balancing Guideline (EBGL) Mapping Table) into the CUSC and to amend the numbering in Section 6 (General Provisions). | National Grid Electricity System Operator (Low Impact) | Fast Track, Self-Governance | No | n/a | n/a | 2020-07-16 | 2020-07-31 | NA - Fast Track | NA - Fast Track | NA - Fast Track | NA - Fast Track | 0 | NA - Fast Track | NA - Fast Track | NA - Fast Track | N/A Self governance mod | N/A Self governance mod | 2020-09-08
CMP349 | Implementation | The July 2020 Panel unanimously agreed that CMP349 met the Self Governance and Fast Track criteria and agreed the modification should be implemented on 1 April 2021 subject to no appeals being raised in the Appeals Window 10 August 2020 to 1 September 2020. No appeals raised in the Appeals Window - Implementation will be 1 April 2021. | n/a | n/a | CUSC | 2020-07-16 | Ren Walker | ESO | Housekeeping Modification to amend Section 11 of the CUSC as a result of CMP320 | To clarify the definition of ‘Identified Onshore Circuit’ within Section 11 (Interpretations and Definitions) of the CUSC as a result of the CMP320 decision. | National Grid Electricity System Operator (Low Impact) | Fast Track, Self-Governance | No | n/a | n/a | 2020-07-16 | 2020-07-31 | NA - Fast Track | NA - Fast Track | NA - Fast Track | NA - Fast Track | 0 | NA - Fast Track | NA - Fast Track | NA - Fast Track | N/A Self governance mod | N/A Self governance mod | 2021-04-01
CMP350 |  | Panel (on 17 July 2020) by majority (of 5 votes to 4) did not recommend that CMP350 should proceed on an urgent timeline. In accordance with CUSC Section 8.24.4, we consulted the Authority on 17 July 2020 as to whether this Modification is an Urgent CUSC Modification Proposal. Ofgem approved Urgent treatment of this Modification on 21 July 2020. July Panel unanimously agreed that Workgroup had met its Terms of Reference and could proceed to Code Administrator Consultation (this was issued 31 July and closed 5pm on 4 August with 13 responses received). The CUSC Panel on 6 August 2020 recommended by majority that only WACM3 better facilitated the CUSC Objectives than the Baseline (the arrangements currently set out in CUSC). However, there was support (4 out of 9 votes) for the CMP350 Original and all other WACMs. Final Modification Report issued to Ofgem on 6 August 2020. Decision received 13 August 2020 and WACM6 Implemented 14 August 2020 (this introduces an overall limit of £100m, changes the BSUoS price cap from £15/MWh to £10/MWh and extends the current support scheme from 31 August 2020 to 25 October 2020). | High | n/a | CUSC | 2020-07-15 | George Moran | British Gas | Changes to the BSUoS Covid Support Scheme | To change the BSUoS Covid Support Scheme introduced by CMP345 by 1) Reducing the current £15/MWh cap to £5/MWh; 2) Extending its application from 31 August 2020 to 30 September 2020; and 3) Introducing a formal limit of £100m for the amount of deferred Covid related BSUoS costs. | High impact on Generators and Suppliers and Medium impact on National Grid ESO | Standard Governance Route (with Urgent timeline) with Workgroup | No | Paul Mullen | Ren Walker | 2020-07-15 | 2020-07-16 | 2020-07-23 | 2020-07-27 | 2020-07-29 | 2020-07-29 | 7 | 2020-07-31 | 2020-08-04 | 2020-08-06 | 2020-08-06 | 2020-08-13 | 2020-08-14
CMP351 | Implementation | The September 2020 CUSC Panel unanimously agreed that CMP351 should follow the standard governance route and proceed to Code Administrator Consultation, once Panel discussions were captured in the Code Administrator Consultation. Code Administrator Consultation issued 22 October 2020 and closed 5pm on 12 November 2020 with 3 responses received. Draft Final Modification Report to be presented for recommendation vote at November 2020 Panel and the Panel unanimously recommended that the CMP351 Original should be implemented. Final Modification Report sent to Ofgem 9 December 2020 with the Proposer seeking implementation by 15 February 2021. Decision received 28 January 2021 approving the Original proposal - this was implemented on 11 February 2021. | n/a | n/a | CUSC | 2020-09-10 | Mark Pearce | Neuconnect | Financial Securities – Timescales for Provision of Cash Deposit into Escrow | To change the timescales by which Cash Deposits need to be provided to National Grid ESO through the bi-annual financial securities process. | High impact on those Parties with a Construction Agreement providing financial securities under the bi-annual securities process by means of a cash deposit into a National Grid ESO managed Escrow Account. Low impact on National Grid ESO | Standard Governance, straight to Code Admin Consultation | No | n/a | n/a | 2020-09-10 | 2020-09-25 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2020-11-12 | 2020-11-27 | 2020-12-09 | 2021-01-28 | 2021-02-11
CMP352 |  | The Panel unanimously agreed that CMP352 met the Self Governance and Fast Track criteria and agreed the modification should be implemented. This was implemented on 17 December 2020 as no appeals were received between 19 November 2020 and 10 December 2020. | n/a | n/a | CUSC | 2020-10-15 | Grahame Neale | ESO | Correction to ‘Revised Indicative Annual TNUoS charge’ formulas in Appendix 2 of CUSC Section 3 | Amend the formulas in Appendix 2 of CUSC section 3 to ensure the 'Revised Indicative Annual TNUoS charge’ is calculated correctly | Low Impact on Suppliers who wish to use the ‘Revised Indicative Annual TNUoS charge’ provisions of Appendix 2 of CUSC section 3. | Fast Track, Self-Governance | No | n/a | n/a | 2020-10-15 | 2020-10-01 | NA - Fast Track | NA - Fast Track | NA - Fast Track | NA - Fast Track | 0 | NA - Fast Track | NA - Fast Track | NA - Fast Track | N/A Self governance mod | N/A Self governance mod | 2020-12-17
CMP353 | Implementation | On 29 October 2020, National Grid ESO raised CMP353. The Proposer sent a request to the CUSC Panel Secretary for the modification to be treated as urgent. The Panel on 30 October 2020 considered CMP353 and the associated request for urgency. The unanimous view of the Panel is that CMP353 does meet Ofgem’s Urgency criteria (a) and should be treated as an Urgent CUSC Modification Proposal - on 3 November 2020, Ofgem approved that CMP353 should follow an urgent timeline. Code Administrator Consultation was issued 2pm on 5 November 2020 and closed 2pm on 19 November 2020 with 25 responses received. Draft Final Modification Report was presented for recommendation vote at Special Panel on 24 November 2020 and Panel unanimously recommended that the CMP353 Original should be implemented. Final Modification Report sent to Ofgem 25 November 2020 and decision received 2 December 2020 approving the Original proposal - this will be implemented on 1 April 2021. | n/a | n/a | CUSC | 2020-10-29 | Grahame Neale | ESO | Stabilising the Expansion Constant and non-specific Onshore Expansion Factors from 1st April 2021 | Seeks to stabilise the locational signal at the start of the RIIO-2 period at the RIIO-1 value plus relevant inflation in each charging year until such time as the effect of any change in the locational signal can be better understood | High impact on all CUSC Users who pay TNUoS tariffs. | Standard Governance (with Urgent timeline), straight to Code Admin Consultation | No | n/a | n/a | 2020-10-29 | 2020-10-30 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2020-11-19 | 2020-11-24 | 2020-11-25 | 2020-12-02 | 2021-04-01
CMP354 | Implementation | The Panel unanimously agreed that CMP354 met the Self-Governance criteria and agreed the modification should proceed to Code Administrator Consultation. Code Administrator Consultation was issued on 2 December 2020 closed 5pm on 23 December 2020 with 2 responses received. Draft Final Modification Report was presented to Panel on 29 January 2021 - Panel unanimously voted that this should be implemented. This will be implemented 1 April 2021 if no appeals raised in the Appeals Window 9 February 2021 to 2 March 2021. | n/a | n/a | CUSC | 2020-11-12 | Katharina Birkner | ESO | Capacity Allocation and Congestion Management Regulation (CACM) cost sharing consequential changes | Seeks to allow the ESO to ensure that any Capacity Allocation and Congestion Management Regulation (CACM) related payments (determined by the Authority) are paid to relevant interconnector licensees in 2021 and to facilitate the interconnector adjustment payment process for future Authority cost recovery decisions. | Medium impact on interconnectors and National Grid ESO | Self-Governance, straight to Code Admin Consultation | No | n/a | n/a | 2020-11-12 | 2020-11-27 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 2/12/20 to 23/12/20 | 2021-01-29 | N/A Self governance mod | N/A Self governance mod | 2021-04-01
CMP355 | Implementation | On 17 December 2020, National Grid ESO raised CMP355 and CMP356. The Proposer sent a request to the CUSC Panel Secretary for these modifications to be treated as urgent. The CUSC Panel on 18 December 2020 considered CMP355 and CMP356 and the associated request for urgency. The unanimous view of the CUSC Panel is that CMP355 and CMP356 do meet Ofgem’s Urgency criteria and should both be treated as Urgent CUSC Modification Proposals. The joint Code Administrator Consultation for CMP355 and CMP356 was issued on 23 December 2020 following Ofgem's decision of 23 December 2020 agreeing that this can be progressed on an Urgent timeline. Code Administrator Consultation closed 7 January 2021 with 1 response received. Draft Final Modification Report was presented to Panel on 13 January 2021 and Panel unanimously recommended that the Original should be implemented. Final Modification Report sent to Ofgem 18 January 2021 with decision approving the Original proposal received 22 January 2021. Implementation Date is 1 April 2021. | n/a | n/a | CUSC | 2020-12-17 | Grahame Neale | ESO | Updating the Indexation methodology used in TNUoS and Transmission Connection Asset charges for RIIO2’ | Currently, Section 14 of CUSC uses the Retail Price Index (RPI) as the measure for index-linking various parts of the charging methodologies. With the RIIO2 Final Decision from Ofgem, the RPI measure of indexation has being replaced and so the CUSC needs to be revised accordingly to use the correct measure for setting TNUoS and Transmission Connection Asset (TCA) charges. CMP355 specifically seeks to change the relevant parts of Section 14 so that references to RPI are revised to the indexation method as set out in the transmission licence. | Medium impact on all CUSC Users who pay TNUoS tariffs or Transmission Connection Asset charges. | Standard Governance (with Urgent timeline), straight to Code Admin Consultation | No | n/a | n/a | 2020-12-17 | 2020-12-18 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 23/12/20 to 7/1/21 | 2021-01-13 | 2021-01-18 | 2021-01-22 | 2021-04-01
CMP356 | Implementation | On 17 December 2020, National Grid ESO raised CMP355 and CMP356. The Proposer sent a request to the CUSC Panel Secretary for these modifications to be treated as urgent. The CUSC Panel on 18 December 2020 considered CMP355 and CMP356 and the associated request for urgency. The unanimous view of the CUSC Panel is that CMP355 and CMP356 do meet Ofgem’s Urgency criteria and should both be treated as Urgent CUSC Modification Proposals. The joint Code Administrator Consultation for CMP355 and CMP356 was issued on 23 December 2020 following Ofgem's decision of 23 December 2020 agreeing that this can be progressed on an Urgent timeline. Code Administrator Consultation closed 7 January 2021 with 1 response received. Draft Final Modification Report was presented to Panel on 13 January 2021 and Panel unanimously recommended that the Original should be implemented. Final Modification Report sent to Ofgem 18 January 2021 with decision approving the Original proposal received 22 January 2021. Implementation Date is 1 April 2021. | n/a | n/a | CUSC | 2020-12-17 | Grahame Neale | ESO | Definition changes for CMP355 | Currently, Section 14 of CUSC uses the Retail Price Index (RPI) as the measure for index-linking various parts of the charging methodologies. With the RIIO2 Final Decision from Ofgem, the RPI measure of indexation has being replaced and so the CUSC needs to be revised accordingly to use the correct measure for setting TNUoS and Transmission Connection Asset (TCA) charges. CMP355 specifically seeks to change the relevant parts of Section 14 so that references to RPI are revised to the indexation method as set out in the transmission licence. CMP356 has been raised to support CMP355 by changing Section 11 to add supporting definitions | Medium impact on all CUSC Users who pay TNUoS tariffs or Transmission Connection Asset charges. | Standard Governance (with Urgent timeline), straight to Code Admin Consultation | No | n/a | n/a | 2020-12-17 | 2020-12-18 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | 0 | NA - Straight to Code Administrator Consultation | 23/12/20 to 7/1/21 | 2021-01-13 | 2021-01-18 | 2021-01-22 | 2021-04-01
CMP357 | Implementation | On 22 December 2020, SSE Generation raised CMP357. The Proposer sent a request to the CUSC Panel Secretary for these modifications to be treated as urgent. The CUSC Panel on 23 December 2020 considered CMP357 and the associated request for urgency. The majority view of the CUSC Panel was that CMP357 does not meet Ofgem’s Urgency criteria; however, Ofgem granted Urgency on 30 December 2020. The CUSC Panel also agreed that this would need to be assessed by a Workgroup. Workgroup was held on 5 January 2021 with Workgroup Consultation issued 6 January 202. This closed 5pm on 8 January 2021 and 16 responses were received. Workgroup held 11 January 2021 to assess Workgroup Consultation responses and hold Workgroup Vote - The Workgroup concluded by majority that the Original and WACM2 better facilitated the CUSC Objectives than the current CUSC arrangements. CUSC Panel on 13 January 2021 agreed that the CMP357 Workgroup had met its Terms of Reference and that this can proceed to Code Administrator Consultation. Code Administrator Consultation opened 14 January 2021 and closed 5pm on 19 January 2021 with 9 responses received. Draft Final Modification Report to be presented for recommendation vote at Panel on 21 January 2021- the CUSC Panel recommended by majority that the Original and WACM2 better facilitated the CUSC Objectives than current CUSC. However, there was also support (4 out of 9 votes) for WACM1. Final Modification Report sent to Ofgem 21 January 2021 with decision requested before 25 January 2021. Decision received directing WACM2 (Implementing a TNUoS Locational Onshore Security Factor that is set to two decimal places and is applied for the duration of the RIIOT2 price control period) to be implemented on 1 April 2021 | n/a | Ofgem granted Urgency on 30 December 2020 so will be moved to top of prioritisation stack | CUSC | 2020-12-22 | Garth Graham | SSE Generation | To improve the accuracy of the TNUoS Locational Onshore Security for the RIIO2 Period | To insert that the security factor for the purpose of calculating TNUoS tariffs will use the result of the assessment expressed to eight decimal places. | Medium impact on all CUSC Users who pay TNUoS tariffs | Standard Governance (with Urgent timeline) with Workgroup | No | Paul Mullen | Joe Henry | 2020-12-22 | 2020-12-23 | 2021-01-05 | 6/1/21 to 8/1/21 | 2021-01-11 | 2021-01-11 | 2 | 2021-01-13 | 14/1/21 to 19/1/21 | 2021-01-21 | 2021-01-21 | 2021-01-25 | 2021-04-01
CMP358 | Workgroup Stage | On 12 January 2021, Afton Wind Farm Limited raised CMP358 and CMP359. The Proposer sent a request to the CUSC Panel Secretary for these modifications to be treated as urgent. The CUSC Panel on 13 January 2021 considered CMP358 and CMP359 and the associated request for urgency. The majority view of the CUSC Panel was that CMP358 and CMP359 did not meet Ofgem’s Urgency criteria - request for Urgency was sent to Ofgem 13 January 2021 for decision by 5pm on 14 January 2021. The CUSC Panel also agreed that this would need to be assessed by a Workgroup. Ofgem rejected the request for Urgency on 15 January 2021. Following Ofgem’s decision on 15 January 2021 not to approve urgent treatment of CMP358/359, the CUSC Panel on 21 January 2021 considered where CMP358/359 would sit within the prioritisation stack. CUSC Panel concluded that CMP358/359 would be placed “Low” in the current prioritisation stack and therefore there will be no CMP358/CMP359 Workgroups in the foreseeable future. Waters Wye, who are representing the Proposer, attended the CUSC Panel on 29 January 2021 to challenge this decision. They primarily cited the compound impact for Scottish Generators of the removal of the Small Generator Discount with the latest Transmission Generation Residual decisions and the current general uncertainty. After careful consideration, the Panel decided to maintain their previous decision for the same reasons they provided at Panel on 21 January 2021. | Low | Following Ofgem’s decision on 15 January 2021 not to approve urgent treatment of CMP358/359, the CUSC Panel on 21 January 2021 considered where CMP358/359 would sit within the prioritisation stack. The majority of the Panel believed that Ofgem have been consistent and explicit that the Small Generator Discount would be removed and didn’t agree with one Panel member’s view that there was an expectation something else would be replacing it. They also noted that there are a lot of other existing Modifications that have yet to be even progressed and did not believe that such a known issue provided a convincing case for CMP358/359 to be placed above these Modifications in the prioritisation stack. The CUSC Panel on 21 January 2021 concluded that CMP358/359 would be placed “Low” in the current prioritisation stack and therefore there will be no CMP358/CMP359 Workgroups in the foreseeable future. Waters Wye, who are representing the Proposer, attended the CUSC Panel on 29 January 2021 to challenge this decision. They primarily cited the compound impact for Scottish Generators of the removal of the Small Generator Discount with the latest Transmission Generation Residual decisions and the current general uncertainty. After careful consideration, the Panel decided to maintain their previous decision for the same reasons they provided at Panel on 21 January 2021. | CUSC | 2021-01-12 | David Bruce | Afton Wind Farm Limited | Implementation of the Small Generator Discount into the CUSC | The Small Generator Discount (SGD) is currently contained in the ESO’s licence. The SGD expires on 1 April 2021. Given the ongoing uncertainty over the Forward Looking and Access SCR, CMP358 proposes that the SGD is put into the CUSC and CMP359 will seek to define SGD and CPI/CPIH. | Medium impact on Generators currently receiving the Small Generators Discount (SGD) and other parties that would benefit if the SGD was removed as currently planned. | Standard Governance with Workgroup | No | TBC | TBC | 2021-01-12 | 2021-01-13 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP359 | Workgroup Stage | On 12 January 2021, Afton Wind Farm Limited raised CMP358 and CMP359. The Proposer sent a request to the CUSC Panel Secretary for these modifications to be treated as urgent. The CUSC Panel on 13 January 2021 considered CMP358 and CMP359 and the associated request for urgency. The majority view of the CUSC Panel was that CMP358 and CMP359 did not meet Ofgem’s Urgency criteria - request for Urgency was sent to Ofgem 13 January 2021 for decision by 5pm on 14 January 2021. The CUSC Panel also agreed that this would need to be assessed by a Workgroup. Ofgem rejected the request for Urgency on 15 January 2021. Following Ofgem’s decision on 15 January 2021 not to approve urgent treatment of CMP358/359, the CUSC Panel on 21 January 2021 considered where CMP358/359 would sit within the prioritisation stack. CUSC Panel concluded that CMP358/359 would be placed “Low” in the current prioritisation stack and therefore there will be no CMP358/CMP359 Workgroups in the foreseeable future. Waters Wye, who are representing the Proposer, attended the CUSC Panel on 29 January 2021 to challenge this decision. They primarily cited the compound impact for Scottish Generators of the removal of the Small Generator Discount with the latest Transmission Generation Residual decisions and the current general uncertainty. After careful consideration, the Panel decided to maintain their previous decision for the same reasons they provided at Panel on 21 January 2021. | Low | Following Ofgem’s decision on 15 January 2021 not to approve urgent treatment of CMP358/359, the CUSC Panel on 21 January 2021 considered where CMP358/359 would sit within the prioritisation stack. The majority of the Panel believed that Ofgem have been consistent and explicit that the Small Generator Discount would be removed and didn’t agree with one Panel member’s view that there was an expectation something else would be replacing it. They also noted that there are a lot of other existing Modifications that have yet to be even progressed and did not believe that such a known issue provided a convincing case for CMP358/359 to be placed above these Modifications in the prioritisation stack. The CUSC Panel on 21 January 2021 concluded that CMP358/359 would be placed “Low” in the current prioritisation stack and therefore there will be no CMP358/CMP359 Workgroups in the foreseeable future. Waters Wye, who are representing the Proposer, attended the CUSC Panel on 29 January 2021 to challenge this decision. They primarily cited the compound impact for Scottish Generators of the removal of the Small Generator Discount with the latest Transmission Generation Residual decisions and the current general uncertainty. After careful consideration, the Panel decided to maintain their previous decision for the same reasons they provided at Panel on 21 January 2021. | CUSC | 2021-01-12 | David Bruce | Afton Wind Farm Limited | Definition changes for CMP358 | The Small Generator Discount (SGD) is currently contained in the ESO’s licence. The SGD expires on 1 April 2021. Given the ongoing uncertainty over the Forward Looking and Access SCR, CMP358 proposes that the SGD is put into the CUSC and CMP359 will seek to define SGD and CPI/CPIH. | Medium impact on Generators currently receiving the Small Generators Discount (SGD) and other parties that would benefit if the SGD was removed as currently planned. | Standard Governance with Workgroup | No | TBC | TBC | 2021-01-12 | 2021-01-13 | TBC | TBC | TBC | TBC |  | TBC | TBC | TBC | TBC | TBC | TBC
CMP360 | Code Admin Consultation | CUSC Panel on 29 January 2021 by majority agreed that CMP360 should follow standard governance route and unanimously agreed that this should proceed to Code Administrator Consultation. Code Administrator Consultation was issued at 9am on 1 February 2021 and will close 5pm on 19 February 2021. | n/a | n/a | CUSC | 2021-01-14 | James Stone | National Grid ESO | Aligning Section 14 of the CUSC ‘ Balancing Services Use of System Charging Methodology’ to the licence changes introduced by RIIO-2 in respect of the ‘System Operator Revenue Restriction’ | To change the relevant parts of Section 14 so that the definitions and formulae used to calculate External and Internal BSUoS charges for each Settlement Period reflect the methodology used in the ESOElectricity System Operator licence for RIIO-2. | Low impact to National Grid Electricity System Operator and those CUSC Users who pay Balancing Services Use of System charges | Standard Governance, straight to Code Admin Consultation | No | n/a | n/a | 2021-01-14 | 2021-01-29 | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation | NA - Straight to Code Administrator Consultation |  | NA - Straight to Code Administrator Consultation | 1/2/21 to 19/2/21 | 2021-03-02 | N/A Self governance mod | N/A Self governance mod | 2021-04-01
CMP361 |  | To be presented at CUSC Panel on 26 February 2021. | TBC at CUSC Panel on 26 February 2021 | To be confirmed at CUSC Panel on 26 February 2021 | CUSC | 2021-02-11 | Katharina Birkner | National Grid ESO | BSUoS Reform: Introduction of an ex ante fixed BSUoS tariff | To introduce an ex ante fixed volumetric BSUoS tariff set over a total fix and notice period of 14 months. This tariff would be split with a different price for the summer and winter periods. This will deliver the recommendations of the Second BSUoS Task Force Modification | High impact on suppliers, generators, final demand and National Grid ESO. | Standard Governance with Workgroup | No | Jennifer Groome | Kavita Patel | 2021-02-11 | 2021-02-26 | 2021-05-04 | 17/5/21 to 7/6/21 | 2021-06-15 | 2021-06-29 |  | 2021-07-30 | 3/8/21 to 23/8/21 | 2021-09-24 | 2021-10-05 | TBC | 2023-04-01
CMP362 |  | To be presented at CUSC Panel on 26 February 2021. | TBC at CUSC Panel on 26 February 2021 | To be confirmed at CUSC Panel on 26 February 2021 | CUSC | 2021-02-11 | Katharina Birkner | National Grid ESO | BSUoS Reform: Consequential Definition Updates | To facilitate the implementation of BSUoS Reform by introducing and updating required definitions into CUSC section 11 from CMP308 and CMP361. Modification | Medium impact on suppliers and final demand. | Standard Governance with Workgroup | No | Jennifer Groome | Kavita Patel | 2021-02-11 | 2021-02-26 | 2021-05-04 | 17/5/21 to 7/6/21 | 2021-06-15 | 2021-06-29 |  | 2021-07-30 | 3/8/21 to 23/8/21 | 2021-09-24 | 2021-10-05 | TBC | 2023-04-01
CMP363 |  | To be presented at CUSC Panel on 26 February 2021. | TBC at CUSC Panel on 26 February 2021 | To be confirmed at CUSC Panel on 26 February 2021 | CUSC | 2021-02-11 | Grahame Neale | National Grid ESO | TNUoS Demand Residual charges for transmission connected sites with a mix of Final and non-Final Demand | CMP363 seeks to clarify the TNUoS Demand Residual charging arrangements for transmission connected sites that have a mix of Final and non-Final Demand. | Medium impact on Transmission connected sites with a mixture of Final and non-Final Demand, the ESO, ELEXON | Standard Governance with Workgroup | No | Paul Mullen | TBC | 2021-02-11 | 2021-02-26 | 2021-04-15 | 26/4/21 to 18/5/21 | 2021-05-27 | 2021-06-04 |  | 2021-06-25 | 28/6/21 to 19/7/21 | 2021-07-30 | 2021-08-10 | TBC | 2022-04-01
CMP364 |  | To be presented at CUSC Panel on 26 February 2021. | TBC at CUSC Panel on 26 February 2021 | To be confirmed at CUSC Panel on 26 February 2021 | CUSC | 2021-02-11 | Grahame Neale | National Grid ESO | Definition changes for CMP363 | CMP363 seeks to clarify the TNUoS Demand Residual charging arrangements for transmission connected sites that have a mix of Final and non-Final Demand. CMP364 is to support CMP363 by changing Section 11 to add/amend/remove definitions as needed | Medium impact on Transmission connected sites with a mixture of Final and non-Final Demand, the ESO, ELEXON | Standard Governance with Workgroup | No | Paul Mullen | TBC | 2021-02-11 | 2021-02-26 | 2021-04-15 | 26/4/21 to 18/5/21 | 2021-05-27 | 2021-06-04 |  | 2021-06-25 | 28/6/21 to 19/7/21 | 2021-07-30 | 2021-08-10 | TBC | 10 working days after Ofgem decision