## Deliverables
Role | Sub activity | Deliverable reference number | Deliverable name | Milestone Description | Milestone date | Milestone Status | Milestone completion date (quarter) | Deliverable commentary
1 | A1.1.Ongoing activities | D1.1.1 | Balance Great Britain’s (GB) demand for energy with supply from generators around the clock. | N/A | N/A | Complete | Q4 2022-23 | Please refer to our Metrics and Regularly Reported Evidence
1 | A1.1.Ongoing activities | D1.1.2 | Maintain security of supply in real time and the ability to restart the system in the event of a partial or total loss of power. | N/A | N/A | Complete | Q4 2022-23 | Please refer to our Metrics and Regularly Reported Evidence
1 | A1.1.Ongoing activities | D1.1.3 | Maintain the integrity of the transmission network, while manage the economical operation of the system. | N/A | N/A | Complete | Q4 2022-23 | Please refer to our Metrics and Regularly Reported Evidence
1 | A1.1.Ongoing activities | D1.1.4 | Liaise with ENTSO-E (European Network for Transmission System Operators – Electricity) and CoOrdination of Electricity System Operators (CORESO) on the ESO’s European operations. Strategic relationships with European institutions are covered in Activity A6.2 European Union (EU) code change and relationships. | European deliverables to meet the requirements of the Trade and Co-operation Agreement (TCA) | Q4 2021-22 | Delayed - External Reasons |  | NGESO has withdrawn its membership of ENTSO-e from the end of 2021 as requested by the TCA. A Memorandum of Understanding (MoU) has been agreed between ENTSO-E and NGESO to define the future cooperation. The original milestone date was proposed in the TCA and it has become clear that defining the future arrangements for cooperation with all European TSOs will take longer than originally anticipated and will require an agreed co-ordinated approach by both the UK and the EU.
1 | A1.1.Ongoing activities | D1.1.4 | Liaise with ENTSO-E (European Network for Transmission System Operators – Electricity) and CoOrdination of Electricity System Operators (CORESO) on the ESO’s European operations. Strategic relationships with European institutions are covered in Activity A6.2 European Union (EU) code change and relationships. | Regional Security Co-ordinators (RSC) security analysis project | Q3 2022-23 | Complete | Q3 2022-23 | NGESO has withdrawn the membership of ENTSO-e from the end of 2021 as requested by TCA. An MoU has been agreed between ENTSO-E and NGESO to define the future cooperation. NGESO receive a daily Day Ahead security analysis report from Coreso for the South Coast GB network.
1 | A1.1.Ongoing activities | D1.1.4 | Liaise with ENTSO-E (European Network for Transmission System Operators – Electricity) and CoOrdination of Electricity System Operators (CORESO) on the ESO’s European operations. Strategic relationships with European institutions are covered in Activity A6.2 European Union (EU) code change and relationships. | Maintain day-ahead congestion forecast process whilst awaiting a decision on the new methodology of Capacity Calculation resulting from the TCA | Q3 2022-23 | Complete | Q3 2022-23 | NGESO has withdrawn the membership of ENTSO-e from the end of 2021 as requested by TCA. An MoU has been agreed by ENTSO-E and NGESO to define the future cooperation.
1 | A1.1.Ongoing activities | D1.1.5 | Upgraded legacy balancing and situational awareness tools to deliver continued service levels whilst new tools are being development. | State of Energy signal defined and implemented for limited energy assets (such as batteries). | TBC (dependent on impact assessment) | Delayed - Internal Reasons |  | We have taken a strategic decision to deliver this functionality in our new Open Balancing Platform following our ongoing industry engagement and as a result we have also set up and are running up a Storage Stakeholder Group to discuss approach and conversations are ongoing Planned to deliver state of energy data/process within our new Open Balancing Platform potentially using Maximum Delivery Volume (Export) and Maximum Delivery Volume (Import). This is subject to discussions around grid code planned at grid code development forum in January 2023 (and beyond). By the end of our Programme Increment 7 (May 2023) agree a solutions for state of energy and this will be taken to grid code by April 2023. If agreed will deliver in OBP in release Q1 2024/25.
1 | A1.1.Ongoing activities | D1.1.6 | Assessment of future operability challenges communicated through the Operability Strategy Report. Published annually. | Publish Operability Strategy Report. Undertake improvements to these publications in accordance with stakeholder feedback and/or ESO internal publication review. | Q3 2021-22 | Complete | Q3 2021-22 | Operability report published 21 December 2021
1 | A1.1.Ongoing activities | D1.1.6 | Assessment of future operability challenges communicated through the Operability Strategy Report. Published annually. | Publish Operability Strategy Report. Undertake improvements to these publications in accordance with stakeholder feedback and/or ESO internal publication review. | Q3 2022-23 | Complete | Q3 2022-23 | Operability report published 21 December 2021. On track to publish update in 2022.
1 | A1.1.Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at dayahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches. Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. Our forecasting enhancements will provide the control room with better quality, more frequent forecasts, allowing them to make better operational decisions. This helps minimise balancing costs and reduce carbon emissions. | Implementation of forecasting products and sharing outputs from mature products externally where possible: Implementation of core forecasting capability (demand, wind and solar power generation forecasts at national and GSP levels) in PEF Embed additional input data into internal forecasting processes – embedded generation metering data, weather data Build further on digital forecasting foundation to deliver improvement in large data processing, model training and forecast prediction time. Decommission existing legacy forecasting capability and system (EFS). | Q1-Q4 2021-22 | Delayed - Internal Reasons |  | Partial delivery of this milestone. PEF is a continuous improvement project to develop and implement ESO’s new forecasting capability. We have delivered and implemented national solar power generation, national demand and GSP net demand forecast products. We have now implemented/delivered two initial releases of this milestone (GSP Forecasts) and we aim to implement remaining GSP level forecasting product (PV & Wind) in FY24 GSP demand machine learning model outputs are now consumed with in operational planning and decision-making timescales. Output from this model is estimated to be ~20% better than legacy energy forecasting system. Model are re-training automatically at least 3 times a week to capture most recent demand patterns and provide accurate possible forecasts to transmission analysis study setups and real time decision making in control room. PEF products also use most recent and weather data inputs During the next phases of the project and in BP2, we are adopting new way of working and start delivering forecasting as a product. We are exploring options to further enhance and implement newly developed forecasting products into operational use and share it with market (where possible)
1 | A1.1.Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at dayahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches. Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. Our forecasting enhancements will provide the control room with better quality, more frequent forecasts, allowing them to make better operational decisions. This helps minimise balancing costs and reduce carbon emissions. | Complete integration of grid supply point (GSP) level demand, solar and wind power forecasts into transmission analysis study and balancing tools (where possible): Make GSP level demand, solar and wind power forecasts available for market participants Make additional improved, granular and frequent forecasting data available in machine readable format for market participants to improve decision making ahead of real time. | Q1-Q4 2022-23 | Delayed - Consumer Benefits |  | Forecasting Platform delivery is now re-prioritised to maximise consumer benefits through reducing technical debt by > delivering PEF on ESO’s strategic cloud platform > integration with ESO’s other strategic initiatives Data analytics platform (DAP) and Open Balancing platform (OBP) in BP2 We will continue to maintain and improve (where possible) forecasting and performance improvements delivered in BP1 and adoption of product model and agile ways of working while we deliver additional features and benefits in BP2. PEF is a continuous improvement project to develop and implement ESO’s new forecasting capability. During BP1, we completed initial releases for National Demand and Grid Supply Point (GSP) forecasting products and delivered enhancements to PEF in the Control Room.
1 | A1.1.Ongoing activities | D1.1.8 | Trading solutions to deliver a safe, secure and economical strategy for the Control Centre. | New interconnectors online, as per Interconnector register1 (subject to change). | Q1-Q4 2021-22 | Complete | Q4 2021-22 | ESO has faciliated bringing IFA2 online, and also facilitated a number of market changes to interconnector intraday markets. Our activities are driven by the timings of new interconnectors connecting and commissioning. The next interconnector to come online will be ElecLink. Preparations are underway to ensure trading systems and processes will be ready for go-live.
1 | A1.1.Ongoing activities | D1.1.8 | Trading solutions to deliver a safe, secure and economical strategy for the Control Centre. | New interconnectors online, as per Interconnector register (subject to change). | Q1-Q4 2022-23 | Complete | Q4 2022-23 | ElecLink has moved to in intraday markets this quarter allowing us to trade with our counterparties on this Interconnector. Our activities are driven by the timings of new interconnectors connecting and commissioning. When new interconnectors are going to come online we will make preparations to ensure trading systems and processes will be ready for go-live.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Start developing foundational infrastructure and tooling to support applications: Testing and automation tools Capacity management tools Alarm and event management Monitoring tools Incident management Coding tools Change management tools Containerisation tools Cyber security tools | Q1 2021-22 | Complete | Q1 2021-22 | The programme is now in the Core Phase. This is where we begin to build out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023. In Q3 2021-22 we engaged with the TAC and a high level to introduce the programme and its aims. An update to the roadmap is not planned at this time.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Build a platform environment to create applications in (collaboration space with servers, storage and code development infrastructure). | Q1 2021-22 | Complete | Q4 2021-22 | Platform environment created to enable code development to start.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Complete foundational infrastructure tooling work. | Q2 2021-22 | Complete | Q4 2022-23 | Foundational infrastructure tooling work is complete as development environments have been created to enable code development to start.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Updated Roadmap agreed with TAC and published. | Q2 2021-22 | Complete | Q3 2021-22 | The programme is now in the Core Phase. This is where we begin to build out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023. In Q3 2021-22 we engaged with the TAC and a high level to introduce the programme and its aims. An update to the roadmap is not planned at this time.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Future system architecture defined, including in-scope modules for future development. | Q4 2021-22 | Complete | Q2 2021-22 | The programme is now in the Core Phase. This is where we begin to build out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023. In Q3 2021-22 we engaged with the TAC and a high level to introduce the programme and its aims. An update to the roadmap is not planned at this time.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Updated Roadmap agreed with TAC and published | Q4 2021-22 | Complete | Q4 2021-22 | The programme is now in the Core Phase. This is where we begin to build out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023. In Q3 2021-22 we engaged with the TAC and a high level to introduce the programme and its aims. Roadmap has now been updated and published.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Sandbox testing environment developed (timescale TBC): Define data inputs and data sets to test components Define expected outputs to compare test against Start testing priority components (to be determined). | Q4 2021-22 | Complete | Q4 2022-23 | • Sandbox testing environment developed (timescale TBC): Complete, We have several Sandbox test environments in operation. • Define data inputs and data sets to test components : Complete, doing this in our system test. • Define expected outputs to compare test against – complete, We have test conditions in the user stories, all user stories have fully documented acceptance criteria. • Start testing priority components (to be determined). – We have a fully testable link between OBP (enhanced balancincing) and BM (existing tools). All OBP components were fully integrated during September 2022. -- The programme is now in the Core Phase. This is where we begin to build out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Migration roadmap development started, providing a view of when new systems will come online, and legacy ones switched off. | Q1 2022-23 | Complete | Q2 2021-22 | The programme is now in the Core Phase. This is where we begin to build out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023. In Q3 2021-22 we engaged with the TAC and a high level to introduce the programme and its aims. An update to the roadmap is not planned at this time.
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Updated Roadmap agreed with TAC and published. | Q2 2022-23 | Complete | Q2 2022-23 | The programme is now in the Core Phase. This is where we begin to build out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023. Updated roadmap has been shared with TAC as part of ongoing engagement
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Updated Roadmap agreed with TAC and published. | Q4 2022-23 | Complete | Q4 2022-23 | Completed - updated roadmap published Updated revisions to roadmap will continued to be been shared with TAC as part of ongoing engagement
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Deliver first application components (timescales TBC): Build the production environment to safely and securely develop code for 24/7 systems Testing in sandbox environment. | Q4 2022-23 | Delayed - Internal Reasons |  | The delivery of this milestone has been re-prioritised to be align with the first release the Open Balancing Platform in Q3 2023/24. The programme is now in the Core Phase. This is where we are building out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023. Updated roadmap has been shared with TAC as part of ongoing engagement
1 | A1.2 Enhanced Balancing Capability | D1.2.1 | Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today. | Ongoing agile delivery of application components, using production environment and sandbox (will be determined by Roadmap at end of RIIO-1). | Q4 2022-23 | Delayed - Internal Reasons |  | The delivery of this milestone has been strategically re prioritised to be align with the first release the Open Balancing Platform in Q3 2023. The programme is now in the Core Phase. This is where we are building out the core of the new platform. For the "build a platform environment" milestone, we are setting up the Development environment to begin building the new platform in February 2022. The "foundational infrastructure tooling work" deliverable also forms part of this activity, and has been re-planned to be delivered just ahead of the first go-live in 2023. Updated roadmap has been shared with TAC as part of ongoing engagement
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Publish Operability Strategy Report (D1.1.6). | Q3 2021-22 | Complete | Q3 2021-22 | Operability report published 21 December 2021. Update published in Q3 2022-23
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Ongoing tool development throughout the year. (Exact challenges and tools are TBC). | Q4 2021-22 | Complete | Q4 2021-22 | The first provider's Inertia forecasting solution is now complete, providing inertia monitoring and forecast for Scotland. Continued assessment of the new inertia monitoring and forecasting methodology and results are taking place with independent third party ahead of implementing within the control room in the late spring / early summer. The second supplier's inertia monitoring solution is continuing to experience technical issues during testing and is now expected to be completed in April 2022.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Ongoing – ESO uses first supplier’s monitoring tool. | Q4 2021-22 | Complete | Q4 2021-22 | "The first provider's Inertia forecasting solution is now complete, providing inertia monitoring and forecast for Scotland. Continued assessment of the new inertia monitoring and forecasting methodology and results are taking place with independent third party ahead of implementing within the control room in the late spring / early summer.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Deliver first supplier inertia forecasting. | Q1-Q2 2021-22 | Complete | Q3 2021-22 | The first provider's Inertia forecasting solution is now complete, providing inertia monitoring and forecast for Scotland. Continued assessment of the new inertia monitoring and forecasting methodology and results are taking place with independent third party ahead of implementing within the control room.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Second supplier delivers inertia monitoring tool. | Q2 2021-22 | Complete | Q2 2022-23 | Reactive Technology Limited deployment successfully completed in early July following resolution of technical issues. Following commissioning the output data will be assessed ahead of the system going live within the Control Room in late summer 2022.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Deliver Stability Pathfinder phase 1, including enduring IT solution. | Q2 2021-22 | Complete | Q2 2021-22 | Initial IS systems have been established to allow operation for Ph1 stability services as they go live. IS systems will be developed further in line with delivery of Phase 2 and Phase 3 contracts.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Requirements and design work for Phase 2. | Q1-Q2 2021-22 | Delayed - External Reasons |  | Design work to be completed by Q3 23/24 following completion of the requirements gathering. As the Stability Phase 2 contracts are not scheduled to start until April 24, therefore the original milestone date is not suitable. We expect the IT design and development work will not delay the commencement of the contracts.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Development and testing work for Phase 2 | Q3-Q4 2021-22 | Delayed - External Reasons |  | Design work to be completed by Q3 23/24 following completion of the requirements gathering. As the Stability Phase 2 contracts are not scheduled to start until April 24, therefore the original milestone date is not suitable. We expect the IT design and development work will not delay the commencement of the contracts.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Visibility: TBC (dependent on impact assessment) - State of Energy signal defined and implemented for limited energy assets (such as batteries). | Q1-Q4 2021-22 | Delayed - Internal Reasons |  | We have set up and are running a Storage Stakeholder Group to discuss approach and conversations are ongoing Planned to deliver state of energy data/process within our new Open Balancing Platform potentially using Maximum Delivery Volume (Export) and Maximum Delivery Volume (Import). This is subject to discussions around grid code planned at grid code development forum in January 2023 (and beyond). By the end of Programme Increment 7 (May 2023) agree a solutions for state of energy and this will be taken to grid code by April 2023. If agreed will deliver in OBP in release Q1 2024/25.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Finish requirement and design work for Mersey Pathfinder. | Q1 2021-22 | Complete | Q1 2021-22 | The design phase is complete and we are undergoing testing for service commencement in Mid 2022
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Development and testing for Mersey Pathfinder. | Q2-4 2021-22 | Complete | Q4 2021-22 | Voltage Mersey - Zenobe: IT solution complete Voltage Mersey - Peakgen: IT solution complete
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Development and testing for Constraints Management Pathfinder. (TBC on impact assessment) | Q1-Q2 2021-22 | Delayed - Internal Reasons |  | The Constraint Management Pathfinder is contracted to commence from October 2023, though ESO have been able to access some units since April 2022. Therefore the original milestone date of Q1-21 was not suitable for these changes. The IT changes to enhance the usage of the CMP service will be delivered in several stages as there are a number IT systems that will be updated. The first of these changes are planned for June 2023 which will include testing with subsequent changes later in 2023. These changes will allow the use of the service to be optimised as further generators are connected and additional circuits are monitored.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Implement Constraints Management Pathfinder. | Q3 2021-22 | Delayed - Internal Reasons |  | The Constraint Management Pathfinder is contracted to commence from October 2023, though ESO have been able to access some units since April 2022. Therefore the original milestone date of Q1-21 was not suitable for these changes. The IT changes to enhance the usage of the CMP service will be delivered in several stages as there are a number IT systems that will be updated. The first of these changes are planned for June 2023 which will include testing with subsequent changes later in 2023. These changes will allow the use of the service to be optimised as further generators are connected and additional circuits are monitored.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Publish Operability Strategy Report (D1.1.6). | Q3 2022-23 | Complete | Q4 2022-23 | Next update of the Operability Strategy report published in Q4 2022-23.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Ongoing tool development throughout the year. (Exact challenges and tools are TBC). | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Data assessment by NPL for both systems progressing along with development of improvements to add situational awareness into Control Room for summer 2023
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Inertia Ongoing use of tools and work with TOs to improve data quality. | Q1-Q4 2022-23 | Delayed - External Reasons |  | Assessment of inertia data accuracy being undertaken by NPL ahead of introducing into operational processes. Continued work with TOs to increase availability of PMU input data for GE inertia tools. SSE data is likely to available mid 2023 to improve accuracy in Scotland however , however NGET have delayed their PMU rollout impacting the likelihood of the system expanding to cover England & Wales in FY23. Now not expected until at least end of FY24. Work planned to investigate extending forecasting to GB ahead of PMU measurements being available
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Stability: development and testing for Phase 2. | Q1-Q3 2022-23 | Delayed - External Reasons |  | Design work to be completed by Q3 23/24 following completion of the requirements gathering. As the Stability Phase 2 contracts are not scheduled to start until April 24, therefore the original milestone date is not suitable. We expect the IT design and development work will not delay the commencement of the contracts.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Deliver Stability Pathfinder phase 2, including enduring IT solution. | Q4 2022-23 | Delayed - External Reasons |  | Design work to be completed by Q3 23/24 following completion of the requirements gathering. As the Stability Phase 2 contracts are not scheduled to start until April 24, therefore the original milestone date is not suitable. We expect the IT design and development work will not delay the commencement of the contracts.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Voltage: Mersey Pathfinder IT work complete. | Q1 2022-23 | Complete | Q1 2022-23 | Voltage Mersey - Supporting IT enhancements was delivered. Peakgen went live successfully in May 2022 and Zenobe in Jan 2023.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Start work on Pennines Pathfinder. | Q1 2022-23 | Complete | Q1 2022-23 | Internal stakeholder and engagement activities completed to capture IT requirements.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Pennines Pathfinder requirements and design work. | Q2-4 2022-23 | Complete | Q4 2022-23 | All requirements captured from relevant stakeholders. No IT changes have been identified.
1 | A1.2 Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Strategy Reports | Mersey Pathfinder go-live. | Q3 2022-23 | Complete | Q3 2022-23 | Voltage Mersey - Supporting IT enhancements was delivered. Peakgen went live successfully in May 2022 and Zenobe in Jan 2023.
1 | A1.2 Enhanced Balancing Capability | D1.2.3 | Projects running, using innovation funding, to consider how greater automation, machine learning and use of artificial intelligence can be used across our activities to handles increases in the amount of data and the number of expected actions. | 0 | N/A | Complete | Q4 2022-23 | New projects will continue to deliver this as a part of the innovation portfolio, current projects include: • Solar Nowcasting: Research & Develop the use of machine learning & satellite images to nowcast PV at GSP-level. Project Recently Completed: • Dynamic Reserve Calculation: Using AI and machine learning to set reserve levels dynamically, day ahead. Delivered successfully on all of it's aims and objectives, now beginning to test the outputs of the model internally.
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | iEMS Life Extension- Vendor negotiations to support life extension. | Q1-Q2 2021-22 | Complete | Q2 2021-22 | Vendor negotiations have been completed with a clear strategy to go-live in July 2022. There will be a transition period from April to July where the new support arrangements are tested.
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | iEMS Life Extension- – Deliver high priority software and hardware life extension projects. | Q3-Q4 2021-22 | Complete | Q4 2022-23 | Work on a Voltage Stability Analysis Tool (VSAT) is continuing and we have completed an upgrade to Industrial Defender Software. However some projects such as Fault Level Enhancements have been delayed due to other projects blocking build deployment paths. Delivery completed in March 2023
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- validate scope and transition strategy, based on Roadmap. | Q1 2021-22 | Complete | Q1 2021-22 | Roadmap and scope of the product are continually updated, however, the core capability scope, transition strategy are complete
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- start procurement activity for core system. | Q1 2021-22 | Complete | Q1 2021-22 | Procurement activity started successfully with multiple potential vendors being assessed
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- commence proof of concept work | Q1 2021-22 | Complete | Q1 2021-22 | Proof of concept work completed with two vendors, POC system was mapped against NGESO Network Control Programme user stories (functional requirements)
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- – determine core system “to be” architecture and options | Q1 2021-22 | Complete | Q1 2021-22 | Derived functional requirements have been mapped into "as is" and "to be" piles. Future core system architecture has been determined (in terms of environments and redundancy strategy)
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- commence core system requirements. | Q1 2021-22 | Complete | Q1 2021-22 | To date the Network Control Management System Project has developed its vision and strategy for the core system. It has also developed a set of requirements against this vision and strategy and is engaging with suppliers via a competitive procurement event to secure these.
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- procurement approach confirmed | Q2 2021-22 | Complete | Q1 2021-22 | Procurement approach has been confirmed and the process is under way.
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- finish core system requirements work. | Q2 2021-22 | Complete | Q2 2021-22 | Core system functional and non-functional requirements have been derived, potential vendors will be sent these requirements to produce proof of concept system that aligns.
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- roadmap updated with input from TAC. | Q2 2021-22 | Complete | Q2 2021-22 | Based on feedback from TAC the Network Control Programme will be enhancing its technology stack to leverage machine learning and engaging heavily with the balancing programme to ensure current disparate systems are brought together, both in the control room and in training environments
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- finish work with NGET on capability mapping. | Q2 2021-22 | Complete | Q1 2021-22 | Capability mapping completed with NGET, with key dependencies and a high level plan derived
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- validate scope and transition strategy, based on Roadmap | Q2 2021-22 | Complete | Q2 2021-22 | Roadmap and scope of the product are continually updated, the core capability scope, transition strategy are complete
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- validate scope and transition strategy, based on Roadmap | Q3 2021-22 | Complete | Q2 2021-22 | Roadmap and scope of the product are continually updated, the core capability scope, transition strategy are complete
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- confirm high level modular design | Q3 2021-22 | Complete | Q3 2021-22 | High level modular design is completed and the core system procurement has commenced with product demos having been completed by suppliers.
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- commence core system design work. | Q3 2021-22 | Complete | Q3 2021-22 | Core system design has commenced is progressing well, product demos from suppliers have been completed
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- finish core system design work | Q4 2021-22 | Complete | Q4 2021-22 | Base core system design complete, refinements now in progress to get richer user stories with specific examples from real-time operations
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- finish procurement activity. Procurement approach confirmed. | Q4 2021-22 | Complete | Q4 2021-22 | Procurement process completed with GE Digital confirmed as winning bidder. Contracts signed. Negotiations on scope with the vendors delayed the award process by a few weeks
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- roadmap updated with input from TAC. | Q4 2021-22 | Complete | Q2 2022-23 | Roadmap updated to focus on:- - Breaking down silod working between the future balancing programme and the Data Analytics Platform - Stressing the role of data and its flow into the NCMS & other systems
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | iEMS Life Extension- Deliver medium priority software and hardware life extension projects. | Q1-Q2 2022-23 | Complete | Q4 2022-23 | Work has completed on a proof of concept for using SSD hard drives. Remediation work following security penetration tests has been completed. The enhancements to our Control Training Unit (CTU) are completed
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | iEMS Life Extension- Deliver low priority software and hardware life extension projects. | Q3-Q4 2022-23 | Complete | Q3 2021-22 | No low priority projects were identified as part of our life extension work
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- build of core situational awareness system. | Q1-Q4 2022-23 | Delayed - Internal Reasons |  | Core system functions and environments have been scoped, final system design to be agreed with winning vendor. Work with data centres underway for initial deployment by mid 2023. A reference environment is stood up in AWS to allow the project team to continue delivery
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- roadmap updated with input from TAC. | Q2 2022-23 | Complete | Q2 2022-23 | Roadmap updated to focus on:- - Breaking down silod working between the future balancing programme and the Data Analytics Platform - Stressing the role of data and its flow into the NCMS & other systems
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- finish proof of concept work. | Q4 2022-23 | Complete | Q4 2021-22 | Proof of concept work completed successfully with two vendors, they have provided systems based on NGESO's functional requirements
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- roadmap updated with input from TAC. | Q4 2022-23 | Complete | Q4 2022-23 | Roadmap updated to focus on:- - Breaking down silod working between the future balancing programme and the Data Analytics Platform - Stressing the role of data and its flow into the NCMS & other systems
1 | A1.3 Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system. | Network control strategy- start project to integrate core system with data and analytics platform. | Q4 2022-23 | Complete | Q4 2022-23 | Regular touch points with Data Analytics Platform team to ensure both programmes are aligned. RFI completed for CNI Central Data Repository to gather market intelligence for CNI specific needs
1 | A1.3 Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time. | Ongoing: Engagement with the TAC on required tools. Scoping and development work. Agile build. Tool delivery. Tools may include: Lookahead capability. Leveraging additional data sources (e.g. Phasor Measurement Units). Heatmaps of network issues. More intuitive display of alarms to speed up root cause analysis. Enhanced analytics. | N/A | Complete | Q4 2022-23 | This is an ongoing activity with scoping being completed, we are now working with the vendors to ensure the Network Control Management System can deliver the functionality and integration levels required as per our requirements
1 | A1.3 Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system. This will allow Control Centre engineers make better and quicker decisions. | Start user experience (desks and graphical user interface) project. | Q1 2022-23 | Complete | Q1 2022-23 | Project Mandate has been raised and project management team put in place.
1 | A1.3 Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system. This will allow Control Centre engineers make better and quicker decisions. | Scope requirements. | Q2 2022-23 | Complete | Q2 2022-23 | Due to begin scoping of Control Room Operator Console work in 2022
1 | A1.3 Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system. This will allow Control Centre engineers make better and quicker decisions. | Begin design work. | Q3 2022-23 | Complete | Q3 2022-23 | A number of user workshops and engagements have taken place which has allowed us to develop the initial Epics and Capabilities.
1 | A1.3 Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system. This will allow Control Centre engineers make better and quicker decisions. | Continue design work. | Q4 2022-23 | Complete | Q4 2022-23 | User stories completed and reference and vendor site visit completed allowing the team to build out the operator console strategy
1 | A1.3 Transform Network Control | D1.3.4 | Increased operational liaison with DNOs. | Engage DNOs to develop view of further information to support service coordination. This may include identifying services covered, granularity of information to be shared in both directions and timescales. | Q1-Q2 2021-22 | Complete | Q2 2021-22 | Initial discussions have been held with some DNOs in the area via ED2 and RDP discussions
1 | A1.3 Transform Network Control | D1.3.4 | Increased operational liaison with DNOs. | Learnings and new ways of working from RDPs incorporated into operational processes and ways of working. | N/A | Complete | Q4 2022-23 | Discussions have been held with DNOs in the role out of the RDP programmes - specifically in the current RDP programmes - MW despatch and GEMS.
1 | A1.3 Transform Network Control | D1.3.4 | Increased operational liaison with DNOs. | Engage DNOs to develop process to share further information to support service coordination. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Initial discussions have been held with some DNOs in the area via ED2 and RDP discussions
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Build data platform foundation. | Q1-Q4 2021-22 | Complete | Q1 2022-23 | First set of foundational platform design patterns have been built and verified by proof-of-concept in the cloud environment. Architectural documentation developed in conjunction with cloud and security teams as a prerequisite to commence sprint-based development of data services. Significant churn of contracted technical resources in the project team has hampered progress, with recruitment under way to backfill a number of key roles. Strategic partner has been onboarded, Discovery (design) phase complete and Build & Configure, phase scheduled to to complete during Q2 2022-23.
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Develop master data management strategy. | Q1-Q4 2021-22 | Complete | Q1 2022-23 | Completed, presentation slide(s) made available
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Phase 1 data management scoping complete for modelling and data management for Operability (Role 3, A15.6.1). | Q2 2021-22 | Complete | Q1 2022-23 | Scope of work, deliverables and priorities complete and agreed with the Operability Intelligence team. Report available
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Regular progress updates with the TAC. | N/A | Complete | Q4 2022-23 | Ongoing engagement, last presentation to TAC on 3rd Mar 2023.
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Continue building data platform foundation. | Q1-Q3 2022-23 | Complete | Q3 2022-23 | MVP Platform released into the Production environment. Final tests completed and DAP launched in December 2022
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Deliver machine learning for balancing and forecasting. | Q3 2022-23 | Complete | Q3 2022-23 | M/L capability available in DAP (Dev) environment. ML requirements for both Balancing (OBP) and Forecasting (PEF) currently under review and will be released and delivered on a use-case basis. AiCOE team developing additional use-cases from across the wider ESO business functions
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Integrate data platform with digital engagement platform | Q4 2022-23 | Complete | Q4 2022-23 | Agreed pilot data sets ingested onto DAP and DAP-connection to CKAN established. DEP connectivity to CKAN planned for Q1 2023-24
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Integrate data platform with single markets platform. | Q4 2022-23 | Complete | Q4 2022-23 | Connection to Salesforce established (Dev) and awaiting Production-connection approval. Backlog engagements inflight, to manage the downstream consumption of SMP data.
1 | A1.4 Control Centre Architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Explore opportunities for Data and Analytics Platform to support real-time operational data exchange in support of Regional Development Programmes. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Initial datasets (DNO Embedded Capacity Registers) ingested onto DAP. Ongoing engagement with RDP initiatives (including the Hartree Centre - STFC) to identify further data sources and consumption expectations
1 | A1.4 Control Centre Architecture | D1.4.2 | Creation of the ESO Technology Advisory Council (TAC), open to external stakeholders, who we will work with on the development of new balancing and control tools. | Regular meetings with the TAC (likely to be at least quarterly). | N/A | Complete | Q4 2022-23 | TAC continues to meet quarterly with the latest meeting in March 2023. There have been four meetings of the "control room of the future" subgroup. All material from the meetings is posted on the TAC section of the ESO website
1 | A17 Transparency and Open Data | D17.1 | Open data portal with limited data sets (initial go live 2019) | Data and analytics platform foundation development and testing. | Q1-Q2 2022-23 | Complete | Q3 2022-23 | MVP Platform released into the Production environment. Final tests completed and DAP launched in December 2022
1 | A17 Transparency and Open Data | D17.1 | Open data portal with limited data sets (initial go live 2019) | Data and analytics platform foundation implementation. | Q3 2022-23 | Complete | Q3 2022-23 | MVP Platform released into the Production environment. Final tests completed and DAP launched in December 2022
1 | A17 Transparency and Open Data | D17.1 | Open data portal with limited data sets (initial go live 2019) | Digital engagement platform development and testing. | Q1-Q3 2022-23 | Complete | Q3 2022-23 | User research has been ongoing since requirements and design and will continue to inform design and development throughout the lifetime of the DEP product. Development sprints have begun for MVP epics and features in advance of go live in Q4. On track to meet RIIO2 milestones.
1 | A17 Transparency and Open Data | D17.1 | Open data portal with limited data sets (initial go live 2019) | Digital engagement platform implementation. | Q4 2022-23 | Complete | Q4 2022-23 | DEP went live in Q4 FY23. The Foundational release includes the new ESO web platform, enhanced navigation, advanced search and new architecture and templates for balancing services content. This release will make ESO content more accessible and discoverable for a wide range of stakeholders. This release also lays the foundations for enhanced features including an ESO account dashboard, integrated query management and personalisation. These features will be prioritised according to customer value and released with a regular cadence starting in Q1 FY24.
1 | A17 Transparency and Open Data | D17.1 | Open data portal with limited data sets (initial go live 2019) | Digital engagement platform integration with data and analytics platform. | Q4 2022-23 | Complete | Q4 2022-23 | There are several elements to this deliverable. The DAP ingestion of data sets for publication on the CKAN data portal was delivered in Q4. This completed an initial integration providing a link from the ESO website (DEP) through to data sets hosted on DAP. The next step with DEP hosting the user interface and integrated across all ESO content and data across all ESO content and data search is on track for delivery in Q2 FY24. The final step will see all published data sets published on DEP and hosted on DAP in Q4 FY24. In parallel further enhancements to our data visualisation capability will be developed in this period.
1 | A17 Transparency and Open Data | D17.1 | Open data portal with limited data sets (initial go live 2019) | Digital engagement platform requirements and design. | Q2-Q4 2021-22 | Complete | Q4 2021-22 | Procurement event in event for main digital experience platform complete. Vendor appointed in Q1 2022-23, development to commence in Q2. Requirements and high level design documented as part of procurement process.
1 | A17 Transparency and Open Data | D17.1 | Open data portal with limited data sets (initial go live 2019) | Digital engagement platform development and testing. | Q1-Q3 2022-23 | Complete | Q3 2022-23 | User research has been ongoing since requirements and design and will continue to inform design and development throughout the lifetime of the DEP product. Development sprints have begun for MVP epics and features in advance of go live in Q4. As we are delivering through an agile methodology development and testing will continue until the delivery of the Q4 implementation milestone and then continuously thereafter.
1 | A17 Transparency and Open Data | D17.1 | Open data portal with limited data sets (initial go live 2019) | Digital engagement platform implementation. | Q4 2022-23 | Complete | Q4 2022-23 | DEP went live in Q4 FY23. The Foundational release includes the new ESO web platform, enhanced navigation, advanced search and new architecture and templates for balancing services content. This release makes ESO content more accessible and discoverable for a wide range of stakeholders. This release also lays the foundations for enhanced features including an ESO account dashboard, integrated query management and personalisation. These features will be prioritised according to customer value and released with a regular cadence starting in Q1 FY24.
1 | A17 Transparency and Open Data | D17.2 | All published ESO data in machine readable format. | All published ESO data in machine readable format. | Q2 2021-22 | Complete | Q2 2021-22 | All suitable datasets are now in machine readable format. We are now publishing over 80 datasets, many new datasets have been informed by engagement through the OTF. Digital Engagement Platform on track to commence procurement activities for new platform.
1 | A17 Transparency and Open Data | D17.2 | All published ESO data in machine readable format. | Further data sets released. | Q1-Q4 2022-23 | Complete | Q3 2021-22 | All suitable datasets are now in machine readable format. We are now publishing over 90 datasets, many new datasets have been informed by engagement through the OTF. Digital Engagement Platform on track to commence procurement activities for new platform.
1 | A17 Transparency and Open Data | D17.2 | All published ESO data in machine readable format. | Further data sets automated. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Further data sets have now been automated, but we are striving to automate as many data sets as possible as the amount of published data grows. this will be an ongoing action for the ODP.
1 | A17 Transparency and Open Data | D17.2 | All published ESO data in machine readable format. | Data and analytics platform foundation development and testing. | Q1-Q2 2022-23 | Complete | Q2 2022-23 | All suitable datasets are now in machine readable format. ESO are now publishing over ~100 datasets, many new datasets have been informed by engagement through the OTF. Digital Engagement Platform (DEP) on track to commence procurement activities for new platform. Work underway to populate DAP with existing datasets, to facilitate visibility and publication via the DEP.
1 | A17 Transparency and Open Data | D17.2 | All published ESO data in machine readable format. | Data and analytics platform foundation implementation. | Q3 2022-23 | Complete | Q3 2022-23 | D17.2: 'All published datasets will meet defined quality standards and we will provide powerful and logical search capabilities that make it faster and easier to navigate our data. All of our data will be available.' The above action is now complete on the ODP. WIP with the DAP team to deliver the MVP for DAP and continue to drive further automated and searchable data sets.
1 | A17 Transparency and Open Data | D17.2 | All published ESO data in machine readable format. | Digital engagement platform development and testing. | Q1-Q3 2022-23 | Complete | Q3 2022-23 | User research has been ongoing since requirements and design and will continue to inform design and development throughout the lifetime of the DEP product. Development sprints have begun for MVP epics and features in advance of go live in Q4. As we are delivering through an agile methodology development and testing will continue until the delivery of the Q4 implementation milestone and then continuously thereafter.
1 | A17 Transparency and Open Data | D17.2 | All published ESO data in machine readable format. | Digital engagement platform implementation. | Q4 2022-23 | Complete | Q4 2022-23 | DEP went live in Q4 FY23. The Foundational release includes the new ESO web platform, enhanced navigation, advanced search and new architecture and templates for balancing services content. This release makes ESO content more accessible and discoverable for a wide range of stakeholders. This release also lays the foundations for enhanced features including an ESO account dashboard, integrated query management and personalisation. These features will be prioritised according to customer value and released with a regular cadence starting in Q1 FY24.
1 | A17 Transparency and Open Data | D17.2 | All published ESO data in machine readable format. | Digital engagement platform integration with data and analytics platform. | Q4 2022-23 | Complete | Q4 2022-23 | There are several elements to this deliverable. The DAP ingestion of data sets for publication on the CKAN data portal was delivered in Q4. This completes an initial integration providing a link from the ESO website (DEP) through to data sets hosted on DAP. The next step with DEP hosting the user interface and advanced search is on track for delivery in Q2 FY24. The final step will see all published data sets published on DEP and hosted on DAP in Q4 FY24. In parallel further enhancements to our data visualisation capability will be developed in this period. Reporting status for overall milestone to be reported as on track.
1 | A17 Transparency and Open Data | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q1 2021-22 | Complete | Q1 2021-22 | Transparency Roadmap re-published on the 'Our Strategy' page of the ESO website during Q1. This identifies actions planned to increase transparency levels over the next year, and delivery against these actions is regularly monitored and tracked.
1 | A17 Transparency and Open Data | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q3 2021-22 | Complete | Q3 2021-22 | Transparency Roadmap re-published on the 'Our Strategy' page of the ESO website during Q3. This identifies actions planned to increase transparency levels over the next year, and delivery against these actions is regularly monitored and tracked.
1 | A17 Transparency and Open Data | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q1 2022-23 | Complete | Q1 2022-23 | Published 28/06 on 'our strategy page'
1 | A17 Transparency and Open Data | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q3 2022-23 | Complete | Q3 2022-23 | Published 19/01 on "Our Strategy" page
1 | A17 Transparency and Open Data | D17.4 | Transparency of operational decision making. | Engage stakeholders to review and refine scope and quality of information shared. Rolling delivery of improvements identified. | Q4 2021-22 | Complete | Q4 2021-22 | This is a regular topic of conversation at the Operational Transparency Forum with planned deep dives into actions where identified.
1 | A17 Transparency and Open Data | D17.4 | Transparency of operational decision making. | Engage stakeholders to review and refine scope and quality of information shared. Rolling delivery of improvements identified. | Q4 2022-23 | Complete | Q4 2022-23 | The Operational Transparency Forum aims to elevate conversations about the operational decisions made and provide additional transparency.
1 | A17 Transparency and Open Data | D17.5 | Trading transparency | Engage stakeholders (through the TAC and surveys at the Transparency Forums) to review and refine scope and quality of information shared. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | ESO completed a survey to determine what data industry wanted the ESO to publish. The Trading team has presented at the weekly operational transparency forum a number of times on all the new data sets and data transparency as a whole. The trading team has started engaging with industry this summer, in order to continuously improve on the published data sets. This year's survey was launched on 11/08/21. We have reviewed the responses and will present findings at the Operational Transparency Forum on 30/03/22.
1 | A17 Transparency and Open Data | D17.5 | Trading transparency | Rolling delivery of improvements identified, informed by stakeholder prioritisation and assessment of deliverability. | Q1-Q4 2021-22 | Complete | Q1 2022-23 | ESO completed a survey to determine what data industry wanted the ESO to publish. The Trading team has presented at the weekly operational transparency forum a number of times on all the new data sets and data transparency as a whole. The trading team has started engaging with industry this summer, in order to continuously improve on the published data sets. This year's survey was launched on 11/08/21. We have reviewed the responses and will present findings at the Operational Transparency Forum on 30/03/22.
1 | A17 Transparency and Open Data | D17.5 | Trading transparency | Engage stakeholders (through TAC?) to review and refine scope and quality of information shared. Rolling delivery of improvements identified. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | The Trading team has continued to present at the operational transparency forum a number of times on and data transparency as a whole. Market behaviour has changed a lot during this year, driven by the prices in various markets and we have shared updates to industry on our increased trading activity and the drivers behind this at the Operational Transparency Forum.
1 | A17 Transparency and Open Data | D17.6 | ESO Transparency Forum | Transparency Forum delivered regularly. | N/A | Complete | Q4 2022-23 | Weekly Operational Transparency Forums are ongoing to enhance industry insight of the operational decisions made by ESO. The questions raised, and feedback given at each forum informs subsequent agendas or deep dive areas.
1 | A2.1 Ongoing activities | D2.1.1 | Develop and drive control centre strategic resource planning, scheduling and training. | 0 | N/A | Complete | Q4 2022-23 | Continued activity as part of BAU. Internal training programme is delivering staff to ENCC. Continuing to recruit externally. Providing development opportunities to enhance knowledge and capability of existing staff.
1 | A2.1 Ongoing activities | D2.1.2 | Incident analysis and investigations of abnormal events, implementing improvements where needed. | 0 | N/A | Complete | Q4 2022-23 | ESO has been consistently reviewing significant incidents that had operational impacts or significant near-misses events/incidents. Where applicable mitigation actions and shared learnings been implemented. Please also refer to Regularly Reported Evidence 1I (Security of Supply)
1 | A2.1 Ongoing activities | D2.1.3 | Monitoring and reporting of system performance to regulatory bodies and ENTSO-E. Reporting to ENTSO-E will depend on the ESO’s future relationship with ENTSO-E | 0 | N/A | Complete | Q4 2022-23 | System Performance Reports published on the NGESO website. (https://www.nationalgrideso.com/industry-information/industry-data-and-reports/system-performance-reports) Published the annual C17 NETS Performance Report and Grid Code OC3, GC0105 and GC0151 monthly System Incidents. Annual report on operational security indicators (Article 15 - ICS). Annual report on load-frequency control (Article 16 - aLFC) and Clean Energy Package Article 13 - Re-dispatching annual report.
1 | A2.1 Ongoing activities | D2.1.4 | Guidance on operational policies for use in the control centre produced. | 0 | N/A | Complete | Q4 2022-23 | Control centre has the most accurate information readily available, is unambiguous and information are kept up to date.
1 | A2.2 Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Develop plan for engaging academia, including detail of the institutions to talk to, how we can work together, understanding the process for creating modules and the skillset for future power system operation. | Q1 2021-22 | Complete | Q2 2021-22 | The scoping and engagement with academia has been carried out and initially two universities have been chosen. We are collaborating with them on scoping ESO specific modules within their Power Engineering BSC & MSC courses. We will be offering a number of summer and 'sandwich' year placements to these universities for their students within the ESO in National Control and Networks. We have submitted a number of research projects to be considered and chosen by Brunel University.
1 | A2.2 Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Work with industry to define skillset for future power system operation. | Q2-4 2021-22 | Complete | Q4 2021-22 | The scoping and engagement with academia has been carried out and initially two universities have been chosen. We are collaborating with them on scoping ESO specific modules within their Power Engineering BSC & MSC courses. We will be offering a number of summer and 'sandwich' year placements to these universities for their students within the ESO in National Control and Networks. Five Industry Based projects have been accepted by Brunel University MSc Students and relationships are positive with Aston and Edinburgh as we move to establish Industry Placements with both Universities.
1 | A2.2 Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Work with institutions to develop new module(s), for delivery in September 2022. | Q3-Q4 2021-22 | Complete | Q4 2021-22 | The scoping and engagement with academia has been carried out and initially two universities have been chosen. We are collaborating with them on scoping ESO specific modules within their Power Engineering BSC & MSC courses. We will be offering a number of summer and 'sandwich' year placements to these universities for their students within the ESO in National Control and Networks. Five Industry Based projects have been accepted by Brunel University MSc Students and relationships are positive with Aston and Edinburgh as we move to establish Industry Placements with both Universities.
1 | A2.2 Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Work with institutions to develop new module(s), for delivery in September 2022. | Q1-Q2 2022-23 | Complete | Q1 2022-23 | ESO Power System Operational Managers have given detailed and relevant System Operation presentations to Brunel University to support the Power System Module, as well as hosting MSc students at Wokingham where they were given further presentations on other subjects such as Demand Forecasting, AI. The updated information was shared with their course director so that modules can be updated accordingly for current and future students.
1 | A2.2 Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Run new university modules | Q3 2022-23 | Complete | Q3 2022-23 | ESO Power System Operational Managers have given detailed and relevant System Operation presentations to Brunel University to support the Power System Module, as well as hosting MSc students at Wokingham where they were given further presentations on other subjects such as Demand Forecasting, AI. The updated information was shared with their course director so that modules can be updated accordingly for current and future students.
1 | A2.2 Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Run new university modules | Q4 2022-23 | Complete | Q4 2022-23 | The ESO have started to review course content to accurately represent the challenges and roles of System Operation with several Universities primarily in Power Engineering for BSC & MSC courses. We are offering a number placements to these universities for their students within the ESO in National Control and Networks.
1 | A2.2 Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry. | Develop plan for engaging with energy industry, including detail of the organisations to talk to, how we can work together. | Q2 2021-22 | Complete | Q2 2021-22
1 | A2.2 Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry. | Understand the requirements for cross-industry secondments including post-COVID-19 safeguards. | Q2 2021-22 | Complete | Q4 2022-23 | We are currently supporting secondments to CORESO, BESI and OFGEM. These are for a minimum of 12 months up to 36 months. We have discussed with some other Energy Industry players the possibility of secondments however they have not expressed an interest to progress with this currently. We would like to approach this subject again after the ESO has separated from National Grid.
1 | A2.2 Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry. | Work with industry to define skillset for future power system operation and understand potential opportunities for wider industry/whole system training in RIIO-2/ED2. | Q3-Q4 2021-22 | Complete | Q4 2021-22 | Initial scoping and idea proposals was delayed due to authorised resource availability and the impact of COVID-19 (due to time to recruit, train and authorise there is no quick fix). This has now started. The framework is now being created to approach a variety of industry members to consider what secondments could be offered, and to understand the benefits these secondments could bring. Initial list of DNO contacts is being created to explore the use of joint simulation training.
1 | A2.2 Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry. | Explore requirements with industry on possible training using enhanced ESO simulators. Engage DNOs on sharing data, what their interest is and how we can help each other. | Q1-Q4 2022-23 | Complete | Q3 2022-23 | Simulation training is rare amongst the DNOs. Future Design Team looking at DSO roles and sharing of knowledge and experience. Hosted successful visit from DNO (WPD) and NGV.
1 | A2.2 Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry. | Implement cross industry development initiatives for individuals (up to and including secondments where possible). | Q1 2022-23 | Complete | Q1 2022-23 | Initial scoping and idea proposals was delayed due to authorised resource availability and the impact of COVID-19 (due to time to recruit, train and authorise there is no quick fix). This has now started. The framework is now being created to approach a variety of industry members to consider what secondments could be offered, and to understand the benefits these secondments could bring. Initial list of DNO contacts is being created to explore the use of joint simulation training.
1 | A2.3 Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Develop plan to explore best practice training and simulation technology including understanding requirements for post-COVID-19 safeguards. | Q1 2021-22 | Complete | Q3 2021-22 | We have arranged to meet with other industry partners to explore their use of simulator training and share best practice amongst ourselves, to better inform future simulator development. Visits are planned for February and March 2022, but these are dependent on COVID restrictions in place at the time. It is not practical to look at other companies' simulators virtually.
1 | A2.3 Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Begin exploring best practice training and simulation technology. | Q2 2021-22 | Complete | Q2 2022-23 | We have held conversations with industry partners to explore their use of simulator training and share best practice amongst ourselves, to better inform future simulator development. Most DNOs do not have simulation as a training resource
1 | A2.3 Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Update existing simulators with scenario snapshots, continue exploring best practice training and simulation technology. | Q3 2021-22 | Complete | Q2 2021-22 | We have arranged to meet with other industry partners to explore their use of simulator training and share best practice amongst ourselves, to better inform future simulator development. Visits are planned for February and March 2022, but these are dependent on COVID restrictions in place at the time. It is not practical to look at other companies' simulators virtually.
1 | A2.3 Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Continue exploring best practice training and simulation technology. | Q4 2021-22 | Complete | Q4 2021-22 | We have arranged to meet with other industry partners to explore their use of simulator training and share best practice amongst ourselves, to better inform future simulator development. Visits are planned for February and March 2022, but these are dependent on COVID restrictions in place at the time. It is not practical to look at other companies' simulators virtually.
1 | A2.3 Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Continue exploring best practice training and simulation technology. | Q1 2022-23 | Complete | Q1 2022-23 | We have arranged to meet with other industry partners to explore their use of simulator training and share best practice amongst ourselves, to better inform future simulator development. Started to engage with wider industry with enhanced training and simulation, Arranged visits to WPD, SSE and EirGrid Trainining centres to understand their current and future training needs, systems and recruitment challenges.
1 | A2.3 Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Continue exploring best practice training and simulation technology. | Q2 2022-23 | Complete | Q2 2022-23 | External best practice training and simulation technology is being explored and development of new simulation systems under design
1 | A2.3 Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Update existing simulators with scenario snapshots, continue exploring best practice training and simulation technology. | Q3 2022-23 | Complete | Q3 2022-23 | Full system updated snapshot completed. Scenarios being developed continuously. Continuing to explore best practice via Network Control Project.
1 | A2.3 Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Continue exploring best practice training and simulation technology. | Q4 2022-23 | Complete | Q3 2022-23 | We hosted visit from WPD who were extremely enthusiastic and found the visit and use of our simulator fascinating, They have requested that we host further visits to continue to educate their control teams on the complexities of operating the GB system.
1 | A2.3 Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff. | Understand lessons learnt from Project TERRE E-learning trial including cost considerations and effectiveness of training delivery. | Q1 2021-22 | Complete | Q1 2021-22 | We are currently designing online training modules using animation to enhance the training programmes and to allow trainees to learn at their own pace.
1 | A2.3 Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff. | Identify and evaluate other opportunities to deploy E-learning and develop plan. | Q1 2021-22 | Complete | Q1 2021-22 | We are currently designing online training modules using animation to enhance the training programmes and to allow trainees to learn at their own pace.
1 | A2.3 Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff. | Develop and deploy of new E-learning modules as required. | Q2-4 2021-22 | Complete | Q4 2021-22 | First three modules have been created and external company engaged and working on new E Learning modules
1 | A2.3 Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff. | Use new video and e-learning training enhancements. | Q1-Q4 2022-23 | Complete | Q3 2022-23 | Training learning videos have been created and are being continually revised and updated to include current and future technology. These are available to the learners to support and enhance their learning.
1 | A2.3 Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff. | Incorporate use of new video and e-learning training enhancements into design of new academic modules, due to start in September 2022. | Q3-Q4 2022-23 | Complete | Q4 2022-23 | We now have a library of 12 videos which are available to trainees to support and enhance their training experience for operational roles within the ENCC. These are held in a central library and available to trainees in National Control, National Access Planning and included as part of the capability work for future Power System Engineer training.
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Evaluate Phase 1 and 2 of Rota management automation project implementation and operation with users | Q1-Q2 2021-22 | Complete | Q2 2021-22 | The project was successfully delivered and the ENCC are now working with an automated rota scheduling system and have the use of a mobile App on their phone to flexibly manage their shift requirements, holidays, training etc.
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Understand capabilities of underlying systems and understand opportunities for enhancement in Phase 3. | Q2 2021-22 | Complete | Q4 2022-23 | Phase 3 is currently being scoped with the provider to understand the capabilities and opportunities to enhance and improve our work processes
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Agree Phase 3 requirements. | Q3 2021-22 | Complete | Q4 2022-23 | Phase 3 requirements have been scoped with the provider and the initial design meetings are underway to look at our needs against the current and future capacity of the salesforce system.
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Define high-level scope for Phase 3 with IT provider. | Q4 2021-22 | Complete | Q4 2022-23 | Phase 3 requirements have been scoped with the provider and the initial design meetings are underway to look at our needs against the current and future capacity of the salesforce system.
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Start work on Phase 3 of Rota management automation project. | Q1 2022-23 | Complete | Q4 2022-23 | Phase 3 requirements have been scoped with the provider and the initial design meetings are underway to look at our needs against the current and future capacity of the salesforce system.
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Start work on document management (e.g. control centre policy) improvements project. | Q1 2022-23 | Complete | Q4 2022-23 | The chosen Vendor has had several major changes which have affected their ability to deliver the solution to ESO. These have included a company buyout, change in personnel and the decommissioning of software applications. Delays caused by the Vendor effecting the previous phases has caused Phase 3 to be delayed as they continue to work on the successful delivery of an automated system that meets National Controls requirements. Project has made some significant progress but not yet able to move to scoping of Phase 3. This is now planned for Q4 2022/3. Both the vendor and our IT support team are confident that this action will be completed before the end of BP1.
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Scope requirements for document management improvements. | Q2 2022-23 | Complete | Q4 2022-23 | The chosen Vendor has had several major changes which have affected their ability to deliver the solution to ESO. These have included a company buyout, change in personnel and the decommissioning of software applications. Delays caused by the Vendor effecting the previous phases has caused Phase 3 to be delayed as they continue to work on the successful delivery of an automated system that meets National Controls requirements. Project has made some significant progress but not yet able to move to scoping of Phase 3. This is now planned for Q3 -4 2022/3. Both the vendor and our IT support team are confident that this action will be completed before the end of BP1.
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Start design work for document management improvements. | Q3 2022-23 | Complete | Q4 2022-23 | Project has made some significant progress but not yet able to move to scoping of Phase 3. Awaiting successful delivery of Phase 1 and Phase 2.
1 | A2.4 Workforce and change management | D2.4.1 | Personalised updates and automated shift logins, allowing for learning and operational investments to made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Continue design work for document management improvements. | Q4 2022-23 | Complete | Q4 2022-23 | Project has made some significant progress but not yet able to move to scoping of Phase 3. Awaiting successful delivery of Phase 1 and Phase 2.
1 | A2.4 Workforce and change management | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | 0 | N/A | Complete | Q4 2022-23 | We are doing this for every new starter in the control room. Base Training plans have been annually reviewed and skills matrix created
1 | A3.1 Ongoing activities | D3.1.1 | Control Centre has fully tested skills, processes, plans and tools to support incident management and disaster recovery | Control Centre staff trained to fulfil their role under new licence condition imposed following publication of Restoration Standard. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | We train Control Centre staff for restoration on a regular basis, and will provide more specific training in relation to the new restoration standard.
1 | A3.1 Ongoing activities | D3.1.1 | Control Centre has fully tested skills, processes, plans and tools to support incident management and disaster recovery | Ongoing training of Control Centre staff to ensure all are aware of their roles under restoration. | Q1-Q4 2022-23 | Complete | Q3 2022-23 | We train Control Centre staff for restoration on a regular basis, and will provide more specific training in relation to the new restoration standard.
1 | A3.1 Ongoing activities | D3.1.2 | Restoration plans for GB with the necessary stakeholders, developed, maintained and validated. | Review and update of plans as required on individual review dates. 2021/22 Black Start Strategy and Procurement Methodology consulted and published. | Q1-Q4 2021-22 | Complete | Q1 2021-22 | We review our restoration plans regularly, this is triggered by a change in providers or the network.
1 | A3.1 Ongoing activities | D3.1.2 | Restoration plans for GB with the necessary stakeholders, developed, maintained and validated. | 2022/23 Black Start Strategy and Procurement Methodology consulted and published System Restoration Plan reviewed and consulted. | Q1-Q4 2022-23 | Complete | Q3 2022-23 | We review our restoration plans regularly, this is triggered by a change in providers or the network.
1 | A3.1 Ongoing activities | D3.1.3 | Engage and collaborate with industry to plan and develop the new GB restoration standard, including the annual assurance framework, consistent with our licence obligations | 0 | N/A | Complete | Q4 2022-23 | A Grid Code working group (GC0156) has now been set up to progress code modifications needed for ESRS Implementation. Progress is being made to update all other relevant regulatory framework. This activity remains ongoing.
1 | A3.1 Ongoing activities | D3.1.4 | Advice and oversight of Black Start and restoration strategy for the future provided. | 0 | N/A | Complete | Q4 2022-23 | The new ESR Assurance Framework for 22/23 is with Ofgem for approval. Draft Assurance Framework for 23/24 is also with Ofgem for review. This activity is an annual requirement
1 | A3.1 Ongoing activities | D3.1.5 | Fully competitive Black Start procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | Deliver competitively tendered Black Start contracts from the South West / Midlands and Northern tenders. | Q1-Q2 2021-22 | Complete | Q2 2021-22 | We have completed the South West and Midlands, and Northern tenders. The service commencement dates are aligned with the published timelines. We will launch the South East tender during 2022-23 rather than 2021-22. We believe that this is the most economic and efficient solution, given the delays to the approval of the restoration standard, and other expected new entrants not being available in the expected timescales and therefore reducing liquidity. This will also allow us to integrate the learnings from the Distributed Restart project.
1 | A3.1 Ongoing activities | D3.1.5 | Fully competitive Black Start procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | Carry out preparatory work for future tender opportunities in South East, in preparation for future tender event. | Q1-Q2 2021-22 | Complete | Q4 2021-22 | We have completed the South West and Midlands, and Northern tenders. The service commencement dates are aligned with the published timelines. We will launch the South East tender during 2022-23 rather than 2021-22. We believe that this is the most economic and efficient solution, given the delays to the approval of the restoration standard, and other expected new entrants not being available in the expected timescales and therefore reducing liquidity. This will also allow us to integrate the learnings from the Distributed Restart project.
1 | A3.1 Ongoing activities | D3.1.5 | Fully competitive Black Start procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | Deliver competitively tendered Black Start contracts from the South East tenders. | Q1-Q2 2022-23 | Complete | Q2 2022-23 | We have completed the South West and Midlands, and Northern tenders. The service commencement dates are aligned with the published timelines. The South East tender was launched in June 2022 rather than 2021-22. We believe that this is the most economic and efficient solution, given the delays to the approval of the restoration standard, and other expected new entrants not being available in the expected timescales and therefore reducing liquidity. We have launched three Restoration Tenders in 2022 (all live and progressing at the moment but at different stages) – South East, Northern (including the North West, North East and Scotland zones) and Wind tenders. The South East and Northern Tenders already allow the participation of Distributed Restart type projects.
1 | A3.1 Ongoing activities | D3.1.5 | Fully competitive Black Start procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | Contract award and service commences. | Q3 2022-23 | Complete | Q3 2022-23 | We have completed the South West and Midlands, and Northern tenders. The service commencement dates are aligned with the published timelines. The South East tender was launched in June 2022 rather than 2021-22. We believe that this is the most economic and efficient solution, given the delays to the approval of the restoration standard, and other expected new entrants not being available in the expected timescales and therefore reducing liquidity. We have launched three Restoration Tenders in 2022 (all live and progressing at the moment but at different stages) – South East, Northern (including the North West, North East and Scotland zones) and Wind tenders. The South East and Northern Tenders already allow the participation of Distributed Restart type projects.
1 | A3.2 Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance process for GB Black Start. [These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement] | Restoration Standard in ESO’s licence conditions. | Q1 2021-22 | Complete | Q3 2021-22 | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard in Q3: https://www.nationalgrideso.com/uk/electricity-transmission/industry-information/balancing-services/electricity-system-restoration-standard We also consulted on the Assurance Framework in Q3: https://www.nationalgrideso.com/document/221926/download
1 | A3.2 Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance process for GB Black Start. [These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement] | External plan for licence implementation consulted on | Q2 2021-22 | Complete | Q3 2021-22 | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard in Q3: https://www.nationalgrideso.com/uk/electricity-transmission/industry-information/balancing-services/electricity-system-restoration-standard We also consulted on the Assurance Framework in Q3: https://www.nationalgrideso.com/document/221926/download
1 | A3.2 Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance process for GB Black Start. [These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement] | Publication of Assurance Framework for consultation. | Q4 2021-22 | Complete | Q3 2021-22 | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard in Q3: https://www.nationalgrideso.com/uk/electricity-transmission/industry-information/balancing-services/electricity-system-restoration-standard We also consulted on the Assurance Framework in Q3: https://www.nationalgrideso.com/document/221926/download
1 | A3.2 Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance process for GB Black Start. [These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement] | Continue implementing GB restoration standard licence conditions. | Q2-4 2021-22 | Delayed - External Reasons |  | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard in Q3: https://www.nationalgrideso.com/uk/electricity-transmission/industry-information/balancing-services/electricity-system-restoration-standard We also consulted on the Assurance Framework in Q3: https://www.nationalgrideso.com/document/221926/download A Grid Code working group (GC0156) has now been set up to progress code modifications needed for ESRS Implementation,
1 | A3.2 Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance process for GB Black Start. [These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement] | Restoration Standard in place. | Q1 2022-23 | Complete | Q3 2021-22 | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard in Q3: https://www.nationalgrideso.com/uk/electricity-transmission/industry-information/balancing-services/electricity-system-restoration-standard We also consulted on the Assurance Framework in Q3: https://www.nationalgrideso.com/document/221926/download
1 | A3.2 Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance process for GB Black Start. [These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement] | Complete annual assurance framework data collection and validation - use outputs to recommend improvements. | Q2 2022-23 | Complete | Q2 2022-23 | Assurance Framework for 2022/23 submitted to Ofgem and awaiting approval.
1 | A3.2 Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance process for GB Black Start. [These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement] | Implement improvements. | Q3 2022-23 | Complete | Q2 2021-22 | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard in Q3: https://www.nationalgrideso.com/uk/electricity-transmission/industry-information/balancing-services/electricity-system-restoration-standard We also consulted on the Assurance Framework in Q3: https://www.nationalgrideso.com/document/221926/download
1 | A3.2 Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. [These timescales are based on the GB standard go-live in April 2021, with ESO having 12 months to implement]. | Produce statement of restoration timescales. | Q1 2021-22 | Complete | Q2 2021-22 | Ofgem shared its final decision in August 2021 and Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard has been in place since October 2021.
1 | A3.2 Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. [These timescales are based on the GB standard go-live in April 2021, with ESO having 12 months to implement]. | Implementation of restoration standard (in line with D3.2.1). | Q2 2021-22 | Delayed - External Reasons | Q1 2022-23 | Ofgem shared its final decision in August 2021 and Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard has been in place since October 2021.
1 | A3.2 Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. [These timescales are based on the GB standard go-live in April 2021, with ESO having 12 months to implement]. | Restoration standard in place (12 months after licence condition). | Q3 2021-22 | Complete | Q3 2021-22 | Ofgem shared its final decision in August 2021 and Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard has been in place since October 2021.
1 | A3.2 Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. [These timescales are based on the GB standard go-live in April 2021, with ESO having 12 months to implement]. | Continue implementing GB restoration standard licence conditions. | Q1-Q2 2022-23 | Complete | Q2 2022-23 | Ofgem shared its final decision in August 2021 and Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard has been in place since October 2021.
1 | A3.2 Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. [These timescales are based on the GB standard go-live in April 2021, with ESO having 12 months to implement]. | Restoration standard in place (12 months after licence condition). | Q1 2022-23 | Complete | Q3 2021-22 | Ofgem shared its final decision in August 2021 and Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard has been in place since October 2021.
1 | A3.2 Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. [These timescales are based on the GB standard go-live in April 2021, with ESO having 12 months to implement]. | Begin validation of restoration timelines using output from first annual assurance process (D3.2.1). | Q3 2022-23 | Complete | Q3 2022-23 | Ofgem shared its final decision in August 2021 and Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard has been in place since October 2021.
1 | A3.2 Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for Black Start capability provision. These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement. | Restoration Standard in ESO’s licence conditions. | Q1 2021-22 | Complete | Q1 2021-22 | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard and Assurance Framework in Q3.
1 | A3.2 Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for Black Start capability provision. These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement. | External plan for licence implementation shared and consulted. | Q2 2021-22 | Complete | Q2 2021-22 | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard and Assurance Framework in Q3.
1 | A3.2 Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for Black Start capability provision. These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement. | Continue implementation of GB Restoration standard through code and or contractual means | Q3-Q4 2021-22 | Delayed - External Reasons |  | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard and Assurance Framework in Q3.
1 | A3.2 Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for Black Start capability provision. These timescales are based on the GB standard go-live in April 2021, with ESO have 12 months to implement. | Continue to implement GB Restoration Standard Licence conditions to meet new obligations | Q1-Q2 2022-23 | Delayed - External Reasons |  | Ofgem shared its final decision in August 2021, and the Secretary of State directed the ESO to implement the new Restoration Standard in October 2021. The ESO will now need to comply with the standard by no later than 31 December 2026. Following discussions with BEIS and Ofgem, all associated changes (codes, markets, assurance frameworks etc) should now be in place by no later than September 2023. Restoration standard included in ESO's licence on 19 October 2021. We consulted on the Restoration Standard and Assurance Framework in Q3.
1 | A3.2 Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations. | Develop high level scope and requirements. | Q3 2021-22 | Complete | Q1 2022-23 | High level scope and requirements identified.
1 | A3.2 Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations. | Restoration decision support tool project start up. | Q4 2021-22 | Complete | Q4 2021-22 | We have started developing the high level scope and requirements for the decision making support tool. This was delayed to allow for stakeholder engagement in development of scope and requirements.
1 | A3.2 Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations. | Finalise restoration decision support tool project start up. - Engage with TAC on project requirements. | Q1 2022-23 | Complete | Q1 2022-23 | We have started developing the high level scope and requirements for the decision making support tool. Extensive Internal engagement on Restoration Decision Support tool with IT delivery team.
1 | A3.2 Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations. | Scope requirements | Q2 2022-23 | Complete | Q4 2022-23 | We have developed high level scope and requirements for the Restoration Decision Support Tool.
1 | A3.2 Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations. | Engage with design authority on design. Commence design work. | Q3 2022-23 | Delayed - Internal Reasons |  | We are at the RFI stage, once a suitable vendor is identified product design will commence, and a prototype will be shared with DA if applicable.
1 | A3.2 Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations. | Commence development work on restoration decision support tool. | Q4 2022-23 | Complete | Q4 2022-23 | We have started developing the high level scope and requirements for the decision making support tool with the IT team for implementation.
1 | A3.3 Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types. Innovation project in restoration will establish a proof of concept for the provision of black start services from Distribute Energy Resources (DER). | Project progress report. | Q1 2021-22 | Complete | Q1 2021-22 | Project progress report published on schedule
1 | A3.3 Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types. Innovation project in restoration will establish a proof of concept for the provision of black start services from Distribute Energy Resources (DER). | implement 2 or 3 proof of concept case studies to confirm feasibility and cost. | Q2 2021-22 | Complete | Q2 2021-22 | PET Workstream members from SPEN & TNEI worked together to research the feasibility of several potential trial sites across the SDP and SP Manweb DNO areas, and eventually settled on three sites, all in the SPD Southern Scotland area - Galloway, Chapelcross & Redhouse. See the Demonstration of Black-Start from DER deliverable for the lates commentary
1 | A3.3 Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types. Innovation project in restoration will establish a proof of concept for the provision of black start services from Distribute Energy Resources (DER). | Refined organisation, systems and telecoms requirements. | Q2 2021-22 | Complete | Q2 2021-22 | Report delivered as per schedule and published on external website
1 | A3.3 Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types. Innovation project in restoration will establish a proof of concept for the provision of black start services from Distribute Energy Resources (DER). | Demonstration of Black Start for DER. | Q3 2021-22 | Complete | Q2 2022-23 | Project end date extended to 31st December 2022 to allow completion of the minimum two case study trials and provide sufficient time for inclusion of the Distributed Restart project final proposals and functional designs report, this milestone is on track to complete before project end. All Participation Agreements now in place Successful live trials in Galloway took place in Oct 2021 (Phases 1 & 2), and April (Phase 3) concluded by Thursday 21st April 2022). These trials were extremely successful and will be publicised for the benefit of industry & consumers The Redhouse case study trial (proof of concept from new technology (grid-forming battery)) is being rescheduled to June 2023 due to delayed (6 months) network protection equipment The Project Team and Steerco Committee have agreed an extension of the PMO (funding & Legal support) and PET functions of the project, to September 2023. Project lead will be submitting a Material Change Request to Ofgem, once they have the confirmed Test plan from our SPEN partner The Chapelcross case study trial took place w/c 20th June 2022. The trial was fully successful in achieving all it's objectives and we will be releasing a press release within the coming weeks. We have now met Ofgem Deliverable 6, but we looking at how we can add the Redhouse BESS trial in the Spring to this key deliverable, with Ofgem's support.
1 | A3.3 Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types. Innovation project in restoration will establish a proof of concept for the provision of black start services from Distribute Energy Resources (DER). | Final version of generic procurement terms. | Q3 2021-22 | Complete | Q3 2021-22 | Report delivered as per schedule and published on external website
1 | A3.3 Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types. Innovation project in restoration will establish a proof of concept for the provision of black start services from Distribute Energy Resources (DER). | Project progress report. | Q3 2021-22 | Complete | Q3 2021-22 | Report delivered as per schedule and published on external website
1 | A3.3 Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types. Innovation project in restoration will establish a proof of concept for the provision of black start services from Distribute Energy Resources (DER). | Final proposals for functional and testing requirements. | Q1 2022-23 | Complete | Q3 2022-23 | The Final Findings and Proposals for Electricity System Restoration from DERs report (Ofgem deliverable #10) has now been published on our Website. The reason for the delay was that we needed to complete the minimum two live Trials at Galloway & Chapelcross (see Ofgem Deliverable #6) and have the subsequent PET Part 2 report findings available for insertion into this Final Findings report.
1 | A3.3 Innovation project in restoration | D3.3.2 | (Subject to project findings) Proof of concept findings implemented and new system and communication methods implemented | Assess learning from innovation project, working with stakeholders across the industry. | Q1-Q2 2022-23 | Complete | Q4 2022-23 | Working with Electricity System Restoration Standard implementation team to integrate project findings into BAU, in conjunction with industry working groups. E.g. Development of industry codes, resilient telecoms, and development of new markets. Final Closedown report due by 31st January 2023
1 | A3.3 Innovation project in restoration | D3.3.2 | (Subject to project findings) Proof of concept findings implemented and new system and communication methods implemented | Engage with industry on productionisation. | Q3 2022-23 | Complete | Q1 2022-23 | Distributed Restart will not be 'Productised' as the BAU Contracts currently under way in the SE Tender process will include Distributed Generation options for DER's wishing to participate in a bottom-up restoration service.
1 | A3.3 Innovation project in restoration | D3.3.2 | (Subject to project findings) Proof of concept findings implemented and new system and communication methods implemented | Produce roadmap for productionisation. | Q4 2022-23 | Complete | Q1 2022-23 | Distributed Restart will not be 'Productised' as the BAU Contracts currently under way in the SE Tender process will include Distributed Generation options for DER's wishing to participate in a bottom-up restoration service.
2 | A4.1 Manage existing balancing services markets | D4.1 | Balancing and ancillary services efficiently procured to deliver security of supply at optimal cost | N/A | N/A | Complete | Q3 2022-23 | Please refer to our Metrics and Regularly Reported Evidence
2 | A4.2 Power Responsive | D4.2.1 | Regular and specific metrics and publications across Distribution System Operator (DSO) development and co-development of local flexibility markets through a variety of innovation projects | N/A | N/A | Complete | Q4 2022-23 | We have now awarded contract to successful vender Piclo (Open Utility Ltd) while relationship management continues with those unsuccessful. Work has started on Service Delivery Kick-off and planning meetings completed to set up workstreams. Control Room usability deep dive sessions completed and service day timings now optimised to best suit ENCC/Trading needs. Plans for Training, stakeholder update and activation all moving forward and service design update is nearing completion and stakeholders will be updated shortly.
2 | A4.2 Power Responsive | D4.2.2 | Regular and specific metrics, and publications for multi sector approaches focusing on opportunities for household, community energy, small business participation, zero carbon technologies, and electrification of heat in Demand Side Flexibility (DSF). | N/A | N/A | Complete | Q4 2022-23 | Power Responsive have updated their internal Strategy with a view to align current projects we are managing and with the future of PR’s key goals in mind. We are also looking at the steering group members to refresh those involved and add any key stakeholders missing. We are working on the PR Annual Report which this year will incorporate a forward look as to what we are working on, this will be released in May 2023. Power responsive is facilitating its SteerCo but also running sub working groups to focus on specifics. Currently our Operational Metering Working group is working with various 3rd parties to run trials on breaking down barriers of entry for domestic assets & DSR, looking at innovative ways to get EV’s into the BM, which is exciting. We are also running an investigation into MIR and the potential impact on future flex. Our Power Responsive lead has agreed to sit on the Flex Assure advisory board and we are looking to do a review into non domestic DSR’s involvement in the future and potential innovative opportunities. That will lead on to a further sub working group focused on the Industrial and commercial’s concerns and how we can aid their growth post triad. We are also focused on engagement, hosting regular meetings with BEIS, The ADE and all other key stakeholders, while facilitating regular steering groups, sub groups, attending and hosting events like EMEX and others to ensure we are really promoting the work going on behind the scenes. We have also started a Cost Benefit analysis on back up diesel generators being retrofitted with catalytic converters to try and bring that back in to operability for DSR.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.2 | Day ahead market for frequency response. | Day ahead market for frequency response operational. | Q1 2021-22 | Complete | Q3 2020-21 | We launched Dynamic Containment (DC) in October 2020 and introduced day-ahead procurement, bringing us ahead of schedule in our RIIO-2 procurement deliverables. In September 2021 we launched DC low frequency on the EPEX auction platform, to introduce more granular, automated procurement. This is the same platform that hosted the weekly frequency response auction trial. The Auction Trial ended on 26 November 2021 and we will use the tools and services available to us to secure our frequency requirements whilst we transition to the new suite of response and reserve products. We are reviewing how providers transition into the new response and reserve products and welcome engagement and discussion from existing providers. We will be taking a stepped approach in phasing out the monthly FFR tender as first we will need to embed the new response services (DM and DR). We will start to transition away from the monthly FFR volumes when the new services Dynamic Moderation (DM) and Dynamic Regulation (DR) are embedded. We are working towards introducing these services in spring 2022.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.2 | Day ahead market for frequency response. | Day ahead response market integrated with foundational market platform (the foundational market platform comprises the automation of a subset of key processes, allowing users to set own parameters) | Q1 2021-22 | Complete | Q4 2021-22 | We launched Dynamic Containment (DC) in October 2020 and introduced day-ahead procurement, bringing us ahead of schedule in our RIIO-2 procurement deliverables. In September 2021 we launched DC low frequency on the EPEX auction platform, to introduce more granular, automated procurement. This is the same platform that hosted the weekly frequency response auction trial. The Auction Trial ended on 26 November 2021 and we will use the tools and services available to us to secure our frequency requirements whilst we transition to the new suite of response and reserve products. We are reviewing how providers transition into the new response and reserve products and welcome engagement and discussion from existing providers. We will be taking a stepped approach in phasing out the monthly FFR tender as first we will need to embed the new response services (DM and DR). We will start to transition away from the monthly FFR volumes when the new services Dynamic Moderation (DM) and Dynamic Regulation (DR) are embedded. We are working towards introducing these services in spring 2022.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.2 | Day ahead market for frequency response. | End of auction trial. | Q3 2021-22 | Complete | Q3 2021-22 | The Auction Trial ended on 26 November 2021 and we will use the tools and services available to us to secure our frequency requirements whilst we transition to the new suite of response and reserve products.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.2 | Day ahead market for frequency response. | Phase out monthly tenders for Firm Frequency Response (FFR). | Q4 2021-22 | Delayed - Internal Reasons |  | This milestone is delayed because we will not fully cease procuring the dynamic FFR service by the end of March 2023. We have steps in place to begin offsetting DFFR, however this will be a steady process, and we expect to continue to procure dynamic FFR into FY2023-24. Specific IT upgrades need to be in place before volume caps are lifted. Access to subject matter experts is currently limited, due to winter activities, and this is impacting our IT development timeframes, which in turn may affect when we can lift the volume caps on DM and DR. It is possible through the continuation of the winter activities work, and with the potential for additional issues to arise over the period, there may be further impacts to BP1 activities with subsequent prioritisation decisions made. Any decision will go through the prioritisation framework in the 2021-23 18-Month Review document, published on 25 October this year. We will provide updates on progress made regarding offsetting dynamic FFR, and volume cap removal in our monthly Market Information Reports, including further details of our expected volume requirements for FFR, DC, DR and DM. These reports can be found on the ESO Data Portal.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.3 | New Reserve Products Development and introduction of a new suite of products to provide reserve to the control room | Control and dispatch solutions for reserve. | Q2 2021-22 | Delayed - Internal Reasons |  | - Winter Operability has impacted the January 2023 delivery for Quick and Slow Reserve. The delivery plan dates of each service have been redrawn as a result. The plan is to deliver Firm/ Optional BM/ NBM Quick Reserve in 'Oct '23 and Slow reserve in Nov '23. - Key dependencies include EAC delivering in Sept '23 and Balancing transformation (IT) providing the changes required for multi-despatch functionality as well as BM/ ASDP changes to include the new services. - Consultation documentation commencing; Begun engagement with Ofgem and exploring where we need to seek derogations.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.3 | New Reserve Products Development and introduction of a new suite of products to provide reserve to the control room | Standard contract terms for reserve. | Q3 2021-22 | Delayed - Internal Reasons |  | - Winter Operability has impacted the January 2023 delivery for Quick and Slow Reserve. The delivery plan dates of each service have been redrawn as a result. The plan is to deliver Firm/ Optional BM/ NBM Quick Reserve in 'Oct '23 and Slow reserve in Nov '23. - Key dependencies include EAC delivering in Sept '23 and Balancing transformation (IT) providing the changes required for multi-despatch functionality as well as BM/ ASDP changes to include the new services. - Consultation documentation commencing; Begun engagement with Ofgem and exploring where we need to seek derogations”.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.3 | New Reserve Products Development and introduction of a new suite of products to provide reserve to the control room | New reserve products go live. | Q4 2021-22 | Delayed - Consumer Benefits |  | - Winter Operability has impacted the January 2023 delivery for Quick and Slow Reserve. The delivery plan dates of each service have been redrawn as a result. The plan is to deliver Firm/ Optional BM/ NBM Quick Reserve in 'Oct '23 and Slow reserve in Nov '23. - Key dependencies include EAC delivering in Sept '23 and Balancing transformation (IT) providing the changes required for multi-despatch functionality as well as BM/ ASDP changes to include the new services. - Consultation documentation commencing; Begun engagement with Ofgem and exploring where we need to seek derogations.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.4 | Full co-optimised auction for Response and Reserve at day ahead or even closer to real time | Single day ahead response and reserve market go live. | Q4 2022-23 | Delayed - Internal Reasons |  | We have gone live with interim capability to provide day ahead markets for both STOR and DC/DR/DM. In early 2023 ESO have run a number of industry webinars sharing our detailed market design work as well as publishing additional educational material in March on aspects such as co-optimisation. We are hoping to shortly publish the EBGL consultation and look forward to seeking feedback during this period from the market. We are still working to plan to be able to launch EAC in the autumn/winter of 2023 and will continue to engage with industry to co create the capabilities of a co-optimised marketplace.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.5 | Auction capability | Auction capability development and testing | Q1-Q3 2021-22 | Delayed - Internal Reasons | Q3 2021-22 | We have gone live with interim capability to provide day ahead markets for both STOR and DC/DR/DM. In early 2023 ESO have run a number of industry webinars sharing our detailed market design work as well as publishing additional educational material in March on aspects such as co-optimisation. We are hoping to shortly publish the EBGL consultation and look forward to seeking feedback during this period from the market. We are still working to plan to be able to launch EAC in the autumn/winter of 2023 and will continue to engage with industry to co create the capabilities of a co-optimised marketplace.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.5 | Auction capability | Auction capability implementation. | Q4 2021-22 | Delayed - Internal Reasons |  | We have gone live with interim capability to provide day ahead markets for both STOR and DC/DR/DM. In early 2023 ESO have run a number of industry webinars sharing our detailed market design work as well as publishing additional educational material in March on aspects such as co-optimisation. We are hoping to shortly publish the EBGL consultation and look forward to seeking feedback during this period from the market. We are still working to plan to be able to launch EAC in the autumn/winter of 2023 and will continue to engage with industry to co create the capabilities of a co-optimised marketplace.
2 | A4.3 Deliver a single day-ahead response and reserve market | D4.3.5 | Auction capability | Electricity Market Reform (EMR) and Contracts for Difference (CfD) integration. | Q4 2022-23 | Milestone no longer valid |  | We have implemented learnings from the weekly FFR innovation project and introduced day ahead procurement via auctions for both STOR and DC. This is delivered through the salesforce (STOR) and EPEX (DC) platforms. Once DM and DR are introduced to the market later this year they will also be procured through the current EPEX auction platform until we have concluded all of the development/implementation work on the enduring auction system. ESO concluded our procurement event in August 22 and were in a position to share the outcome with industry in Sept 22. We have held our first kick off workshop with our new partners and now move into the design and delivery phase. We anticipate being able to share more information with industry as we onboard our new supplier and shape the projects plans. We are unsure if a single day ahead response and reserve market is the correct answer. These may need to be separate markets depending on auction tender exercise, and further thinking around what the new products look like and how they can interact from an operational perspective.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.1 (shared with D5.2) | A market platform through which market participants will be able to participate in balancing and capacity markets. The markets platform will cover the end to end process for market participation including: communications, data input and management, messaging and validation | Day Ahead response market integrated with foundational market platform for subset of processes. | Q1 2021-22 | Complete | Q1 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email We have also marked the "Asset register requirements and design" as complete, as the foundational delivery meets the ambition to be able to integrate with EMR if required in the future.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.1 (shared with D5.2) | A market platform through which market participants will be able to participate in balancing and capacity markets. The markets platform will cover the end to end process for market participation including: communications, data input and management, messaging and validation | Single markets platform requirements and design | Q4 2021-22 | Complete | Q4 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email We have also marked the "Asset register requirements and design" as complete, as the foundational delivery meets the ambition to be able to integrate with EMR if required in the future
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.1 (shared with D5.2) | A market platform through which market participants will be able to participate in balancing and capacity markets. The markets platform will cover the end to end process for market participation including: communications, data input and management, messaging and validation | Reserve products integrated with foundational market platform for subset of processes. | Q4 2021-22 | Complete | Q4 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. Data tables within the first successful release for SMP include those items that will be needed for new Reserve products into the future. As new Reserve products are developed these will be hosted on SMP. In the meantime the DA STOR market is managed through an alternate solution on Salesforce that is providing critical learning for SMP development. Additional functionality and more balancing services will then be released in stages in subsequent releases.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.1 (shared with D5.2) | A market platform through which market participants will be able to participate in balancing and capacity markets. The markets platform will cover the end to end process for market participation including: communications, data input and management, messaging and validation | Asset register requirements and design. | Q3 2021-22 | Complete | Q3 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email We have also marked the "Asset register requirements and design" as complete, as the foundational delivery meets the ambition to be able to integrate with EMR if required in the future
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.1 (shared with D5.2) | A market platform through which market participants will be able to participate in balancing and capacity markets. The markets platform will cover the end to end process for market participation including: communications, data input and management, messaging and validation | Asset register development and testing. | Q4 2021-22 | Complete | Q4 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email We have also marked the "Asset development and testing" as complete, as the foundational delivery meets the ambition to be able to integrate with EMR if required in the future
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.1 (shared with D5.2) | A market platform through which market participants will be able to participate in balancing and capacity markets. The markets platform will cover the end to end process for market participation including: communications, data input and management, messaging and validation | Single markets Platform Development and testing. | Q3 2022-23 | Complete | Q3 2022-23 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. As at 16 December 2022 we have delivered a total of 7 releases during the calendar year. This has progressively delivered functionality to improve the users experience, include more services and respond to prioritised tactical services (such as Demand Flexibility Service and Balancing Reserve). SMP has a strong backlog of work to deliver across the rest of RIIO-2 Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email We have also marked the "Asset register requirements and design" as complete, as the foundational delivery meets the ambition to be able to integrate with EMR if required in the future
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.1 (shared with D5.2) | A market platform through which market participants will be able to participate in balancing and capacity markets. The markets platform will cover the end to end process for market participation including: communications, data input and management, messaging and validation | Procurement of all ESO balancing and ancillary services through single markets platform for full range of processes | Q4 2022-23 | Delayed - External Reasons |  | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. SMP first went live in February 2022 to support the onboarding process for new and enduring frequency response products. Since then a further 7 releases have taken place and we have actively developed a backlog of functionality that has been co-created and prioritised with our users. Based on the backlog of requirements it is now expected that the procurement of all appropriate balancing services through SMP will extend into BP2 timescales. This will ensure that we are able to focus on the development of value adding functionality for new and existing Day Ahead markets over simply integrating all services. Our plan for BP2 is already well structured and is being communicated with our stakeholders.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.1 (shared with D5.2) | A market platform through which market participants will be able to participate in balancing and capacity markets. The markets platform will cover the end to end process for market participation including: communications, data input and management, messaging and validation | Asset register implementation | Q1 2022-23 | Complete | Q4 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. The foundational delivery can be shared and can be expected to be interoperable with DSO / Flexibility Markets as they are developed in the future within the Open Networks and ED2 outputs NGESO is working with the DNOs on the Open Networks Project including on primacy rules and trials for interaction between ESO and DSO / Flexibility products in the future. NGESO has also provided feedback on ED2 proposals and stand ready to support the DNOs in the development of the industry platforms and share how we are developing the Single Markets Platform. Whilst functionality has been designed with future needs in mind, more certainty is needed on what markets will exist and how they will interact to facilitate detailed discussions into the alignment of platforms.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Day Ahead response market integrated with foundational market platform for subset of processes | Q1 2021-22 | Complete | Q1 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email" We have also marked the "Asset register requirements and design" as complete as the foundational delivery can be shared and can be expected to be interoperable with DSO / Flexibility Markets as they are developed in the future within the Open Networks and ED2 outputs NGESO is working with the DNOs on the Open Networks Project including on primacy rules and trials for interaction between ESO and DSO / Flexibility products in the future. NGESO has also provided feedback on ED2 proposals and stand ready to support the DNOs in the development of the industry platforms and share how we are developing the Single Markets Platform. Whilst functionality has been designed with future needs in mind, more certainty is needed on what markets will exist and how they will interact to facilitate detailed discussions into the alignment of platforms.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Provide input into RIIO-ED2 business plans to promote alignment of ESO and DSO markets and platforms. | Q3 2021-22 | Complete | Q3 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email" We have also marked the "Asset register requirements and design" as complete as the foundational delivery can be shared and can be expected to be interoperable with DSO / Flexibility Markets as they are developed in the future within the Open Networks and ED2 outputs NGESO is working with the DNOs on the Open Networks Project including on primacy rules and trials for interaction between ESO and DSO / Flexibility products in the future. NGESO has also provided feedback on ED2 proposals and stand ready to support the DNOs in the development of the industry platforms and share how we are developing the Single Markets Platform. Whilst functionality has been designed with future needs in mind, more certainty is needed on what markets will exist and how they will interact to facilitate detailed discussions into the alignment of platforms.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Single markets platform requirements and design. | Q4 2021-22 | Complete | Q4 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. The foundational delivery can be shared and can be expected to be interoperable with DSO / Flexibility Markets as they are developed in the future within the Open Networks and ED2 outputs NGESO is working with the DNOs on the Open Networks Project including on primacy rules and trials for interaction between ESO and DSO / Flexibility products in the future. NGESO has also provided feedback on ED2 proposals and stand ready to support the DNOs in the development of the industry platforms and share how we are developing the Single Markets Platform. Whilst functionality has been designed with future needs in mind, more certainty is needed on what markets will exist and how they will interact to facilitate detailed discussions into the alignment of platforms.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Reserve products integrated with foundational market platform for subset of processes. | Q4 2021-22 | Delayed - Internal Reasons |  | The delay to the launch of the new reserve product suite (D4.3.3) means that the products are not yet ready to be included on the SMP.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Asset register requirements and design | Q3 2021-22 | Complete | Q3 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email" We have also marked the "Asset register requirements and design" as complete as the foundational delivery can be shared and can be expected to be interoperable with DSO / Flexibility Markets as they are developed in the future within the Open Networks and ED2 outputs NGESO is working with the DNOs on the Open Networks Project including on primacy rules and trials for interaction between ESO and DSO / Flexibility products in the future. NGESO has also provided feedback on ED2 proposals and stand ready to support the DNOs in the development of the industry platforms and share how we are developing the Single Markets Platform. Whilst functionality has been designed with future needs in mind, more certainty is needed on what markets will exist and how they will interact to facilitate detailed discussions into the alignment of platforms.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Asset register development and testing. | Q4 2021-22 | Complete | Q4 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. Elements of the foundational SMP deployed and operational in Q1 (see D.4.3.2) as part of the day ahead frequency response auction trial include: - Service providers have a single log-in for the auction platform and associated functionality - Automatic loading of service provider registration information in to the EPEX auction platform where users can view it - Bids are submitted via the platform as opposed to spreadsheet or email We have also marked the "Asset development and testing" as complete as the foundational delivery can be shared and can be expected to be interoperable with DSO / Flexibility Markets as they are developed in the future within the Open Networks and ED2 outputs NGESO is working with the DNOs on the Open Networks Project including on primacy rules and trials for interaction between ESO and DSO / Flexibility products in the future. NGESO has also provided feedback on ED2 proposals and stand ready to support the DNOs in the development of the industry platforms and share how we are developing the Single Markets Platform. Whilst functionality has been designed with future needs in mind, more certainty is needed on what markets will exist and how they will interact to facilitate detailed discussions into the alignment of platforms.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Single markets Platform Development and testing. | Q3 2022-23 | Complete | Q3 2022-23 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. As at 16 December 2022 we have delivered a total of 7 releases during the calendar year. This has progressively delivered functionality to improve the users experience, include more services and respond to prioritised tactical services (such as Demand Flexibility Service and Balancing Reserve). SMP has a strong backlog of work to deliver across the rest of RIIO-2 The foundational delivery can be shared and can be expected to be interoperable with DSO / Flexibility Markets as they are developed in the future within the Open Networks and ED2 outputs NGESO is working with the DNOs on the Open Networks Project including on primacy rules and trials for interaction between ESO and DSO / Flexibility products in the future. NGESO has also provided feedback on ED2 proposals and stand ready to support the DNOs in the development of the industry platforms and share how we are developing the Single Markets Platform. Whilst functionality has been designed with future needs in mind, more certainty is needed on what markets will exist and how they will interact to facilitate detailed discussions into the alignment of platforms.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Procurement of all ESO balancing and ancillary services through single markets platform for full range of processes | Q4 2022-23 | Delayed - External Reasons |  | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. SMP first went live in February 2022 to support the onboarding process for new and enduring frequency response products. Since then a further 7 releases have taken place and we have actively developed a backlog of functionality that has been co-created and prioritised with our users. Based on the backlog of requirements it is now expected that the procurement of all appropriate balancing services through SMP will extend into BP2 timescales. This will ensure that we are able to focus on the development of value adding functionality for new and existing Day Ahead markets over simply integrating all services. Our plan for BP2 is already well structured and is being communicated with our stakeholders.
2 | A4.4 Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Asset register implementation | Q1 2022-23 | Complete | Q4 2021-22 | The Single Market Platform (SMP) will evolve over time. Different elements of functionality will be deployed for different markets and services at different times in a co-ordinated release train. The first successful release for SMP was on 10 February 2022 and supports the onboarding of the new DR and DM frequency response products that go live in March / April 2022. Accounts and data for DC providers were also created proactively. Additional functionality and more balancing services will then be released in stages in subsequent releases. The foundational delivery can be shared and can be expected to be interoperable with DSO / Flexibility Markets as they are developed in the future within the Open Networks and ED2 outputs NGESO is working with the DNOs on the Open Networks Project including on primacy rules and trials for interaction between ESO and DSO / Flexibility products in the future. NGESO has also provided feedback on ED2 proposals and stand ready to support the DNOs in the development of the industry platforms and share how we are developing the Single Markets Platform. Whilst functionality has been designed with future needs in mind, more certainty is needed on what markets will exist and how they will interact to facilitate detailed discussions into the alignment of platforms.
2 | A4.5 Alignment of ESO-DSO flexibility markets | D4.5.1 | ESO-DSO flexibility services contract alignment. | Commence implementation of agreed contract alignment. Delivery of this activity is dependent on the coordinated actions of the ESO with the ENA and 6 Distributed Network Operators (DNOs). | Q1-Q4 2021-22 | Complete | Q4 2021-22 | Milestone complete
2 | A4.5 Alignment of ESO-DSO flexibility markets | D4.5.1 | ESO-DSO flexibility services contract alignment. | Complete implementation of ESO-DSO Contract alignment. Delivery of this activity is dependent on the coordinated actions of the ESO with the ENA and 6 Distributed Network Operators (DNOs). | Q1-Q4 2022-23 | Complete | Q4 2022-23 | The ESO-led common contract / standard agreement for flexibility services is now finalised following industry consultation. It is now being used by ESO as the basis of the contract for Dynamic Containment, Dynamic Moderation and Dynamic Regulation services.
2 | A4.5 Alignment of ESO-DSO flexibility markets | D4.5.2 | ESO-DSO flexibility services tendering and procurement timescales alignment. | Commence implementation of ESO-DSO flexibility services tendering and procurement timescales alignment. Delivery of this activity is dependent on the coordinated actions of the ESO with the ENA and 6 Distributed Network Operators (DNOs). | Q1-Q4 2021-22 | Complete | Q4 2021-22 | Milestone complete
2 | A4.5 Alignment of ESO-DSO flexibility markets | D4.5.2 | ESO-DSO flexibility services tendering and procurement timescales alignment. | Complete implementation of ESO-DSO flexibility services tendering and procurement timescales alignment. Delivery of this activity is dependent on the coordinated actions of the ESO with the ENA and 6 DNOs. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Following industry consultation, the ESO-led work on procurement processes identified a number of areas where greater visibility and transparency of flexibility procurement could support market participants.
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | Award contacts for stability pathfinder phase 2. | Q2 2021-22 | Complete | Q4 2021-22 | Contracts for Stability Phase 2 were awarded in Q4 2021/22
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | Implement enduring IT solution for phase 1 (IT investment 130). | Q2 2021-22 | Complete | Q2 2021-22 | In 2021/22, 2 units from KEITH, 2 units from Killingholme and 1 unit from RASSAU successfully went live, with further units at Lister Drive and Grain starting in Q4 2022-23. The IT solution has been delivered to allow ESO to instruct these units.
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | Complete design of IT solution for phase 2 (IT investment 130). | Q3 2021-22 | Delayed - External Reasons |  | Design work to be completed by Q3 23/24 following completion of the requirements gathering. As the Stability Phase 2 contracts are not scheduled to start until April 24, therefore the original milestone date is not suitable. We expect the IT design and development work will not delay the commencement of the contracts.
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | As required review Great Britain wide requirements at a regional level for stability | Q1-Q4 2021-22 | Complete | Q4 2021-22 | In Q2 2020-21 we kicked off an innovation project: Stability Market Design. This project will consider current stability arrangements and investigate a potential high-level option for an end-to-end stability market. [URL https://www.nationalgrideso.com/future-energy/projects/stability-market-design] As we communicated to market, awarding contracts for Phase 2 of the Stability Pathfinder has been delayed to Q4 2021/22.
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | Expand pathfinder process to further region(s) and align with voltage requirements | Q1-Q4 2021-22 | Complete | Q4 2021-22 | In Q2 2020-21 we kicked off an innovation project: Stability Market Design. This project will consider current stability arrangements and investigate a potential high-level option for an end-to-end stability market. [URL https://www.nationalgrideso.com/future-energy/projects/stability-market-design] Contracts were awarded for Phase 2 of the Stability Pathfinder in Q4 2021/22. In February 2021 we assessed the need for for further stability requirements and initiated Pathfinder Stability 3 - Tender results were published in Q3 2022-23.
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | Define scope of stability market development and start engagement with industry. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | In Q4 2021-22 we continued our work on the Stability Market Design NIA project. We had our second industry engagement webinar on 8th Feb, where we shared early thinking around the preferred way forward and provided an opportunity for feedback. The webinar received positive feedback. We published the NIA report and a 'thought piece' on 29th March indicating key learnings from this phase of the project and plans for the next steps. Stability Market Design URL: https://www.nationalgrideso.com/future-energy/projects/stability-market-design
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | Develop plan to deliver stability market. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | In Q4 2021-22 we continued our work on the Stability Market Design NIA project. We had our second industry engagement webinar on 8th Feb, where we shared early thinking around the preferred way forward and provided an opportunity for feedback. The webinar received positive feedback. We published the NIA report and a 'thought piece' on 29th March indicating key learnings from this phase of the project and plans for the next steps. Stability Market Design URL: https://www.nationalgrideso.com/future-energy/projects/stability-market-design
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | As required Complete implementation of IT solutions for phase 2 (IT investment 130 Emergent technology and system management). | Q1-Q4 2022-23 | Delayed - External Reasons |  | Design work to be completed by Q3 23/24 following completion of the requirements gathering. As the Stability Phase 2 contracts are not scheduled to start until April 24, therefore the original milestone date is not suitable. We expect the IT design and development work will not delay the commencement of the contracts.
2 | A4.6 New services market development | D4.6.1 | Development of competitive approaches to procurement of stability. | As required Initiate plan to deliver stability market. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Phase 2 of the Stability Market Design Network Innovation Allowance (NIA) project is nearing its conclusion. The project recommends at least 3 discrete markets – Long-term (Y-4), Mid-term (Y-1), and Short-term (D-1) – to procure stability services in an effective way. For each of these markets, fundamental questions on eligibility and contract structure have been answered, and there is a core recommendation to launch the Y-1 Mid-term market as a priority. This is to harness additional inertia capability from existing units, to provide an enduring route to market for existing assets currently contracted under the Pathfinder framework, and to build investor confidence that stability services will be procured on a regular basis. The plan for launching the Y-1 market is set out in the 2023 Markets Roadmap publication which signposts industry to key reforms across operability themes, including stability. We have conducted 3 industry expert panel sessions to gather initial feedback on our market design approach as part of the innovation project. Next, the imminent step following the publication of the roadmap is to share a Y-1 mid-term market technical specification with wider industry and to resource the project team internally to deliver the Y-1 market, as outlined. In parallel to initiating the delivery of the Y-1 stability market in 2023, ESO will be completing further process mapping and system impact assessments to establish achievable plans for developing the short-term stability market and a regular framework for initiating new-build procurement in the long-term, if required.
2 | A4.6 New services market development | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Define and agree scope of reactive power services reform with industry (including suitability of ongoing mandatory reactive power service). | Q3 2021-22 | Complete | Q4 2021-22 | Reactive market NIA project is completed for the phase 1 work; The final report is published together with the planned activities for next phase of market development. We have also planned an industry webinar at April to discuss these outputs with Q&AWe have also planned an industry webinar at April to discuss these outputs with Q&A
2 | A4.6 New services market development | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Identify, agree and publish plan with industry to deliver reactive reform. | Q4 2021-22 | Complete | Q4 2021-22 | Reactive market NIA project is completed for the phase 1 work; The final report is published together with the planned activities for next phase of market development. We have also planned an industry webinar at April to discuss these outputs with Q&A
2 | A4.6 New services market development | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Award contract for Pennines Pathfinder. | Q4 2021-22 | Complete | Q4 2021-22 | Contracts successfully awarded and communicated with market. The event saw the first OFTO asset for a wind farm being awarded a contract and along with the other successful solutions is expected to save consumers millions of pounds through the competitive event.
2 | A4.6 New services market development | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Expand pathfinder process to further region(s) and issue tender (aligned with stability requirements). | Q4 2021-22 | Complete | Q4 2021-22 | The reactive market design project has been progressing with external consultancy through NIA funding. The project output is expected to inform the direction and scope of reactive reform; In Q3 the project has completed various industry workshops, webinars and questionnaire with industry to share and discuss the key design questions. The feedback received will be considered in the design work next; this is currently expected to deliver by March (Q4 2021/22). This deliverable is the same as the one 'Identify, agree and publish plan with industry to deliver reactive reform.' Initial review has not identified a need for new voltage pathfinders however this is an ongoing assessment process and as requirements emerge we will initiate new procurement events
2 | A4.6 New services market development | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Initiate delivery of enduring plan for reactive reform as required | Q1-Q4 2022-23 | Delayed - Internal Reasons |  | Work has been started to further assess and develop the proposed market design option from phase 1 of the innovation project with regards to feasibility. Feasibility study work has started to assess the propose market design option and identify any gaps from process, system and resource perspective. 20+ workshops were planned with SMEs. The output was analysed to indicate the work next step. Majority work from project is being suspended after Aug due to the prioritisation for winter preparation.
2 | A4.6 New services market development | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Deliver IT changes for Mersey pathfinder. | Q1 2022-23 | Complete | Q1 2022-23 | Voltage Mersey - IT change was delivered
2 | A4.6 New services market development | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Go-live of new Mersey pathfinder reactive service. | Q3 2022-23 | Complete | Q4 2022-23 | Voltage Mersey - Zenobe: unit went live on 27 Jan 23. Voltage Mersey - Peakgen: unit went live successfully at May 2022
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1 .1 | Continuation of EMR Delivery Body obligations. | Publish a cocreated guidance document covering 2021 rule changes (in collaboration with Ofgem, BEIS and industry) open within 4 weeks of the rules being laid. | Q1 2021-22 | Complete | Q1 2021-22 | Draft CM Prequalification guidance published on 29 June 2021. In response to customer feedback, the guidance was simplified, broken down into smaller pieces and published in advance of the process commencing. A survey was published with the guidance, allowing us to respond to feedback and co-create with our CM customers. In addition to the guidance, we have also published numerous podcasts and YouTube videos to support and guide applicants through this year's process. An event took place on 13 July 2021 to formally launch this year's process. Around 250 stakeholders signed up, and just under 50% of the agenda was Q&A to ensure customers continue to have the opportunity to comment and help us to co-create guidance.
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1 .1 | Continuation of EMR Delivery Body obligations. | Use previous Customer Relationship Management (CRM) tool data to upskill front desk and feed any frequently asked questions into guidance documentation. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | Draft CM Prequalification guidance published on 29 June 2021. In response to customer feedback, the guidance was simplified, broken down into smaller pieces and published in advance of the process commencing. A survey was published with the guidance, allowing us to respond to feedback and co-create with our CM customers. In addition to the guidance, we have also published numerous podcasts and YouTube videos to support and guide applicants through this year's process. An event took place on 13 July 2021 to formally launch this year's process. Around 250 stakeholders signed up, and just under 50% of the agenda was Q&A to ensure customers continue to have the opportunity to comment and help us to co-create guidance. We have captured customer engagement and feedback and fed this into the development of our guidance and frequently asked questions documents. We have also used the feedback and updated guidance/FAQ documents to train our team. In addition to this, the whole Delivery Body team has completed specific customer engagement training.
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1 .1 | Continuation of EMR Delivery Body obligations. | Guidance to rule changes are incorporated into Portal | Q1 2022-23 | Delayed - Internal Reasons |  | The Delivery Body experienced delays to the implementation of the New EMR Portal, due to internal and external factors. Transparent engagement has taken place with stakeholders, including consultation on the preferred option to deliver, with implementation in Q1 2024-25 receiving clear backing. The initial release included system architecture, registration, portfolio management and user management. CM Prequalification application submission, assessment and results release, as well as specific agreement management functionalities have been developed. The functionality has been demonstrated to the customer user group and released in Beta environment, for customer familiarisation. The delivery roadmap has been realigned to enable implementation in Q1 2024-25, detailing the key milestones. The Delivery Body will engage customers to review the options to integrate guidance after which it will be delivered as part of the roadmap.
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1 .1 | Continuation of EMR Delivery Body obligations. | EMR portal will allow disputes to be attached to applications, reducing the burden to appeal. | Q2-Q3 2022-23 | Delayed - Internal Reasons |  | he Delivery Body experienced delays to the implementation of the New EMR Portal, due to internal and external factors. Transparent engagement has taken place with stakeholders, including consultation on the preferred option to deliver, with implementation in Q1 2024-25 receiving clear backing. The initial release included system architecture, registration, portfolio management and user management. CM Prequalification application submission, assessment and results release, as well as specific agreement management functionalities have been developed. The functionality has been demonstrated to the customer user group and released in Beta environment, for customer familiarisation. The delivery roadmap has been realigned to enable implementation in Q1 2024-25, detailing the key milestones. The disputes functionality has been designed and will allow linking of disputes to applications in the New EMR Portal. Delivery is planned for Q4 2023-24
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1.2 | An improved prioritisation process in how we implement change in the EMR Delivery Body. This is about embedding the process and not the delivery of specific changes for each year. | EMR Delivery Body delivers full assessments of the backlog of changes with estimated impacts of implementation | Q1 2021-22 | Complete | Q1 2021-22 | The EMR Delivery Body completed a full assessment of the backlog of changes. It also developed and agreed a process for prioritising the backlog of change with Ofgem, BEIS and other EMR Delivery Partners. This ongoing process is now being overseen by the Regulatory Change Advisory Board (RCAB).
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1.2 | An improved prioritisation process in how we implement change in the EMR Delivery Body. This is about embedding the process and not the delivery of specific changes for each year. | Backlog of change is prioritised at RCAB to understand changes for next delivery cycle. | Q2 2021-22 | Complete | Q2 2021-22 | A process for prioritising the backlog of change has been developed and agreed with Ofgem, BEIS and other EMR Delivery Partners. This ongoing process is now being overseen by the Regulatory Change Advisory Board (RCAB).
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1.2 | An improved prioritisation process in how we implement change in the EMR Delivery Body. This is about embedding the process and not the delivery of specific changes for each year. | Delivery Body implements a robust estimation process for assessing future changes using robust and transparent criteria including: Whether there are any unintended consequences of the change, anticipating the impact on all stakeholders (ESO, applicants, Delivery Partners etc), the anticipated impact on the Delivery Body Portal and IT and ultimately the overall cost to consumer | Q3 2021-22 | Complete | Q3 2021-22 | A process for assessing and prioritising the backlog of change has been developed and agreed with Ofgem, BEIS and other EMR Delivery Partners. This was used to agree the list of regulatory changes for 2022 with Ofgem and BEIS. The prioritisation process is now being overseen by the Regulatory Change Advisory Board (RCAB).
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1.2 | An improved prioritisation process in how we implement change in the EMR Delivery Body. This is about embedding the process and not the delivery of specific changes for each year. | Outputs shared with wider industry | Q4 2021-22 | Complete | Q4 2021-22 | A process for prioritising the backlog of change has been developed and agreed with Ofgem, BEIS and other EMR Delivery Partners. This ongoing process is now being overseen by the Regulatory Change Advisory Board (RCAB). In light of Ofgem's plans to establish a Capacity Market Advisory Group (CMAG) with industry during 2022, the ESO will not undertake a separate engagement exercise regarding the prioritisation process with industry. Instead, the Delivery Body will capture rule improvement ideas based on feedback received from customers and feed this into the CMAG process as appropriate where these can be discussed with industry.
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1.2 | An improved prioritisation process in how we implement change in the EMR Delivery Body. This is about embedding the process and not the delivery of specific changes for each year. | EMR Delivery Body runs informal consultation with industry to refine the improved prioritisation process for changes that are deliverable and ensure transparency of those that are not. | Q1 2022-23 | Milestone no longer valid |  | In light of Ofgem's plans to establish a Capacity Market Advisory Group (CMAG) with industry in October 2022, the ESO will not undertake a separate engagement exercise regarding the prioritisation process with industry. We are also mindful that BEIS is now reviewing the wider EMR policy and change governance, incl. the CM Policy Board and RCAB. The Delivery Body will therefore capture rule improvement ideas based on feedback received from customers and feed this into the CMAG process as appropriate where these can be discussed with industry.
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1.2 | An improved prioritisation process in how we implement change in the EMR Delivery Body. This is about embedding the process and not the delivery of specific changes for each year. | Improved change prioritisation process is published by EMR Delivery Body. | Q2 2022-23 | Milestone no longer valid |  | In light of Ofgem's plans to establish a Capacity Market Advisory Group (CMAG) with industry in October 2022, the ESO will not undertake a separate engagement exercise regarding the prioritisation process with industry. We are also mindful that BEIS is now reviewing the wider EMR policy and change governance, incl. the CM Policy Board and RCAB. The Delivery Body will therefore capture rule improvement ideas based on feedback received from customers and feed this into the CMAG process as appropriate where these can be discussed with industry.
2 | A5.1 Electricity Market Reform (EMR) Delivery Body | D5.1.2 | An improved prioritisation process in how we implement change in the EMR Delivery Body. This is about embedding the process and not the delivery of specific changes for each year. | Industry take part in prioritisation process. | Q3 2022-23 | Milestone no longer valid |  | In light of Ofgem's plans to establish a Capacity Market Advisory Group (CMAG) with industry in October 2022, the ESO will not undertake a separate engagement exercise regarding the prioritisation process with industry. We are also mindful that BEIS is now reviewing the wider EMR policy and change governance, incl. the CM Policy Board and RCAB. The Delivery Body will therefore capture rule improvement ideas based on feedback received from customers and feed this into the CMAG process as appropriate where these can be discussed with industry.
2 | A5.2 Deliver an enhanced platform for the Capacity Market within the single, integrated ESO markets platform | D5.2 (shared with D4.4) | IT system to allow all participants in ESO markets (including CM and CfD) a single point of access for services and data | Essential regulatory changes delivered on existing EMR portal. | Q1 2021-22 | Complete | Q1 2021-22 | Significant Customer improvements were delivered into the EMR portal in April 2021, and further mandatory changes to facilitate the 2021 CM process were delivered in July 2021. The Delivery Body worked with customers to prepare co-created guidance which supported customers with the rule changes.
2 | A5.2 Deliver an enhanced platform for the Capacity Market within the single, integrated ESO markets platform | D5.2 (shared with D4.4) | IT system to allow all participants in ESO markets (including CM and CfD) a single point of access for services and data | First elements of the new EMR Portal delivered via agile delivery. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | The ESO delivered the first release of the new EMR portal in March 2022. This covered the process for company and CMU registration. This released enables the ESO to work with customers to help them with the migration of their data from the legacy portal to the new solution.
2 | A5.2 Deliver an enhanced platform for the Capacity Market within the single, integrated ESO markets platform | D5.2 (shared with D4.4) | IT system to allow all participants in ESO markets (including CM and CfD) a single point of access for services and data | Additional elements of the new EMR Portal delivered through prioritised agile delivery. | Q1-Q4 2022-23 | Delayed - Internal Reasons |  | The Delivery Body experienced delays to the implementation of the New EMR Portal, due to internal and external factors. Transparent engagement has taken place with stakeholders, including consultation on the preferred option to deliver, with implementation in Q1 2024-25 receiving clear backing. The initial release included system architecture, registration, portfolio management and user management. CM Prequalification application submission, assessment and results release, as well as specific agreement management functionalities have been developed. The functionality has been demonstrated to the customer user group and released in Beta environment, for customer familiarisation. The delivery roadmap has been realigned to enable implementation in Q1 2024-25, detailing the key milestones. The Delivery Body is currently in the process of communicating the revised roadmap with customers and stakeholders. It is understood that the REMA consultation and associated assessment will influence the delivery assessment for CfD processes in the New EMR Portal.
2 | A5.3 Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling. | Production of the Electricity Capacity Report | Q1 2021-22 | Complete | Q1 2021-22 | The 2021 Electricity Capacity Report was submitted to BEIS on 28 May 2021. The report was considered Confidential EMR Information until it was published on 8 July 2021. A link to the published report is shown below: https://www.emrdeliverybody.com/Capacity%20Markets%20Document%20Library/Electricity%20Capacity%20Report%202021.pdf" Development projects to enhance security of supply modelling are now progressing. These projects were identified in collaboration with BEIS and Ofgem and reflect feedback from BEIS' PTE in their published 2021 Report. Outcomes from the development projects will be presented in the 2022 Electricity Capacity Report.
2 | A5.3 Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling. | In line with the prioritisation agreed with the Panel of Technical Experts (PTE), BEIS and Ofgem enhancements will be made to our modelling. Following the production of the Electricity Capacity Report in Q1 we will agree with the PTE, BEIS and Ofgem and begin to work through, the prioritised list of enhancements. It is not possible to provide a more granular timescale for this activity. Priorities are expected to include; enhancements to the modelling for distributed generation, durationlimited storage and demand response, maximising the use of the data from the DCUSA modification in RIIO-1; and enhancements of European market modelling, as level of interconnection increases over RIIO-2 period. This includes supporting ENTSO-E in developing a methodology for crossborder participation in the CM. | Q4 2021-22 | Complete | Q4 2021-22 | Development projects to enhance security of supply modelling have been undertaken in line with the prioritisation process agreed with BEIS and Ofgem. These projects have sought to enhance a number of areas of the modelling including: non-delivery, risks due to adverse weather, new model functionality to provide better insight on interconnector modelling, industry consultation on appropriateness of new data to calculate Capacity Market de-rating factors for some embedded generation technologies. Full details of these projects will be reported in the 2022 Electricity Capacity Report.
2 | A5.3 Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling. | Production of the Electricity Capacity Report | Q1 2022-23 | Complete | Q1 2022-23 | The 2022 Electricity Capacity Report was submitted to BEIS by 1 June 2022 in line with our obligations.
2 | A5.3 Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling. | In line with the prioritisation agreed with the PTE, BEIS and Ofgem enhancements will be made to our modelling. Following the production of the Electricity Capacity Report in Q1 we will agree with the PTE, BEIS and Ofgem and begin to work through, the prioritised list of enhancements. It is not possible to provide a more granular timescale for this activity. Priorities are expected to include; improved modelling of security of supply for intermittent technology and Demand Side Response (DSR); support modelling changes to the review of the reliability standards, in particular around the implementation of the clean energy package; and review and continued enhancements of European market modelling, as level of interconnection increases over RIIO-2 period. | Q4 2022-23 | Complete | Q4 2022-23 | Development projects for 2022/23 were prioritised in Sep 2022 in line with our established process. Projects have now been completed and will be reported on in the 2023 Electricity Capacity Report expected to be published in July 2023, as per the well-established annual process.
2 | A6.1 Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of Great Britain driven regulatory change through the open governance process. | GC0137/139/145 code change process completed. Post TCR modification proposals identified. | Q1 2021-22 | Delayed - External Reasons |  | Targeted Charging Review - work is continuing on this. CMP363/364 has now been approved by OFGEM and will be implemented. CMP316 - co-location of generation assets, this work continues to progress and has finished the Code Administration Consultation in October 2022. It will be submitted in early 2023 as an extra workgroup is required to finalise legal text. BSUoS Reform - CMP308 removal of BSUOS charges from generation has been approved by OFGEM and will be implemented for April 2023. CMP361/362 introducing an ex ante fixed BSUoS tariff and associated definitions is currently awaiting a decision at time of writing. Other related items to note the Market Wide Half Hourly programme is being progressed. The TNUoS Taskforce has been paused following re-prioritisation from OFGEM. Work is underway within the ESO to gather analysis ahead of formal sessions being re-started. GC145 - has now concluded as we are now longer participating in MARI GC0139 - in workgroup phase, complex modification working through legal text GC0137 Grid Forming - This is now complete and is in the code GC0154 - This modification is currently going through a tender for a CBA to be undertaken. FRCR - this has now been consulted on and as gone through the SQSS panel to be submitted to ofgem by 1st April SQSS modifications are still in design as the Holistic Network Design work continues, we are looking to set up industry workshops in the new year to support the design of these modifications. ESRS modifications - delays due to complexity of modifications and impacts to parties, however still progressing in a way that will ensure all impacted parties can be compliant by 26 GC139 following the governance process in legal text phase once submitted to Ofgem this milestone will be complete - expected by Q1 23/24
2 | A6.1 Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of Great Britain driven regulatory change through the open governance process. | Raise Access and Forward Looking Charges Modification Proposals. Clean Energy Package non-BM imbalance correction proposal submitted to Authority | Q3 2021-22 | Delayed - External Reasons |  | Ofgem have changed the scope of the Access SCR, it is no longer expected that any TNUoS related modifications are required at this stage as a result of the SCR. Therefore, this milestone is no longer required. P412 - Proposal to put P412 on hold until the Open balancing Platform is complete. The reason it is on hold/delayed is because of the lack of consumer benefit this change brings. This change will cost several millions to deliver for no real benefit other than compliance. Next steps - Reconvene the P412 workgroup and propose delay until the open balancing platform is complete.
2 | A6.1 Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of Great Britain driven regulatory change through the open governance process. | Management of any further modifications received through open governance for which the resource requirement can vary considerably | Q1-Q4 2021-22 | Complete | Q4 2021-22 | GC0151 - mod clarifying the process to be followed after a suspected generator failure to ride through a transmission fault approved by Ofgem in Nov 21 allowing the ESO to seek immediate agreement to restrict a generator until compliance issues are resolved. Very important to maintain system security as fault ride-through becomes more of an issue in a low inertia system - GC0137 - 'grid forming' specification mod approved by Ofgem Jan 22. This allows participation of converter connected technology in stability markets/pathfinders and is a key enabler for net zero and a world first by GB in achieving this step - Mods in progress to revise generator thresholds for participation in the BM and to provide services (GC0117), and to codify arrangements for interconnector ramping (GC0155), both of which have significant operational impact in adapting to changes in the system and participants Targeted Charging Review - The ESO has continued to support Ofgem with the changes required for the Targeted Charging Review progressing key modifications for demand and generation charging (CMP363/4 and CMP368/9) through the Working Group process. These are either with Ofgem or will shortly be sent to Ofgem for a decision. CMP298 - Statement of works changes have progressed well with key elements of the mod now supporting DNOs and TOs in terms of the assessment of the connection. CMP316 - Co-location of generation assets, following de-prioritisation of this by the CUSC Panel work has picked up again. We expect that this will lead to consultation and a submission to Ofgem for decision in 2022. Urgent BSUoS modifications - the ESO has supported CMP381 to provide industry support up to £200m against high BSUoS costs. We have provided daily reporting to show the cumulative total of support provided when the £20/MWh cap has been breached. We have also raised CMP383 to provide maximum transparency to industry of when the costs will be recovered through FY22/23.
2 | A6.1 Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of Great Britain driven regulatory change through the open governance process. | Submit Access and Forward Looking Charges Modification Proposals to Authority | Q2 2022-23 | Milestone no longer valid |  | Ofgem have changed the scope of the Access SCR, it is no longer expected that any TNUoS related modifications are required at this stage as a result of the SCR. Therefore, this milestone is no longer required and is being re-drafted following the agreed process.
2 | A6.1 Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of Great Britain driven regulatory change through the open governance process. | Management of any further modifications received through open governance for which the resource requirement can vary considerably. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Targeted Charging Review - work is continuing on this. CMP363/364 has now been approved by OFGEM and will be implemented April 2023. CMP316, continues to progress. A further WG meeting is required to finalise legal text. BSUoS Reform - CMP308 & CMP361/362 have both now been approved and will be implemented April 2023. Other related items to note the Market Wide Half Hourly programme continues to be progressed. During the summer of 2022, Ofgem paused the TNUoS Task Force meetings for the remainder of the year. We have secured innovation funding for consultancy support to review the key defects which look at improvements to both cost reflectivity and also predictability of transmission charges. CMP376 is progressing with the Workgroup vote being held. Next steps are for the Workgroup report to be presented to CUSC Panel. CMP315/CMP375 has draft legal text for both modifications. Significant work undertaken with Transmission Owners (TOs) to discuss data requirements. Tariff analysis on course to be provided by end of March for review at next Workgroup meeting. GC145 - has now concluded as we are no longer participating in MARI. GC0139 - in workgroup phase, complex modification working through legal text. GC0137 Grid Forming - This is now complete and is in the code. GC0154 - This modification is currently going through a tender for a CBA to be undertaken. FRCR - this has now been consulted on and as gone through the SQSS panel to be submitted to ofgem by 1st April. SQSS modifications are still in design as the Holistic Network Design work continues, we are looking to set up industry workshops to support the design of these modifications. ESRS modifications - delays due to complexity of modifications and impacts to parties, however still progressing in a way that will ensure all impacted parties can be compliant by 26. GC139 following the governance process in legal text phase once submitted to Ofgem.
2 | A6.2 European Union (EU) code change and relationships | D6.2 | Continued facilitation of EU driven code changes into Great Britain market. | Develop a plan for implementing harmonised Redispatching and Countertrading as per the TCA | Q4 2021-22 | Complete | Q4 2021-22 | A plan has been developed for RD CT and has been shared with GB ICs, and OFGEM as part of the intraday workshop.
2 | A6.2 European Union (EU) code change and relationships | D6.2 | Continued facilitation of EU driven code changes into Great Britain market. | Develop a Technical Procedure for Day Ahead Capacity Calculation | Q3 2021-22 | Delayed - External Reasons |  | The ESO are continuing to lead and progress industry workshops on Day Ahead Capacity Calculation, in line with the TCA requirements. There has been limited engagement from EU TSOs on Capacity Calculation so the development of the technical procedure has been delayed. The ESO is awaiting guidance from the Specialised Committee of Energy to progress this work with EU TSOs. In the mean time, the ESO will continue to develop a UK position with UK TSOs. In February 2023, the Specialised Committee of Energy directed EU and UK TSOs (via letters from ENTSOE and DESNZ) to recommence work on day ahead Capacity Allocation (namely multi regional loose volume coupling). The ESO will therefore progress the work on Capacity Allocation with UK and EU TSOs and await further guidance on Capacity Calculation. Note - This milestone is marked as delayed because EU TSOs are not yet engaging on Capacity Calculation. A technical procedure that is fit for purpose for UK and EU TSOs cannot be drafted until EU TSOs start engaging on this topic.
2 | A6.2 European Union (EU) code change and relationships | D6.2 | Continued facilitation of EU driven code changes into Great Britain market. | Develop Technical Procedure for Cross Border Balancing and other time frame Capacity Calculation in collaboration with UK TSOs and EU TSOs | Q3 2022-23 | Delayed - External Reasons |  | Cross border balancing has progressed from a GB perspective, but we've had little to no engagement from EU TSOs on this matter - this will cause a delay to progress if this continues. The ESO gained innovation funding to complete a CBA for cross border balancing options. This CBA will be used to show benefits of a new CBB market between UK and EU TSOs, therefore encouraging further development of this work. Compass Lexecon (the third party who was awarded the contract for this work) will share the final CBA report in April 2023 and they will also host a webinar with industry to present the results. Note - The original date for completion of the CBA was December 2022. This has been delayed slightly, by 3 months, because of reprioritisation of Winter planning activities, namely the urgent gas deficit BSC and Grid Code modification. Other timeframes for capacity calculation - little progress has been made on other timeframes because of lack of engagement from EU TSOs. UK TSOs will prioritise the day ahead capacity calculation and use the principles of this technical procedure to then develop the process for other timeframes.
2 | A6.2 European Union (EU) code change and relationships | D6.2 | Continued facilitation of EU driven code changes into Great Britain market. | Clean Energy Package – changes for Short Term Operating Reserve (STOR) ready for new auctions. | Q2 2021-22 | Complete | Q2 2021-22 | STOR is now live and procured at day ahead timescales.
2 | A6.2 European Union (EU) code change and relationships | D6.2 | Continued facilitation of EU driven code changes into Great Britain market. | Grid code and BSC change for Emergency and Restoration (Supporting activity A3 in Role 1). | Q2 2021-22 | Complete | Q1 2021-22 | This action has been completed.
2 | A6.2 European Union (EU) code change and relationships | D6.2 | Continued facilitation of EU driven code changes into Great Britain market. | IT investment 270 clean energy package development and testing. | Q3 2022-23 | Delayed - Consumer Benefits |  | Clean Energy Package: 6(4) Pricing Proposal was approved by OFGEM on 20th May 2022. Minor revisions were made and version 1.1 has been submitted for publication on the ESO website in March 2023. Clean Energy Package: P412. Proposal to put P412 on hold (delay P412) until the Open balancing Platform is complete. The reason it is on hold/delayed is because of the lack of consumer benefit this change brings. This change will cost several millions to deliver for no real benefit other than compliance. The BSC panel granted the ESO a 9 month extension in January 2023. Next steps - Next steps - Reconvene the P412 workgroup, update the IT impact assessment and CBA, propose delay until the open balancing platform is complete.
2 | A6.2 European Union (EU) code change and relationships | D6.2 | Continued facilitation of EU driven code changes into Great Britain market. | Full compliance with Article 6 of the Clean Energy Package. | Q2 2022-23 | Delayed - Consumer Benefits |  | Article 6.2 - Derogation for Static FFR approved by OFGEM 10th Feb 2023. Moved static FFR procurement from monthly to daily so no further derogations are required for this product as procurement timescales are now compliance with Article 6. Article 6.4 - OFGEM approved the Pricing Proposal on 20th May 2022. Each new product will need to go through an assessment to establish whether it needs to be pay as clear (legacy products not in scope). Article 6.5 (P412) Delayed. Proposal to put P412 on hold (delay P412) until the Open balancing Platform is complete. Next steps - Reconvene the P412 workgroup and propose delay. P412 is delayed because of a lack of consumer benefits. Article 6.9 (up and down) MFR - Derogation has been granted until 2025. Next steps - focus on the MFR decision letter actions. Article 6.9 - derogation approved by OFGEM for Dynamic FFR 10th March 2023. Next steps for ESO - replace DFFR with new frequency products.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Investment 290 Charging and Billing Asset Health Deliver critical system changes necessary to improve/ sustain the foundation of the CAB system in order to deliver the regulatory changes (investment 300) up to April 2022. Asset health improvements will be delivered quarterly throughout the year. Change delivery for Investment 300 Charging Regime and CUSC Changes include: Transmission Demand Residual bandings and allocation (CMP343 - TCR TNUoS); | Q1-Q4 2021-22 | Complete | Q4 2022-23 | We have made the decision to re-platform our charging and billing system to a new system, known as STAR, which will enable us to be more agile and efficient to implement future regulatory changes in charging. Delivery of AAHEDC billing and many of the fundamental building blocks needed for other charge types was delivered in Feb 2023.. TNUoS TCR changes have been delivered in STAR and BSUoS Reform changes have been delivered in CAB, ready for 1 April 2023 deadlines. We are developing the roadmap beyond Apr 23 to ensure efficient transition of remaining charging activities from existing CAB system, to support future regulatory changes, customer improvements and improved compliance.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Enabling reform of residual network charging as directed by the TCR (P402): Requirements and design | Q1 2021-22 | Complete | Q2 2021-22 | "After intensive analysis and assessment, we have made the decision to re-platform our charging and billing system to Oracle MSM. This new system will enable us to be more agile and efficient to implement and comply with the regulatory changes in charging methodology including the Transmission Charging Review (TCR) and BSUoS Taskforce decision. The project team has been mobilised and we are currently on track for system development and delivery. In the meantime, we have completed the improvement work in the current charging and billing system to ensure its stability and reliability until the new system is in place. In terms of P402, the alternative has been approved and the exact data requirement including the format from DNOs to ESO is being finalised following industry consultation Changes associated with reform of residual network charging have been re-planned, as Ofgem has delayed implementation to April 2023. System changes to support this will now be delivered in Q3 2022/23 as part of the new STAR system which replaces the legacy CAB system.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Enabling reform of residual network charging as directed by the TCR (P402): Development and Testing | Q2-Q3 2021-22 | Complete | Q4 2022-23 | TCR changes are to be implemented on 1 Apr 2023, which is later than original expectations due to ongoing industry discussions. CUSC mods were approved by Ofgem on 10 Mar 2022. The changes have been successfully delivered as part of STAR project during FY22/23, with new billing ready to be issued on 1 Apr 2023. Regarding P402, the system changes went live in June 2022.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Enabling reform of residual network charging as directed by the TCR (P402): Implementation | Q4 2021-22 | Complete | Q4 2022-23 | TCR changes are to be implemented on 1 Apr 2023, which is later than original expectations due to ongoing industry discussions. CUSC mods were approved by Ofgem on 10 Mar 2022. The changes have been successfully delivered as part of STAR project during FY22/23, with new billing ready to be issued on 1 Apr 2023. Regarding P402, the system changes went live in June 2022.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Investment 290 Charging and Billing Asset Health Minimum Viable Product for an enduring solution which will enable delivery of regulatory changes under investment 300 - Charging regime and CUSC changes, including Access & Forward Looking Charges | Q1-Q4 2022-23 | Complete | Q4 2022-23 | We have made the decision to re-platform our charging and billing system to a new system, known as STAR, which will enable us to be more agile and efficient to implement future regulatory changes in charging. Delivery of AAHEDC billing and many of the fundamental building blocks needed for other charge types was delivered in Feb 2023.. TNUoS TCR changes have been delivered in STAR and BSUoS Reform changes have been delivered in CAB, ready for 1 April 2023 deadlines. We are developing the roadmap beyond Apr 23 to ensure efficient transition of remaining charging activities from existing CAB system, to support future regulatory changes, customer improvements and improved compliance.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Start up | Q1 2022-23 | Complete | Q1 2022-23 | "After intensive analysis and assessment, we have made the decision to re-platform our charging and billing system to Oracle MSM. This new system will enable us to be more agile and efficient to implement and comply with the regulatory changes in charging methodology including the Transmission Charging Review (TCR) and BSUoS Taskforce decision. The project team has been mobilised and we are currently on track for system development and delivery. In the meantime, we have completed the improvement work in the current charging and billing system to ensure its stability and reliability until the new system is in place. In terms of P402, the alternative has been approved and the exact data requirement including the format from DNOs to ESO is being finalised following industry consultation Changes associated with reform of residual network charging have been re-planned, as Ofgem has delayed implementation to April 2023. System changes to support this will now be delivered in Q3 2022/23 as part of the new STAR system which replaces the legacy CAB system.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Requirements and design | Q2 2022-23 | Delayed - Internal Reasons |  | After intensive analysis and assessment, we have made the decision to re-platform our charging and billing system to Oracle MSM. This new system will enable us to be more agile and efficient to implement and comply with the regulatory changes in charging methodology including the Transmission Charging Review (TCR) and BSUoS Taskforce decision. The project team has been mobilised and we are currently on track for system development and delivery. In the meantime, we have completed the improvement work in the current charging and billing system to ensure its stability and reliability until the new system is in place. In terms of P402, the alternative has been approved and the exact data requirement including the format from DNOs to ESO is being finalised following industry consultation Changes associated with reform of residual network charging have been re-planned, as Ofgem has delayed implementation to April 2023. The invoices for TNUoS demand were generated from STAR which represents introduction of the material changes to the Charging Methodology that the industry has been working on for years. BSUoS changes for the fixed BSUoS tariff from 1 April 2023. have been delivered onto the legacy systems to meet regulatory timelines and mark a significant industry change to the charging regime. These services will be migrated onto STAR as per the BP2 STAR roadmap.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Development and Testing | Q3 2022-23 | Delayed - Internal Reasons |  | After intensive analysis and assessment, we have made the decision to re-platform our charging and billing system to Oracle MSM. This new system will enable us to be more agile and efficient to implement and comply with the regulatory changes in charging methodology including the Transmission Charging Review (TCR) and BSUoS Taskforce decision. The project team has been mobilised and we are currently on track for system development and delivery. In the meantime, we have completed the improvement work in the current charging and billing system to ensure its stability and reliability until the new system is in place. In terms of P402, the alternative has been approved and the exact data requirement including the format from DNOs to ESO is being finalised following industry consultation Changes associated with reform of residual network charging have been re-planned, as Ofgem has delayed implementation to April 2023. The invoices for TNUoS demand were generated from STAR which represents introduction of the material changes to the Charging Methodology that the industry has been working on for years. BSUoS changes for the fixed BSUoS tariff from 1 April 2023. have been delivered onto the legacy systems to meet regulatory timelines and mark a significant industry change to the charging regime. These services will be migrated onto STAR as per the BP2 STAR roadmap.
2 | A6.3 Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Implementation | Q4 2022-23 | Delayed - Internal Reasons |  | After intensive analysis and assessment, we have made the decision to re-platform our charging and billing system to Oracle MSM. This new system will enable us to be more agile and efficient to implement and comply with the regulatory changes in charging methodology including the Transmission Charging Review (TCR) and BSUoS Taskforce decision. The project team has been mobilised and we are currently on track for system development and delivery. In the meantime, we have completed the improvement work in the current charging and billing system to ensure its stability and reliability until the new system is in place. In terms of P402, the alternative has been approved and the exact data requirement including the format from DNOs to ESO is being finalised following industry consultation Changes associated with reform of residual network charging have been re-planned, as Ofgem has delayed implementation to April 2023. The invoices for TNUoS demand were generated from STAR which represents introduction of the material changes to the Charging Methodology that the industry has been working on for years. BSUoS changes for the fixed BSUoS tariff from 1 April 2023. have been delivered onto the legacy systems to meet regulatory timelines and mark a significant industry change to the charging regime. These services will be migrated onto STAR as per the BP2 STAR roadmap.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Dedicated ESO legal support for code changes. | Q1 2021-22 | Complete | Q3 2021-22 | Dedicated legal support in place.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Recruit people and set up new teams and investigate the methods to transform the process to amend our codes. | Q2 2021-22 | Complete | Q2 2021-22 | Recruitment completed
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Stakeholder engagement and consultation on the process to amend our codes. | Q3 2021-22 | Delayed - External Reasons |  | Delayed due to awaiting the outcome of the Energy Code Review consultation. Ofgem has published a further Call for Input on Energy Code Reform which we have responded to and committed to working closely with Ofgem. Detail on the fundamental changes required to transform are not yet clear. In the meantime we will continue to consult and co-create with our stakeholders on more incremental changes that set ourselves up best for when more guidance becomes available, so we do not cause further delay for the transformation.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Investigate licence changes required to transform the process to amend our codes. | Q4 2021-22 | Delayed - External Reasons |  | Delayed due to awaiting the outcome of the Energy Code Review consultation. Ofgem has published a further Call for Input on Energy Code Reform which we have responded to and committed to working closely with Ofgem. Detail on the fundamental changes required to transform are not yet clear. In the meantime we will continue to consult and co-create with our stakeholders on more incremental changes that set ourselves up best for when more guidance becomes available, so we do not cause further delay for the transformation.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Create plan to deliver the transformed codes process. | Q4 2021-22 | Delayed - External Reasons |  | Delayed due to awaiting the outcome of the Energy Code Review consultation. Ofgem has published a further Call for Input on Energy Code Reform which we have responded to and committed to working closely with Ofgem. Detail on the fundamental changes required to transform are not yet clear. In the meantime we will continue to consult and co-create with our stakeholders on more incremental changes that set ourselves up best for when more guidance becomes available, so we do not cause further delay for the transformation.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Consult stakeholders on plan to deliver the transformed codes process. | Q4 2021-22 | Complete | Q4 2022-23 | Following some ECR detail and understanding of timescales the ESO has run a consultation process on what improvements stakeholders would like to see as incremental change. We will consult on that plan now feedback has been received in Q1 23/24. This will allow us to move to a good place prior to any more fundamental changes that occur in the ECR process.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Initiate licence change to support transform the process to amend our codes. | Q1 2022-23 | Delayed - External Reasons |  | Delayed whilst awaiting more guidance on how the larger, more fundamental moves such as licence changes will take place.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Begin detailed scoping and prioritising work for new process go live. | Q2 2022-23 | Delayed - External Reasons |  | Detailed scoping and prioritisation of work for the new process can only take place once more information comes out of the Energy Code Reform on how code administrators will make fundamental changes to the existing process. In the meantime, the ESO Code Administrator will continue to make incremental improvements to the existing process to set ourselves up best for transformation.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | An ambitious go live in Q4 of Transform the process to amend our codes (subject to outcome of Energy Codes Review and scope of change required). | Q4 2022-23 | Delayed - External Reasons |  | Delayed whilst further guidance from the Energy Code Reform becomes available that details how larger, more strategic changes can take place for all code administrators as well as clarity on the final position for code reform. We will continue to support Ofgem as they develop their thinking over the course of 23/24.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Strategic and incremental industry change plan implemented. | Q4 2022-23 | Delayed - External Reasons |  | Survey completed and results received to review and discuss the working relationships with ESO and industry stakeholders as well as improvements needed to better the communication and relationship. Plan of action following the results received will be reviewed and put into place in BP2 during Q1 of 23/24. Due to delays in ECR versus original BP1 expectation this allows us to incorporate stakeholder feedback into our change process to realise quick wins.
2 | A6.4 Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | Greater emphasis on larger and more coordinated programmes of work for our codes. | Q4 2022-23 | Complete | Q4 2022-23 | We have taken steps to internally align our code governance and code development teams to align technical and administrative expertise. This should improve further on some of the points we have highlighted below. Co-ordination of large suites of modifications for e.g ESRS (CUSC, STC, Grid Code, D-Code and BSC) Using webinars to support the completion of consultations (GC0117 and GC0156) Being an active member of CACoP Forum, we led the change of the horizon scan format which is now used across all codes Appointing the code governance manager as the STC Panel Chair to provide additional oversight of the consequential modifications from CUSC and Grid Code. Ensured co-ordination and completion of TCR related BSUoS and TNUoS changes including managing through a difficult period with the final CMP361 approvals.
2 | A6.5 Work with all stakeholders to create a fully digitalised, whole system Grid Code by 2025 | D6.5 | The Grid code combines transmission and distribution codes in an IT system with AI-enabled navigation and, document and workflow management tools. | Recruit people and set up project team. | Q1 2021-22 | Complete | Q2 2021-22 | Since commencing the project, FTE for the project team are now in place.
2 | A6.5 Work with all stakeholders to create a fully digitalised, whole system Grid Code by 2025 | D6.5 | The Grid code combines transmission and distribution codes in an IT system with AI-enabled navigation and, document and workflow management tools. | Scope detailed project work plan. | Q2 2021-22 | Complete | Q3 2021-22 | Project plan has been created and is regularly shared with the steering group. This will continue to evolve over the BP1 and BP2 periods as the scoping documents and areas of progression are more fully considered and developed by us and stakeholders.
2 | A6.5 Work with all stakeholders to create a fully digitalised, whole system Grid Code by 2025 | D6.5 | The Grid code combines transmission and distribution codes in an IT system with AI-enabled navigation and, document and workflow management tools. | Engage and consult industry to refine scope, in particular distribution stakeholders, on whole system Grid Code and digitalised capability. | Q4 2021-22 | Complete | Q4 2021-22 | Industry engagement at various forums since June 2021 was focussed on building awareness of the project and informed our Consultation 1. We have engaged with the Balancing and Settlement Code Panel, Ofgem (technical codes representatives), DNOs (bilateral meetings), Grid Code Review Panel, Grid Code Development Forum, Industry Technical Codes Group, The Association for Decentralised Energy Flexibility Forum, Flexible Generation Group, Major Energy Users' Council, Renewable UK’s Networks & Charging forum, BEIS and Distribution Code Users. Consultation 1’s aim was to gather views on the scope, objectives, and approach, and guide the formation of an industry-led governance structure for the project. Whilst Consultation 1 was open, there were 18 attendees across the 6 webinars we held to discuss the consultation and enable industry participants to ask questions and provide feedback. There were 25 Consultation 1 responses: 12 written, 8 verbal and 5 both written & verbal. Since inception, we have engaged with over 500 industry stakeholders at different forum, bilateral and project specific meetings. In line with stakeholder feedback, a steering group (with wide representation of industry) is in place to oversee and facilitate the progression of the digitalised Whole System Technical Code (WSTC) project with their 1st meeting on 15/12/21. It comprises; Distribution Code Parties, Grid Code Parties, DNOs, NGESO, IDNOs, Wider Industry, Consumer Groups, Trade Associations, Distribution Code Administrator, Grid Code Administrator, Offshore Transmission Owners, Onshore Transmission Owners, Ofgem(non-voting) and BEIS(non-voting) The Steering Group and ESO team have considered the consultation feedback and developed key areas for scoping. A key focus has been to deprioritise the consolidation element while the Energy Code Reform work is ongoing and try to realise the benefits of the digitalisation and simplification elements.
2 | A6.5 Work with all stakeholders to create a fully digitalised, whole system Grid Code by 2025 | D6.5 | The Grid code combines transmission and distribution codes in an IT system with AI-enabled navigation and, document and workflow management tools. | Go/No go decision on whole system digitalised Grid Code. | Q4 2021-22 | Complete | Q4 2021-22 | Go decision received for 7 of the workstreams that emerged from the consultation responses with further detail being agreed with the Steering Group. Scoping documents for these workstreams are currently under development and will feed into the next stages of work in 2022/23
2 | A6.5 Work with all stakeholders to create a fully digitalised, whole system Grid Code by 2025 | D6.5 | The Grid code combines transmission and distribution codes in an IT system with AI-enabled navigation and, document and workflow management tools. | First code modifications and licence changes initiated. | Q1 2022-23 | Delayed - External Reasons |  | We have descoped significant changes to the codes as a result of the WSTC in BP1, therefore this objective will not be met but has been overtaken by other priorities. This is in line with stakeholder feedback and expectations and is being guided by input from the external WSTC steering group.
2 | A6.5 Work with all stakeholders to create a fully digitalised, whole system Grid Code by 2025 | D6.5 | The Grid code combines transmission and distribution codes in an IT system with AI-enabled navigation and, document and workflow management tools. | Continue to deliver against detailed stakeholder-backed plan by raising and progressing code modifications and licence changes, and digitalising codes | Q2-Q4 2022-23 | Delayed - External Reasons |  | Next steps are for the steering group to develop and publish the project scope, objective and approach through the scoping documents. Due to the approach adopted by the steering group and the focus on digitalisation this will not lead to code modification proposals as first envisaged as part of the original plan. We will continue to work with stakeholders on the benefits of and timing for any Whole System Technical Code including engaging with Ofgem and DESNZ's Energy Code Reform programme, however, this milestone no longer appears valid due to this stakeholder led prioritisation activity.
2 | A6.6 Look at fully or partially fixing one or more components of Balancing Services Use of System (BSUoS) | D6.6 | Delivery of the recommendation from the BSUoS taskforce around reducing the volatility of BSUoS forecasting. This requires the collection of BSUoS to change from an arrangement in which charges are set after the costs have been incurred, to one whereby charges are set on the basis of an ESO forecast. | Continue the process to modify industry codes to allow for a fixed BSUoS price – including industry engagement, project implementation and ESO financing arrangements. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | The ESO has worked with industry to ensure the CUSC modifications are being progressed in good time. These are now with Ofgem concluding the ESO's involvement in the proposal and meeting this objective.
3 | A10.1 Support DNOs to develop NOA type assessment processes | D10.1 | NOA expertise shared with DNOs | Engage with ENA Open Networks work stream, to continue discussions with DNOs. | Q1-Q4 2021-22 | Complete | Q2 2022-23 | We are engaging with the DNOs through ongoing ENA Open Networks work, and we are actively looking at ways to enhance that relationship to provide a more proactive and collaborative SME support around CBAs and NOA-type assessments.
3 | A10.1 Support DNOs to develop NOA type assessment processes | D10.1 | NOA expertise shared with DNOs | Engage with DNOs to support them to develop NOA type proposals for the RIIO-ED2 business plans. | Q1 2021-22 | Complete | Q1 2021-22 | We are engaging with the DNOs through ongoing ENA Open Networks work, and we are actively looking at ways to enhance that relationship to provide a more proactive and collaborative SME support around CBAs and NOA-type assessments.
3 | A10.1 Support DNOs to develop NOA type assessment processes | D10.1 | NOA expertise shared with DNOs | Engage with DNOs on what support they want to develop NOA type proposals; develop support materials for DNOs as required on the existing NOA methodology. | Q1 2022-23 | Complete | Q2 2022-23 | We are engaging with the DNOs through ongoing ENA Open Networks work, and we are actively looking at ways to enhance that relationship to provide a more proactive and collaborative SME support around CBAs and NOA-type assessments.
3 | A10.1 Support DNOs to develop NOA type assessment processes | D10.1 | NOA expertise shared with DNOs | Continue to provide support to DNOs heading into the RIIO-ED2 period. | Q2-Q4 2022-23 | Complete | Q4 2022-23 | We are engaged with the DNOs through ENA Open Networks work, and have provided a more proactive and collaborative support around CBAs and NOA-type assessments. This included activities in Whole System CBA and the Common Evaluation Methodology tool.
3 | A11.1 Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Start Economic Assessment (EA) tool refresh. | Q1 2021-22 | Complete | Q1 2021-22 | We have gathered current and future requirements for a tool and have started a tender exercise in order to procure a solution (either from the existing provider, Afry, or another) that fulfils those requirements. Due to procurement timescales, completion will be in 2022-23.
3 | A11.1 Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Gather requirements and design / procure future EA tool. | Q2-Q3 2021-22 | Complete | Q1 2022-23 | Procurement has now completed.
3 | A11.1 Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Commence development and testing of EA tool. | Q4 2021-22 | Complete | Q1 2022-23 | Implementation of new EA tool now in progress
3 | A11.1 Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Continue development and testing of EA tool, including parallel working with existing tool. Given the complexity of the tool, seek independent analysis to provide assurance of the new model. | Q3 2022-23 | Delayed - Internal Reasons |  | Work is ongoing to deploy a new pan-European market dispatch model (economic assessment tool). Deployment at the standard we require has proven more challenging than first anticipated. This has led us to a phased approach with two of three phases (and associated work items) migrating on to the new tool within this financial year. The third is delayed with UAT and go-live continuing through Q1 2023-24.
3 | A11.2 Implement probabilistic modelling | D11.2 | Improved identification of network needs | Gather requirements and design Probabilistic Model (PM). | Q1 2021-22 | Complete | Q1 2021-22 | A proof of concept tool is in place and being used alongside network analysis for NOA7 to demonstrate capability for further integration. The Q2 2021-22 milestone has been re-planned to fit better with the cyclical NOA process.
3 | A11.2 Implement probabilistic modelling | D11.2 | Improved identification of network needs | Develop and test PM; Proof of Concept for a bespoke joint network and market tool for probabilistic thermal analysis. Proof of concept for integrating probabilistic network analysis into the NOA process. | Q2 2021-22 | Complete | Q4 2021-22 | A proof of concept tool is in place and being used alongside network analysis for NOA7 to demonstrate capability for further integration. The Q2 2021-22 milestone has been re-planned to fit better with the cyclical NOA process.
3 | A11.2 Implement probabilistic modelling | D11.2 | Improved identification of network needs | Data and analytics platform foundational architecture in place. | Q3 2022-23 | Complete | Q3 2022-23 | We have reviewed our specific tool development requirements and interface with DAP, we now conclude that this tool development does not rely on the DAP and it will progress independent of the DAP. This tool will be developed with built-in functionality to interface with DAP in the future if it's needed.
3 | A11.2 Implement probabilistic modelling | D11.2 | Improved identification of network needs | Implement PM. | Q4 2022-23 | Complete | Q4 2022-23 | We have developed, delivered, and tested the year-round probabilistic analysis tool (POUYA). We are now during warranty period. The solution relies on the Azure ML cloud platform enabling distributed optimization and multi-processing.
3 | A11.3 Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Start full Voltage Optimisation (VO) tool development. Dependent on the success of the innovation project we would look to start this work earlier. | Q4 2021-22 | Complete | Q4 2021-22 | Work on voltage optimisation tool started which completes the deliverable
3 | A11.3 Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Gather requirements and design VO tool. | Q1-Q2 2022-23 | Complete | Q3 2022-23 | The proof of concept testing for a voltage tool has been completed. We have developed upon and tested two tools and benchmarked results from the tools with the voltage pathfinder results. We have engaged with a range of stakeholders to identify key requirements to inform the next stage of full development of a Voltage Optimiser tool.
3 | A11.3 Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Data and analytics platform foundational architecture in place | Q3 2022-23 | Complete | Q3 2022-23 | We have reviewed our specific tool development requirements and interface with DAP, we now conclude that this tool development does not rely on the DAP and it will progress independent of the DAP. This tool will be developed with built-in functionality to interface with DAP in the future if it's needed.
3 | A11.3 Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Develop and test VO tool. | Q3-Q4 2022-23 | Complete | Q4 2022-23 | This milestone is following on from the Proof of Concepts for the development of a VO tool(already completed) and integrating year-round voltage analysis into NOA (Q4 2022/23). Now we have developed a prototype Voltage Optimiser tool which has been applied into some NOA studies as a test. The successful learning will be applied in our IT product development of Voltage tool in BP2.
3 | A11.3 Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Proof of concept for integrating year-round voltage analysis into the NOA process. | Q4 2022-23 | Complete | Q4 2022-23 | As part of this Proof of Concept (PoC), we developed and tested multiple case studies to assess how the economic analysis for year-round voltage needs will be undertaken to integrate into future NOA.
3 | A11.4 Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Work Package 3 completed: Trialling on Full GB Model. | Q1 2021-22 | Complete | Q4 2021-22 | Deliverables on the project have been rebased for delivery in January 2022. These are reduced in scale to account for difficulties applying the new application to our current models while still gaining value from the project.
3 | A11.4 Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Work Package 4 completed: Future Roadmap and Plan for implementation. | Q2 2021-22 | Complete | Q1 2022-23 | WP4 completed with paired back road map reflecting challenges within the project. As we continue with this workstream we will continue to evolve the road map.
3 | A11.4 Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Start-up phase for full Stability Assessment (SA) tool development. | Q2 2022-23 | Complete | Q2 2022-23 | Start-up phase complete. Following successful closure of the NIA Stability project with TNEI, we have started internal model testing that will support the subsequent Q3-Q4 milestone on gathering requirements for the full stability assessment tool.
3 | A11.4 Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Data and analytics platform foundational architecture in place. | Q3 2022-23 | Complete | Q3 2022-23 | We have reviewed our specific tool development requirements and interface with DAP, we now conclude that this tool development does not rely on the DAP and it will progress independent of the DAP. This tool will be developed with built-in functionality to interface with DAP in the future if it's needed.
3 | A11.4 Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Gather requirements and design SA tool. | Q3-Q4 2022-23 | Complete | Q4 2022-23 | We have collected the requirements initially via our NIA project. We have engaged with internal and external stakeholders to complete our requirements assessment. We have completed the initial engagement with IT project delivery and we are ready to start the project to design and test the SA tool from April 2023.
3 | A12.1 Scope project, building on the BEIS recommendations. A12.2 Identify solutions. A12.3 Implement changes to the SQSS. A12.3 Implement changes to the SQSS | D12.1 | SQSS updated to ensure it is designed to enable decarbonisation of the electricity system | Engage key stakeholders and initiate scope review. | Q1 2021-22 | Complete | Q1 2021-22 | Further engagement has been done in Q3 through Grid code development forum, DNO forum etc and the potential lists have been discussed further with different stakeholders, the draft list and modification plan have been presented to SQSS panel.
3 | A12.1 Scope project, building on the BEIS recommendations. A12.2 Identify solutions. A12.3 Implement changes to the SQSS. A12.3 Implement changes to the SQSS | D12.1 | SQSS updated to ensure it is designed to enable decarbonisation of the electricity system | Consult on SQSS Review scope, issues and options. | Q2 2021-22 | Complete | Q2 2021-22 | Further engagement has been done in Q3 through Grid code development forum, DNO forum etc and the potential lists have been discussed further with different stakeholders, the draft list and modification plan have been presented to SQSS panel.
3 | A12.1 Scope project, building on the BEIS recommendations. A12.2 Identify solutions. A12.3 Implement changes to the SQSS. A12.3 Implement changes to the SQSS | D12.1 | SQSS updated to ensure it is designed to enable decarbonisation of the electricity system | Engage stakeholders (including network companies) to co-create prioritised list of issues and action plan. | Q2-Q3 2021-22 | Complete | Q3 2021-22 | Further engagement has been done in Q3 through Grid code development forum, DNO forum etc and the potential lists have been discussed further with different stakeholders, the draft list and modification plan have been presented to SQSS panel.
3 | A12.1 Scope project, building on the BEIS recommendations. A12.2 Identify solutions. A12.3 Implement changes to the SQSS. A12.3 Implement changes to the SQSS | D12.1 | SQSS updated to ensure it is designed to enable decarbonisation of the electricity system | Publish prioritised list of issues to be addressed and action plan. Engage stakeholders. | Q4 2021-22 | Complete | Q4 2021-22 | Further engagement has been done in Q4, the final scope consultation document has been published and final report will be issued on time
3 | A12.1 Scope project, building on the BEIS recommendations. A12.2 Identify solutions. A12.3 Implement changes to the SQSS. A12.3 Implement changes to the SQSS | D12.1 | SQSS updated to ensure it is designed to enable decarbonisation of the electricity system | Publish plan for quick wins and initiate action if appropriate. | Q4 2021-22 | Complete | Q4 2021-22 | Further engagement has been done in Q3 through Grid code development forum, DNO forum etc and the potential lists have been discussed further with different stakeholders, the draft list and modification plan have been presented to SQSS panel.
3 | A12.1 Scope project, building on the BEIS recommendations. A12.2 Identify solutions. A12.3 Implement changes to the SQSS. A12.3 Implement changes to the SQSS | D12.1 | SQSS updated to ensure it is designed to enable decarbonisation of the electricity system | Milestones on delivery of quick wins and initiation of actions on broader topics are dependent on the outputs delivered in 2021/2022. | Q1-Q4 2022-23 | Delayed - Internal Reasons |  | Several workshops have been arranged for both demand connection criteria and offshore infeed review, the generation connection criteria modification is being prepared. Both offshore infeed review, the generation connection will need economic impact assessment on frequency response, the team are focusing on winter preparation so that the supports to SQSS modifications are not available in this year as originally planned, as a result the work is more likely to be completed in 2023-2024
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Winter Review | Q1 2021-22 | Complete | Q1 2021-22 | Winter Review document was published on ESO website on 24 June.
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | FES Call for Evidence | Q2 2021-22 | Complete | Q2 2021-22 | FES Call for Evidence published September 2021
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | FES Launch | Q2 2021-22 | Complete | Q2 2021-22 | The FES was published on ESO website on 12th July
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | FES Network Forum (this is a new initiative) | Q2-Q3 2021-22 | Complete | Q3 2021-22 | Winter Review document was published on ESO website on 24 June. The FES was published on ESO website on 12 July The Winter Outlook was published on 7 October FES Network forum has been hosted every 2 months providing valuable two-way feedback between the ESO and network companies
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | FES Stakeholder Feedback Document | Q4 2021-22 | Complete | Q4 2021-22 | We published the Ofgem approved stakeholder feedback document on the website at the beginning of March.
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Winter Outlook | Q3 2021-22 | Complete | Q3 2021-22 | The Winter Outlook was published on 7th October
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Summer Outlook | Q4 2021-22 | Complete | Q4 2021-22 | The Summer Outlook was published on 14th April
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Winter Review | Q1 2022-23 | Complete | Q1 2022-23 | Document published on ESO website on 21/06/22
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | FES Call for Evidence | Q2 2022-23 | Complete | Q2 2022-23 | Complete
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | FES Launch | Q2 2022-23 | Complete | Q2 2022-23 | Future Energy Scenarios were published in July 22
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | FES Network Forum | Q2-Q3 2022-23 | Complete | Q3 2022-23 | Network forum to continue to meet regularly
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | FES Stakeholder Feedback Document | Q3 2022-23 | Complete | Q3 2022-23 | The FES Stakeholder Feedback document has been published and provided to Ofgem as per licence requirement
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Winter Outlook | Q3 2022-23 | Complete | Q3 2022-23 | Winter Outlook Report published on 6 Oct 2022
3 | A13.1 Carry out analysis and scenario modelling on future energy demand & supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Summer Outlook | Q4 2022-23 | Complete | Q4 2022-23 | The 2023 Summer Outlook will be published in April 2023
3 | A13.2 Conduct mathematical and modelling and market research on local and wider geographic demand information | D13.2 | Created pan-European and country level electricity and energy demand models | Work with ENTSO-E to collate the latest European “Ten Year Network Development Plan” (TYNDP) 2020 scenarios, cleanse the data, and incorporate the resulting data in to our pan-European dispatch model. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | We have developed two new European scenarios out to 2050 that are now included within our pan-European market dispatch model, as used in FES and NOA. Both new scenarios are compatible with the EU's new net zero targets and therefore represent a more accurate forecast for our interconnected markets than the data they replace.
3 | A13.2 Conduct mathematical and modelling and market research on local and wider geographic demand information | D13.2 | Created pan-European and country level electricity and energy demand models | As the TYNDP is only published every 2 years, we would use this year to gather updates from key neighbouring TSOs and to update these in our pan-European dispatch model. This will help us keep in sync with any net zero policy changes occurring in the EU without having to wait for the next TYNDP cycle. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | yes we have received the data and will be fully signed off and in our database before the end of March
3 | A13.3 Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Develop a communication strategy aligned to target audiences. Create future energy insights content to share through selected channels. | Q1 2021-22 | Complete | Q1 2021-22 | This refers to the Comms strategy for the FES 2021 publication and launch events and beyond (e.g. Bridging the Gap). The FES launch took place w/c 12 July and all elements connected to that are complete (i.e. we sent out an FAQ document as usual as well as more podcasts and a thought piece on regionalisation of heat). It includes future stakeholder engagement activities such as call for evidence (now closed), workshops and bilateral meetings as well as provisions of information (e.g. thought-pieces and related ESO work in the FES Newsletter as well as supporting info such as blogs and podcasts).
3 | A13.3 Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Future Energy Scenarios Publication and Launch Events; Introduce Bridging the gap topic and invite core stakeholders to co-creation events. | Q2 2021-22 | Complete | Q2 2021-22 | This refers to the Comms strategy for the FES 2021 publication and launch events and beyond (e.g. Bridging the Gap). The FES launch took place w/c 12 July and all elements connected to that are complete (i.e. we sent out an FAQ document as usual as well as more podcasts and a thought piece on regionalisation of heat). It includes future stakeholder engagement activities such as call for evidence (now closed), workshops and bilateral meetings as well as provisions of information (e.g. thought-pieces and related ESO work in the FES Newsletter as well as supporting info such as blogs and podcasts).
3 | A13.3 Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Future Energy Scenarios Call for evidence, workshops and bilateral meetings; Bridging the gap stakeholder events | Q3 2021-22 | Complete | Q3 2021-22 | This refers to the Comms strategy for the FES 2021 publication and launch events and beyond (e.g. Bridging the Gap). The FES launch took place w/c 12 July and all elements connected to that are complete (i.e. we sent out an FAQ document as usual as well as more podcasts and a thought piece on regionalisation of heat). It includes future stakeholder engagement activities such as call for evidence (now closed), workshops and bilateral meetings as well as provisions of information (e.g. thought-pieces and related ESO work in the FES Newsletter as well as supporting info such as blogs and podcasts).
3 | A13.3 Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Future Energy Scenarios Bilateral meetings; Bridging the gap report launch Annual FES activities comprise continuous engagement with stakeholders throughout the year. Communication is managed via various communication channels such as: email, FES newsletter, Social media, FES website and the ESO website. | Q4 2021-22 | Complete | Q4 2021-22 | Significant amounts of stakeholder engagement have been carried out (e.g. Call for Evidence, forums and bilaterals) in addition to the insights that we shared during and post-launch. Engagement is still ongoing as we are keen to make it more of an all-year-round activity.
3 | A13.3 Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication and Launch Events | Q2 2022-23 | Complete | Q2 2022-23 | Publication and launch have been completed for the FES 22 cycle. Due to record temperatures the initial launch event was moved to a virtual event. The following 'Deep Dive' sessions changed focus this year to be based around the Key Messages.
3 | A13.3 Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Call for evidence, workshops and bilateral meetings | Q3 2022-23 | Complete | Q3 2022-23 | The call for evidence is completed and we have completed the majority of bilaterals. Stats on engagement remain in line with last year. Table topic talks now also complete with great feedback. analysis now underway on the back of the stakeholder feedback. engagement continues as we test some of our assumptions and analysis with key stakeholders. all milestones and key deliverables complete. general engagement, as always, will continue throughout the year based on our needs and those of our stakeholders.
3 | A13.3 Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Bilateral meetings | Q4 2022-23 | Complete | Q4 2022-23 | complete - analysis following bilaterals now underway
3 | A13.4 FES: Bridging the gap to net zero | D13.4 | This work draws from each annual FES publication, and the engagement activity referenced in A13.3 above, to provide insights and analysis beyond FES. We look to ensure that we are examining topics of relevance to our stakeholders which can inform energy policy development and the strategic thinking of our customers and stakeholders | Establish broad industry engagement and interactive collaborative spaces | Q3 2021-22 | Complete | Q3 2021-22 | Bridging the Gap 22 will be published in March 22. External stakeholder engagement has been completed and we're currently writing up our findings and recommendations.
3 | A13.4 FES: Bridging the gap to net zero | D13.4 | This work draws from each annual FES publication, and the engagement activity referenced in A13.3 above, to provide insights and analysis beyond FES. We look to ensure that we are examining topics of relevance to our stakeholders which can inform energy policy development and the strategic thinking of our customers and stakeholders | Publish focused and extensive whole energy system report | Q4 2021-22 | Complete | Q4 2021-22 | Bridging the Gap 22 was published on 16th March 2022. The final project incorporates two elements - a report describing a day in the life of the 2035, fully decarbonised electricity system and a timeline of actions needed in order to make this system a reality.
3 | A13.4 FES: Bridging the gap to net zero | D13.4 | This work draws from each annual FES publication, and the engagement activity referenced in A13.3 above, to provide insights and analysis beyond FES. We look to ensure that we are examining topics of relevance to our stakeholders which can inform energy policy development and the strategic thinking of our customers and stakeholders | Establish broad industry engagement and interactive collaborative spaces | Q3 2022-23 | Complete | Q3 2022-23 | External engagement was undertaken in November with in person and online workshops. Over 40 organisations took part and positive feedback was received.
3 | A13.4 FES: Bridging the gap to net zero | D13.4 | This work draws from each annual FES publication, and the engagement activity referenced in A13.3 above, to provide insights and analysis beyond FES. We look to ensure that we are examining topics of relevance to our stakeholders which can inform energy policy development and the strategic thinking of our customers and stakeholders | Publish focused and extensive whole energy system report | Q4 2022-23 | Complete | Q4 2022-23 | Bridging the Gap report published with associated webinar on 8th March. Presented to 150 attendees across industry in the webinar. Also received positive NPS score for recommending Bridging the Gap (+26) and sought feedback on how to iterate Bridging the Gap into 2023-24
3 | A13.5 FES: Integrating with other networks and supporting DNOs to develop their own DFES processes. FES: Integrating with other networks and supporting DNOs to develop their own Distribution FES (DFES) processes. | D13.5.1 | Working with DNOs to understand what information we need to share to support development of DFES and ED-2 submissions Working with DNOs to understand what information we need to share to support development of DFES and RIIO -ED2 submissions | Completed ESO electricity demand modelling requirements gathering and design work. Bring DNO data into the process (enhanced building blocks information as a result of a DCUSA modification) to compare with national data in order to inform discussions on how we can support DNOs to develop their own regional DFES (and inform ESO FES each year). | Q2 2021-22 | Complete | Q2 2021-22 | "“We have been working with the DNOs to ensure that their Embedded Capacity Registers can be used as the main input data to our embedded generation forecast within the Future Energy Scenarios. This will ensure that we are aligned with the networks and their DFES publications within this aspect of the analysis.” • DCUSA modification has improved the ECR data which has been reflected in the DNO’s electricity supply building blocks, which we have used in our embedded generation process • We have agreed and published a second set of building blocks alongside FES this year • We completed work with the building blocks as part of the ETYS spatial process, aligning baseline data • We have raised at the ENA FES / DFES group that we want to further work on alignment of building blocks starting with confirming year 0 is aligned then comparing building blocks data for later years and agreeing as a collective areas of focus to address differences and timescales to close gaps ready for input into GB FES and DFES. • We have engaged with the DNOs on regional FES and what they would like to see from further regionalisation of the FES and how it will feed into DFES and ED2 business plan. We are using the engagement to help shape the outcomes.
3 | A13.5 FES: Integrating with other networks and supporting DNOs to develop their own DFES processes. FES: Integrating with other networks and supporting DNOs to develop their own Distribution FES (DFES) processes. | D13.5.1 | Working with DNOs to understand what information we need to share to support development of DFES and ED-2 submissions Working with DNOs to understand what information we need to share to support development of DFES and RIIO -ED2 submissions | Engage with DNOs and provide input to RIIO-ED2 business plans. | Q3 2021-22 | Complete | Q3 2021-22 | "“We have been working with the DNOs to ensure that their Embedded Capacity Registers can be used as the main input data to our embedded generation forecast within the Future Energy Scenarios. This will ensure that we are aligned with the networks and their DFES publications within this aspect of the analysis.” • DCUSA modification has improved the ECR data which has been reflected in the DNO’s electricity supply building blocks, which we have used in our embedded generation process • We have agreed and published a second set of building blocks alongside FES this year • We completed work with the building blocks as part of the ETYS spatial process, aligning baseline data • We have raised at the ENA FES / DFES group that we want to further work on alignment of building blocks starting with confirming year 0 is aligned then comparing building blocks data for later years and agreeing as a collective areas of focus to address differences and timescales to close gaps ready for input into GB FES and DFES. • We have engaged with the DNOs on regional FES and what they would like to see from further regionalisation of the FES and how it will feed into DFES and ED2 business plan. We are using the engagement to help shape the outcomes.
3 | A13.5 FES: Integrating with other networks and supporting DNOs to develop their own DFES processes. FES: Integrating with other networks and supporting DNOs to develop their own Distribution FES (DFES) processes. | D13.5.1 | Working with DNOs to understand what information we need to share to support development of DFES and ED-2 submissions Working with DNOs to understand what information we need to share to support development of DFES and RIIO -ED2 submissions | Share FES building block data with industry parties and engage with stakeholders; Develop and share data reports and insights (with DNOs) to further develop our regional assumptions | Q2 2022-23 | Complete | Q2 2022-23 | Latest iteration of building blocks shared with the DNOs alongside the FES publication. These have also been published on our website and shared with industry. We will be meeting with the DNOs and continuing work to identify areas for alignment with the Embedded Capacity Registers, GSP definitions and aligning the baseline as focus areas. This has been agreed with the DNOs through the ENA Open Networks work
3 | A13.5 FES: Integrating with other networks and supporting DNOs to develop their own DFES processes. FES: Integrating with other networks and supporting DNOs to develop their own Distribution FES (DFES) processes. | D13.5.2 | Developed new energy demand model – this brings together all energy demand data in one place | Completed review of available energy data and established stakeholder modelling requirements | Q3 2021-22 | Complete | Q3 2021-22 | Review of requirements has been completed and information on data that we currently use or could use has been gathered. We have asked for suggestions for other data sources in the Call For Evidence. We have spoken to other network companies in the Network Forum. "Voice of the customer" interviews covering requirements of our FES modelling have been conducted by Accenture.
3 | A13.5 FES: Integrating with other networks and supporting DNOs to develop their own DFES processes. FES: Integrating with other networks and supporting DNOs to develop their own Distribution FES (DFES) processes. | D13.5.2 | Developed new energy demand model – this brings together all energy demand data in one place | Developed energy demand model plan, including pilots and full-scale development. | Q1 2022-23 | Delayed - Internal Reasons |  | We are focussing on integrating our new dispatch model within the FES processes which will enhance our abilities model key aspects of flexibility within the energy sector and ensuring that the models we have align with strategic priorities, such as FSO and ETNPR outcomes. As a result this milestone will not now be delivered within BP1.
3 | A13.5 FES: Integrating with other networks and supporting DNOs to develop their own DFES processes. FES: Integrating with other networks and supporting DNOs to develop their own Distribution FES (DFES) processes. | D13.5.2 | Developed new energy demand model – this brings together all energy demand data in one place | Built, tested and validated model. | Q3 2022-23 | Delayed - Internal Reasons |  | We are focussing on integrating our new dispatch model within the FES processes which will enhance our abilities model key aspects of flexibility within the energy sector and ensuring that the models we have align with strategic priorities, such as FSO and ETNPR outcomes. As a result this milestone will not now be delivered within BP1.
3 | A13.5 FES: Integrating with other networks and supporting DNOs to develop their own DFES processes. FES: Integrating with other networks and supporting DNOs to develop their own Distribution FES (DFES) processes. | D13.5.2 | Developed new energy demand model – this brings together all energy demand data in one place | Implemented model. | Q4 2022-23 | Delayed - Internal Reasons |  | We are focussing on integrating our new dispatch model within the FES processes which will enhance our abilities model key aspects of flexibility within the energy sector and ensuring that the models we have align with strategic priorities, such as FSO and ETNPR outcomes. As a result this milestone will not now be delivered within BP1.
3 | A14.1 Provide contractual expertise and management of connection contracts including provision of connection offers to customers | D14.1.1 | Managing an increasing volume of connection offers for customers (with technical support provided via activity A15. | As required | N/A | Complete | Q4 2022-23 | This is an ongoing business-as-usual activity
3 | A14.1 Provide contractual expertise and management of connection contracts including provision of connection offers to customers | D14.1.2 | Contract management of connection agreements | As required | N/A | Complete | Q4 2022-23 | This is an ongoing business-as-usual activity
3 | A14.2 Ensure Grid Code compliance of new connections | D14.2.1 | Compliance monitoring of new connections in accordance with Grid Code provisions | As required | N/A | Complete | Q4 2022-23 | This is an ongoing business-as-usual activity
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function – this is to support smaller parties, who are not our direct customers and who may have transmission-related issues with their connection applications. The type of support we can provide includes information about system charges and securities, commercial opportunities in system services, contractual / code arrangements and the works required to facilitate their connection | Review DER internal processes; engage customers and foster closer working relationships with DNOs on the scope of the new proposed DER function. | Q1 2021-22 | Complete | Q3 2021-22 | "New Customer Connections Team structure now in use as from beginning of September to enable just one team to interact with DNOs; GB Demand Team Manager and team members continue to work closely with ESO WES Team, DNO and DSO Teams to look at improvements - continuous activity'; GB Demand team supporting delivery of RDPs and new steering groups set with DNOs; GB Demand Team supporting Connections Reform Project; GB Demand team continue to work with DNOs on enduring basis to improve process and engagement; Team continues to grow in line with the forecast
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function – this is to support smaller parties, who are not our direct customers and who may have transmission-related issues with their connection applications. The type of support we can provide includes information about system charges and securities, commercial opportunities in system services, contractual / code arrangements and the works required to facilitate their connection | Establish DER management function (through appropriate training); engage with customers on the new function and identify any additional areas of potential support required. | Q2 2021-22 | Complete | Q2 2021-22 | "New Customer Connections Team structure now in use as from beginning of September to enable just one team to interact with DNOs; Next step is to interact further with Following the setup of the new GB Demand Team engagement with DNOs and customers has begun. Internal engagement with the Whole System team is also an ongoing activity. The first DNO / DER specific Customer Seminar was held in July 2022; Feedback gained from from stakeholders at this event will drive process / service improvements. GB Team Demand Manager has started to attend meetings with DNOs already held by Whole System Team and other steering meetings have been set up to act as escalation or setting direction Webinars have been held with industry to explain Appendix G process; ESO Connections Team is supporting DNO Webinars; GB Demand team are supporting GB Connections Reform Process and ENA Strategic Connections Group Team continue to grow in line with the FTE forecast for BP2
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function – this is to support smaller parties, who are not our direct customers and who may have transmission-related issues with their connection applications. The type of support we can provide includes information about system charges and securities, commercial opportunities in system services, contractual / code arrangements and the works required to facilitate their connection | Request feedback from customers and DNOs. | Q4 2021-22 | Complete | Q4 2022-23 | Following the setup of the new GB Demand Team engagement with DNOs and customers has begun. Internal engagement with the Whole System team is also an ongoing activity. The first DNO / DER specific Customer Seminar was held in July 2022; Feedback gained from from stakeholders at this event will drive process / service improvements. GB Team Demand Manager has started to attend meetings with DNOs already held by Whole System Team and other steering meetings have been set up to act as escalation or setting direction Webinars have been held with industry to explain Appendix G process; ESO Connections Team is supporting DNO Webinars; GB Demand team are supporting GB Connections Reform Process and ENA Strategic Connections Group
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function – this is to support smaller parties, who are not our direct customers and who may have transmission-related issues with their connection applications. The type of support we can provide includes information about system charges and securities, commercial opportunities in system services, contractual / code arrangements and the works required to facilitate their connection | Continue to deliver the DER function and make improvements to the service delivered in line with customer feedback. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | GB Demand Team established; Whole systems focus via seminars, bilateral engagement, working with whole electricity systems team; Support to RDPs and working with ENA; Growth of the team to match volume of work and growth support for BP2
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties. | D14.3.2 | Deliver first whole electricity system connections seminar – these seminars will incorporate DNO input in addition to existing involvement from the TOs to the customer seminars that we already offer to customers. | Engage with DNOs on new approach to forthcoming seminar. | Q4 2021-22 | Complete | Q4 2022-23 | The first DNO / DER specific Customer Seminar was held in July 2022; Feedback gained from from stakeholders at this event will drive process / service improvements. Seminars focused on DNO and whole system will be a feature of the connections teams seminar yearly programme.
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties. | D14.3.2 | Deliver first whole electricity system connections seminar – these seminars will incorporate DNO input in addition to existing involvement from the TOs to the customer seminars that we already offer to customers. | Prepare and plan for whole system seminar; engage DNOs and TOs on approach and content. | Q1 2022-23 | Complete | Q2 2022-23 | Following the setup of the new GB Demand Team engagement with DNOs and customers has begun. Internal engagement with the Whole System team is also an ongoing activity. The first DNO / DER specific Customer Seminar to be held in July 2022; Feedback gained from from stakeholders at this event will drive process / service improvements. We shall be delivering more seminars such as this in coming years as the feedback from attendees was positive, 4.5 out of 5.
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties. | D14.3.2 | Deliver first whole electricity system connections seminar – these seminars will incorporate DNO input in addition to existing involvement from the TOs to the customer seminars that we already offer to customers. | Engage TOs and DNOs on seminar preparation and content; deliver first whole system seminar. | Q2 2022-23 | Complete | Q4 2022-23 | First whole system / DNO seminar was held on the 20th of July 2022. Seminars focused on DNO and whole system will be a feature of the connections teams seminar yearly programme. Feedback from the event was 4.5 out of 5, thus supporting the value of holding this event.
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties. | D14.3.2 | Deliver first whole electricity system connections seminar – these seminars will incorporate DNO input in addition to existing involvement from the TOs to the customer seminars that we already offer to customers. | Gather and process feedback on seminar. | Q3 2022-23 | Complete | Q4 2022-23 | All the feedback from the Seminars held in 2023 has been processed and also shared back with Customers via Connections Agora webinar; ESO Seminars for 2023 will be focused on tactical initiatives, connections reform project, connections portal and whole system to enable overview of our engagement with DNOs and projects delivered such as RDPs ESO Connections team are now also supporting DNO webinars
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties. | D14.3.3 | Whole electricity system connection seminars on an ongoing basis having delivered the first one in the previous deliverable. | Engage with DNOs on new approach to the first whole system seminar. | Q4 2021-22 | Complete | Q2 2022-23 | Following the setup of the new GB Demand Team engagement with DNOs and customers has begun. Internal engagement with the Whole System team is also an ongoing activity. The first DNO / DER specific Customer Seminar to be held in July 2022; Feedback gained from from stakeholders at this event will drive process / service improvements. GB Team Demand Manager has started to attend meetings with DNOs already held by Whole System Team.
3 | A14.3 Further enhance the customer connection experience, including broader support for smaller parties. | D14.3.3 | Whole electricity system connection seminars on an ongoing basis having delivered the first one in the previous deliverable. | Refine seminar planning and engagement process from first seminar; deliver second whole system seminar. | Q4 2022-23 | Complete | Q4 2022-23 | The first DNO / DER specific Customer Seminar was held in July 2022; Feedback gained from from stakeholders at this event will drive process / service improvements. GB Team Demand Manager has started to attend meetings with DNOs already held by Whole System Team and other steering meetings have been set up to act as escalation or setting direction Webinars have been held with industry to explain Appendix G process; ESO Connections Team is supporting DNO Webinars; GB Demand team are supporting GB Connections Reform Process and ENA Strategic Connections Group
3 | A14.4 Facilitate development of the customer connections hub | D14.4.1 | Implement first phase of the ESO connections hub, including online account management and integration with other network organisation websites | Commence project start up; engage the TOs on their portal proposals | Q1 2021-22 | Complete | Q1 2021-22 | Workshop sessions have been held with DNOs to obtain insight on their needs and requirements, which has been factored into the design assumptions. During the design and development phase, we learned that the build of the new portal was more complex than originally anticipated, and reviewed its level of functionality to ensure that the final product will meet our customers' needs and expectations. This had an impact on the delivery date for the phase 1 of the Customer Portal. Development and testing is currently underway, with the initial release of the portal now anticipated in July 2022. The customer focus group and overall stakeholder engagement will take place continuously between January and September 2022. We will engage with customers during the first stage of delivery in July, so we can take the opportunity to undertake any fixes or enhancement to the portal to complete phase 1 delivery in September 2022. Following this, any updates identified by stakeholders post implementation will be reviewed and implemented where possible, using an Agile process.
3 | A14.4 Facilitate development of the customer connections hub | D14.4.1 | Implement first phase of the ESO connections hub, including online account management and integration with other network organisation websites | Conduct work on requirements & design; engage with key stakeholders, the ENA and TOs on scope of Phase 1. | Q2 2021-22 | Complete | Q2 2021-22 | Workshop sessions have been held with DNOs to obtain insight on their needs and requirements, which has been factored into the design assumptions. During the design and development phase, we learned that the build of the new portal was more complex than originally anticipated, and reviewed its level of functionality to ensure that the final product will meet our customers' needs and expectations. This had an impact on the delivery date for the phase 1 of the Customer Portal. Development and testing is currently underway, with the initial release of the portal now anticipated in July 2022. The customer focus group and overall stakeholder engagement will take place continuously between January and September 2022. We will engage with customers during the first stage of delivery in July, so we can take the opportunity to undertake any fixes or enhancement to the portal to complete phase 1 delivery in September 2022. Following this, any updates identified by stakeholders post implementation will be reviewed and implemented where possible, using an Agile process.
3 | A14.4 Facilitate development of the customer connections hub | D14.4.1 | Implement first phase of the ESO connections hub, including online account management and integration with other network organisation websites | Develop & test NGESO portal; establish a customer focus group for testing & engage TOs to align with their portals. | Q3 2021-22 | Complete | Q3 2021-22 | Customer Focus group now established. First show an tell session has taken place and customer feedback on functionality is being gathered. Customer feedback will be used to inform the development of the portal for the July release and future releases.
3 | A14.4 Facilitate development of the customer connections hub | D14.4.1 | Implement first phase of the ESO connections hub, including online account management and integration with other network organisation websites | Implementation; check in with key stakeholders | Q4 2021-22 | Complete | Q4 2022-23 | Workshop sessions have been held with customers and TOs to obtain insight on their needs and requirements, which has been factored into the design assumptions. During the design and development phase, we learned that the build of the new portal was more complex than originally anticipated, and reviewed its level of functionality to ensure that the final product will meet our customers' needs and expectations. This had an impact on the delivery date for the phase 1 of the Customer Portal. Development and testing is currently underway, with the initial release of the portal now anticipated in January and March 2023. The customer focus group and overall stakeholder engagement will take place continuously between now and the planned release date. Following this, any updates identified by stakeholders post implementation will be reviewed and implemented where possible, using an Agile process.
3 | A14.4 Facilitate development of the customer connections hub | D14.4.1 | Implement first phase of the ESO connections hub, including online account management and integration with other network organisation websites | Further development & testing; engage with customer focus group and TOs. | Q1 2022-23 | Complete | Q4 2022-23 | This is a continuous activity following release of the portal. Now the customer focus group has been setup, engagement will be continuous throughout project delivery. Each chunk of functionality will be reviewed and tested by the focus group with comments fed back into the development process. Development, testing and engagement will be an ongoing activity into FY22/23.
3 | A14.4 Facilitate development of the customer connections hub | D14.4.1 | Implement first phase of the ESO connections hub, including online account management and integration with other network organisation websites | Implementation of updates to NGESO portal. | Q2 2022-23 | Complete | Q4 2022-23 | This is a BP2 Deliverable - Dates for future releases of the portal past March 2023 have yet to be identified. The plan is to continually build on the base functionality with numerous further releases in FY 2023/24. Stakeholder comments will feed in heavily to the additional functionality within these releases.
3 | A14.4 Facilitate development of the customer connections hub | D14.4.1 | Implement first phase of the ESO connections hub, including online account management and integration with other network organisation websites | Further development & testing; engage with customer focus group and TOs to further align with their portals. | Q3 2022-23 | Complete | Q4 2022-23 | Dates for future releases of the portal past December 2022 have yet to be identified. The plan is to continually build on the base functionality with numerous further releases in FY 2022/23. Stakeholder comments will feed in heavily to the additional functionality within these releases. Update - Phase 1 Portal was released on the 13th of March;
3 | A14.4 Facilitate development of the customer connections hub | D14.4.1 | Implement first phase of the ESO connections hub, including online account management and integration with other network organisation websites | Implementation of phase 1 of the connections hub. | Q4 2022-23 | Complete | Q4 2022-23 | Workshop sessions have been held with customers and TOs to obtain insight on their needs and requirements, which has been factored into the design assumptions. During the design and development phase, we learned that the build of the new portal was more complex than originally anticipated, and reviewed its level of functionality to ensure that the final product will meet our customers' needs and expectations. This had an impact on the delivery date for the phase 1 of the Customer Portal. Development and testing is currently underway, with the initial release of the portal now anticipated in January and March 2023. The customer focus group and overall stakeholder engagement will take place continuously between now and the planned release date. Following this, any updates identified by stakeholders post implementation will be reviewed and implemented where possible, using an Agile process. Update 13th March 2023: As planned, Phase 1 of the Portal was successfully released today
3 | A14.4 Facilitate development of the customer connections hub | D14.4.2 | Phase 2 of the connections hub concluded | N/A – activity does not commence until BP2. | N/A | Complete | Q4 2022-23 | This activity does not commence until BP2.
3 | A15.1 Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues. | D15.1.1 | System Operability Framework (SOF) documentation – to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications to a schedule in response to real time system operation events or other system developments. These currently include: Low Demand- Lessons from COVID19 and implications for future operability. Impact of future system trends on Power Quality. National System Performance Trend and Insights. Undertake improvements to these publications in accordance with stakeholder feedback and/or the ESO internal publication review | Q1-Q4 2021-22 | Complete | Q2 2022-23 | Publications on 3 topics have been planned for the 2021-22 year.
3 | A15.1 Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues. | D15.1.2 | Innovation projects developing new operability solutions – undertake innovation projects, as appropriate, to test operability solutions | Deliver system operability publications to a schedule in response to real time system operation events or other system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to these publications in accordance with stakeholder feedback and/or the ESO internal publication review. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | New research project strength to connect and Data-Driven Online Monitoring and Early Warning For System Stability have been initiated and SOF publication on Operability Strategy Report is published and system strength and power quality are being progressed
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.1 | Review the Connections and Infrastructure Options Note (CION) process: Drive improvements to the CION that encourage coordination | Full CION review complete. Stakeholders engaged in the process and conclusions published. Process designed, with a process map published, to carry out single CION assessments for specific geographical regions. | Q1 - Q4 2021-22 | Milestone no longer valid |  | Since proposing these deliverables the Offshore Transmission Network Review has progressed significantly and our deliverables have changed as a result. In the shorter term (in line with the DESNZ/Ofgem set Terms of Reference) the Holistic Network Design process in the Pathway to 2030 workstream has replaced the traditional CION process for in-scope projects. In the longer term we will aim to develop a new coordinated offshore connection offer process, to enable the agreed future framework, and ensure it has the appropriate level of formalisation. This will come out of decisions on the back of DESNZ's September 2021 Enduring Regime consultation and any subsequent consultations and policy developments. In September 2021 we published an open letter to offshore developers setting out that this is the case.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.1 | Review the Connections and Infrastructure Options Note (CION) process: Drive improvements to the CION that encourage coordination | New CION process developed that will work for coordinated offshore projects. Revised CION becomes BAU. The process is more efficient with greater collaboration and communication between parties. Evidenced through positive customer feedback. | Q1-Q4 2022-23 | Milestone no longer valid |  | Since proposing these deliverables the Offshore Transmission Network Review has progressed significantly and our deliverables have changed as a result. In the shorter term (in line with the DESNZ/Ofgem set Terms of Reference) the Holistic Network Design process in the Pathway to 2030 workstream has replaced the traditional CION process for in-scope projects. In the longer term we will aim to develop a new coordinated offshore connection offer process, to enable the agreed future framework, and ensure it has the appropriate level of formalisation. This will come out of decisions on the back of DESNZ's September 2021 Enduring Regime consultation and any subsequent consultations and policy developments. In September 2021 we published an open letter to offshore developers setting out that this is the case.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.2 | Review the Connections and Infrastructure Options Note (CION) process: Drive improvements to the CION that encourage coordination | Taking the outputs from D15.10.1, a formal process developed for CION assessments and the resulting connection offers. Where the review in D15.10.1 concludes to codify the CION within CUSC, Code modification is drafted and raised through formal governance. | Q1 - Q4 2021-22 | Milestone no longer valid |  | Since proposing these deliverables the Offshore Transmission Network Review has progressed significantly and our deliverables have changed as a result. In the shorter term (in line with the DESNZ/Ofgem set Terms of Reference) the Holistic Network Design process in the Pathway to 2030 workstream has replaced the traditional CION process for in-scope projects. In the longer term we will aim to develop a new coordinated offshore connection offer process, to enable the agreed future framework, and ensure it has the appropriate level of formalisation. This will come out of decisions on the back of DESNZ's September 2021 Enduring Regime consultation and any subsequent consultations and policy developments. In September 2021 we published an open letter to offshore developers setting out that this is the case.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.2 | Review the Connections and Infrastructure Options Note (CION) process: Drive improvements to the CION that encourage coordination | Review the success of any projects going through the process and refine as appropriate. | Q1-Q4 2022-23 | Milestone no longer valid |  | Since proposing these deliverables the Offshore Transmission Network Review has progressed significantly and our deliverables have changed as a result. In the shorter term (in line with the DESNZ/Ofgem set Terms of Reference) the Holistic Network Design process in the Pathway to 2030 workstream has replaced the traditional CION process for in-scope projects. In the longer term we will aim to develop a new coordinated offshore connection offer process, to enable the agreed future framework, and ensure it has the appropriate level of formalisation. This will come out of decisions on the back of DESNZ's September 2021 Enduring Regime consultation and any subsequent consultations and policy developments. In September 2021 we published an open letter to offshore developers setting out that this is the case.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.3 | Package or coordinate connection offers: Investigate, in conjunction with The Crown Estate and Crown Estate Scotland, whether it would be possible to package a connection offer with the seabed lease agreement to encourage greater coordination. This would focus connection applications on a specific time window as far as possible and would therefore also potentially facilitate the management of applications as a group. | Scope for deliverable is agreed with key stakeholders; Work is progressed in line with scope. Agreement on whether it is possible to award seabed leases that have connection agreements attached. Through engagement with Crown Estates and wind farm developers determine whether a packaged seabed lease and relevant connection agreement are key milestones that would enable a more coordinated approach. Identify corresponding pre-requisites for Crown Estates to change their relevant processes. | Q1 - Q4 2021-22 | Delayed - External Reasons |  | The milestones were developed before the OTNR was initiated and they became dependent on the Enduring Regime/Future Framework direction, hence we haven’t completed them in the originally proposed timescales. The decision on the DESNZ Future Frameworks consultation remains unpublished and offshore wind connections are now also being considered as part of our broader Connections Reform project. Therefore, once DESNZ have published their Future Frameworks decision and once our Connections Reform project has made its final recommendations, we can agree an implementation plan with Crown Estate Scotland and The Crown Estate in respect of any necessary process changes to better co-ordinate future seabed leasing rounds and the future connections process. Once necessary process changes have been identified we can agree an action plan with those parties (and others) and deliver against it, but this cannot be done prior to the future frameworks and connections reform outputs being known in respect of any future offshore wind connections. In the short term we have already made significant improvements to seabed leasing and connection process co-ordination by working with The Crown Estate to better co-ordinate the Celtic Sea leasing round development process with the HNDFUE. We are also in discussion with Marine Scotland and Crown Estate Scotland in relation to the INTOG leasing round and its potential interactions with the HNDFUE.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.3 | Package or coordinate connection offers: Investigate, in conjunction with The Crown Estate and Crown Estate Scotland, whether it would be possible to package a connection offer with the seabed lease agreement to encourage greater coordination. This would focus connection applications on a specific time window as far as possible and would therefore also potentially facilitate the management of applications as a group. | If agreed to proceed, a combined leasing and connection offer process designed ready for implementation in the next leasing round. | Q1-Q4 2022-23 | Delayed - External Reasons |  | The milestones were developed before the OTNR was initiated and they became dependent on the Enduring Regime/Future Framework direction, hence we haven’t completed them in the originally proposed timescales. The decision on the DESNZ Future Frameworks consultation remains unpublished and offshore wind connections are now also being considered as part of our broader Connections Reform project. Therefore, once DESNZ have published their Future Frameworks decision and once our Connections Reform project has made its final recommendations, we can agree an implementation plan with Crown Estate Scotland and The Crown Estate in respect of any necessary process changes to better co-ordinate future seabed leasing rounds and the future connections process. Once necessary process changes have been identified we can agree an action plan with those parties (and others) and deliver against it, but this cannot be done prior to the future frameworks and connections reform outputs being known in respect of any future offshore wind connections. In the short term we have already made significant improvements to seabed leasing and connection process co-ordination by working with The Crown Estate to better co-ordinate the Celtic Sea leasing round development process with the HNDFUE. We are also in discussion with Marine Scotland and Crown Estate Scotland in relation to the INTOG leasing round and its potential interactions with the HNDFUE.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.4 | Review where the risk sits for financial liabilities for offshore connections: Undertake a review of financial liabilities risk and ensure that this is optimal for encouraging coordination | An understanding of the liabilities framework if someone is building a coordinated offshore network i.e. whether it increases or decreases the risk. If a coordinated design approach is established and this is seen to increase the risk for developers, it will be necessary to identify options. Options therefore identified for reducing the risk, in conjunction with BEIS/Ofgem. | Q1 - Q4 2021-22 | Complete | Q3 2021-22 | These milestones are considerations within all of the three main OTNR workstreams - Early Opportunities, Pathway to 2030 and Enduring Regime. We have and will continue to assess this along with other considerations in line with the OTNR timeline. Following the publication of Ofgem's decision in relation to this (18/10/22) we raised the required code modification in November.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.4 | Review where the risk sits for financial liabilities for offshore connections: Undertake a review of financial liabilities risk and ensure that this is optimal for encouraging coordination | An agreed way forward on the approach to take on liabilities and how it fits with the wider work of the BEIS-led Offshore Transmission Network Review (OTNR). | Q1-Q4 2022-23 | Complete | Q3 2021-22 | These milestones are considerations within all of the three main OTNR workstreams - Early Opportunities, Pathway to 2030 and Enduring Regime. We have and will continue to assess this along with other considerations in line with the OTNR timeline. Following the publication of Ofgem's decision in relation to this (18/10/22) we raised the required code modification in November.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.5 | Improve the efficiency and customer focus of the CION decision making process: Formalise developers’ roles in the CION process within the System Operator- Transmission Owner Code (STC), dependent on the outcome of the OTNR. | Understanding the direction of travel of the OTNR and the implications for this deliverable. The actions required will depend on the delivery model taken forward. | Q1 - Q4 2021-22 | Milestone no longer valid |  | Since proposing these deliverables the Offshore Transmission Network Review has progressed significantly and our deliverables have changed as a result. In the shorter term (in line with the DESNZ/Ofgem set Terms of Reference) the Holistic Network Design process in the Pathway to 2030 workstream has replaced the traditional CION process for in-scope projects. In the longer term we will aim to develop a new coordinated offshore connection offer process, to enable the agreed future framework, and ensure it has the appropriate level of formalisation. This will come out of decisions on the back of DESNZ's September 2021 Enduring Regime consultation and any subsequent consultations and policy developments. In September 2021 we published an open letter to offshore developers setting out that this is the case.
3 | A15.10 Develop a regime for an integrated offshore grid | D15.10.5 | Improve the efficiency and customer focus of the CION decision making process: Formalise developers’ roles in the CION process within the System Operator- Transmission Owner Code (STC), dependent on the outcome of the OTNR. | Progression of agreed actions to implement the intended model. This would ideally be a holistic approach to code changes, covering all the required changes to implement the OTNR direction of travel. Code change process timings will dictate how far this can be progressed during the period. | Q1-Q4 2022-23 | Milestone no longer valid |  | Since proposing these deliverables the Offshore Transmission Network Review has progressed significantly and our deliverables have changed as a result. In the shorter term (in line with the DESNZ/Ofgem set Terms of Reference) the Holistic Network Design process in the Pathway to 2030 workstream has replaced the traditional CION process for in-scope projects. In the longer term we will aim to develop a new coordinated offshore connection offer process, to enable the agreed future framework, and ensure it has the appropriate level of formalisation. This will come out of decisions on the back of DESNZ's September 2021 Enduring Regime consultation and any subsequent consultations and policy developments. In September 2021 we published an open letter to offshore developers setting out that this is the case.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.11.1 | RDP – N-3 | Completion (subject to obtaining NGET outage availability) | Q3 2021-22 | Delayed - External Reasons |  | SSEN has had some technical issues which have delayed the delivery of this element of work and will mean the milestone will not complete until later in 2023.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.11.2 | RDP - Generation Export Management Scheme (GEMS) | Detailed design & development of IT solution complete | Q3 2021-22 | Delayed - External Reasons |  | Delays due to SPT vendor selection and functional design specification.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.11.2 | RDP - Generation Export Management Scheme (GEMS) | IT installation complete. | Q4 2021-22 | Delayed - External Reasons |  | Delays due to SPT vendor selection and functional design specification.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.11.2 | RDP - Generation Export Management Scheme (GEMS) | IT commissioning complete and GEMS go-live. | Q3 2022-23 | Delayed - External Reasons |  | Delays due to SPT vendor selection and functional design specification.
3 | A15.2 Provide technical support to the connections process | D15.2.1 | Updates to customer offers and agreements – provide technical support to the connection offer process (as set out in activity A14.1) and assess offers to determine future operability need | As required and provide technical support to delivery of the connections hub in activity group A14. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | We have been continuously providing technical support to facilitate the customer connection process.
3 | A15.2 Provide technical support to the connections process | D15.2.1 | Updates to customer offers and agreements – provide technical support to the connection offer process (as set out in activity A14.1) and assess offers to determine future operability need | As required and provide technical support to delivery of the connections hub in activity group A14. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | We have been continuously providing technical support to facilitate the customer connection process.
3 | A15.3 Assess the technical implications of framework developments and implement changes into business procedures and systems. | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. This activity provides technical support to modifications managed by frameworks teams in activity A6.1, Role 2 | GC0137/139/145 code change process completed. Provide ongoing technical support to modifications as required (including those raised through open governance) the level of resource required can vary hugely from one modification to the next. | Q1 2021-22 | Complete | Q1 2021-22 | The overall timescale for this work is set by the code change progress, please refer to deliverable D6.1 for further details. However we have provided the technical support required for the modification. Further support will be available if needed.
3 | A15.3 Assess the technical implications of framework developments and implement changes into business procedures and systems. | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. This activity provides technical support to modifications managed by frameworks teams in activity A6.1, Role 2 | Provide ongoing technical support to modifications as required (including those raised through open governance) – the level of resource required can vary hugely from one modification to the next. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | The overall timescale for this work is set by the code change progress, please refer to deliverable D6.1 for further details. Support to current modification GC0155 is on going.
3 | A15.3 Assess the technical implications of framework developments and implement changes into business procedures and systems. | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. This activity provides technical support to modifications managed by frameworks teams in activity A6.1, Role 2 | Develop and agree a plan with stakeholders to implement necessary planning process changes relating to voltage management across the transmission-distribution interface | Q1-Q4 2021-22 | Complete | Q4 2021-22 | A plan to continue long term voltage assessment, use Joint System Design Liaison forum to engage DNOs and TOs and NIC project QUEST to explore voltage management across the transmission-distribution interface
3 | A15.3 Assess the technical implications of framework developments and implement changes into business procedures and systems. | D15.3.2 | Lead the Loss of Mains Protection setting programme | Lead the Accelerated Loss of Mains programme and provide assurance of value for money via quarterly performance reporting, subject to the need for programme continuation | Q1-Q4 2021-22 | Complete | Q4 2021-22 | The programme is ongoing with 19.4 GW of generation capacity engaged, and physical changes now made on over 10.7GW of plant.
3 | A15.3 Assess the technical implications of framework developments and implement changes into business procedures and systems. | D15.3.2 | Lead the Loss of Mains Protection setting programme | Lead the Accelerated Loss of Mains programme and provide assurance of value for money via quarterly performance reporting, subject to the need for programme continuation | Q1-Q4 2022-23 | Complete | Q4 2022-23 | The programme has confirmed the compliance of 95.3% (24.44GW) of capacity in-scope of G59/3-7, and enforcement action is being discussed with Ofgem and DNOs on the remaining sites. £44m p.a. savings have been achieved, so far against counter-factual costs for a one-off programme cost to date of £30.6m. In addition FRCR recommends reducing the inertia holding level to 120 GVAs primarily as a result of ALoMCP delivery which is forecast to save an additional £65m p.a.
3 | A15.4 Manage operational data and modelling requirements for the ESO | D15.4.1 | Data transfers between network organisations in accordance with current Grid Code and STC requirements – managing operational data flows across network companies to underpin offline network analysis in the ESO. | As required | N/A | Complete | Q4 2022-23 | We are engaging regularly with all system users to ensure that the required exchange of data occurs in the timescales specified in the industry codes.
3 | A15.4 Manage current operational data and modelling requirements for the ESO | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | Deliver ETYS and NOA models | Q3 2021-22 | Complete | Q3 2021-22 | 2021 ETYS/NOA datasets were completed on time.
3 | A15.4 Manage current operational data and modelling requirements for the ESO | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | Deliver ETYS and NOA models | Q3 2022-23 | Complete | Q3 2022-23 | 2022 ETYS/NOA process completed on time
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.1 | Start RDP1 of RIIO-2 – Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Start RDP1 IT requirements and design stage. | Q1 2021-22 | Complete | Q1 2021-22 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.1 | Start RDP1 of RIIO-2 – Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | IT Requirements & design stage complete | Q3 2021-22 | Complete | Q3 2021-22 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.1 | Start RDP1 of RIIO-2 – Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | IT Development & testing phase commences | Q4 2021-22 | Complete | Q4 2021-22 | Milestone complete.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.1 | Start RDP1 of RIIO-2 – Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | IT implementation phase complete | Q4 2022-23 | Delayed - Internal Reasons |  | DER Service Terms finalised and signed off. SMP functionality released - DER registrations to commence in spring 2023. MPLS link delivery delays have delayed release of ESOs ASDP (dispatch) functionality beyond March 2023.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.2 | Start RDP2 of RIIO-2 - Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Detailed RDP IT development commences | Q1 2021-22 | Complete | Q1 2021-22 | Milestone complete.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.2 | Start RDP2 of RIIO-2 - Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Detailed RDP IT development complete | Q2 2021-22 | Complete | Q1 2021-22 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.2 | Start RDP2 of RIIO-2 - Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Start RDP2 IT requirements and design phase. | Q3 2021-22 | Complete | Q1 2021-22 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.2 | Start RDP2 of RIIO-2 - Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | IT Requirements & design stage complete. | Q1 2022-23 | Complete | Q4 2022-23 | Milestone Complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.2 | Start RDP2 of RIIO-2 - Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | IT development & testing commences. | Q2 2022-23 | Complete | Q4 2022-23 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.3 | Start RDP3 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Viability of market solution confirmed | Q2 2021-22 | Complete | Q2 2022-23 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.3 | Start RDP3 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Detailed RDP development starts. | Q3 2021-22 | Complete | Q2 2022-23 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.3 | Start RDP3 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Detailed RDP development complete | Q4 2021-22 | Delayed - Consumer Benefits |  | This deliverable has been delayed to better align with other RDP and connections initiatives. It is now undertaking a feasibility assessment of the proposal to connect battery storage non-firm.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.3 | Start RDP3 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Start RDP3 IT requirements and design phase. | Q1 2022-23 | Delayed - Consumer Benefits |  | This deliverable has been delayed to better align with other RDP and connections initiatives. It is now undertaking a feasibility assessment of the proposal to connect battery storage non-firm.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.3 | Start RDP3 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | IT Requirements & design stage complete. | Q3 2022-23 | Delayed - Consumer Benefits |  | This deliverable has been delayed to better align with other RDP and connections initiatives. It is now undertaking a feasibility assessment of the proposal to connect battery storage non-firm.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.3 | Start RDP3 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | IT development & testing commences. | Q4 2022-23 | Delayed - Consumer Benefits |  | This deliverable has been delayed to better align with other RDP and connections initiatives. It is now undertaking a feasibility assessment of the proposal to connect battery storage non-firm.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.4 | Start RDP4 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Identify outline need for RDP 4. | Q4 2021-22 | Complete | Q4 2021-22 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.4 | Start RDP4 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Detailed RDP development starts. | Q1 2022-23 | Complete | Q1 2022-23 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.4 | Start RDP4 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Detailed RDP development complete. | Q3 2022-23 | Delayed - Internal Reasons |  | This deliverable has been delayed to better align with other RDP and connections initiatives. It is now undertaking a feasibility assessment of the proposal to connect battery storage non-firm.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.4 | Start RDP4 of RIIO-2: Regional development plans provide a means to working with other network parties to facilitate connection of low carbon energy sources in capacity constrained areas. We plan to undertake 6 RDPs in RIIO-2 | Start RDP4 IT requirements and design phase. | Q4 2022-23 | Complete | Q4 2022-23 | Project works have begun to extend ICCP functionality into UKPN's EPN region and map required data points.
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.5 | Development of roadmap to deliver GB rollout of functionality (visibility & control of DER) developed through initial RDPs. | DNO & TO engagement to understand determine needs case for greater visibility & control of DER. | Q1-Q3 2021-22 | Complete | Q4 2021-22 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.5 | Development of roadmap to deliver GB rollout of functionality (visibility & control of DER) developed through initial RDPs. | Review of RDP projects to date to understand potential learnings and synergies | Q4 2021-22 | Complete | Q4 2021-22 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.5 | Development of roadmap to deliver GB rollout of functionality (visibility & control of DER) developed through initial RDPs. | Development of aligned proposals for GB wide rollout | Q1-Q3 2022-23 | Complete | Q4 2022-23 | Milestone complete
3 | A15.5 Develop Regional Development Programmes (RDPs) | D15.5.5 | Development of roadmap to deliver GB rollout of functionality (visibility & control of DER) developed through initial RDPs. | Publication of roadmap for national rollout. | Q4 2022-23 | Complete | Q4 2022-23 | Milestone complete
3 | A15.6 Transform our capability in modelling and data management | D15.6.1 | Phase 1 data management scoping complete to feed into data & analytics platform (see Role 1 D1.4.1) – modelling and data expertise will be used to scope planning data requirements for the data & analytics platform | Phase 1 modelling scoping complete to feed into requirements and design stage of the data & analytics platform (foundation implementation | Q2 2021-22 | Complete | Q3 2021-22 | Minimum Viable Product (MVP) requirements have been defined. First data scoping document has been produced.
3 | A15.6 Transform our capability in modelling and data management | D15.6.1 | Phase 1 data management scoping complete to feed into data & analytics platform (see Role 1 D1.4.1) – modelling and data expertise will be used to scope planning data requirements for the data & analytics platform | Modelling scoping complete to feed into platform extension requirements phase (D15.6.3) | Q2 2022-23 | Complete | Q2 2022-23 | Phase 1 modelling scope complete and second stage of the data scoping work is on track.
3 | A15.6 Transform our capability in modelling and data management | D15.6.1 | Phase 1 data management scoping complete to feed into data & analytics platform (see Role 1 D1.4.1) – modelling and data expertise will be used to scope planning data requirements for the data & analytics platform | Data & analytics platform foundation complete. (D15.6.4). | Q3 2022-23 | Complete | Q3 2022-23 | Phase 1 scoping complete and DAP foundation platform in place.
3 | A15.6 Transform our capability in modelling and data management | D15.6.2 | Further Grid Code mods (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Determine what data is required, from which parties and any associated issues with obtaining the data. Any further data-driven Grid Code mods scoped and raised as required. Engage with DNOs on any specific requirements as they develop their RIIO-ED2 plans | Q1 2021-22 | Complete | Q2 2021-22 | Data requirements have been fed into GC0139 (Enhanced Planning-Data Exchange to Facilitate Whole System Planning) which is currently at Working Group stage "
3 | A15.6 Transform our capability in modelling and data management | D15.6.2 | Further Grid Code mods (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Code mods or agreements to obtain new data progressed in accordance with governance requirements as required. | Q2-Q3 2021-22 | Complete | Q4 2022-23 | The GC139 modification is in final stages of drafting. GC139 will enable data to be exchanged between DNO's and ESO using Common In formation Model (CIM) . The drafting is to be concluded at the working group meeting on 29th March 2023 and then submitted for Industry consultation and approval.
3 | A15.6 Transform our capability in modelling and data management | D15.6.2 | Further Grid Code mods (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Grid Code mods submitted for approval / agreements progressed to facilitate transmission-distribution data exchange | Q4 2021-22 | Delayed - External Reasons |  | "Work depends on D15.8.1. GC0139 (Enhanced Planning-Data Exchange to Facilitate Whole System Planning) is currently at Working Group stage " and was delayed due to external factors. The GC139 modification is in final stages of drafting, which is expected to be concluded at the working group meeting on 29th March 2023 and then submitted for Industry consultation and approval. Anticipated completion is now Summer 2023.
3 | A15.6 Transform our capability in modelling and data management | D15.6.2 | Further Grid Code mods (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the Code modification process as required. Provide ongoing technical support and input to the code modification process as required | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Horizon scanning to see any upcoming impact on data and modelling management
3 | A15.6 Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. This upgrade will include tactical enhancements, for example, compliance with Capacity Allocation and Congestion Management (CACM), as well as establishing the development roadmap for the multi-layered off-line modelling capability needed to facilitate operation of a zero carbon system. | Engagement with TOs on CACM requirements. | Q1-Q2 2021-22 | Complete | Q2 2021-22 | Engagement with relevant TOs and stakeholders to understand CACM and short-circuit technical requirements on offline modelling works has been completed.
3 | A15.6 Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. This upgrade will include tactical enhancements, for example, compliance with Capacity Allocation and Congestion Management (CACM), as well as establishing the development roadmap for the multi-layered off-line modelling capability needed to facilitate operation of a zero carbon system. | CACM and short circuit go-live in offline network modelling. | Q3 2021-22 | Complete | Q4 2022-23 | There was a delay of 6 months due to new components required to meet FSO security requirements. OLTA hardware upgrade delivered and went live in Azure cloud in Jan 2023. New software successfully tested on 21st March 2023 which enables CACM and new short circuit capability in OLTA.
3 | A15.6 Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. This upgrade will include tactical enhancements, for example, compliance with Capacity Allocation and Congestion Management (CACM), as well as establishing the development roadmap for the multi-layered off-line modelling capability needed to facilitate operation of a zero carbon system. | Produce Offline modelling development road-map | Q2 2022-23 | Complete | Q2 2022-23 | Engaged with stakeholders and Offline Modelling roadmap complete at this time
3 | A15.6 Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. This upgrade will include tactical enhancements, for example, compliance with Capacity Allocation and Congestion Management (CACM), as well as establishing the development roadmap for the multi-layered off-line modelling capability needed to facilitate operation of a zero carbon system. | Produce Offline modelling development roadmap. | Q2 2022-23 | Complete | Q2 2022-23 | Engaged with stakeholders and Offline Modelling roadmap complete at this time
3 | A15.6 Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. This upgrade will include tactical enhancements, for example, compliance with Capacity Allocation and Congestion Management (CACM), as well as establishing the development roadmap for the multi-layered off-line modelling capability needed to facilitate operation of a zero carbon system. | Engage stakeholders on further iteration of the development roadmap | Q2-Q3 2022-23 | Complete | Q3 2022-23 | Stakeholder engagement completed at this time.
3 | A15.6 Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. This upgrade will include tactical enhancements, for example, compliance with Capacity Allocation and Congestion Management (CACM), as well as establishing the development roadmap for the multi-layered off-line modelling capability needed to facilitate operation of a zero carbon system. | Offline modelling development roadmap finalised | Q4 2022-23 | Complete | Q3 2022-23 | Stakeholder engagement has been completed, offline modelling review report published with roadmap
3 | A15.6 Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling - this will enable higher volumes of network data, regional models and outage planning data to be exchanged, used and shared by network companies. This activity enables the network access planning activity A16.3 | feed findings from deliverable A16.3.2 and any relevant Grid code modifications into future modelling scoping and development | Q4 2021-22 | Complete | Q4 2021-22 | High level requirements have been fed into future modelling development to support A16.3 Deeper Outage Planning.
3 | A15.6 Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling - this will enable higher volumes of network data, regional models and outage planning data to be exchanged, used and shared by network companies. This activity enables the network access planning activity A16.3 | Data and analytics platform foundational architecture complete | Q3 2022-23 | Complete | Q3 2022-23 | Data and Analytics platform foundational architecture in place
3 | A15.6 Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling - this will enable higher volumes of network data, regional models and outage planning data to be exchanged, used and shared by network companies. This activity enables the network access planning activity A16.3 | feed findings from deeper access work into offline network modelling development Work with DNOs to develop IT requirements for deeper outage planning | Q4 2022-23 | Delayed - External Reasons |  | This milestone links to A16.3 which has been marked ‘Delayed external reasons has been agreed with James Hill (Ofgem). This milestone should, from the outset, have been identified for completion in BP2.’
3 | A15.7 Deliver an operable zero carbon system by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) stage roll out. This activity seeks to roll out a system that has been tested on a small scale via the Enhanced Frequency Control Capability (EFCC) innovation project and is comprised of 5 phases. | Start-up for Phases 1 and 2: Identify industry parties to participate in the Phase 1 non-operational demonstration | Q1 2021-22 | Complete | Q2 2021-22 | Industry participants for Phase 1 are identified,
3 | A15.7 Deliver an operable zero carbon system by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) stage roll out. This activity seeks to roll out a system that has been tested on a small scale via the Enhanced Frequency Control Capability (EFCC) innovation project and is comprised of 5 phases. | Phase 1 and Phase 2 Requirements and design. | Q2 2021-22 | Complete | Q3 2021-22 | Requirements for Phase 1 and design has been defined
3 | A15.7 Deliver an operable zero carbon system by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) stage roll out. This activity seeks to roll out a system that has been tested on a small scale via the Enhanced Frequency Control Capability (EFCC) innovation project and is comprised of 5 phases. | Phase 1 Development and testing: Engage with key stakeholders | Q3 2021-22 | Complete | Q4 2021-22 | Engaged with all project participants and wider stakeholders as well.
3 | A15.7 Deliver an operable zero carbon system by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) stage roll out. This activity seeks to roll out a system that has been tested on a small scale via the Enhanced Frequency Control Capability (EFCC) innovation project and is comprised of 5 phases. | Commence implementation of Phase 1 non- operational demonstration | Q4 2021-22 | Complete | Q4 2021-22 | Project team is mobilised and works commenced for Phase 1 implementation.
3 | A15.7 Deliver an operable zero carbon system by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) stage roll out. This activity seeks to roll out a system that has been tested on a small scale via the Enhanced Frequency Control Capability (EFCC) innovation project and is comprised of 5 phases. | Phase 2 (Develop operational demonstration) Development and testing. | Q1-Q2 2022-23 | Milestone no longer valid |  | EFC and Dynamic Containment (DC) covers the same solution space. In Phase 0, further studies have been carried out and studies concluded that DC was sufficient as a post fault frequency response for a network with minimum post event inertia of 90 GVA-s. RAPID process recommended to cancel Phase 2 - Phase 5. It has been approved by Design Authority and presented to OFGEM.
3 | A15.7 Deliver an operable zero carbon system by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) stage roll out. This activity seeks to roll out a system that has been tested on a small scale via the Enhanced Frequency Control Capability (EFCC) innovation project and is comprised of 5 phases. | Phase 3 (Operational Demonstration) Implementation. | Q3-Q4 2022-23 | Milestone no longer valid |  | EFC and Dynamic Containment (DC) covers the same solution space. In Phase 0, further studies have been carried out and studies concluded that DC was sufficient as a post fault frequency response for a network with minimum post event inertia of 90 GVA-s. RAPID process recommended to cancel Phase 2 - Phase 5. It has been approved by Design Authority and presented to OFGEM.
3 | A15.7 Deliver an operable zero carbon system by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) stage roll out. This activity seeks to roll out a system that has been tested on a small scale via the Enhanced Frequency Control Capability (EFCC) innovation project and is comprised of 5 phases. | Phase 4 (First stage rollout) Start-up. | Q1-Q2 2022-23 | Milestone no longer valid |  | EFC and Dynamic Containment (DC) covers the same solution space. In Phase 0, further studies have been carried out and studies concluded that DC was sufficient as a post fault frequency response for a network with minimum post event inertia of 90 GVA-s. RAPID process recommended to cancel Phase 2 - Phase 5. It has been approved by Design Authority and presented to OFGEM.
3 | A15.7 Deliver an operable zero carbon system by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) stage roll out. This activity seeks to roll out a system that has been tested on a small scale via the Enhanced Frequency Control Capability (EFCC) innovation project and is comprised of 5 phases. | Phase 4 Requirements | Q3-Q4 2022-23 | Milestone no longer valid |  | EFC and Dynamic Containment (DC) covers the same solution space. In Phase 0, further studies have been carried out and studies concluded that DC was sufficient as a post fault frequency response for a network with minimum post event inertia of 90 GVA-s. RAPID process recommended to cancel Phase 2 - Phase 5. It has been approved by Design Authority and presented to OFGEM.
3 | A15.8 Provide technical support to DSO and whole electricity system alignment | D15.8.1 | Completion of any DSO associated code changes ahead of RIIO-ED2 to facilitate system operation activities. | Work with stakeholders, including Open Networks, to identify, scope and submit relevant DSO associated Code mods ahead of RIIO-ED2. This is to include active engagement in Ofgem work on DSO policy | Q1-Q4 2021-22 | Complete | Q3 2021-22 | Milestone complete
3 | A15.8 Provide technical support to DSO and whole electricity system alignment | D15.8.1 | Completion of any DSO associated code changes ahead of RIIO-ED2 to facilitate system operation activities. | Undertake active engagement in the Open Networks project to support ongoing developments and lead Work Stream 4 Whole Energy Systems | Q1-Q4 2021-22 | Complete | Q3 2021-22 | Milestone complete
3 | A15.8 Provide technical support to DSO and whole electricity system alignment | D15.8.1 | Completion of any DSO associated code changes ahead of RIIO-ED2 to facilitate system operation activities. | Business plan alignment discussions with DNOs conclude ahead of draft RIIO-ED2 business plan submissions. | Q1 2021-22 | Complete | Q1 2021-22 | Milestone complete
3 | A15.8 Provide technical support to DSO and whole electricity system alignment | D15.8.1 | Completion of any DSO associated code changes ahead of RIIO-ED2 to facilitate system operation activities. | Business plan alignment discussions with DNOs conclude ahead of final RIIO-ED2 business plan submissions. | Q3 2021-22 | Complete | Q3 2021-22 | Milestone complete
3 | A15.8 Provide technical support to DSO and whole electricity system alignment | D15.8.1 | Completion of any DSO associated code changes ahead of RIIO-ED2 to facilitate system operation activities. | Undertake active engagement in the Open Networks project to support ongoing developments and lead Work Stream 4 Whole Energy Systems. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | From January 2023 the ENA Open Networks Programme has a new structure. ESO now chairs the Network Operation workstream and continues to lead and support other technical working groups.
3 | A15.8 Provide technical support to DSO and whole electricity system alignment | D15.8.1 | Completion of any DSO associated code changes ahead of RIIO-ED2 to facilitate system operation activities. | Review and provide support to the RIIO-ED2 business plan development process and broader initiatives as required ensuring alignment with ESO business plan. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | We continue working with our stakeholders as they prepare for RIIO-ED2. We continue to support policy areas and are awaiting next updates on the local energy institutions and governance CfI.
3 | A15.9 Identify Future operability needs across whole energy system | D15.9.1 | Trial new innovation projects for whole energy system operability | Evolve existing approach to identifying innovation projects to give a broader cross-vector view | Q1-Q4 2021-22 | Complete | Q4 2021-22 | Working with ESO Innovation team and wider industry to explore best innovation opportunities.
3 | A15.9 Identify Future operability needs across whole energy system | D15.9.1 | Trial new innovation projects for whole energy system operability | seek innovation project opportunities to trial whole energy system operability tools in response to operability requirements identified in SOF publications. Provide technical support to further ESO innovation events such as Open Innovation days and to initiatives driven by external stakeholders. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | Plan on track, new innovation project strength to connect has been initiated also the project on oscillation has been agreed in open innovation event.
3 | A15.9 Identify Future operability needs across whole energy system | D15.9.2 | Commence RDP approach to whole energy system challenges – build on the RDP approach used in the electricity sector to develop cross sector operability solutions | initial scoping for this activity to take place in 2023/24 so no milestones applicable here | N/A | Milestone no longer valid |  | ‘Milestone no longer Valid’ This activity was scheduled to start after BP1. It has subsequently been removed from our BP2 business plan submission..
3 | A15.9 Identify Future operability needs across whole energy system | D15.9.3 | Second whole energy system RDP launched | work to commence on this activity in 2024/25 | N/A | Milestone no longer valid |  | ‘Milestone no longer Valid’ This activity was scheduled to start after BP1. It has subsequently been removed from our BP2 business plan submission.
3 | A16.1 Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them. | D16.1.1 | Year ahead regional outage programmes developed in liaison with network parties. | deliver regional outage programmes | Q4 2021-22 | Complete | Q4 2021-22 | In line with the SO-TO Code and Grid Code OC2, the TOs have submitted their provisional outage plans to ESO and we expect to share the relevant information with each party by the end of week 28.
3 | A16.1 Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them. | D16.1.1 | Year ahead regional outage programmes developed in liaison with network parties. | deliver regional outage programmes | Q4 2022-23 | Complete | Q4 2022-23 | In line with the SO-TO Code and Grid Code OC2, the TOs have submitted their provisional outage plans to ESO and we shared the relevant information with each party by the end of week 28.
3 | A16.1 Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them. | D16.1.2 | Detailed week and day ahead operational documentation produced for National Control | Weekly / Day ahead outage plans | N/A | Complete | Q4 2022-23 | Please refer to our Metrics and Regularly Reported Evidence
3 | A16.2 Enhance the Network Access Policy (NAP) process with TOs | D16.2.1 | GB wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area ahead of RIIO-2. | GB wide NAP process go-live (and any further mechanisms progressed as appropriate). Draft revised process for STCP 11-4 following engagement with the TOs | Q1 2021-22 | Complete | Q1 2021-22 | The STCP 11-4 process and costing methodology were reviewed and implemented from 1 April 2021. Potential services from TOs have been proposed by ESO and TOs, and those which are forecast to reduce constraint spend have been progressed. Year ahead constraints have been published on the data portal providing increased visibility. The constraint forecasting team are building a model for publication of constraint cost forecast. For the Q3 milestone, TO engagement has taken place. We are waiting on the implementation of 2 year ahead constraint cost forecasting which is expected to deliver in Q4 21-22. Then we will determine whether any further cost information needs to be shared, and how we can implement process improvements.
3 | A16.2 Enhance the Network Access Policy (NAP) process with TOs | D16.2.1 | GB wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area ahead of RIIO-2. | Consult on how the new methodology should be implemented | Q2 2021-22 | Complete | Q1 2021-22 | The STCP 11-4 process and costing methodology were reviewed and implemented from 1 April 2021. Potential services from TOs have been proposed by ESO and TOs, and those which are forecast to reduce constraint spend have been progressed. Year ahead constraints have been published on the data portal providing increased visibility.
3 | A16.2 Enhance the Network Access Policy (NAP) process with TOs | D16.2.1 | GB wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area ahead of RIIO-2. | Review process with TOs and discuss process improvement. Engage with TOs on type of cost information they would want to see from the ESO | Q3 2021-22 | Complete | Q2 2022-23 | The STCP 11-4 process and costing methodology were reviewed and implemented from 1 April 2021. Potential services from TOs have been proposed by ESO and TOs, and those which are forecast to reduce constraint spend have been progressed. Year ahead constraints have been published on the data portal providing increased visibility. TO engagement has taken place. In April 2022 the 24 month constraint cost forecast was published. A working group has been set up with the ESO and TOs to agree improvements to the process.
3 | A16.2 Enhance the Network Access Policy (NAP) process with TOs | D16.2.1 | GB wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area ahead of RIIO-2. | Provide increased visibility of outage change cost - provide more visibility on an ad hoc basis. | Q4 2021-22 | Complete | Q4 2021-22 | The STCP 11-4 process and costing methodology were reviewed and implemented from 1 April 2021. Potential services from TOs have been proposed by ESO and TOs, and those which are forecast to reduce constraint spend have been progressed. The implementation of 2 year ahead constraint cost forecast was delivered in April 22. We are working on further cost developments, and how we can implement process improvements. Constraint costings provided to the TOs when requested as part of optimisation.
3 | A16.2 Enhance the Network Access Policy (NAP) process with TOs | D16.2.1 | GB wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area ahead of RIIO-2. | Output from innovation informs new change to outage cost visibility process | Q2 2022-23 | Complete | Q3 2022-23 | Deliverables developed and agreed with the TOs. Completed.
3 | A16.2 Enhance the Network Access Policy (NAP) process with TOs | D16.2.1 | GB wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area ahead of RIIO-2. | Implement this cost visibility process with the TOs | Q3 2022-23 | Complete | Q4 2022-23 | Deliverables developed and data being sent to the TOs as per the agreed timetable. Completed.
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.1 | Conclude trials on closer working relationships with DNOs and DER to enhance co-ordination of system access and development of flexibility markets (commenced in 2019-21 Forward Plan). | Ongoing engagement with trial partner(s). Engage and update DNOs on trial progress to inform their RIIO-ED2 plan development. Explore the principle of introducing Network Access Policy-type frameworks with DNOs for coordinating distribution and transmission outage planning. | Q1-Q2 2021-22 | Complete | Q3 2021-22 | Future processes have been outlined and mapped and currently the ESO and DNO parties are investigating methods to ensure model compatibility and constraint reduction savings. All DNOs were engaged
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.1 | Conclude trials on closer working relationships with DNOs and DER to enhance co-ordination of system access and development of flexibility markets (commenced in 2019-21 Forward Plan). | Completion of trials | Q2 2021-22 | Complete | Q3 2021-22 | Future processes have been outlined and mapped and currently the ESO and DNO parties are investigating methods to ensure model compatibility and constraint reduction savings. All DNOs were engaged
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.1 | Conclude trials on closer working relationships with DNOs and DER to enhance co-ordination of system access and development of flexibility markets (commenced in 2019-21 Forward Plan). | Trials concluded | Q3 2021-22 | Complete | Q3 2021-22 | Future processes have been outlined and mapped and currently the ESO and DNO parties are investigating methods to ensure model compatibility and constraint reduction savings. All DNOs were engaged
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.2 | Learnings from trials shared alongside recommendations for GB roll out such that best practice is applied to ongoing processes | Engage relevant parties on ongoing conclusions and learnings from trials. Feed findings into RIIO ED-2 business planning processes. | Q1-Q3 2021-22 | Complete | Q3 2021-22 | Future processes have been outlined and mapped and currently the ESO and DNO parties are investigating methods to ensure model compatibility and constraint reduction savings. All DNOs were engaged
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.2 | Learnings from trials shared alongside recommendations for GB roll out such that best practice is applied to ongoing processes | Develop and share learnings and recommendations for GB roll out, including whether to introduce NAP-type frameworks with DNOs for coordinating distribution and transmission outages. | Q4 2021-22 | Complete | Q4 2021-22 | Future processes have been outlined and mapped and currently the ESO and DNO parties are investigating methods to ensure model compatibility and constraint reduction savings. All DNOs were engaged
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.2 | Learnings from trials shared alongside recommendations for GB roll out such that best practice is applied to ongoing processes | Progress recommendations in accordance with GB roll out recommendations. Engage with relevant parties to support successful delivery | Q1-Q4 2022-23 | Complete | Q4 2022-23 | The learning were being gathered from RDP trials with DNOs throughout FY22/23. 2 Major DNOs had learning points shared in Q1 of 22/23 and their experiences were used to formulate case studies. The learnings from all trials have now been disseminated at all interested parties at the March OC2 forum. From this forum the ESO have gathered extensive feedback, advice and commentary which has been used to develop the project plan for delivery of the remainder of the A16.3 milestones in BP2. This action can be considered as complete
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in A16.3.1 and A16.3.2 | feed findings from deliverable A16.3.2 into preliminary code modification discussions. Instances of conflict of service evidenced from the trials to be a key consideration. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | Joint operating procedures have been drafted with the trial partners and will be used to inform development of future frameworks.
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in A16.3.1 and A16.3.2 | Code modification requirements assessed, scoped and raised as required | Q1 2022-23 | Delayed - External Reasons |  | Joint operating procedures have been drafted with the trial partners and will be used to inform development of future frameworks. New processes with trial partners are understood as MVP products but are yet to be rolled out for use. Milestone delayed as new processes are not ready to inform code modifications discussions. Delays have been driven by slower than expected progress with data exchange methodologies. It has been agreed that a new approach of utilising case studies will be adopted prior to GB roll out. This new approach is a deviation from the previous attempt to map stakeholder end to end requirements. Milestone incorrectly entered - Should be a 24/25 Milestone Delayed external agreed with James Hill Ofgem
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in A16.3.1 and A16.3.2 | Modifications progressed through governance | Q2-Q4 2022-23 | Delayed - External Reasons |  | Joint operating procedures have been drafted with the trial partners and will be used to inform development of future frameworks. Code modifications will not progress to governance in BP1 following required scoping so this will be delayed to Q2 2023/2024. It has been agreed that a new approach of utilising case studies will be adopted prior to GB roll out. This new approach is a deviation from the previous attempt to map stakeholder end to end requirements. Milestone incorrectly entered - Should be a 24/25 Milestone Delayed external agreed with James Hill Ofgem
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in A16.3.1 and A16.3.2 | Code change process concluded, mods submitted to Authority for decision | Q4 2022-23 | Delayed - External Reasons |  | Joint operating procedures have been drafted with the trial partners and will be used to inform development of future frameworks. Code change process will not progress in BP1 following required scoping so this will be delayed to Q2 2023/2024. It has been agreed that a new approach of utilising case studies will be adopted prior to GB roll out. This new approach is a deviation from the previous attempt to map stakeholder end to end requirements. ENCC input will be required so could be further delayed by winter operability challenges. Milestone incorrectly entered - Should be a 24/25 Milestone Delayed external agreed with James Hill Ofgem
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | feed findings from deliverable A16.3.2 into future modelling scoping and development | Q1-Q4 2021-22 | Complete | Q4 2021-22 | Findings from the trials fed into discussions with the DNOs via monthly joint forums. Finding from MVP from MWD, N-3 were fed into PODE workstream 2 and 3
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | DNOs engaged in the lead up to submission of their RIIO-ED2 business plans on the aims of deeper access. | Q2 2021-22 | Complete | Q2 2021-22 | DNOs were engaged in 2020 at the OC2 forum and continue to be engaged at monthly forums.
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | Data and analytics platform foundational architecture complete | Q3 2022-23 | Delayed - External Reasons |  | Future processes have been outlined and mapped, and currently the ESO and DNO parties are investigating methods to ensure model compatibility and constraint reduction savings. Delayed external reasons has been agreed with James Hill (Ofgem). This milestone should, from the outset, have been identified for completion in BP2.
3 | A16.3 Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | feed findings from A16.3.3 into further offline network modelling development, assess IT impact of any code modifications to facilitate deeper access planning. Work with DNOs to develop IT requirements for deeper outage planning. | Q4 2022-23 | Delayed - External Reasons |  | Future processes have been outlined and mapped, and currently the ESO and DNO parties are investigating methods to ensure model compatability and constraint reduction savings
3 | A16.4 TOGA / Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Complete remaining parts of TOGA system replacement (eNAMS) | Q1 2021-22 | Complete | Q2 2021-22 | eNAMS went live on 1 September 2021. Following go-live, further enhancements will be delivered ahead of March 2022. Five development sprints have been planned to deliver eNAMS enhancements identified by key customers and stakeholders. The sprints will complete by mid March 2022. Weekly engagement sessions are scheduled with the main customers and stakeholders to agree enhancement priorities and demonstrate the enhancements as they're developed. The scoping exercise refers to the Planning and Outage Data Exchange (PODE) work, which is separate from completing the eNAMS work. The scoping activity for PODE is delayed due to the knock on impact of delayed implementation of eNAMS.
3 | A16.4 TOGA / Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Commence scoping activity and engage with key stakeholders. Align model development and requirements with output from deliverable A16.3.2 (recommendations for roll out of deeper access planning | Q3 2021-22 | Delayed - External Reasons |  | Awaiting completion of D16.3.3. Initial milestone date made no allowance for the completion of activity D16.3.3. This activity is now expected to start in 2023/24
3 | A16.4 TOGA / Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | scoping exercise concluded and published | Q2 2022-23 | Delayed - External Reasons |  | This can be started after the output of D16.3.3 is available.
3 | A16.4 TOGA / Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | commence IT project start-up phase. | Q3 2022-23 | Delayed - External Reasons |  | This can be started after the output of D16.3.3 is available.
3 | A16.4 TOGA / Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the TOGA system to become a more interactive experience for customers, stakeholders and the market. | Commence scoping activity and engage with key stakeholders. Align model development and requirements with output from deliverable A16.3.2 (recommendations for roll out of deeper access planning | Q3 2021-22 | Delayed - External Reasons |  | Enams has been delivered. High level scoping activity has commenced and engagement has been carried out with stakeholders. This requires the completion of D16.3.3, it has been misaligned from the outset and should not have been due for completion in Q3 2021/2022
3 | A16.4 TOGA / Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the TOGA system to become a more interactive experience for customers, stakeholders and the market. | scoping exercise concluded and published | Q2 2022-23 | Delayed - External Reasons |  | This can be started after the output of D16.3.3 is available.
3 | A16.4 TOGA / Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the TOGA system to become a more interactive experience for customers, stakeholders and the market. | commence IT project start-up phase. | Q3 2022-23 | Delayed - External Reasons |  | Awaiting completion of D16.3.3. Initial milestone date made no allowance for the completion of activity D16.3.3. This activity is now expected to start in 2023/24
3 | A7.1 Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Review usefulness of System Requirements Form (SRF) for interested options submission process and work with industry to improve the needs information | Q1-Q2 2021-22 | Complete | Q2 2021-22 | ETYS 2021 was successfully published on 29 Nov 2021 with some key enhancements to our boundary charts to show the impact of previous NOA recommendations. This is in response to stakeholder feedback and improves our communication of system need. The ETYS web-based publication has also been improved based on stakeholder feedback and website analytics to make it easier for our stakeholders to engage with our ETYS content. A Proof of Concept for integrating Pouya (PM) into the NOA process by providing circuit-based constraints on top of the boundary constraints has been developed and tested. Work is ongoing reviewing how pathfinder needs could be integrated in future ETYS.
3 | A7.1 Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Proof of Concept for a bespoke joint network and market tool for probabilistic thermal analysis. | Q2 2021-22 | Complete | Q2 2021-22 | ETYS 2021 was successfully published on 29 Nov 2021 with some key enhancements to our boundary charts to show the impact of previous NOA recommendations. This is in response to stakeholder feedback and improves our communication of system need. The ETYS web-based publication has also been improved based on stakeholder feedback and website analytics to make it easier for our stakeholders to engage with our ETYS content. A Proof of Concept for integrating Pouya (PM) into the NOA process by providing circuit-based constraints on top of the boundary constraints has been developed and tested. Work is ongoing reviewing how pathfinder needs could be integrated in future ETYS.
3 | A7.1 Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Proof of Concept for integration of probabilistic network analysis into the NOA process. | Q2 2021-22 | Complete | Q4 2021-22 | ETYS 2021 was successfully published on 29 Nov 2021 with some key enhancements to our boundary charts to show the impact of previous NOA recommendations. This is in response to stakeholder feedback and improves our communication of system need. The ETYS web-based publication has also been improved based on stakeholder feedback and website analytics to make it easier for our stakeholders to engage with our ETYS content. A Proof of Concept for integrating Pouya (PM) into the NOA process by providing circuit-based constraints on top of the boundary constraints has been developed and tested. Work is ongoing reviewing how pathfinder needs could be integrated in future ETYS.
3 | A7.1 Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Review how pathfinder needs could be integrated into the ETYS whilst retaining flexibility to publish needs via RFIs outside of the main publication. | Q3-Q4 2021-22 | Complete | Q4 2022-23 | We published ETYS on 31st Jan 2023 and included the outcomes of our review on how pathfinder needs could be integrated into ETYS. We have communicated our enduring plan to integrate Voltage needs into ETYS and will now progress the implementation.
3 | A7.1 Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Create slimmed down ETYS publication with traditional chapters available on our website and results visualised through interactive website content. | Q3-Q4 2021-22 | Complete | Q3 2021-22 | ETYS 2021 was successfully published on 29 Nov 2021 with some key enhancements to our boundary charts to show the impact of previous NOA recommendations. This is in response to stakeholder feedback and improves our communication of system need. The ETYS web-based publication has also been improved based on stakeholder feedback and website analytics to make it easier for our stakeholders to engage with our ETYS content. A Proof of Concept for integrating Pouya (PM) into the NOA process by providing circuit-based constraints on top of the boundary constraints has been developed and tested. Work is ongoing reviewing how pathfinder needs could be integrated in future ETYS.
3 | A7.1 Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Show a greater integration of all types of system needs within the ETYS publication. | Q2 2022-23 | Complete | Q4 2022-23 | We published ETYS on 31st Jan 2023 and included a dedicated chapter showcasing our year-round thermal needs and the enduring process we've developed to integrate voltage needs into ETYS. We also share our work towards including stability needs as we look to expand ETYS to communicate all types of system needs.
3 | A7.1 Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Review how ETYS can help signal needs considering the Whole system across Transmission / Distribution interface. | Q2-Q3 2022-23 | Complete | Q3 2022-23 | We have undertaken a review of how we can signal needs across the transmission/distribution interface. We have progressed discussions through the ENA Workstream 1B - Product 5 on Network Development. Over the past year, ESO has facilitated discussions with the TOs and DNOs to review how improvements can be made to transmission reporting and where best any reporting should be published (ETYS or otherwise). We have agreed to publish a transmission view alongside the DNO Scenario Headroom reports (rather than ETYS) where it helps provides that full picture of DNO headroom with a view on transmission. The outcomes of discussions are captured in the latest Form of Statement of NDP - 2022 transmission reporting section which will be published by the ENA December 2022. The Transmission owners have agreed to review provision of data by March 2023 to be included in the DNO Network Scenario Headroom reports that will be published in May 2023.
3 | A7.2 Advise on economic efficient ways to address networks needs | D7.2 | NOA Annual Report | Review outputs from our Offshore Wider Works assessment in NOA 20/21 and devise the process and tool requirements to fully evaluate the benefit of OWW options. | Q1 2021-22 | Complete | Q1 2021-22 | This has been completed. The assessment of OWW was delivered in the Holistic Network Development which use various tools to assess the impact of offshore connections and help propose an offshore and onshore coordinated network.
3 | A7.2 Advise on economic efficient ways to address networks needs | D7.2 | NOA Annual Report | Review outputs from NOA 20/21 and consider extension of Least Worst Regret approach to Least Worst Weighted Regret (LWWR) to explore sensitives to different scenarios, to inform NOA 2021/22 methodology. | Q1 2021-22 | Complete | Q1 2021-22 | This is completed - we reviewed the LWWR methodology and how it grants recommendations based on the number of scenarios the reinforcement was seen to be needed. We published this in the draft NOA methodology consultation which has been approved by Ofgem.
3 | A7.2 Advise on economic efficient ways to address networks needs | D7.2 | NOA Annual Report | Create slimmed down NOA publication with traditional chapters available on our website and results visualised through interactive website content. | Q3-Q4 2021-22 | Complete | Q4 2021-22 | This was delivered. We looked at the entire NOA publication and made it more streamlined and efficient. The NOA 2021 was 184 pages however, the NOA 2022 was only 40 pages. In July 2022, we also produced the interactive maps that allow users to visualise the network and see NOA/HND schemes overlaid on the geographic network diagram
3 | A7.2 Advise on economic efficient ways to address networks needs | D7.2 | NOA Annual Report | Undertake enhancements to the NOA Annual Report in response to stakeholder feedback. | Q1 2022-23 | Complete | Q2 2022-23 | The NOA report was published on 31st January 2022. The NOA report combined the feedback from the consultation run in the NOA methodology and were included the publication.
3 | A7.2 Advise on economic efficient ways to address networks needs | D7.2 | NOA Annual Report | Review and consolidation of NOA methodology, including learning from the LWWR investigation. | Q2 2022-23 | Complete | Q2 2022-23 | This activity has been completed. The NOA methodology was reviewed and the draft was consulted in the industry. We updated the methodology following feedback and submitted this to Ofgem for approval and has been approved.
3 | A7.2 Advise on economic efficient ways to address networks needs | D7.2 | NOA Annual Report | Establish a process to assess the benefits of OWW including the wider social benefits alongside onshore transmission reinforcement plans [this milestone is dependent upon the outcome of preceding development work and on developments made as part of the BEIS Offshore Transmission Network Review]. | Q4 2022-23 | Complete | Q2 2022-23 | The benefits of OWW was delivered in the Pathway to 2030 works which covered the Holistic Network Development activities and the NOA refresh. One of the design principles in HND was to look into community and social impacts in the network design process. The outputs of this was delivered earlier in the NOA refresh as pat of the Pathway to 2030 suite of publication. There is further development work that is underway which we plan to implement in tCSNP due in December 2023 however, we will do a more robust integration on this in CSNP in BP2.
3 | A7.3 Undertake ad hoc analysis in response to external requests | D7.3 | Strategic Wider Works (SWW) (or Large Onshore Transmission Projects (LOTI) for RIIO-2) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Finalise processes to facilitate LOTI requirements in collaboration with TOs and Ofgem. | Q1 2021-22 | Complete | Q1 2021-22 | We continue to work in partnership with the Transmission Owners, to deliver the important load-flow analysis to support the initial and final needs cases for TO LOTI projects. We will continue to work with TOs and Ofgem to continually improve the process, and ensure the output is meeting the needs of the TOs and Ofgem to allow them to make the investment decisions needed to deliver the future net zero transmission system.
3 | A7.3 Undertake ad hoc analysis in response to external requests | D7.3 | Strategic Wider Works (SWW) (or Large Onshore Transmission Projects (LOTI) for RIIO-2) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Adhoc support as required | Q1-Q4 2022-23 | Complete | Q4 2022-23 | We worked in partnership with the Transmission Owners, to deliver the important load-flow analysis to support the initial and final needs cases for TO LOTI projects. We worked with TOs and Ofgem to continually improve the process, and ensure the output is meeting the needs of the TOs and Ofgem to allow them to make the investment decisions needed to deliver the future net zero transmission system.
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Annual assessment undertaken to identify system needs / next priority area. Pennines voltage pathfinder outputs /recommendation is available. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | Pennines Pathfinders Tender process has been successfully concluded and the results were published on 7th Feb 2022 We are assessing future requirement for both Constraint Management and Voltage services and will go out to the Market if and when requirements identified.
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Conclusion (contracts awarded) of Stability Phase 2 tender. | Q2 2021-22 | Complete | Q4 2021-22 | The Stability Phase 2 tender is now complete. Contracts have been awarded and the results have been publicised.
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Conclusion (contracts awarded) of Pennines voltage tender. | Q4 2021-22 | Complete | Q4 2021-22 | Contracts successfully awarded and communicated with market. The event saw the first OFTO asset for a wind farm being awarded a contract and along with the other successful solutions is expected to save consumers millions of pounds through the competitive event.
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Constraint management pathfinder outputs are incorporated into the NOA methodology. | Q4 2021-22 | Complete | Q2 2022-23 | The NOA methodology has now been approved by Ofgem and they welcomed the inclusion of the constraint management pathfinder methodology.
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Constraint management pathfinder phase 1 year 1 tender concluded. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | Constraint Pathfinder for B6 tender concluded and contract awarded and agreed. On Schedule for service delivery in 2023
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Constraint management pathfinder phase 1 year 2 tenders communicated. | Q1-Q4 2021-22 | Complete | Q4 2021-22 | The Tender for CMP B6 phase 1 year 2 is open (08/08/2022 - 16/09/2022) and contracts were awarded in October 2022.
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Annual assessment undertaken to identify system needs. | Q1-Q4 2022-23 | Complete | Q3 2022-23 | Annual voltage screening report was published on 30th June 2022. Internal review of voltage needs has been completed for 2025 to identify areas of need in England and Wales. We have worked with NGET to refine the high voltage requirements for 2025 which has led to the consideration of new reactive investments by NGET supported by ESO analysis for delivery in 2025. We are now working on initiating further procurement through a competitive tender process for delivery in 2026 for economic benefits.
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Review of constraint management pathfinder success | Q1-Q4 2022-23 | Complete | Q3 2022-23 | Lessons learned sessions have been completed for both CMP (2023/24) and CMP (2024/25) and lessons will be integrated into the tender design for subsequent tender events. Between April - July 2022, CMP delivered consumer saving of £30m which is a real success for the project.
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Constraint management pathfinder phase 1 year 2 tenders concluded. | Q1-Q4 2022-23 | Complete | Q3 2022-23 | 260922 - 1. The B6 CMP 24/25 Tender has now closed and we are currently in the evaluation phase. 2. Process is on schedule and expected to conclude with contracts awarded before Q4 22/23
3 | A8.1 Rollout of pathfinder approach and optimise assessment and communication of future needs | D8.1 | New areas of need identified, and 3-6 tenders run. | Constraint management pathfinder phase 1 year 3 tenders communicated. | Q1-Q4 2022-23 | Complete | Q4 2022-23 | 280223 - External comms released on next steps for B6 (next tender in 18 months to allow for redesign), new EC5 service, and indicative timelines. Forums were the Wind Advisory Group, Future of Balancing Services Newsletter, Strategic Network Development Newsletter, Corp Affairs press release, and Industry wide webinar.
3 | A8.2 Enhance tendering models | D8.2 | Improved tender approaches that enable more participants to enter the market. | New areas of need identified that will be tendered. Through lessons learned on earlier tender exercises undertaken in consultation with tender participants and wider industry, we will strive to improve the tendering experience. We will seek to broaden the market by reducing barriers to entry, increasing the scope of participants where possible (see D8.3 below). Specific timing of the lessons learned process is dependent upon tender timescales. | Q4 2021-22 | Complete | Q3 2021-22 | We are currently assessing what future Pathfinders may be required We continue to undertake lessons learnt from each pathfinder we run and where appropriate implement that learning in subsequent pathfinders. This year we intend to implement bay reservation into stability 3 Pathfinder as a consequence of the feedback from market parties and TO's.
3 | A8.2 Enhance tendering models | D8.2 | Improved tender approaches that enable more participants to enter the market. | Tenders prepared and run on 2021-22 work (which are currently not known) | Q4 2022-23 | Complete | Q2 2022-23 | Lessons learnt & STC Modifications have been made to improve tender approach for Stability 3 Pathfinder
3 | A8.3 Support Ofgem to establish enabling regulatory and funding frameworks | D8.3 | Frameworks based on competitive regime not monopoly regime. | Identify further possible changes to CUSC to remove blockers to competition depending on the outcome of CMP334. | Q1 2021-22 | Complete | Q1 2021-22 | As Pathfinders have evolved we have identified a number of areas, both in the different codes and processes, which would benefit from being amended - we are working with BEIS, Ofgem and the industry to look at these solutions. CMP334 is now approved by Ofgem which has resulted in voltage pathfinder projects no longer being treated as final demand. We will keep under review other Pathfinder projects and any further changes required to the codes.
3 | A8.3 Support Ofgem to establish enabling regulatory and funding frameworks | D8.3 | Frameworks based on competitive regime not monopoly regime. | Assess and adapt processes to accommodate any new regulatory funding arrangements. | Q4 2021-22 | Complete | Q4 2021-22 | As Pathfinders have evolved we have identified a number of areas, both in the different codes and processes, which would benefit from being amended - we are working with BEIS, Ofgem and the industry to look at these solutions. CMP334 is now approved by Ofgem which has resulted in voltage pathfinder projects no longer being treated as final demand. We will keep under review other Pathfinder projects and any further changes required to the codes.
3 | A8.3 Support Ofgem to establish enabling regulatory and funding frameworks | D8.3 | Frameworks based on competitive regime not monopoly regime. | Work with industry and BEIS (for wider policy aspects) to identify and implement any other framework changes that may be needed; support Ofgem to consider RIIO-ED2 funding implications. | Q1-Q4 2022-23 | Complete | Q2 2022-23 | As Pathfinders have evolved we have identified a number of areas, both in the different codes and processes, which would benefit from being amended - we are working with BEIS, Ofgem and the industry to look at these solutions. CMP334 is now approved by Ofgem which has resulted in voltage pathfinder projects no longer being treated as final demand. We will keep under review other Pathfinder projects and any further changes required to the codes.
3 | A9.1 Expand network planning processes to enable more connections wider works to be assessed | D9.1 | Developed and trialled connection wider works (CWW) processes with TOs. | Review existing network planning processes and identify where and how to extend. | Q3 2021-22 | Milestone no longer valid |  | This deliverable is to be marked as "Milestone no longer valid", This has been approved by Ofgem and will be picked up in the whole network planning review process (NPR) which will look at improving the whole network planning process including identifying wider transmission investment works driven by new connections
3 | A9.1 Expand network planning processes to enable more connections wider works to be assessed | D9.1 | Developed and trialled connection wider works (CWW) processes with TOs. | Undertake initial conversations with TOs and Ofgem, and explore initial technical feasibility, and potential exchange processes. | Q2 2022-23 | Milestone no longer valid |  | This deliverable is to be marked as "Milestone no longer valid", This has been approved by Ofgem and this deliverable will be picked up in the whole network planning review process (NPR) which will look at improving the whole network planning process including identifying wider transmission investment works driven by new connections
3 | A9.1 Expand network planning processes to enable more connections wider works to be assessed | D9.1 | Developed and trialled connection wider works (CWW) processes with TOs. | Undertake trial. | Q3 2022-23 | Milestone no longer valid |  | This deliverable is to be marked as "Milestone no longer valid", This has been approved by Ofgem and this deliverable will be picked up in the whole network planning review process (NPR) which will look at improving the whole network planning process including identifying wider transmission investment works driven by new connections
3 | A9.2 Trial assessment of all connection wider works in one region | D9.2 | Completed and published connection wider works trials, in selected geographic regions, in NOA. | Review existing network planning processes and identify where and how to extend. | Q3 2021-22 | Milestone no longer valid |  | This deliverable is to be marked as "Milestone no longer valid", This has been approved by Ofgem and this deliverable will be picked up in the whole network planning review process (NPR) which will look at improving the whole network planning process including identifying wider transmission investment works driven by new connections
3 | A9.2 Trial assessment of all connection wider works in one region | D9.2 | Completed and published connection wider works trials, in selected geographic regions, in NOA. | Complete and publish outputs from connection wider works trials, based on the study work and trial undertaken in A9.1. | Q4 2022-23 | Milestone no longer valid |  | This deliverable is to be marked as "Milestone no longer valid", This has been approved by Ofgem and this deliverable will be picked up in the whole network planning review process (NPR) which will look at improving the whole network planning process including identifying wider transmission investment works driven by new connections
3 | A9.3 Expand to all Connections Wider Works (CWW) | D9.3 | Incremental expansion of the process (following trials) which results in making recommendations on all connections wider works in NOA 2026. | See D9.1 and D9.2 for deliverables which enable this deliverable. | N/A | Milestone no longer valid |  | This deliverable is to be marked as "Milestone no longer valid", This has been approved by Ofgem and this deliverable will be picked up in the whole network planning review process (NPR) which will look at improving the whole network planning process including identifying wider transmission investment works driven by new connections
3 | A9.4 Develop process with TOs to input into ESO analysis of end of life asset replacement decisions | D9.4 | Efficient planning process agreed with TOs | We will start to engage with TOs to determine, evaluate and agree the eligible set of criteria: Identify equipment categories to be evaluated and Undertake investigatory runs using the NOA tools to understand if feasible and sensible to do so. | Q1 2022-23 | Milestone no longer valid |  | This deliverable is to be marked as "Milestone no longer valid", This has been approved by Ofgem and this deliverable will be picked up in the whole network planning review process (NPR) which will look at improving the whole network planning process including identifying options and strategies for replacing assets on the transmission system