## Sheet1
CMP316 Action Log
Action Number | Workgroup raised | Owner | Action | Comment | Due by | Status
1 | WG1 | NW/AH | Examples of the various permutations. | Six examples provided in WG2. Further examples to be provided: - 3 technology type - At least 2 months of temporary TEC (LDTEC and STEC) - Positive and negative tariffs (made up) | WG3 | Open
2 | WG1 | NW/AH | Declaration process vs contracts | Further explore declaration process route Provide further evidence to support using capacity in contracts. And explanation of how the proportions are derived. | WG3 | Open
3 | WG1 | NW/AH | Provide a list of the relevant definitions | Provided WG2 | WG2 | Close
4 | WG1 | AH | Consider impact to connection agreements |  | WG2 | Close
5 | WG1 | NW | Consider transitional arrangements for implementation | Talk to sub groups and trade associations. | WG3 | Open
6 | WG2 | JG/RGA | Include within WG Consultation/Report any discussion on how this process would work for embedded gens with less than 100MW TEC | So far discussed concerns that some of these do not have TEC. Flag consultation to DNOs. | WG4 | Open
7 | WG2 | All | Explain impacts on ALF setting process | Confirm - if there are no separate meters - what ALF is used. | WG3 | Open
8 | WG2 | AH | Provide relevant published documents on how many co-located sites there may be in the future |  | WG3 | Open
9 | WG2 | JG/RGA | Circulated examples spreadsheet and updated slides |  | WG3 | Open