## CUSC Prioritisation
CUSC - Prioritisation Stack
Mod Number | Panel Comments on Prioritisation as at 29 October 2021 | Proposer Name | Proposer Organisation | Title
High - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP315 and CMP375 | • Panel recognised there is a material impact here; however, argued that need to understand the TCR outcome before progressing further November 2020 Panel agreed to move CMP315 from “Low to Medium” to “High” in light of recent developments re: the Expansion Constant. April 2021 Panel noted that no CMP315 Workgroups were planned to be held until the ESO have clarified their wider solution on the Expansion Constant (Modification CMP375 was raised at June 2021 Panel) but the ESO, the CMP315 Proposer would continue to discuss data requirements with the Transmission Owners. On balance, April 2021 Panel agreed to keep CMP315 high in the prioritisation stack given the materiality of the proposed change even though there will be no Workgroups planned for the foreseeable future. ESO's modification re: the wider solution on the Expansion Constant (CMP375) was presented to the June 2021 Panel. Panel agreed that CMP315 will be progressed in parallel with CMP375 with Workgroups on the same day. Panel noted that CMP375 is a complex change and agreed that it is better to commence this as soon as possible and provide clarity for stakeholders on the future of the Expansion Constant and placed this “High” in the prioritisation stack. Given the interaction with CMP315, CMP315 will remain high in the prioritisation stack. At October 2021 Panel, a Panel Member proposed moving the priority from “High” to “Medium” on the basis that this may be better progressed as part of a broader review of TNUoS and Ofgem have launched a Call for Evidence on this (1 October 2021 to 12 November 2021). Other Panel Members, noted that as this is just at the Call for Evidence stage, it would be more appropriate to revisit priority at January 2022 Panel. However, Panel did agree that this does not need to be progressed at current pace but the pace needs to be in line with that for other “High” priority Modifications. | Nick Sillito (CMP315) Grahame Neale (CMP375) | PeakGen ESO | TNUoS: Review of the expansion constant and the elements of the transmission system charged for (CMP315) Enduring Expansion Constant & Expansion Factor Review (CMP375)
CMP328 | • Raised on behalf of all DNOs • Needs to be progressed in parallel with completion of Transmission and Distribution interactivity process (expected to be completed ~ April 2021) • Significant volumes of these Tertiary Windows connections already progressing so there is a pressing need for a solution Panel have previously expressed concern on the direction of travel; however October Panel noted recent progress made and re-assessed priority at November Panel following the Workgroup on 19 November 2020. The Panel noted the complexity of CMP328 and the need for one more Workgroup in January 2021 prior to the Workgroup Consultation being issued. The November 2020 Panel were content to defer the decision on CMP328 until January 2021 Panel with the expectation that the Workgroup Consultation had been issued by then. However, as the Workgroup has been delayed at Proposer's request to 10 February 2021, Code Admin proposed that the decision on CMP328 prioritisation was deferred until February 2021 Panel. Panel agreed to this request. February 2021 noted that Workgroup Consultation was issued on 19 February 2021 and left priority unchanged. | Joanna Knight | Scottish and Southern Energy Power Distribution Limited | Connections Triggering Distribution Impact Assessment
CMP361/CMP362 | CUSC Panel on 26 February 2021 agreed to place high in the prioritisation stack as this addresses the 2nd deliverable of the 2nd BSUoS Taskforce. CMP308, which addresses the 1st deliverable of the 2nd BSUoS Taskforce, is already placed high in the prioritisation stack | Jenny Doherty | ESO | BSUoS Reform: Introduction of an ex ante fixed BSUoS tariff (CMP361) and Consequential Definition Updates (CMP362)
CMP363/CMP364 | CUSC Panel on 26 February 2021 agreed to place high in the prioritisation stack as this is related to the TCR and an Ofgem decision is needed by 1 October 2021. June 2021 Panel noted that implementation is expected to be delayed by 1 year from 1 April 2022 to 1 April 2023. However, as this is only Ofgem's minded to position (and therefore is not yet confirmed), the June 2021 Panel agreed to leave CMP363/364 as "High" in the prioritisation stack and re-consider at the next Panel after Ofgem's minded to position is confirmed | Grahame Neale | ESO | TNUoS Demand Residual charges for transmission connected sites with a mix of Final and non-Final Demand (CMP363) and Definition changes for CMP363 (CMP364)
Medium to High - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP300 | July 2021 Panel noted that Ofgem have requested the Final Modification Report to be updated and returned to them as soon as possible. Panel members noted that whilst there is a low materiality, it is better to address now rather than later and agreed that it should be prioritised the same as CMP344. Therefore, CMP300 has been prioritised as "Medium to High" | Paul Youngman | Drax | Cost reflective Response Energy Payment for Generators with low or negative marginal costs
CMP316 | • Although not many co-located sites currently, this complex change needs to be progressed before volumes become large and unmanageable • Clarity needed ahead of Contracts for Difference Auctions in 2021 • April 2022 Implementation February 2021 Panel agreed to leave priority unchanged; however, Code Admin noted that as CMP304 and CMP316 are next in the prioritisation stack that they would contact Proposers of these Modifications to agree number and content of Workgroups pre and post Workgroup Consultation and agree a suitable end to end timeline based on re-starting in ~ August 2021. At June 2021 Panel, some Panel members noted that there has been greater interest in co-location over the last 2-3 months and a Panel Member believed more sites will be re-purposed in the near future. Therefore, the June 2021 Panel agreed to change the priority from "Medium" to Medium to High". | Nicola White | ESO | TNUoS Charging Methodology for Co-located Generation
CMP330/CMP374 | • Simple change and potential for cost savings and faster connections • Clarity needed ahead of Contracts for Difference Auctions in 2021 October Panel were content with progress made and agreed to leave priority unchanged. May 2021 Panel agreed that this should be amalgamated with CMP330 and it’s position to remain unchanged with the prioritisation stack. | Andy Pace | Energy Potential Limited | Allowing new Transmission Connected parties to build Connection Assets greater than 2km in length
CMP344 | Panel noted that Ofgem have requested the Final Modification Report to be updated and returned to them as soon as possible. Some Panel members argued that this should be High in the prioritisation stack as this is where CMP344 was placed previously; however other Panel members noted that CMP344 had a time constraint before. Overall, Panel agreed for this to be Medium to High priority and believed that 2 Workgroups would be needed, which are anticipated to start from September 2021. | Ton Steward | RWE | Clarification of Transmission Licensee revenue recovery and the treatment of revenue adjustments in the Charging Methodology
CMP376 | July 2021 Panel placed this as "Medium to High" in the prioritisation stack. Panel noted the high materiality and there a number of unanswered questions, which a CUSC Workgroup will need to address. Given the extensive work already done on "Queue Management" and that the process will be used across industry imminently, the July 2021 Panel agreed that this should be progressed sooner rather than later. | Keren Kelly | ESO | Inclusion of Queue Management process within the CUSC
Medium - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP286 / CMP287 | At March 2021 Panel, the CUSC Panel reviewed CMP286/287 following a stakeholder’s question about why this wasn’t currently being progressed. CUSC Panel’s views were mixed on the materiality of the proposed change and specifically re: CMP287 a Panel member noted that CMP343 (if implemented) would improve the predictability of TNUoS, However, before they consider amending CMP286/287’s position in the prioritisation stack, they needed assurance that the Proposer still wishes to progress this. Code Admin noted they have already tried to make contact with the Proposer but would contact them again ahead of April 2021 Panel and provide them with some options on next steps. April 2021 Panel left priority unchanged. They noted that Paul Mullen spoke to Proposer on 1 April 2021 and that the Proposer remains keen to move this forward. However, the Proposer acknowledged they may need to review their solution following the TCR decisions. Proposer sought re-prioritisation of this Modification at October 2021 Panel and Panel agreed to move the priority from Low to Medium as there is now clear drive from the Proposer and the lower risk premiums (that Suppliers will include) will benefit consumers. | Niall Coyle | Npower | Improving TNUoS Predictability Through Increased Notice of: The Target Revenue used in the TNUoS Tariff Setting Process (CMP286); and Inputs Used in the TNUoS Tariff Setting Process (CMP287)
CMP288 / CMP289 | • Panel recognised a lot of work done on this, but Workgroup Members on the Panel questioned whether or not 2 workgroups are sufficient to complete this • Materiality unclear as proposal seeks to add transparency to the existing arrangements February 2021 Panel noted the Proposer's view that continued delay has caused issues agreeing One-off Works charges between customers, the ESO and NGET Transmission Owner (TO). They argued that this could lead to a risk of legitimate TO-incurred costs not being recoverable from customers via the ESO. However, Panel members agreed to leave priority unchanged. Given the interest in this progressing (2 different parties wished to become Proposer) , the July 2021 Panel agreed for the priority to move from "Low to Medium" to "Medium". Workgroups to re-commence from December 2021. | Jon Wisdom | ESO | Explicit charging arrangements for customer delays and backfeeds (CMP288); Consequential change to support the introduction of explicit charging arrangements for customer delays and backfeeds via CMP288 (CMP289)
CMP298 | • Will have long term benefits to consumers (by allowing more projects to connect and so provide more competition in the generation market • Complex change • This is a process improvement modification and is seeking to reflect current working practice. However, there is risk of inconsistency in its application by Network Operators so important that Code changes are progressed. October Panel reviewed the request from the Open Networks to re-start Workgroups and noted the increasing risk of divergence in treatment across Network Operators. Therefore, priority was raised from Low to Medium. Workgroups re-commenced 23 February 2021. | Grahame Neale | ESO | Updating the Statement of Works process to facilitate aggregated assessment of relevant and collectively relevant embedded generation
CMP304 | • Modification seeks to apply a different timescale to the provision on reactive power – Panel divided though on whether this is a simple change as solution still needs to be clarified • Ofgem cannot make a final decision on CMP305 until CMP304 is completed • Decreased cost to consumers if more competition February 2021 Panel agreed to leave priority unchanged; however Code Admin noted that as CMP304 and CMP316 are next in the prioritisation stack that they would contact Proposers of these Modifications to agree number and content of Workgroups pre and post Workgroup Consultation and agree a suitable end to end timeline based on re-starting in ~ July 2021. An end to end timeline was indicatively agreed with the Proposer based on re-starting in July 2021; however, other pressing priorities (notably GC0151 and CMP368/369) means this needs to be revisited and a meeting has been sought with the Proposer to discuss with a view to re-starting Workgroups in November 2021. | Garth Graham | SSE | Improving the Enhanced Reactive Power Service by making it fit for purpose
Low to Medium - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP379 | September 2021 Panel placed this as "Low to Medium" in the prioritisation stack as they considered this has a low materiality and a decision is not needed until end December 2022. Therefore, Workgroups will not commence in 2021. | James Stone | ESO | Determining TNUoS demand zones for transmission-connected demand at sites with multiple Distribution Network Operators (DNOs)
Low - note that the Modifications are listed in numerical order and are not in priority order within this priority category
CMP291 | • Complex change • Enduring requirement but no compliance date set February 2021 Panel agreed to leave priority unchanged. At June 2021 Panel, a Panel Member (and Proposer of CMP291) noted that the revised terms of reference for GC0117 ask the GC0117 Workgroup to consider the work done on CMP291). Therefore, although the Panel Member (and Proposer of CMP291) was not specifically seeking to raise the priority of CMP291, it now seems that CMP291 is considered relevant to the work of both GC0117 and also the Open Networks project and therefore there is a case for it to be moved up the prioritisation stack. Panel questioned whether there was indeed any dependency on GC0117 needing CMP291 to progress and Code Admin agreed to discuss with the Grid Code Review Panel ESO and Code Admin representatives to understand this further and the Grid Code Review Panel ESO representative confirmed that progression of GC0117 is not dependent on CMP291 progressing . Therefore, CMP291 will remain “Low” in the prioritisation stack. | Garth Graham | SSE | The open, transparent, non discriminatory and timely publication of the harmonised rules for grid connection (in accordance with the RfG, DCC and HVDC) and the harmonised rules on system operation set out within the Bilateral Agreements
CMP311 | • Important in current Covid-19 environment to provide as much clarity for suppliers as possible • Solution already consulted on and even with revised solution anticipate 2 Workgroups to get this to Panel Workgroups were due to commence from November 2020; however, at September Panel, ESO highlighted that the RIIO draft determinations are due to be published in December and the ESO are anticipating that this will resolve the issue that CMP311 addresses. As this won’t be confirmed until the determinations are published, October Panel agreed to de-prioritise and revisit at February 2021 Panel. February 2021 Panel agreed to leave priority unchanged. | James Stone | ESO | Reassessment of CUSC credit requirements for Suppliers, specifically for “User Allowed Credit” as defined in Section 3, Part III section 3.27 of the CUSC
CMP331 | • April 2022 Implementation at earliest • Materiality on the wider charging base not clear October Panel agreed to leave priority unchanged but noted requested implementation date of 1 April 2022. February 2021 Panel noted that even if Workgroups started now, no decision would be achieved (without Urgency) in time to meet a 1 April 2022 Implementation Date. Panel also agreed to leave priority unchanged. | Andy Pace | Energy Potential Limited | Option to replace generic Annual Load Factors (ALFs) with site specific ALFs
CMP341 | • Complex • Although a CACOP and Ofgem driven initiative, there does not appear to be any current industry appetite to progress February 2021 Panel agreed to leave priority unchanged. | Rob Wilson | ESO | CUSC Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions
CMP358/CMP359 | Following Ofgem’s decision on 15 January 2021 not to approve urgent treatment of CMP358/359, the CUSC Panel on 21 January 2021 considered where CMP358/359 would sit within the prioritisation stack. The majority of the Panel believed that Ofgem have been consistent and explicit that the Small Generator Discount would be removed and didn’t agree with one Panel member’s view that there was an expectation something else would be replacing it. They also noted that there are a lot of other existing Modifications that have yet to be even progressed and did not believe that such a known issue provided a convincing case for CMP358/359 to be placed above these Modifications in the prioritisation stack. The CUSC Panel on 21 January 2021 concluded that CMP358/359 would be placed “Low” in the current prioritisation stack and therefore there will be no CMP358/CMP359 Workgroups in the foreseeable future. Waters Wye, who are representing the Proposer, attended the CUSC Panel on 29 January 2021 to challenge this decision. They primarily cited the compound impact for Scottish Generators of the removal of the Small Generator Discount with the latest Transmission Generation Residual decisions and the current general uncertainty. After careful consideration, the Panel decided to maintain their previous decision for the same reasons they provided at Panel on 21 January 2021. Proposer updated their assessment against the prioritisation criteria and this was presented to February 2021 Panel - Panel did not believe there was any strong evidence to change priority and agreed to leave priority unchanged. | David Bruce | Afton Wind Farm Limited | Implementation of the Small Generator Discount into the CUSC (CMP358) and Definition changes for CMP358 (CMP359)
CUSC Prioritisation Criteria
Section 8: 8.19.1.(e) makes the following provision for the Panel and states “Having regard to the complexity, importance and urgency of particular CUSC Modification Proposals, the CUSC Modifications Panel may determine the priority of CUSC Modification Proposals and may (subject to any objection from the Authority taking into account all those issues) adjust the priority of the relevant CUSC Modification Proposal accordingly”
Complexity | The modification is viewed as being resource intensive and will most likely require a higher than average number of workgroups to conclude the process. Additionally, the modification defect is viewed to have implications for many different areas of the energy market which need to be taken into consideration throughout the process.
Importance | The perceived value & risk associated with the proposed modification. The value / risk could be considered from a number of different perspectives i.e. financial / regulatory / licence obligations both directly for customer and end consumers more generally.
Urgency | A modification which requires speedy consideration within the code governance process, both complexity and importance should be factors considered in evaluating urgency as well as the timescales for implementation within the respective code.