Stability Phase 2 Project Plan Report

|  |  |
| --- | --- |
| **Date of Report:** |  |
| **Project Name:** |  |
| **Contract No:** |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Section** | **Summary of updates/progress/issues** | **Summary of updates/progress/issues** | **Initial completion date (from tender submission)** | **Latest completion date** |
| Financing | Internal sanction/approval/investment decision secured for project |  |  |  |
| Access to financing/credit secured - applies to internal and external means of finance |  |  |  |
| Connection Agreement | Application submitted for connection agreement |  |  |  |
| Connection agreement signed |  |  |  |
| Commencement of connection work by the TO |  |  |  |
| Completion of connection work by the TO |  |  |  |
| Planning | Submission of site investigation works application |  |  |  |
| Submission of Highways Agency planning application |  |  |  |
| Submission of environmental planning application |  |  |  |
| Submission of construction planning application |  |  |  |
| Approvals received for all planning applications |  |  |  |
| Land rights | Access to land secured |  |  |  |
| Are there any third-party dependencies to meeting this date? |  |  |  |
| Equipment | Orders placed for facility |  |  |  |
| Orders placed for cables |  |  |  |
| Balance of plant | Procurement exercise carried out to select BOP contractor |  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Site works | Access to site secured |  |  |  |
| Commencement of demolition works on site (If applicable) |  |  |  |
| Clearing of site ahead of construction |  |  |  |
| Construction | Construction of foundations |  |  |  |
| Delivery of equipment to site |  |  |  |
| Installation of equipment |  |  |  |
| Commissioning testing complete |  |  |  |
| Synchronisation to the NETS |  |  |  |
| Completion of Grid Code compliance tests |  |  |  |
| Completion of Commercial contract Proving tests |  |  |  |