## Sheet1
CMP316 Action Log
Action Number | Workgroup raised | Owner | Action | Comment | Due by | Status
1 | WG1 | NW/AH | Examples of the various permutations. | Six examples provided in WG2. Provided WG3: - 3 technology type - At least 2 months of temporary TEC (LDTEC and STEC) For WG4: - Positive and negative tariffs (made up) - Extreme case examples on large and small load factors | WG3 | Open
2 | WG1 | NW/AH | Declaration process vs contracts | Further explore declaration process route Provide further evidence to support using capacity in contracts. And explanation of how the proportions are derived. Check declaration process in TDR mods and how this could be applied to CMP316. | WG3 | Open
3 | WG1 | NW/AH | Provide a list of the relevant definitions | Provided WG2 | WG2 | Closed
4 | WG1 | AH | Consider impact to connection agreements |  | WG2 | Closed
5 | WG1 | NW | Consider transitional arrangements for implementation | Comms will be provided to sub groups and trade associations. Decision prior to draft tariffs being published. Process for declarations needs to be factored into timeline | WG3 | Open
6 | WG2 | JG/RGA | Include within WG Consultation/Report any discussion on how this process would work for embedded gens with less than 100MW TEC | So far discussed concerns that some of these do not have TEC. Flag consultation to DNOs. Ensure clear in the report that an assumption has been made that if TNUoS is extended to embedded gens less than 100MW then this will be based on TEC | WG4 | Open
7 | WG2 | All | Explain impacts on ALF setting process | Confirm - if there are no separate meters - what ALF is used. Working assumption is that there is a separate BMU. | WG3 | Open
8 | WG2 | AH | Provide relevant published documents on how many co-located sites there may be in the future |  | WG3 | Closed
9 | WG2 | JG/RGA | Circulated examples spreadsheet and updated slides |  | WG3 | Closed
10 | WG3 | NW | Check risk of the mod leading to parties taking out multiple temporary TEC contracts to game system |  | WG4 | Open
11 | WG3 | NW | Different technologies behind an inverter - how does this work | Working assumption is that there is a separate BMU. | WG4 | Open
12 | WG3 | JG/RGA | Explain within WG report that no costs for existing contracts intended |  | WG4 | Open
13 | WG3 | JG/RGA | Recirculate amended examples spreadsheet - typo corrected |  | WG4 | Open