## Plan
Proposed CMP298 Implementation Plan (v1)
Key
Trance | Month | [24 empty] | Comments | All - Project set up & GSP tranche allocation
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  | DNO - data gathering & submission
0 | [25 empty] | To be done before decision | All - data query/updates
1 | [25 empty] | Assumed extra time needed as first tranche | ESO/TO - Offer creation
2 | [25 empty] | Assumed extra time needed as first tranche | DNO - offer review, queries & acceptance
3 | [25 empty] | Assumed extra time needed as first tranche
4 | [25 empty] | Assumed lower acceptance time from this point | No. of contracts to be updated
5 | [26 empty] | 200
6
7 | [26 empty] | Average No. GSPs per trance
8 | [26 empty] | 29
Notes
Regular dialogue/discussion not shown but expected
Project set up occurs before implementation (shown as month 0, including allocating GSPs to tranches)
Assumes no progress on data provision before implementation
If a GSP mod-apps during the process, we will update the T&Cs on to new format so can be removed from tranche
If an offer isn't accepted, GSP would be added back in to the 'pot' to be reallocated to a tranche (may not be the original tranche the GSP was in)
Tranche 8 to be a 'sweep up' tranche
Assumes ETI trigger criteria remains largely unchanged. If ETI trigger criteria is changed. This will impact workload and so needs early comms
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimate April 2022 but dependant on Ofgem decision timescales
Note on Q13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could reduce DNO data gathering time

## GSP List
GSP | DNO | Tranche
To be filled in!