## North_of_Scotland
Appendix A present the NOA 2021/22 Refresh recommendations from our economic cost–benefit analysis.
Code | Option Name | EISD | RISD | Optimal delivery date | NOA 2021/22 Refresh recommendation | Cost band | Eligible for competition?
BBNC | Beauly to Blackhillock 400 kV double circuit addition | 2030 |  | 2030 | HND essential option | £100m-£500m | Y
BDUP | Uprate the Beauly to Denny 275 kV circuit to 400 kV | 2029 |  | 2030 | Hold
BLN4 | Beauly to Loch Buidhe 400 kV reinforcement | 2031 | 2030 | 2030 | HND essential option | £100m-£500m | Y
BPNC | A new 400 kV double circuit between Blackhillock and Peterhead | 2031 | 2030 | 2030 | HND essential option | £100m-£500m | Y
DLNC | Loch Buidhe to Dounreay 400 kV reinforcement | 2031 |  |  | Do not start
DLUP | Windyhill-Lambhill-Denny North 400 kV reinforcement | 2029 |  | 2029 | Proceed
DNEU | Denny North 400/275 kV second supergrid transformer | 2025 |  | 2026 | Hold
DSDC | Dounreay - Thurso - Spittal 400 kV reinforcement | 2030 |  |  | Do not start
DWNO | Denny to Wishaw 400 kV reinforcement | 2028 |  | 2028 | Proceed
DWUP | Kincardine - Wishaw 400 kV reinforcement | 2026 |  | 2026 | Proceed
E4D3 | Eastern Scotland to England link: Peterhead to Drax subsea HVDC Link | 2029 |  | 2029 | HND essential option | £2000m-£2500m | Y
E4L5 | Eastern Scotland to England 3rd link: Peterhead to the south Humber subsea HVDC Link | 2031 | 2030 | 2030 | HND essential option | £2000m-£2500m | Y
LWUP | Kincardine 400 kV reinforcement | 2027 |  | 2027 | Proceed
PSDC | Spittal to Peterhead HVDC reinforcement | 2030 |  | 2030 | HND essential option | £1000m-£1500m | Y
SLU4 | New network need between Loch Buidhe and Spittal | 2030 |  | 2030 | HND essential option | £100m-£500m | Y
TFPC | Power flow control device along Tealing to Westfield | 2025 |  | 2027 | Hold
TKU2 | Alternative East Coast Onshore Phase 2 reinforcement | 2031 |  |  | Do not start
TKUP | East Coast Onshore 400 kV Phase 2 reinforcement | 2032 | 2030 | 2030 | HND essential option | £500m-£1000m | Y (part)

## Central belt&Anglo_Scottish Bor
Appendix A present the NOA 2021/22 Refresh recommendations from our economic cost–benefit analysis.
Code | Option Name | EISD | RISD | Optimal delivery date | NOA 2021/22 Refresh recommendation | Cost band | Eligible for competition?
BSHW | Blyth to Stella West circuits thermal uprating | 2024 |  | 2031 | Hold
CDHW | Cellarhead to Drakelow circuits thermal uprating | 2023 |  | 2023 | Proceed
CDP3 | Additional alternative power control devices along Cellarhead to Drakelow | 2024 |  | 2027 | HND essential option
CGNC | A new 400 kV double circuit between Creyke Beck and the south Humber | 2031 | 2030 | 2030 | HND essential option | £500m-£1000m | Y
CKPC | Power control device along Creyke Beck to Keadby to Killingholme | 2024 |  | 2025 | HND essential option
CLNC | New North West England to Lancashire reinforcement | 2034 |  | 2036 | Hold | £500m-£1000m | Y
CMNC | South east Scotland to north west England AC onshore reinforcement | 2033 |  | 2033 | Proceed | £100m-£500m | Y
CS05 | Commercial solution for Scotland and the north of England - stage 1 | 2024 |  | 2024 | Proceed
CS06 | Commercial solution for Scotland and the north of England - stage 2 | 2024 |  | 2024 | Proceed
CS11 | Commercial solution for the north of England - stage 1 | 2024 |  | 2024 | Proceed
CS12 | Commercial solution for the north of England - stage 2 | 2025 |  | 2025 | Proceed
CWPC | Power control device along Cottam to West Burton | 2024 |  | 2027 | HND essential option
E2DC | Eastern subsea HVDC link from Torness to Hawthorn Pit | 2027 |  | 2027 | HND essential option | £1000m-£1500m | Y
EHRE | Elvanfoot to Harker reconductoring | 2028 |  | 2030 | HND essential option
GWNC | A new 400 kV double circuit between the south Humber and south Lincolnshire | 2031 | 2030 | 2030 | HND essential option | £500m-£1000m | Y
HAE2 | Harker supergrid transformer 6 replacement | 2023 |  | 2023 | Proceed
HAEU | Harker supergrid transformer 5 and supergrid transformer 9A banking arrangement | 2022 |  | 2022 | Proceed
KCEU | Creyke to Keadby to Killingholme circuits thermal uprating | 2022 |  | 2025 | HND essential option
KCRE | Reconductor Cottam to Keadby 400 kV double circuit | 2025 |  | 2025 | HND essential option
KWHW | Keadby to West Burton circuits thermal uprating | 2024 |  | 2024 | HND essential option
KWP2 | Additional power control devices along the Keadby to West Burton number 1 circuit | 2025 |  | 2026 | HND essential option
KWPC | Power control device along Keadby to West Burton | 2024 |  | 2024 | HND essential option
LCU2 | Eastern B5 400 kV reinforcement | 2031 |  | 2037 | Hold
LNRE | Reconductor Lackenby to Norton 400 kV single circuit | 2024 |  | 2030 | HND essential option
LPD2 | Additional new HVDC link between North West England and North Wales | 2035 |  | 2037 | Hold
LPDC | New HVDC link between North West England and North Wales | 2035 |  | 2036 | Hold
MRP2 | Additional power control devices at both Harker and Penwortham | 2022 |  | 2022 | Proceed
NEMS | 225 MVAr MSCs within the north east region | 2025 |  | 2026 | Hold
NEP1 | Power control device along Blyth to Tynemouth and Blyth to South Shields | 2025 |  | 2025 | Proceed
NEPC | Power control device along Blyth to Tynemouth and Blyth to South Shields | 2024 |  | 2024 | Proceed
NOR4 | Reconductor a short span of the Norton-Osbaldwick 2 400 kV circuit | 2024 |  | 2030 | HND essential option
NOR5 | Reconductor a short span of the Norton-Osbaldwick 1 400 kV circuit | 2024 |  | 2027 | HND essential option
NOR6 | Reconductor the existing double circuit which runs from Norton to Osbaldwick | 2028 |  | 2037 | Hold
OPN2 | A new 400 kV double circuit between the existing Norton to Osbaldwick circuit and Poppleton and relevant 275 kV upgrades | 2027 |  | 2027 | HND essential option | £100m-£500m | Y (part)
PWMS | Two 225MVAr MSCs at Penwortham | 2025 |  | 2027 | Hold
SHNS | Upgrade substation in the south Humber area | 2031 | 2030 | 2030 | HND essential option
SNHW | Spennymoor to Norton circuit thermal uprating | 2024 |  | 2027 | Hold
SNRE | Reconductor the existing double circuit which runs from Spennymoor to Norton | 2027 |  | 2037 | Hold
SPRE | Reconductor the existing double circuit which runs from Spennymoor to Stella West | 2027 |  | 2037 | Hold
SSHW | Stella West to Spennymoor circuit thermal uprating | 2024 |  | 2027 | Hold
TGDC | Eastern subsea HVDC Link from east Scotland to south Humber area | 2031 | 2030 | 2030 | HND essential option | £1500m-£2000 | Y
TLNO | East Coast Anglo-Scottish onshore reinforcement | 2037 |  | 2037 | Proceed | £500m-£1000m | Y
VERE | Strathaven - Elvanfoot OHL conductor replacement | 2030 |  | 2030 | HND essential option
VSRE | Strathaven - Smeaton OHL conductor replacement | 2027 |  | 2027 | HND essential option
WCD2 | Second West Coast HVDC Link - Scotland to North Wales | 2036 |  |  | Do not start
WCNC | West Coast onshore Anglo-Scottish new circuit | 2036 |  | 2036 | Proceed | £1000m-£1500m | Y
WRRE | Reconductor West Burton to Ratcliffe-on-Soar circuit | 2028 |  | 2030 | HND essential option

## Midlands_South_East_of_England
Appendix A present the NOA 2021/22 Refresh recommendations from our economic cost–benefit analysis.
Code | Option Name | EISD | RISD | Optimal delivery date | NOA 2021/22 Refresh recommendation | Cost band | Eligible for competition?
AENC | A new 400 kV double circuit in north East Anglia | 2030 |  | 2030 | HND essential option | £100m-£500m | Y
ATNC | A new 400 kV double circuit in south East Anglia | 2030 |  | 2030 | HND essential option | £500m-£1000m | Y
BFHW | Bramley to Fleet circuits thermal uprating | 2024 |  | 2025 | Hold
BFPC | Power control device along Bramley to Fleet | 2025 |  | 2029 | Hold
BFRE | Bramley to Fleet reconductoring | 2025 |  | 2026 | Hold
BMM2 | Install new MSCs at Burwell Main | 2022 |  | 2022 | HND essential option
BPRE | Reconductor the newly formed second Bramford to Braintree to Rayleigh Main circuit | 2028 |  | 2028 | HND essential option
BRRE | Reconductor remainder of Bramford to Braintree to Rayleigh route | 2023 |  | 2023 | HND essential option
BTNO | A new 400 kV double circuit between Bramford and Twinstead | 2028 |  | 2028 | HND essential option | £100m-£500m | Y
BWRE | Reconductor Barking to West Ham double circuit | 2025 |  | 2028 | Hold
CDP1 | Power control device along Cellarhead to Drakelow | 2024 |  | 2027 | HND essential option
CDP2 | Power control device along Cellarhead to Drakelow | 2024 |  | 2027 | HND essential option
CS07 | Commercial solution for East Anglia - stage 1 | 2025 |  | 2025 | Proceed
CS08 | Commercial solution for East Anglia - stage 2 | 2025 |  | 2025 | Proceed
CTRE | Reconductor remainder of Coryton South to Tilbury circuit | 2022 |  | 2022 | Proceed
DFRE | Reconductor Drax to Fenwick Tee 400 kV circuit | 2026 |  | 2030 | HND essential option
DREU | Generator circuit breaker replacement to allow Thornton to run a two-way split | 2025 |  | 2025 | HND essential option
EBRE | Reconductor Enderby to Patford Bridge to East Claydon 400 kV double circuit | 2026 |  | 2030 | HND essential option
EDEU | 400 kV upgrade of Brinsworth to Chesterfield double circuit and Chesterfield to High Marnham double circuit. New High Marnham and Chesterfield 400 kV substations | 2027 |  | 2028 | HND essential option | £100m-£500m | Y (part)
EDN2 | New Chesterfield to Ratcliffe-on-Soar 400 kV double circuit | 2032 | 2030 | 2030 | HND essential option | £100m-£500m | Y
ERPC | Power control devices along the Enderby to Ratcliffe circuits | 2026 |  | 2033 | Hold
ESC1 | Second Elstree to St John’s Wood 400 kV circuit | 2026 |  | 2029 | HND essential option
FHRE | Reconductor the existing 400 kV single circuit which runs from Feckenham to Hams Hall | 2027 |  | 2033 | Hold
GCHW | Cottam to Market Harborough to Grendon circuit thermal uprating | 2025 |  | 2030 | HND essential option
GCRE | Reconductor the existing double circuit which runs from Cottam to Grendon | 2028 |  | 2037 | Hold
HWUP | Uprate Hackney, Tottenham and Waltham Cross 275 kV to 400 kV | 2027 |  | 2027 | HND essential option
IFR1 | Feckenham to Ironbridge circuit reconductoring | 2025 |  | 2030 | HND essential option
LRN2 | New network need from South Lincolnshire to East Midlands | 2033 |  |  | Do not start
LRN3 | New network need between South Lincolnshire and the South East | 2033 |  |  | Do not start
LRN4 | New network need from North Lincolnshire to Hertfordshire | 2033 | 2030 | 2030 | HND essential option | £500m-£1000m | Y
LRNC | South Lincolnshire to Rutland reinforcement | 2032 |  |  | Stop
MBHW | Bramley to Melksham circuits thermal uprating | 2024 |  | 2026 | Hold
MBRE | Bramley to Melksham reconductoring | 2026 |  | 2027 | Hold
NBEU | Thermal upgrade for Bramford and Norwich 400 kV substations | 2025 |  | 2028 | Hold
NBRE | Reconductor Bramford to Norwich double circuit | 2023 |  | 2023 | HND essential option
NTP1 | Power control device north of Tilbury 400 kV | 2024 |  | 2024 | Proceed
PEM1 | 225 MVAr MSCs at Pelham | 2024 |  | 2024 | Proceed
PEM2 | 225 MVAr MSCs at Pelham | 2024 |  | 2024 | Proceed
RHM1 | 225 MVAr MSCs at Rye House | 2024 |  | 2024 | Proceed
RHM2 | 225 MVAr MSCs at Rye House | 2024 |  | 2024 | Proceed
RTRE | Reconductor remainder of Rayleigh to Tilbury circuit | 2022 |  | 2022 | Proceed
SCD1 | New Offshore HVDC link between Suffolk and Kent option 1 | 2030 |  | 2030 | HND essential option | £1000m-£1500m | Y
SEEU | Reactive compensation protective switching scheme | 2024 |  | 2024 | Proceed
SER1 | Elstree to Sundon reconductoring | 2024 |  | 2024 | HND essential option
SER2 | Elstree to Sundon 2 circuit turn-in and reconductoring | 2026 |  | 2029 | HND essential option
TGP1 | Power control device along Tilbury to Grain | 2024 |  | 2024 | Proceed
TKP1 | Power control device along Tilbury to Kingsnorth | 2024 |  | 2026 | Hold
TKRE | Tilbury to Grain and Tilbury to Kingsnorth upgrade | 2028 |  | 2028 | Proceed
TWNC | Upgrade Wymondley, Waltham Cross and Tilbury 275 kV to 400 kV | 2033 |  | 2033 | Proceed | £100m-£500m | Y (part)
WAM1 | 225 MVAr MSCs at Walpole | 2025 |  | 2025 | Proceed
WAM2 | 225 MVAr MSCs at Walpole | 2025 |  | 2025 | Proceed
WCC1 | Cable replacement at Hinksey | 2027 |  | 2037 | Hold
WSEU | Thermal upgrade for Sundon and Wymondley 400 kV substation | 2024 |  | 2025 | HND essential option
WWNC | New South Lincolnshire to East Anglia double circuit | 2032 |  | 2033 | Hold
WYTI | Turn-in of the Pelham - Sundon 400 kV circuit into Wymondley substation | 2024 |  | 2028 | HND essential option

## Wales and Celtic Sea
Appendix A present the NOA 2021/22 Refresh recommendations from our economic cost–benefit analysis.
Code | Option Name | EISD | RISD | Optimal delivery date | NOA 2021/22 Refresh recommendation | Cost band | Eligible for competition?
CS20 | Commercial solution for north of Wales - stage 1 | 2026 |  | 2033 | Hold
CS21 | Commercial solution for north of Wales - stage 2 | 2026 |  | 2033 | Hold
HBUP | Uprate Bridgewater to 400 kV and reconductor the route to Hinkley | 2024 |  | 2027 | Hold
NWNC | New network need from North Wales to West Midlands | 2037 |  |  | Do not start
PSNC | New network need from North Wales to South Wales | 2037 | 2030 | 2030 | HND essential option | £2500m-£3000m | Y
PTC1 | Pentir to Trawsfynydd cable replacement | 2027 |  | 2028 | HND essential option
PTNO | A second transmission circuit on the existing Pentir to Trawsfynydd route | 2028 |  | 2029 | HND essential option
WPDC | New network need (alternative option) between North Wales and South Wales | 2035 |  |  | Do not start

## Version
Version control
2022-07-20 | Competition eligibility and cost bands added for eligible options. Option names updated to match NOA Refresh report.