## Intro
Appendix 1 - HND list of required Onshore and Offshore works
North
North West
South West
East
System Wide View
Introduction
This Appendix provides a list of all works identified as part of the Holistic Network Design (HND).
The Appendix can be navigated by clicking on the regional links to the right.
The regional sheets identify all the HND essential works required to connect the offshore windfarms in scope in that region. This covers both onshore and offshore works.
The system-wide view sheet identifies the wider network reinforcements which have been identified as required by either the NOA process or the connection assessment process for the HND and highlights their optimal delivery dates.
The HND recommendations outlined in Appendix 1 reflect our current and best view, based on information available today. As the development of these projects progresses towards delivery, more details will emerge and variations to the designs or delivery considerations may occur due to supply chain, network access, or other constraints. Furthermore, combining multiple projects into a single optimised delivery programme could result in currently unforeseen challenges. Therefore, these recommended delivery dates may be subject to change in future.
Some works require acceleration in their current estimated Earliest In Service Date (EISD) to deliver for 2030. Delivering these projects by 2030 will be challenging and will be reliant on the commitments outlined in the British Energy Security Strategy published in April 2022.
HND Recommendation Definitions
All works listed in this Appendix are required to achieve the Government’s ambition of connecting 50GW of offshore wind by 2030.
A more detailed HND recommendation is identified for all onshore works in the following sheets. The definition of this recommendation is explained below:
Required for connections that deliver 2030 targets:
These works are essential to connecting the 23 GW of in scope generation for the HND to the transmission system by 2030.
Required for [DATE]:
These works were found optimal by the NOA to be delivered on [DATE] because they provide significant consumer benefit through the reduction of constraints costs. This reinforcement may also be required on this date to ensure delivery dates are optimised with access to the system in order to take outages.

## 1 - North West
North West Region
Onshore Works
Short Description of Works | Type of works | Interface Point | NOA ref | HND Recommendation | Project Status | Notes
Busbar extension at Penwortham 400kV substation | Interface point | Penwortham | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Busbar extension at Penwortham 400kV substation | Interface point | Penwortham | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install additional bays at Bodelwyddan 400kV substation | Interface point | Boddlewyddan | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Modify Bodelwyddan circuits to a double turn in arrangement | Interface point | Boddlewyddan | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
New network need between North Wales and South Wales | NOA | N/A | PSNC | Required for 2030 | Scoping | Option requires acceleration to meet 2030 targets
Install a power control device on the Rugeley-Drakelow circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Feckenham - Minety 400kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Drakelow - Rugeley 400kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Ironbridge - Rugeley 400kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprate cable sections of Bishops Wood - Penn 275kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Drakelow - Hams Halls 400kV | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Bodelwyddan - Connahs Quay circuits | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
A second circuit on the existing Pentir to Trawsfynydd route | NOA | N/A | PTNO | Required for 2029 | Strategic Optioneering
Feckenham to Ironbridge circuit reconductoring | NOA | N/A | IFR1 | Required for 2030 | Strategic Optioneering
Reconductor the Padiham - Penwortham 400kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Carrington to Penwortham circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of SGT at Penwortham substation | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of the Kirkby leg of the Kirkby - Washway Farm - Penwortham circuit 1 | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of the Penwortham leg of the Kirkby - Washway Farm - Penwortham circuit 1 | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of the Kirkby leg of the Kirkby - Washway Farm - Penwortham circuit 2 | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of the Penwortham leg of the Kirkby - Washway Farm - Penwortham circuit 2 | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Replacement of a transformer at Rochdale | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of Drakelow - Hams Hall 400kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of Feckenham - Walham 400kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install power control devices on Cellarhead - Drakelow circuits | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Autoclosing scheme at Bishops Wood 132kV substation | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductoring the Cellarhead - Drakelow 400kV circuits | NOA | N/A | CDRE | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Connahs Quay leg of Connahs Quay - Legacy - Trawsfynydd circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Legacy leg of Connahs Quay - Legacy - Trawsfynydd circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install MSC's at Daines 400kV substation | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install MSC's at Ironbridge 400kV substation | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install MSC's at Drakelow 400kV substation | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Busbar extension at Pentir 400kV substation | Interface point | Pentir | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Installation of a new bay at Pentir 400kV substation | Interface point | Pentir | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Power control device along Cellarhead to Drakelow | NOA | N/A | CDP1 | Required for 2027 | Strategic Optioneering
Power control device along Cellarhead to Drakelow | NOA | N/A | CDP2 | Required for 2027 | Strategic Optioneering
Additional alternative power control devices along Cellarhead to Drakelow | NOA | N/A | CDP3 | Required for 2027 | Strategic Optioneering
Additional Power Control technology along Cellarhead-Drakelow overhead line A501 & A574 | Connection | NGET for the North West Options | CDP4 | Required for connections that deliver 2030 targets | Strategic Optioneering
Install power control devices on Bodelwyddan-Connahs Quay circuits | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Drakelow-Willington 400kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor part of the Drakelow-Ratcliffe on Soar 400kV circuit to increase circuit rating | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconfigure Bushbury-Drakelow 275kV circuit | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Turn-in of Bushbury-Drakelow 275kV circuit at Rugeley and uprate the new Rugeley-Drakelow circuit to 400kV | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install a new interbus tranformer at Rugeley 400kV | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconfigure Drakelow to uprate Rugeley-Drakelow to 400kV | Connection | NGET for the North West Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Busbar extension at Pentir 400kV substation | Interface point | Pentir | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Transfer of the existing Bodelwyddan-Connahs Quay 2 circuit to the extended substation | Interface point | Pentir | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Extension of the existing 400kV GIS building at Hunterston including additional bays for connection to the offshore network. The extent of the building extension will only be confirmed during the detailed design stage. | Interface point | Hunterston | N/A | Required for connections that deliver 2030 targets | Scoping
Eastern offshore HVDC link from Torness to Hawthorn Pit | NOA | N/A | E2DC | Required for 2027 | Planning/consenting
Eastern offshore HVDC link from Peterhead to Drax | NOA | N/A | E4D3 | Required for 2029 | Planning/consenting
Strathaven - Elvanfoot overhead line (OHL) Conductor Replacement | NOA | N/A | VERE | Required for 2030 | Scoping
Elvanfoot - Harker OHL Conductor Replacement | NOA | N/A | EHRE | Required for 2030 | Scoping
Offshore Works
Node 1 | Node 2 | Circuit capacity (MW) | Technology
SW_W1 | T-point | 2000 | DC 525 kV XLPE pair with co-axial metallic return
Hunterston | T-point | 2000 | DC 525 kV XLPE pair with co-axial metallic return
T- point | Pentir | 2000 | DC 525 kV XLPE pair with co-axial metallic return
R4_4 | Bodelwyddan | 1500 | AC 3-4 cables
R4_5 | Penwortham | 480 | AC 1 cable
R4_6 | Penwortham | 1500 | AC 3 cables

## 2 - North
North Region
Onshore Works
Short Description of Works | Type of works | Interface Point | NOA ref | HND Recommendation | Project Status | Notes
Establish a new 400kV substation site in the vicinity of the existing Spittal 275kV substation including bays for connection to the coordinated offshore network and works to connect the new site to the existing substation. The location of the new site is still to be confirmed. | Interface point | Spittal | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Establish a 1.8GW monopole HVDC link from a new 275kV substation site on the Western Isles, including bays for connection to the coordinated offshore network, to a site on the GB mainland. The location of the new site on the Western Isles and the site on the GB mainland is still to be confirmed | Interface point | Arnish | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Beauly to Loch Buidhe 400 kV reinforcement | NOA | N/A | BLN4 | Required for connections that deliver 2030 targets | Strategic Optioneering
New network need between Loch Buidhe and Spittal | NOA | N/A | SLU4 | Required for connections that deliver 2030 targets | Strategic Optioneering
Spittal to Peterhead HVDC reinforcement | NOA | N/A | PSDC | Required for connections that deliver 2030 targets | Strategic Optioneering
Beauly to Blackhillock 400 kV double circuit addition | NOA | N/A | BBNC | Required for connections that deliver 2030 targets | Design/development and consenting
Offshore Works
Node 1 | Node 2 | Circuit capacity (MW) | Technology
SW_N1 | Spittal | 2250 | AC 4-6 cables
SW_N4 | Arnish | 740 | AC 2-3 cables

## 3 - East
East Region
Onshore Works
Short Description of Works | Type of works | Interface Point | NOA ref | HND Recommendation | Project Status | Notes
Establish a new substation site in the vicinity of the existing Peterhead 400kV substation including bays for connection to the coordinated offshore network and works to connect the new site to the existing substation. The location of the new site is still to be confirmed. | Interface point | Peterhead | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Eastern offshore HVDC link from Peterhead to the south Humber | NOA | N/A | E4L5 | 2030 | Strategic Optioneering | Option requires acceleration to meet 2030 targets
Establish bays for connection to the coordinated offshore network at the existing Fetteresso 400kV substation. | Interface point | Feteresso | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install new bays, transformers and intertripping scheme at Blyth 400kV | Interface point | Blyth | N/A | Required for connections that deliver 2030 targets | Scoping
Reonfigure Blyth-Stella West 275kV circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
install power flow control devices on the Keadby-West Burton 2 400kV circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor Lackenby - Thornton 400kV circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Establish bays for connection to the coordinated offshore network at the existing New Deer 400kV substation. | Interface point | New Deer | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
A new 400 kV double circuit between Blackhillock and Peterhead | NOA | N/A | BPNC | 2030 | Scoping | Option requires acceleration to meet 2030 targets
East Coast Onshore 400 kV Phase 2 reinforcement | NOA | N/A | TKUP | 2030 | Strategic Optioneering | Option requires acceleration to meet 2030 targets
Eastern offshore HVDC link from Torness to Hawthorn Pit | NOA | N/A | E2DC | Required for 2027 | Planning/consenting
Eastern offshore HVDC link from Peterhead to Drax | NOA | N/A | E4D3 | Required for 2029 | Planning/consenting
Strathaven - Elvanfoot OHL Conductor Replacement | NOA | N/A | VERE | Required for 2030 | Scoping
Elvanfoot to Harker Reconductoring | NOA | N/A | EHRE | Required for 2030 | Scoping
Install new bays at Creyke Beck 400kV substation | Interface point | New Creyke Beck | N/A | Required for connections that deliver 2030 targets | Scoping
Install new bays at Creyke Beck 400kV substation | Interface point | New Creyke Beck | N/A | Required for connections that deliver 2030 targets | Scoping
Install new bays at Lincolnshire Connection Node 400kV substation | Interface point | Lincolnshire Connection Node | N/A | Required for connections that deliver 2030 targets | Scoping
Reconductor Sundon-Wymondley 400kV circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor Lackenby-Norton single 400kV circuit | NOA | N/A | LNRE | 2030 | Strategic Optioneering
Reconfigure Drakelow-Ratcliffe on Soar circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconfigure Grimsby West - South Humber Bank and Killingholme - South Humber Bank circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
A new 400 kV double circuit in north East Anglia | NOA | N/A | AENC | 2030 | Design/development and consenting
A new 400 kV double circuit in south East Anglia | NOA | N/A | ATNC | 2030 | Design/development and consenting
Install new MSCs at Burwell Main | NOA | N/A | BMM2 | 2022 | Design/development and consenting
Reconductor the newly formed second Bramford to Braintree to Rayleigh Main circuit | NOA | N/A | BPRE | 2028 | Strategic Optioneering
Reconductor remainder of Bramford to Braintree to Rayleigh route | NOA | N/A | BRRE | 2023 | Strategic Optioneering
A new 400 kV double circuit between Bramford and Twinstead | NOA | N/A | BTNO | 2028 | Planning/consenting
A new 400 kV double circuit between Creyke Beck and the south Humber area | NOA | N/A | CGNC | 2030 | Design/development and consenting | Option requires acceleration to meet 2030 targets
Generator circuit breaker replacement to allow Thornton to run a two-way split | NOA | N/A | DREU | 2025 | Strategic Optioneering
Second Elstree to St John’s Wood 400 kV circuit | NOA | N/A | ESC1 | 2029 | Strategic Optioneering
Uprate Hackney, Tottenham and Waltham Cross 275 kV to 400 kV | NOA | N/A | HWUP | 2027 | Design/development and consenting
Reconductor Bramford to Norwich double circuit | NOA | N/A | NBRE | 2023 | Strategic Optioneering
A new 400 kV double circuit between the existing Norton to Osbaldwick circuit and Poppleton and relevant 275 kV upgrades | NOA | N/A | OPN2 | 2027 | Planning/consenting
New Offshore HVDC link between Suffolk and Kent | NOA | N/A | SCD1 | 2030 | Design/development and consenting
Elstree to Sundon 1 reconductoring | NOA | N/A | SER1 | 2024 | Strategic Optioneering
Elstree to Sundon 2 circuit turn-in and reconductoring | NOA | N/A | SER2 | 2029 | Strategic Optioneering
South Humber substation upgrade | NOA | N/A | SHNS | 2030 | Design/development and consenting | Option requires acceleration to meet 2030 targets
Eastern offshore HVDC link from east Scotland to south Humber area | NOA | N/A | TGDC | 2030 | Strategic Optioneering | Option requires acceleration to meet 2030 targets
Thermal upgrade for Sundon and Wymondley 400 kV substation | NOA | N/A | WSEU | 2025 | Strategic Optioneering
Turn-in of the Pelham - Sundon 400kV circuit into Wymondley substation | NOA | N/A | WYTI | 2028 | Strategic Optioneering
400 kV upgrade of Brinsworth to Chesterfield double circuit and Chesterfield to High Marnham double circuit. New High Marnham and Chesterfield 400 kV substations | NOA | N/A | EDEU | 2028 | Strategic Optioneering
New Chesterfield to Ratcliffe-on-Soar 400 kV double circuit | NOA | N/A | EDN2 | 2030 | Strategic Optioneering
New network need between North Lincolnshire to Hertfordshire | NOA | N/A | LRN4 | 2030 | Scoping
Reconductor West Burton to Ratcliffe-on-Soar circuit | NOA | N/A | WRRE | 2030 | Strategic Optioneering
Keadby to West Burton circuits thermal uprating | NOA | N/A | KWHW | 2024 | Strategic Optioneering
Cottam to Market Harborough to Grendon circuit thermal uprating | NOA | N/A | GCHW | 2030 | Strategic Optioneering
Reconductor Cottam to Keadby 400 kV double circuit | NOA | N/A | KCRE | 2025 | Strategic Optioneering
Reconductor Enderby to Patford Bridge to East Claydon 400 kV double circuit | NOA | N/A | EBRE | 2030 | Strategic Optioneering
Uprating of Creyke Beck - Garforth tee - Keadby circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install voltage compensation on Keadby-Fenwick Tee circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor Fenwick Tee - Thorpe Marsh circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprate cable section on the Drax-Thorpe Marsh circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install power flow control devices on the Creyke Beck - Keadby - Humber Refinery circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor Ratcliffe on Soar - Enderby 400kV circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install power flow control devices on the Cottam - West Burton 1 400kV circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor Cowley - East Claydon 1 circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor Grendon - Sundon 400kV circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of Ryhall - Eaton Socon - Wymondley circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of Drax - Eggborough circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating of Burwell Main - Pelham 2 circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install power flow control devices on Spalding - Weston Marsh circuits | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install reactive compensation equipment across multiple substation in Yorkshire and the Humber region | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor a short span of the Norton-Osbaldwick 2 400kV circuit | NOA | N/A | NOR4 | 2030 | Strategic Optioneering
Reconductor Norton - Osbaldwick circuit | Connection | NGET for the East England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Offshore Works
Node 1 | Node 2 | Circuit capacity (MW) | Technology
R4_1 | SW_E1a | 1800 | DC 525 kV XLPE bundled pair
R4_1 | R4_2 | 1500 | AC 3-4 cables
R4_1 | Creyke Beck | 1800 | DC 525 kV XLPE bundled pair
R4_2 | Creyke Beck | 1800 | DC 525 kV XLPE bundled pair
R4_2 | Lincolnshire Connection Node | 1800 | DC 525 kV XLPE bundled pair
R4_2 | PA 1 | 1320 | AC 3-4 cables
R4_3 | Lincolnshire Connection Node | 1500 | AC 3-4 cables
PA_2 | Blyth | 1800 | DC 525 kV XLPE pair with metallic return
SW_E1a | SW_E1b | 1200 | AC 3-4 cables
SW_E1a | Hawthorn Pit | 1800 | DC 525 kV XLPE bundled pair
SW_E1a | Fetteresso | 2000 | AC 3-4 cables
SW_NE7 | Peterhead | 1500 | DC 525 kV XLPE pair with metallic return
SW_NE4 | New Deer | 1500 | AC 3-4 cables
Note 1: The offshore works listed above identify coordinated connections between in scope wind farms, to enable the design to be describe clearly as a number of offshore transmission circuits. It is anticipated that a modular and staged build approach will be adopted for the construction of the offshore network. Some change and refinement to the works are expected as they pass through more detailed design and delivery.

## 4 - South West
South West Region
Onshore Works
Short Description of Works | Type of works | Interface Point | NOA ref | HND Recommendation | Project Status | Notes
Install new bays at Pembroke 400kV substation | Interface point | Pembroke | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Uprating equipment on the Pembroke - Swansea circuits | Interface point | Pembroke | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install new bay at Pembroke 400kV substation | Interface point | Pembroke | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Turn-in the Pembroke-Walham circuit at Swansea North and substation modifications | Connection | NGET for the South West England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Cowley - Minety circuit | Connection | NGET for the South West England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Cowley - Walham circuit | Connection | NGET for the South West England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Feckenham - Walham circuit | Connection | NGET for the South West England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Reconductor the Feckenham - Minety circuit | Connection | NGET for the South West England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Install power flow control devices on Melksham - Minety circuits | Connection | NGET for the South West England Options | N/A | Required for connections that deliver 2030 targets | Strategic Optioneering
Offshore Works
Node 1 | Node 2 | Circuit capacity (MW) | Technology
CS_FW_1 | Pembroke | 1000 | AC 2-3 cables
CS_FW_2a | CS_FW_1 | 700 | AC 2 cables
CS_FW_2b | CS_FW_2a | 400 | AC 1-2 cables

## 5 - System-wide view
System-Wide View
Onshore Works
Short Description of Works | Type of works | NOA ref | Required In Service Date (RISD) | NOA Earliest In Service Date (EISD) | NOA Earliest Optimal Delivery Date | HND Recommendation | Project Status | Notes
A new 400 kV double circuit in north East Anglia | NOA | AENC | N/A | 2030 | 2030 | 2030 | Design/development and consenting
A new 400 kV double circuit in south East Anglia | NOA | ATNC | N/A | 2030 | 2030 | 2030 | Design/development and consenting
Beauly to Blackhillock 400 kV double circuit addition | NOA | BBNC | N/A | 2030 | 2030 | 2030 | Design/development and consenting
Uprate the Beauly to Denny 275 kV circuit to 400 kV | NOA | BDUP | N/A | 2029 | 2030 | 2030 | Design/development and consenting
Bramley to Fleet circuits thermal uprating | NOA | BFHW | N/A | 2024 | 2025 | 2025 | Strategic Optioneering
Power control device along Bramley to Fleet | NOA | BFPC | N/A | 2025 | 2029 | 2029 | Strategic Optioneering
Bramley to Fleet reconductoring | NOA | BFRE | N/A | 2025 | 2026 | 2026 | Strategic Optioneering
Beauly to Loch Buidhe 400 kV reinforcement | NOA | BLN4 | 2030 | 2031 | 2030 | 2030 | Strategic Optioneering | Option requires acceleration to meet 2030 targets
Install new Mechanically Switched Capacitors (MSCs) at Burwell Main | NOA | BMM2 | N/A | 2022 | 2022 | 2022 | Design/development and consenting
A new 400 kV double circuit between Blackhillock and Peterhead | NOA | BPNC | 2030 | 2031 | 2030 | 2030 | Scoping | Option requires acceleration to meet 2030 targets
Reconductor the newly formed second Bramford to Braintree to Rayleigh Main circuit | NOA | BPRE | N/A | 2028 | 2028 | 2028 | Strategic Optioneering
Reconductor remainder of Bramford to Braintree to Rayleigh route | NOA | BRRE | N/A | 2023 | 2023 | 2023 | Strategic Optioneering
A new 400 kV double circuit between Bramford and Twinstead | NOA | BTNO | N/A | 2028 | 2028 | 2028 | Planning/consenting
Reconductor Barking to West Ham double circuit | NOA | BWRE | N/A | 2025 | 2028 | 2028 | Strategic Optioneering
Cellarhead to Drakelow circuits thermal uprating | NOA | CDHW | N/A | 2023 | 2023 | 2023 | Strategic Optioneering
Power control device along Cellarhead to Drakelow | NOA | CDP1 | N/A | 2024 | N/A | 2027 | Strategic Optioneering
Power control device along Cellarhead to Drakelow | NOA | CDP2 | N/A | 2024 | 2027 | 2027 | Strategic Optioneering
Additional alternative power control devices along Cellarhead to Drakelow | NOA | CDP3 | N/A | 2024 | 2027 | 2027 | Strategic Optioneering
A new 400 kV double circuit between Creyke Beck and the south Humber area | NOA | CGNC | 2030 | 2031 | 2031 | 2030 | Design/development and consenting | Option requires acceleration to meet 2030 targets
Power control device along Creyke Beck to Keadby to Killingholme | NOA | CKPC | N/A | 2024 | 2025 | 2025 | Strategic Optioneering
Reconductor remainder of Coryton South to Tilbury circuit | NOA | CTRE | N/A | 2022 | 2022 | 2022 | Construction
Power control device along Cottam to West Burton | NOA | CWPC | N/A | 2024 | 2027 | 2027 | Strategic Optioneering
Reconductor Drax to Fenwick Tee 400 kV circuit | NOA | DFRE | N/A | 2026 | 2033 | 2030 | Strategic Optioneering
Windyhill-Lambhill-Denny North 400 kV reinforcement | NOA | DLUP | N/A | 2029 | 2029 | 2029 | Strategic Optioneering
Denny North 400/275 kV second supergrid transformer | NOA | DNEU | N/A | 2025 | 2026 | 2026 | Design/development and consenting
Generator circuit breaker replacement to allow Thornton to run a two-way split | NOA | DREU | N/A | 2025 | 2025 | 2025 | Strategic Optioneering
Denny to Wishaw 400 kV reinforcement | NOA | DWNO | N/A | 2028 | 2028 | 2028 | Design/development and consenting
Kincardine - Wishaw 400 kV reinforcement | NOA | DWUP | N/A | 2026 | 2026 | 2026 | Strategic Optioneering
Eastern offshore HVDC link from Torness to Hawthorn Pit | NOA | E2DC | N/A | 2027 | 2027 | 2027 | Planning/consenting
Eastern offshore HVDC link from Peterhead to Drax | NOA | E4D3 | N/A | 2029 | 2029 | 2029 | Planning/consenting
Eastern offshore HVDC link from Peterhead to the south Humber | NOA | E4L5 | 2030 | 2031 | 2030 | 2030 | Strategic Optioneering | Option requires acceleration to meet 2030 targets
Reconductor Enderby to Patford Bridge to East Claydon 400 kV double circuit | NOA | EBRE | N/A | 2026 | 2031 | 2030 | Strategic Optioneering
400 kV upgrade of Brinsworth to Chesterfield double circuit and Chesterfield to High Marnham double circuit. New High Marnham and Chesterfield 400 kV substations | NOA | EDEU | N/A | 2027 | 2028 | 2028 | Strategic Optioneering
New Chesterfield to Ratcliffe-on-Soar 400 kV double circuit | NOA | EDN2 | 2030 | 2032 | 2033 | 2030 | Strategic Optioneering | Option requires acceleration to meet 2030 targets
Elvanfoot to Harker reconductoring | NOA | EHRE | N/A | 2028 | 2031 | 2030 | Scoping
Second Elstree to St John’s Wood 400 kV circuit | NOA | ESC1 | N/A | 2026 | 2029 | 2029 | Strategic Optioneering
Cottam to Market Harborough to Grendon circuit thermal uprating | NOA | GCHW | N/A | 2025 | 2030 | 2030 | Strategic Optioneering
A new 400 kV double circuit between the south Humber and south Lincolnshire | NOA | GWNC | 2030 | 2031 | 2031 | 2030 | Design/development and consenting | Option requires acceleration to meet 2030 targets
Harker supergrid transformer 6 replacement | NOA | HAE2 | N/A | 2023 | 2023 | 2023 | Design/development and consenting
Harker supergrid transformer 5 and supergrid transformer 9A banking arrangement | NOA | HAEU | N/A | 2022 | 2022 | 2022 | Design/development and consenting
Uprate Bridgewater to 400 kV and reconductor the route to Hinkley | NOA | HBUP | N/A | 2024 | 2027 | 2027 | Design/development and consenting
Uprate Hackney, Tottenham and Waltham Cross 275 kV to 400 kV | NOA | HWUP | N/A | 2027 | 2027 | 2027 | Design/development and consenting
Feckenham to Ironbridge circuit reconductoring | NOA | IFR1 | N/A | 2025 | 2034 | 2030 | Strategic Optioneering
Creyke to Keadby to Killingholme circuits thermal uprating | NOA | KCEU | N/A | 2022 | 2025 | 2025 | Strategic Optioneering
Reconductor Cottam to Keadby 400 kV double circuit | NOA | KCRE | N/A | 2025 | 2025 | 2025 | Strategic Optioneering
Keadby to West Burton circuits thermal uprating | NOA | KWHW | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
Additional power control devices along the Keadby to West Burton number 1 circuit | NOA | KWP2 | N/A | 2025 | 2026 | 2026 | Strategic Optioneering
Power control device along Keadby to West Burton | NOA | KWPC | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
Reconductor Lackenby to Norton 400 kV single circuit | NOA | LNRE | N/A | 2024 | 2031 | 2030 | Strategic Optioneering
New network need between North Lincolnshire to Hertfordshire | NOA | LRN4 | 2030 | 2033 | 2033 | 2030 | Scoping | Option requires acceleration to meet 2030 targets
Kincardine 400 kV reinforcement | NOA | LWUP | N/A | 2027 | 2027 | 2027 | Strategic Optioneering
Bramley to Melksham circuits thermal uprating | NOA | MBHW | N/A | 2024 | 2026 | 2026 | Strategic Optioneering
Bramley to Melksham reconductoring | NOA | MBRE | N/A | 2026 | 2027 | 2027 | Strategic Optioneering
Additional power control devices at both Harker and Penwortham | NOA | MRP2 | N/A | 2022 | 2022 | 2022 | Construction
Thermal upgrade for Bramford and Norwich 400 kV substations | NOA | NBEU | N/A | 2025 | 2028 | 2028 | Strategic Optioneering
Reconductor Bramford to Norwich double circuit | NOA | NBRE | N/A | 2023 | 2023 | 2023 | Strategic Optioneering
225 MVAr MSCs within the north east region | NOA | NEMS | N/A | 2025 | 2026 | 2026 | Strategic Optioneering
Power control device along Blyth to Tynemouth and Blyth to South Shields | NOA | NEP1 | N/A | 2025 | 2025 | 2025 | Strategic Optioneering
Power control device along Blyth to Tynemouth and Blyth to South Shields | NOA | NEPC | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
Reconductor a short span of the Norton-Osbaldwick 2 400kV circuit | NOA | NOR4 | N/A | 2024 | 2031 | 2030 | Strategic Optioneering
Reconductor a short span of the Norton-Osbaldwick 1 400kV circuit | NOA | NOR5 | N/A | 2024 | 2027 | 2027 | Strategic Optioneering
Power control device north of Tilbury 400 kV | NOA | NTP1 | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
A new 400 kV double circuit between the existing Norton to Osbaldwick circuit and Poppleton and relevant 275 kV upgrades | NOA | OPN2 | N/A | 2027 | 2027 | 2027 | Planning/consenting
225 MVAr MSCs at Pelham | NOA | PEM1 | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
225 MVAr MSCs at Pelham | NOA | PEM2 | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
Spittal to Peterhead HVDC reinforcement | NOA | PSDC | N/A | 2030 | 2030 | 2030 | Strategic Optioneering
New network need between North Wales and South Wales | NOA | PSNC | 2030 | 2037 | 2037 | 2030 | Scoping | Option requires acceleration to meet 2030 targets
Pentir to Trawsfynydd cable replacement | NOA | PTC1 | N/A | 2027 | 2028 | 2028 | Strategic Optioneering
A second transmission circuit on the existing Pentir to Trawsfynydd route | NOA | PTNO | N/A | 2028 | 2029 | 2029 | Strategic Optioneering
Two 225MVAr MSCs at Penwortham | NOA | PWMS | N/A | 2025 | 2027 | 2027 | Strategic Optioneering
225 MVAr MSCs at Rye House | NOA | RHM1 | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
225 MVAr MSCs at Rye House | NOA | RHM2 | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
Reconductor remainder of Rayleigh to Tilbury circuit | NOA | RTRE | N/A | 2022 | 2022 | 2022 | Construction
New Offshore HVDC link between Suffolk and Kent option 1 | NOA | SCD1 | N/A | 2030 | 2030 | 2030 | Design/development and consenting
Reactive compensation protective switching scheme | NOA | SEEU | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
Elstree to Sundon reconductoring | NOA | SER1 | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
Elstree to Sundon 2 circuit turn-in and reconductoring | NOA | SER2 | N/A | 2026 | 2029 | 2029 | Strategic Optioneering
Upgrade substation in the south Humber area | NOA | SHNS | 2030 | 2031 | 2031 | 2030 | Design/development and consenting | Option requires acceleration to meet 2030 targets
New network need between Loch Buidhe and Spittal | NOA | SLU4 | N/A | 2030 | 2030 | 2030 | Strategic Optioneering
Spennymoor to Norton circuit thermal uprating | NOA | SNHW | N/A | 2024 | 2027 | 2027 | Strategic Optioneering
Stella West to Spennymoor circuit thermal uprating | NOA | SSHW | N/A | 2024 | 2027 | 2027 | Strategic Optioneering
Power flow control device along Tealing to Westfield | NOA | TFPC | N/A | 2025 | 2027 | 2027 | Scoping
Eastern offshore HVDC link from east Scotland to south Humber area | NOA | TGDC | 2030 | 2031 | 2031 | 2030 | Strategic Optioneering | Option requires acceleration to meet 2030 targets
Power control device along Tilbury to Grain | NOA | TGP1 | N/A | 2024 | 2024 | 2024 | Strategic Optioneering
Power control device along Tilbury to Kingsnorth | NOA | TKP1 | N/A | 2024 | 2026 | 2026 | Strategic Optioneering
Tilbury to Grain and Tilbury to Kingsnorth upgrade | NOA | TKRE | N/A | 2028 | 2028 | 2028 | Strategic Optioneering
East Coast Onshore 400 kV Phase 2 reinforcement | NOA | TKUP | 2030 | 2032 | 2030 | 2030 | Strategic Optioneering | Option requires acceleration to meet 2030 targets
Strathaven - Elvanfoot OHL conductor replacement | NOA | VERE | N/A | 2030 | N/A | 2030 | Scoping
Strathaven - Smeaton OHL conductor replacement | NOA | VSRE | N/A | 2027 | 2027 | 2027 | Strategic Optioneering
225 MVAr MSCs at Walpole | NOA | WAM1 | N/A | 2025 | 2025 | 2025 | Strategic Optioneering
225 MVAr MSCs at Walpole | NOA | WAM2 | N/A | 2025 | 2025 | 2025 | Strategic Optioneering
Reconductor West Burton to Ratcliffe-on-Soar circuit | NOA | WRRE | N/A | 2028 | 2030 | 2030 | Strategic Optioneering
Thermal upgrade for Sundon and Wymondley 400 kV substation | NOA | WSEU | N/A | 2024 | 2025 | 2025 | Strategic Optioneering
Turn-in of the Pelham - Sundon 400kV circuit into Wymondley substation | NOA | WYTI | N/A | 2024 | 2028 | 2028 | Strategic Optioneering
Ex-ante onshore works
Short Description of Works | Type of works | NOA ref | NOA Earliest In Service Date (EISD)
East Coast onshore 275kV upgrade | Ex-ante | ECU2 | 2023
East Coast onshore 400kV incremental reinforcement | Ex-ante | ECUP | 2026
Eccles Hybrid Synchronous Compensators and Real-Time Rating System | Ex-ante | ECVC | 2026
Hunterston - Neilston 400kV reinforcement | Ex-ante | HNNO | 2023
Windyhill to Lambhill to Longannet 275kV Circuit Turn In to Denny North 275kV Substation | Ex-ante | WLTI | 2022

## Sheet1 (hidden)
Scoping
Strategic Optioneering
Design, Development & Consenting
Planning & Consenting
Consents Approved
Construction