## Deliverables Tracker
Role | Sub activity | Deliverable reference number | Deliverable name | Milestone Description | Milestone date | Milestone Status | Milestone completion date (quarter) | Commentary
1 | Ongoing activities | D1.1.1 | Balance Great Britain’s (GB) demand for energy with supply from generators around the clock | Meeting agreed metrics on balancing costs and security of supply. | Q4 2024-25 | Complete | Q4 2024-25 | Throughout the course of BP2, NESO have tracked and reported on how we perform against this deliverable and its metrics. NESO have finished meeting expectations in the cost metric.
1 | Ongoing activities | D1.1.2 | Maintain security of supply in real time and the ability to restart the system in the event of a partial or total loss of power | Meeting agreed metrics on balancing costs and security of supply. Carry out necessary work to meet GB restoration standard as described in A3.2. | Q4 2024-25 | Complete | Q4 2024-25 | Throughout the course of BP2, NESO have tracked and reported on how we perform against this deliverable and its metrics. NESO have finished meeting expectations in the cost metric.
1 | Ongoing activities | D1.1.3 | Maintain the integrity of the transmission network, while managing the economical operation of the system | Meeting agreed metrics on balancing costs and security of supply. | Q4 2024-25 | Complete | Q4 2024-25 | Throughout the course of BP2, NESO have tracked and reported on how we perform against this deliverable and its metrics. NESO have finished meeting expectations in the cost metric.
1 | Ongoing activities | D1.1.4 | Support development of new methodology under Trade and Cooperation Agreement and support European cooperation including and with the European Network of Transmission System Operators for Electricity (ENTSO-E) based on the outcome of Memorandum of Understanding (MoU) with ENTSO and CORESO based on the agreement with EU NRAs. Strategic relationships with European institutions are covered in Activity A21 Role in Europe. | Enhanced cooperation between EU and GB on electricity operation following EU-Exit. Support the development, delivery and implementation of new interconnector capacity calculation methodology. Maintain the delivery of the Day Ahead NG Security Analysis process in the NG control centre in preparation for future developments | Q4 2023-24 | Delayed - External Reasons |  | The Day Ahead Security Analysis (SA) process was being maintained in preparation for the conclusion of the ongoing workstream which sought to find a replacement for CACM as prescribed in the TCA following Brexit. This workstream has been on hold for several years and was awaiting approval from the EC to allow EU TSOs to engage with UK TSOs on this issue. Whilst the SA process was on hold, there had been significant IT issues that prevented the SA process from running and the costs to resolve were deemed too significant for the low value being realised from the process. This process was therefore stopped but the functionality to send IGM files, if required for any potential future methodology that replaces CACM, can be re-activated if the need arises. The final version of the ENTSO-E cooperation agreement (TCA Working Arrangements) was approved by the SCE in November 2024, allowing ENTSO-e and UK TSOs to formally cooperate. Whilst this is a positive step, there wasn’t any significant progress prior to the end of BP2 and hence this will be delayed into BP3 for external reasons.
1 | Ongoing activities | D1.1.4 | Support development of new methodology under Trade and Cooperation Agreement and support European cooperation including and with the European Network of Transmission System Operators for Electricity (ENTSO-E) based on the outcome of Memorandum of Understanding (MoU) with ENTSO and CORESO based on the agreement with EU NRAs. Strategic relationships with European institutions are covered in Activity A21 Role in Europe. | Enhanced cooperation between EU and GB on electricity operation following EU-Exit. Support the development, delivery and implementation of new interconnector capacity calculation methodology. Maintain the delivery of the Day Ahead NG Security Analysis process in the NG control centre in preparation for future developments | Q4 2024-25 | Delayed - External Reasons |  | The Day Ahead Security Analysis (SA) process was being maintained in preparation for the conclusion of the ongoing workstream which sought to find a replacement for CACM as prescribed in the TCA following Brexit. This workstream has been on hold for several years and was awaiting approval from the EC to allow EU TSOs to engage with UK TSOs on this issue. Whilst the SA process was on hold, there had been significant IT issues that prevented the SA process from running and the costs to resolve were deemed too significant for the low value being realised from the process. This process was therefore stopped but the functionality to send IGM files, if required for any potential future methodology that replaces CACM, can be re-activated if the need arises. The final version of the ENTSO-E cooperation agreement (TCA Working Arrangements) was approved by the SCE in November 2024, allowing ENTSO-e and UK TSOs to formally cooperate. Whilst this is a positive step, there wasn’t any significant progress prior to the end of BP2 and hence this will be delayed into BP3 for external reasons.
1 | Ongoing activities | D1.1.5 | Upgraded legacy balancing and situational awareness tools to deliver continued service levels whilst new tools are being developed | Priority asset health improvements made to meet expectations as per the ESO Roles Guidance. Priority Control Centre user enhancements made to tools, including greater automation and upgrades to the bulk dispatch tool, to help meet efficient balancing expectations in the ESO Roles Guidance and improved stability situational awareness such as oscillation monitoring. Increased PMU location coverage and improved situational awareness. Replacement FATE system fully integrated with legacy balancing tools. | Q4 2023-24 | Complete | Q4 2023-24 | Legacy Dispatch Systems (Notable Features): •Complete: Jun23 (BM Release 3) Situational awareness improvements for utilisation of bi-directional units and fixes around bulk instruction/send of reason codes. •Complete: Jul23-ASDP (Release 14a) Dynamic Response enhancements to visualise contracted units Physical Notification data. •Complete: Sep23-ASDP (Release 15) Technical go live of the MW Dispatch service for NGED, asset health and control room improvements. •Complete: Sep23-BM (Interim Release 4) Upgrades and security patches. Inertia data integration for the decommissioning of EBS. •Complete: Dec23-BM (Release 4) Improving unit and constraint visibility and navigation, nuisance alarms, and process automation. Interfaces between BM & Open Balancing Platform (OBP), changes to dispatch to enable the Balancing Reserve (BR), and processes to BM to support decommissioning of EBS. •Complete: Dec23-ASDP (Release 16) Features of MW Dispatch for UK Power Network (UKPN), asset health and control room improvements. •Complete: Mar 24-BM Interim (Release 5) Code and hardware performance improvements, final process changes for EBS decommissioning, work to enable Greenlink commissioning and further changes to support BR dispatch. •Complete: Mar 24-ASDP (Release 17) UKPN MW dispatch technical go live, Dynamic Response enhancements for disarming, asset health and control room improvements. Network Control (Situational Awareness): Work ongoing to deliver oscillation monitoring within the new situational awareness tools. Offline analysis tools brought forward and are available for post event analysis. •New Oscillation situational awareness tool, Oscillation Guard Pro, delivered in 4 months providing indication of Scottish Oscillations is in use. Discussions are on going to widen this up to all GB later in FY25. •Access SSE production PMU data was established in January 2024, enabling additional data to be available. •Milestone completed.
1 | Ongoing activities | D1.1.5 | Upgraded legacy balancing and situational awareness tools to deliver continued service levels whilst new tools are being developed | Priority asset health improvements made to meet expectations as per the ESO Roles Guidance. Priority Control Centre user enhancements made to tools, including greater automation and upgrades to the bulk dispatch tool, to help meet efficient balancing expectations in the ESO Roles Guidance and improved stability situational awareness such as oscillation monitoring. Increased PMU location coverage including potentially within DNOs. | Q4 2024-25 | Complete | Q4 2024-25 | Legacy Dispatch Systems in FY25: •Electricity Balancing System (EBS) Decommissioning •Ancillary Services Dispatch Platform (ASDP) Activities: •Jun: Dynamic Response enhancements to disarm and Mega Watt (MW) Dispatch enhancements. •Sep: Technical and asset health improvements •Nov: Dynamic Response (Arm/Disarm & visualisation, MW dispatch improvements, rebranding updates •BM Releases 6 - Priority work for skip rates (Vergil enhancements). Advance contract data loading to support Constraint Management Pathfinder (CMP). Extract of real time constraint data to enable delivery of Dispatch Efficiency Monitor in Q4. Network Control Management System (NCMS) Generation Schedule from BM system of expected MW levels for all BMUs. Open Balancing Platform (OBP) - interface work to enable manual instructions. Priority control room enhancements and Critical National Infrastructure (CNI) Asset Health. •Future Work: IR7 Priority control room enhancements and CNI Asset Health. Network Control: • Work to deliver oscillation monitoring within the new situational awareness tools (NCMS) - Part of the WAMs project which will be delivered alongside NCMS. Testing is due to start in June 2025. • Oscillation Guard Pro extended for all GB and released to Control Room in Dec. Enhancements to this tool with Reactive Technologies - OGP already in control room to monitor Oscillations, training materials are being developed. • Frequency And Time Error (FATE) Replacement User Interface enhancements released in Dec. National Grid Electricity Transmission (NGET) data due June 2025 - FATE R already released for awareness at present. Suggested fixes from control room have been delivered. Continuous activity into BP3 - marked as complete as requested
1 | Ongoing activities | D1.1.6 | Assessment of future operability challenges communicated through the Operability Strategy Report. Published annually | Publish Operability Strategy Report | Q3 2023-24 | Complete | Q3 2023-24 | The report was published on the 28 Dec 2023. External comms followed w/c 8 Jan 2024. Webinar was held on 23 Jan. 89% learnt something new and scored the webinar 3.9/5
1 | Ongoing activities | D1.1.6 | Assessment of future operability challenges communicated through the Operability Strategy Report. Published annually | Publish Operability Strategy Report | Q3 2024-25 | Complete | Q4 2024-25 | published on 27 March 2025 (delayed from 25 March due to Heathrow incident).
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Solar Power Product Implementation | Q1 2023-24 | Complete | Q4 2024-25 | The initial phase of the Solar Power product has been successfully developed in BP1, delivering value to consumers. In BP2, our objective is to transition the existing product from the current ORACLE Cloud Infrastructure (OCI) solution to a strategic Azure cloud solution. Once migrated the remaining feature delivery can be prioritised to further enhance and therefore improve our 1B demand forecasting accuracy metric . This will be delivered In Q4 FY25. To ensure alignment with consumer value and business requirements, we have re-prioritised the forecasting roadmap/backlog through the cost monitoring framework (CMF). We now have an updated PEF strategy with a revalidated forecasting roadmap. This will accelerate the retirement of legacy forecasting systems (EFS, Operational PEF) and remove operational and business debt/risk while we deliver new and existing products and features on our strategic Azure cloud platform. The Solar Power Product has been migrated to the Azure platform in Q4 FY25 following continuous enhancements made in Q2 and Q3 FY25 enabling the retirement of OCI PEF. This product feeds control room visualisations and, as part of our decommissioning plans will begin to feed into our demand forecasting product.
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Wind Power & National Demand Product Implementation | Q4 2023-24 | Complete | Q4 2024-25 | In order to enhance deliverability confidence for the milestones and address an error in the BP2 submission (two milestones as one), a reassessment has been conducted regarding the priority, size, and complexity of this milestone. As a result, the milestone has been split into two separate milestones. The target completion dates have been set as follows: 1. Wind Power Milestone: Q3-FY25 2. National Demand Milestone: Q4-FY25 The Wind Power product has been successfully deployed into the new strategic Azure cloud platform. The new model's performance has significantly improved our 1C metric during November and December 2024. Furthermore, the initial phase of the National Demand product has been successfully delivered during BP1, already providing value to consumers. As part of our objective in BP2 we planned to transition this product from the current ORACLE Cloud Infrastructure (OCI) solution to a strategic Azure cloud solution. In November 2024 we took the decision to migrate an evolved version of this product that has been developed separately. This alternative model was developed as part of NESO's focus on reducing uneconomical dispatch, the migration of this alterantive model will complete within the same timeframes and within BP2 but delivery significant improvements over the current model in ORACLE. We now have an updated PEF strategy with a revalidated forecasting roadmap. This will accelerate the retirement of the legacy Energy Forecasting System (EFS, Operational PEF) and remove operational and business debt/risk while we deliver new and existing products and features on our strategic Azure cloud platform. The National Demand product has been migrated to the Azure platform in Q4 FY25 following continuous enhancements made in Q2 and Q3 FY25 enabling the retirement of OCI PEF. The enhancements are providing improved forecasts into downstream demand forecasting processes and into the control room.
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Integration with OBP and DAP (as far as possible) | Q4 2024-25 | Delayed - Internal Reasons |  | Strategic PEF has its first set of APIs for integration with the Open Balancing Platform (OBP), OBP will integrate with PEF in FY26. Discovery work is in progress with OBP to align for further integrations as part of their roadmap. Integration with DAP had been temporarily de-coupled and will be considered following the migration of PEF to our NESO tenancy and as part of the decommissioning strategy during FY26. Delay caused by architectural alignment of the DAP roadmap with the PEF roadmap during BP2. Integration was decoupled to allow unconstrained progression within Azure PEF. The overall deliverable has not been affected. We are still planning to integrate with DAP by the end of FY2026. There is no impact on NESO or the consumer as access to the data is still available. This is an internal integration which will deliver efficiencies.
1 | Ongoing activities | D1.1.8 | Trading solutions to deliver a safe, secure and economical strategy for the Control Centre | Delivery of a business continuity solution for trade capture and notification will allow trading to continue in the event that our primary systems became unavailable. Success looks like processes which are more robust and reliable, supported appropriately and automation is increased, reducing the risk of error occurring in manual processes. | Q4 2023-24 | Complete | Q4 2023-24 | Trading tool (Faradyn) now in place which reduces trade data entry errors. Common failure point (LIMS) being investigated for improvements with trade notifications. 25/3/24 We have confirmation that a major counterparty has the ability to notify on our behalf following a system failure (written in the GTMA). This means that we have a limited route to market following system failure.
1 | Ongoing activities | D1.1.8 | Trading solutions to deliver a safe, secure and economical strategy for the Control Centre | Delivery of a business continuity solution for trade capture and notification will allow trading to continue in the event that our primary systems became unavailable. Success looks like processes which are more robust and reliable, supported appropriately and automation is increased, reducing the risk of error occurring in manual processes. | Q4 2024-25 | Complete | Q1 2024-25 | Trading tool (Faradyn) now in place which reduces trade data entry errors. Common failure point (LIMS) being investigated for improvements with trade notifications. 25/3/24 We have confirmation that a major counterparty has the ability to notify on our behalf following a system failure (written in the GTMA). This means that we have a limited route to market following system failure.Settlements changing internal reporting to display and changing GTMA with another 3 counterparties to carry out testing.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 8. Issued an end of Increment report on Earned Value and Progress. | Q1 2023-24 | Complete | Q1 2023-24 | Completed on 18 July as per original plan
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | First release of OBP to the Control Room. This will improve efficiency and reduce workload by enabling multi-dispatch instruction, which will reduce unit skips. Functionality for Real-Time Energy Balancing in OBP. First tranche of margin analysis in OBP. | Q3 2023-24 | Delayed - Consumer Benefits |  | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme ensuring engagement events for our balancing transformation roadmap plan we are on track against our existing plan. OBP lite released in Q3 2023-24 has been integrated with the training simulator. Full integration of OBP strategic is on track for Q2 FY26 Training simulator integration decoupled and delivered beyond BP3 In Q1 FY26 additionally, we will deliver functionality to enable additional storage parameters to represent the energy available of these limited energy assets. In Q1 FY26 we will implement rule based Dispatch capability for Wind BM Units, Constraint Management and bulk-dispatch bid/offer instruction capability for Pumped Storage BM Units. Delay caused by architectural alignment of the DAP roadmap with the PEF roadmap during BP2. Integration was decoupled to allow unconstrained progression within Azure PEF. The overall deliverable has not been affected. We are still planning to integrate with DAP by the end of 2026. There is no impact on NESO or the consumer as access to the data is still available. This is an internal integration which will deliver efficiencies.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | Initial integration of OBP with the Data and Analytics Platform which will replace our long-term retention and analytics capability. Integration of unit contract data with OBP to ensure procured services are scheduled, optimised and available for dispatch. | Q4 2023-24 | Complete | Q4 2024-25 | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme enduring engagement events for our balancing transformation roadmap plan we have completed the deliverables against our existing plan. OBP had prioritised the delivery of new services such as BM Quick Reserve and so delayed integration with DAP. We have completed the Integration to SMP which includes unit contract data with OBP to enable the scheduling, optimisation and dispatch of procured services. OBP and DAP Intergretation will be delivered in Q4 FY25 (Change request in process), to be delivered on 9th January 2025 OBP and DAP Intergretation has been completed in Q4 FY25
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | Delivered functionality for Unit Pre-qualification, Contracts, registration in OBP. Predicted Generation Forecasting functionality in OBP. Provision of Meter, Market, Network, and constraints data for improved situational awareness in OBP. Integration with Ancillary Services Dispatch (ASDP): Ability for Open Balancing Platform to send and receive data via ASDP APIs to control points. | Q1 2024-25 | Delayed - Consumer Benefits |  | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme enduring engagement events for our balancing transformation roadmap plan we have completed the deliverables against our existing plan. Following prioritisation, the interface to SMP and IEMS was delivered in Q2 FY25 Readiness to decommission ASDP is a planned enabler for Q2 FY26 Network and constraints management have been delayed due to re-prioritisation of the newly baselined roadmap, both are dependent on the price stack and will be delivered in Q1 FY26 Predicted Generation forecast will now come from PEF and will be delivered in Q3 FY26 (December)
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | Release of new National Optimiser (Modern Dispatch Algorithm (MDA)), reducing energy balancing costs. | Q3 2024-25 | Delayed - Consumer Benefits |  | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme enduring engagement events for our balancing transformation roadmap plan we are on track against our existing plan. In Q2 FY25 (2024-25), we have delivered functionality to enable go-live of BM quick Reserve and we will bring forward a requirement as part of a staged set of activities to be able to issue manual instructions for all BMUs including pump storage and wind in Q4 FY25 to enable more efficient architectural design of our suite of Balancing products. Additionally in Q2 FY25 (2024-25) we have delivered enhanced fast despatch. Additionally, we are doing discovery and elaboration work for PEF integration and constraint optmisation in Q3 FY25 and beyond so they can be delivered in Q1 FY26. Delivery of MDA (National Optimiser) has therefore been reprioritised for the above activities and is now planned for delivery in Q1 FY26 (2025-26).
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | Full integration with the training simulator, increasing effectiveness in the Control Room (note this is ongoing as new functionality in delivered in OBP it is added to the simulator). | Q4 2024-25 | Delayed - Internal Reasons |  | In alignment with our current industry agreed plan, looking to deliver consumer benefits in a prioritised way and following ongoing engagement through our balancing programme ensuring engagement events for our balancing transformation roadmap plan we are on track against our existing plan. OBP lite released in Q3 2023-24 has been integrated with the training simulator. Full integration of OBP strategic is on track for Q2 FY26 Training simulator integration decoupled and delivered beyond BP3 In Q1 FY26 additionally, we will deliver functionality to enable additional storage parameters to represent the energy available of these limited energy assets. In Q1 FY26 we will implement rule based Dispatch capability for Wind BM Units, Constraint Management and bulk-dispatch bid/offer instruction capability for Pumped Storage BM Units.
1 | Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Requirements Reports | Integrate inertia data with Data and Analytics Platform | Q4 2023-24 | Complete | Q3 2023-24 | Improvements to the DAP platform ingesting inertia data have been made enabling enhanced displays to be created as additional operational data is integrated into DAP. This milestone should have aligned with that shown in Annex 4 (DDT) of BP2 which is March 2024 and has delivered the improved integration ahead of this date. Continued enhancements will be made to dashboards to increase benefits to operational users.
1 | Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Requirements Reports | Integrate tools created with network control tool Inertia monitoring tools integrated with DAP and enhanced balancing capability | Q4 2024-25 | Delayed - Internal Reasons |  | These integrations are likely to be via DAP or GridOS Data Fabric and final delivery will align with the end project (OBP and Network Control / Operator Console) priorities and timelines. NB CRs submitted under IT process. Internal delay caused by us still working with RTL to develop the measurement accuracy for inertia. We are also still waiting for the inertia tool from GE and the PMU data from NGET. We are still working on all fronts to deliver this milestone. We are unable to deliver this deliverable until we have delivered the inertia tools and received the PMU data from NGET. We are hoping this will be delivered by Q3 2025/26 The delay will delay the control room having visibility of accurate inertia indications.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Look Ahead Iteration 1 / VSAT/OSA hosted in new DCs | Q1 2024-25 | Delayed - Internal Reasons |  | Delay is due to the vendor being unable to provide a build to ESO to install in our ESO Data Centres. As a mitigation sample Input Look Ahead data has been developed, work is ongoing with vendor to map this data for use in the Look Ahead toolset. VSAT/OSA environment strategy has been completed and procurement of necessary hardware is underway.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Look Ahead functionality running in Development Environments | Q2 2023-24 | Complete | Q4 2024-25 | Dates to be revised to align with new Data Centre delivery dates. Not expected to knock-on to any other milestones Subsequent delay due to vendor (G.E.) not providing deployment capability to NESO. Mitigation is to use GE development environments
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Commence Build of Voltage Stability Analysis Tool (VSAT) and Online Stability Assessment (OSA) Tool Environments | Q3 2023-24 | Complete | Q3 2023-24 | Complete - awaiting Data Centre delivery.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Shadow Control Centre established Initial Data and Analytics Platform (DAP) integration | Q4 2023-24 | Delayed - Internal Reasons |  | Shadow Control facilities to be developed as part of the training suite for new NCMS with the option to develop further into a proposed FSO Contingency Control Centre post-project completion. DAP integration PoC successful in Q3 24-25 and NCMS training simulator due Q4 24-25. The delivery plan for this milestone has been revised to accommodate the re-baseline of DAP and NCMS delivery plans and also to consider the new requirements for a NESO Contingency Control Centre Proof of concept has been completed between NCMS stub and DAP stub. Final procurement ongoing to kick of complete integration between NCMS and TSDH (DAP) within enterprise.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | NGET receiving RTU Data DAP & balancing integration | Q2 2024-25 | Delayed - External Reasons |  | NGET SCADA delivery has been delayed and the need for NGET to receive RTU Data has now been re-prioritised to Q1 2025/27 to align with NGET revised plan. DAP integration proof of concept has successfully completed and the timeline for full integration has moved to align with the NCMS GridOS pivot plan. This should have the technology in place by the end of Q2 2025/26 Sample files have been received from Balancing – with a revised integration target date Q4 2024-25 to align to the latest plan Balancing metering data feed is in place between iEMS and OBP ahead of switching over to NCMS. Work is now being done to expand the amount of Realtime data needed by OBP inline with there roadmaps Consumer benefit is realised by re-baselining our plan to include the adoption of the new GridOS platform from GE and this has been discussed and agreed with Ofgem through the CMF process.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Serial RTU connections removed | Q3 2024-25 | Delayed - External Reasons |  | Due to external supplier constraints and change of delivery team this has been delayed post August 2024. This is now being additionally complicated with the transition between National Grid CNI suppliers. Site survey and LLD are due to be completed by the incumbent supplier by Q2 FY26. The remaining implementation will be completed by the new supplier and the delivery schedule is being reviewed by the new supplier.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Deliver integrated network control tool (inc VSAT & Look Ahead OSA), including its specific digital twin | Q4 2024-25 | Delayed - Consumer Benefits |  | Date to be changed to Q3 FY26 following a re-baseline of plan that has taken place to understand the impact of GE product pivot to new GridOS technology. Consumer benefit is realised by re-baselining our plan to include the adoption of the new GridOS platform from GE and this has been discussed and agreed with Ofgem through the CMF process.
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Common Information Model (CIM) Integration Requirements Complete | Q3 2023-24 | Complete | Q2 2023-24 | CIM model integration requirements completed and aligned with NCMS product delivery plan
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Integrate with enhanced balancing tool | Q4 2023-24 | Delayed - Internal Reasons |  | Reviewed against latest NCMS and Balancing delivery plans and integration target date is now January 2026. No anticipated knock-on to other milestones. Delay is caused by a few internal factors: - - NCMS Pivot to GridOS - the focus on the pivot to GridOS from an NCMS perspective has meant the integration work with OBP (enhanced balancing tool) has been re-prioritised. - Due to the complexity of both the NCMS and OBP toolsets, requirement development for the interfaces and functionality to be shared between the two tools has taken longer than expected and is still ongoing in a number of areas (for example Constraint Visualisation). A high level plan for delivery of the integrations between NCMS and OBP are now in place.
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Common Information Model (CIM) Integration Complete | Q3 2024-25 | Complete | Q3 2024-25 | CIM model integration aligned with NCMS product delivery plan
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Integrate with Network Control Management System (NCMS) | Q4 2024-25 | Complete | Q4 2024-25 | Integration aligned with NCMS product delivery plan.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Complete UI/UX requirements for ENCC Operator Console | Q1 2023-24 | Complete | Q1 2023-24 | User requirements completed and design is now underway.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Design Phase | Q2 2023-24 | Complete | Q2 2023-24 | User requirements completed and conceptual solution architecture is complete and now informing the procurement of the solution
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Build | Q3 2023-24 | Delayed - Internal Reasons |  | User requirements have been completed the supplier pre-qualification questionnaire (PQQ) has completed. We are now moving to a Formal Request for Proposal (RFP). Overall the project is behind due to a number of Architecture and supplier delays but is still expected to be delivered to aligned to NCMS and OBP deliveries.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Scope requirement and start design of video walls | Q4 2023-24 | Complete | Q4 2023-24 | User Requirements have been gathered and EPRI work has been completed. Solution procurement strategy now identified with design work underway.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Solution Testing | Q1 2024-25 | Delayed - Internal Reasons |  | User requirements have been completed the supplier pre-qualification questionnaire (PQQ) has completed. We are now moving to a Formal Request for Proposal (RFP). Overall the project is behind due to a number of Architecture and supplier delays but is still expected to be delivered to aligned to NCMS and OBP deliveries.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | ENCC Operator Console build complete. Move to implementation and enhanced testing | Q3 2024-25 | Delayed - Internal Reasons |  | User requirements have been completed the supplier pre-qualification questionnaire (PQQ) has completed. We are now moving to a Formal Request for Proposal (RFP) . Overall the project is behind due to a number of Architecture and supplier delays but is still expected to be delivered to align to NCMS and OBP deliveries. Proof of Concept Desk deployed
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Development and testing of user experience tools and video walls | Q4 2024-25 | Delayed - Internal Reasons |  | User requirements have been completed the supplier pre-qualification questionnaire (PQQ) has completed. We are now moving to a Formal Request for Proposal (RFP) . Overall the project is behind due to a number of Architecture and supplier delays but is still expected to be delivered to align to NCMS and OBP deliveries. Proof of Concept Desk deployed
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Enhanced Balancing data discovery & ingestion | Q3 2023-24 | Complete | Q2 2024-25 | Regular consultations being held with the OBP team to align each team's roadmap. After re-prioritisation both teams have committed to new dates. Due to industry demands the OBP team is committed to delivering BM reserve causing the delivery of audit data for DAP to move to later in the year. The design work by the DAP team has now been completed . An connection test was completed in June and the Ingestion of an test dataset completed in July 2024.. Formal ingestion of audit datasets into DAP now scheduled for completion in November. This activity is completed now.
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Integrate data platform with enhanced balancing tool | Q4 2023-24 | Complete | Q4 2024-25 | Regular consultations being held with the OBP team to align each team's roadmap. Following the successful connection and ingestion test in the summer; work commenced on the formal ingestion of audit datasets into DAP. This work was finalised in December 2024 and this milestone is considered complete.
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Network Control tool data discovery & data ingestion | Q3 2024-25 | Delayed - Internal Reasons |  | The delivery team for the new time series data historian is running a procurement exercise to find a vendor for the tool. This exercise is targeted to complete with installation of the selected tool forecast for Q3 FY25/26. This means the timeframes for the Data and Analytics milestones need to re-align to correspond with the new timetable. The only impact is a change in timelines as resources have been reassigned to other deliverables in the interim. The deliverable is now expected to be delivered during Q3-Q4 2025/26 Due to the delay, an interim solution for the current use case that relies on data from the time series data historian is being put in place, with an anticipated timeframe of Q1 2025/26.
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Integrate data platform with new network control tool | Q4 2024-25 | Delayed - Internal Reasons |  | The delivery team for the new time series data historian is running a procurement exercise to find a vendor for the tool. This exercise is targeted to complete with installation of the selected tool forecast for Q3 FY25/26. This means the timeframes for the Data and Analytics milestones need to re-align to correspond with the new timetable. The only impact is a change in timelines as resources have been reassigned to other deliverables in the interim. The deliverable is now expected to be delivered during Q3-Q4 2025/26 Due to the delay, an interim solution for the current use case that relies on data from the time series data historian is being put in place, with an anticipated timeframe of Q1 2025/26.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q1 2023-24 | Complete | Q1 2023-24 | THE TAC meetings are happening quarterly as planned. After having an initial 2 year agreement with the members we have successfully renewed commitment from 95% to continue supporting us going forward. We are looking to utilise their advice further by creating additional sub groups for specific purposes
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q2 2023-24 | Complete | Q2 2023-24 | The TAC meetings are continuing to happen quarterly as planned. We had the first in person TAC this quarter.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q3 2023-24 | Complete | Q3 2023-24 | THE TAC meetings are happening quarterly as planned. Both the control room of the future sub group and the new Digital and data strategy met in this quarter.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups Publication of annual report into the TAC's work and "you said we did" | Q4 2023-24 | Complete | Q4 2023-24 | "You Said We Did" has been published as part of the meeting slides. TAC's is happening on a quarterly basis we now have 2 subgroups one of which has a regular quarterly cadence with the other recently getting a new internal chair who’s working on a regular cadence. All discussions in the last session and published in the slides on the NESO website.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q1 2024-25 | Complete | Q1 2024-25 | The TAC quarterly meeting happened 7th June, we also had both sub group meetings in the last quarter.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q2 2024-25 | Complete | Q2 2023-24 | TAC is happening on a quarterly basis we now have 2 subgroups one of which has a regular quarterly cadence with the other recently getting a new internal chair who’s working on a regular cadence. The main TAC recently hired a new chair after the previous one resigned and he was in attendance at the last meeting.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q3 2024-25 | Complete | Q3 2024-25 | As always TAC is happening on a quarterly basis we now have 2 subgroups one of which has a regular quarterly cadence with the other recently getting a new internal chair who’s working on a regular cadence.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups Publication of annual report into the TAC's work and "you said we did" | Q4 2024-25 | Complete | Q4 2024-25 | TAC is happening on a quarterly basis we now have 2 subgroups one of which has a regular quarterly cadence with the other recently getting a new internal chair who’s working on a regular cadence. The main TAC recently hired a new chair after the previous one resigned and he was in attendance at the last meeting.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Initiate operational input into project scoping to enable operational visibility of DER (aligned with D15.8.2) | Q1 2023-24 | Complete | Q1 2023-24 | Operational input initiated with internal ESO stakeholders. We have now performed test despatches with NGED based DERs and the system is now live.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into technical standards (aligned with D15.8.2) | Q2 2023-24 | Complete | Q2 2023-24 | The standards and discussion with MWD and NGED complete, we are still discussing some finer points with UKPN as they want to do something slightly different, but effectively the discussions are complete, what we are now discussing is small details in terms of how the process will work.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into IT discovery phase (aligned with D15.8.2) | Q3 2023-24 | Complete | Q3 2023-24 | This is complete for NGED and UKPN. Further discussions are now required on next developments.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into IT discovery phase (aligned with D15.8.2) | Q4 2023-24 | Complete | Q3 2023-24 | This is complete for NGED and UKPN. Further discussions are now required on next developments.
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into requirements and design phase to enable operational visibility of DER (aligned with D15.8.2) | Q1 2024-25 | Complete | Q1 2024-25 | Linked to OBP project
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into delivery of DER data into the Control Centre | Q4 2024-25 | Complete | Q4 2024-25 | Tied to OBP project
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into IT discovery phase (as ref in 15.8.3) | Q1 2023-24 | Complete | Q4 2023-24 | Operational input has been provided into MW dispatch project - implemented with NGED, and advanced discussions with UKPN.
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into completion of IT discovery phases and costs (as ref in 15.8.3) | Q2 2023-24 | Complete | Q2 2023-24 | Operational input has been provided into MW dispatch project - implemented with NGED, and advanced discussions with UKPN.
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into primacy rule enhancements and further use cases. Provide operational engagement with DER service providers on operational impact of primacy rules. | Q4 2023-24 | Complete | Q1 2024-25 | Now supporting DER visibility manager along with connecting to DNO control room managers to widen debate.
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into primacy rule enhancements and further use cases. Provide operational engagement with DER service providers on operational impact of primacy rules. | Q4 2024-25 | Complete | Q4 2024-25 | Now supporting DER visibility manager along with connecting to DNO control room managers to widen debate.
1 | Operational coordination with DER and DSO | D1.5.3 | Development of RDP and LCM functionality into real-time environment | Continue to provide operational input into LCM and RDPs | Q4 2023-24 | Complete | Q4 2023-24 | Update 22/01/2025 LCM has moved past development stages and trials, is now live and embedded into ENCC process. LCM was rolled out as a live BAU service in Dec 23 and we have been working to grow MWs in the platform since. We have collaborated with industry to explore and remove barriers for aggregators (ABSVD Opt Out, Asset Metering, <1MW). We have coordinated closely with Scottish DNOs to support in their concerns around LV Domestic Demand Turn up and Fault escalation. While there are still a number of challenges, the LCM functionality has been added in to real-time environment as required in the D1.5.3 deliverable and we have efficiently worked to remove barriers for aggregators.
1 | Operational coordination with DER and DSO | D1.5.3 | Development of RDP and LCM functionality into real-time environment | Continue to provide operational input into LCM and RDPs | Q4 2024-25 | Complete | Q4 2024-25 | LCM is now live, and being embedded into ENCC process
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Establish a forum and ToR for operational flexibility service coordination with DSOs | Q1 2023-24 | Complete | Q1 2023-24 | Operational forum established with DNOs to facilitate operational discussions, bilateral discussions take place on specific service co-ordination issues (for example LCM/MW dispatch)
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Deliver new meetings | Q2 2023-24 | Complete | Q3 2023-24 | Complete - continue to update for next quarter
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Continue with regular meetings | Q4 2024-25 | Complete | Q4 2024-25 | In progress
1 | Minimising Balancing Costs | D1.6.1 | Constraint boundary optimisation | Achieve coverage of additional constraint management role in Control Centre | Q3 2023-24 | Complete | Q4 2024-25 | Role has been interviewed, and offers have been made. The respective CoEs will start in the new roles in April.
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Programme plan shared | Q1 2023-24 | Complete | Q1 2023-24 | Balancing Costs Strategy has been shared with Incentives Performance Panel and Ofgem.
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q3 2023-24 | Complete | Q3 2023-24 | Balancing Costs Strategy has been shared but more detail to be added following stakeholder engagement.
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q1 2024-25 | Complete | Q1 2024-25 | We plan to continue to develop and add detail to our balancing costs strategy.
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q3 2024-25 | Complete | Q3 2023-24 | We are continuing to develop and add detail to our balancing costs strategy.
1 | Minimising Balancing Costs | D1.6.3 | Stakeholder Engagement on Minimising Balancing Costs | Regular sessions with stakeholders to discuss opportunities to minimise balancing cost. | Q2 2023-24 | Complete | Q2 2023-24 | We hosted a workshop last year in July 2023 on our Balancing Costs analysis and strategy that we developed last year. There was a lot of engagement from industry participants. We are also about to publish an annual report on balancing costs with updated analysis and an identification of key decisions that need to be made to reduce Balancing Costs. It is expected to be published in May 2024.
1 | Minimising Balancing Costs | D1.6.3 | Stakeholder Engagement on Minimising Balancing Costs | Continuing Stakeholder Engagement forum on Balancing Cost Minimisation | Q4 2024-25 | Complete | Q4 2024-25 | There is always ongoing stakeholder engagement on minimising balancing costs through our regular channels, such as OTF, Ofgem/DESNZ/NESO trilaterals and the Metric 1A reporting. More specifically we are redeveloping our balancing costs strategy with a review of its effectiveness. There will also be an updated report published to industry on Balancing Cost projections. Engagement with industry will occur in Q1 and Q2 of 2025, following publication.
1 | Ongoing activities | D2.1.1 | Develop and drive control centre strategic resource planning, scheduling and training. | Fully staffed ENCC rota. Redesigned training schemes to facilitate needs of future ESO capabilities. New recruits direct entry from academia. | Q4 2023-24 | Complete | Q4 2023-24 | The external recruitment campaigns have resulted in a FTE of 121 with additional offers being made imminently. This meets the ENCC budget headcount for 2023 and lines us up for success to meet the 2024 headcount which is increased to meet the changing needs of the business including the introduction of flexible working within the control rooms.
1 | Ongoing activities | D2.1.1 | Develop and drive control centre strategic resource planning, scheduling and training. | Fully staffed ENCC rota. Redesigned training schemes to facilitate needs of future ESO capabilities. New recruits direct entry from academia. | Q4 2024-25 | Complete | Q4 2024-25 | ENCC headcount is at its highest with many new trainees . We continue to recruit and train for our highly technical and industry specific roles. We continue to attract post graduate students to our graduate training programme with 18 joining in September 24. In addition we have 23 Higher Apprentices who have joined our new Engineering Training Programme.
1 | Ongoing activities | D2.1.2 | Incident analysis and investigations of abnormal events, implementing improvements where needed. | The recommendations and actions from the incident investigation will help the ESO to operate the system more efficiently and securely. All root causes will be identified, and measures put in place to mitigate against any reoccurrence. Learnings shared with system users where applicable. | Q4 2024-25 | Complete | Q4 2024-25 | We have been consistently reviewing any significant incidents that had operational impact or significant near-miss events/incidents. Where applicable shared learnings are circulated with relevant parties.
1 | Ongoing activities | D2.1.3 | Monitoring and reporting of system performance to regulatory bodies. | All regulatory reports are created to time and quality. | Q4 2024-25 | Complete | Q4 2024-25 | On track - System Performance Reports: All regulatory reports have been published on time. GC105 and GC151 monthly System Incidents are reported on the NESO website. NESO continuing publishing the annual report of E7 (previously know as C17) NETS Performance, ICS (Incident Classification Scale), aLFC (annual Load-frequency Control) and CEP (Clean Energy Package) Article 13 - Redispatching. https://www.neso.energy/industry-information/industry-data-and-reports/system-performance-reports
1 | Ongoing activities | D2.1.4 | Guidance on operational policies for use in the control centre produced. | The guidance is unambiguous and the information are kept up to date. | Q4 2024-25 | Complete | Q4 2024-25 | On track - Control Centre has the most accurate information readily available, is unambiguous and information are kept up to date.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Deliver work based placement years | Q1 2023-24 | Complete | Q1 2023-24 | 12 one year Industrial placements have been issued. 5 for power system engineering, 3 for commercial analysts and 4 for data scientist. All are due to start with the ESO in from July 2023 and come from a wide range of UK universities.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Deliver reviewed modules and year 3 placement opportunities defined | Q2 2023-24 | Delayed - Internal Reasons |  | Due to creation of the Early Careers team in NESO, this work has been delayed. Resource is now in place with the plan to grow relationships with academia, however the milestone won't be delivered within BP2. In order to maintain relatinships, we continue to sit on industry advisory boards with several universities and have delivered lectures to MSc Students on the role and challenges of GB System Operation. NESO continues to offer industrial placements (8 in calendar year 2024) and summer placements to Power Academy students.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Delivery of placement opportunities | Q3 2023-24 | Complete | Q3 2023-24 | We have 12 Industrial Placement students currently placed in the ESO.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Delivery of modules and receive feedback on placement opportunities | Q4 2023-24 | Delayed - Internal Reasons |  | Due to resourcing challenges in the operational teams we have been unable to continue the work we had started with academia. We have also seen a marked reduction in students studying power system management with some universities no longer offering the course.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Review and update summer placements for 2024 | Q1 2024-25 | Complete | Q2 2024-25 | Summer placements for 2025 will be offered to the 'Power Academy' and then the NESO industrial placement programme. Adverts for IP programme will go live Q3 2024.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Update placement opportunities for one year placements | Q3 2024-25 | Complete | Q2 2024-25 | NESO continues to offer industrial placements (8 in calendar year 2024) and summer placements to Power Academy students.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Refresh and run existing courses | Q4 2024-25 | Delayed - Internal Reasons |  | Due to resourcing challenges in the operational teams we have been unable to continue the work we had started with academia. We have also seen a marked reduction in students studying power system management with some universities no longer offering the course.
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Further develop cross industry secondments | Q1 2023-24 | Complete | Q1 2023-24 | We have discuss with some industry parties future cross industry secondments and found there to be little interest at this stage. The reason being stated are the constant resource challenges many are facing. We will continue to work with our current secondment organisations such as CORESO and BEIS whilst we explore this option further.
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Engage with selected DNOs with potential cross simulator training options | Q2 2024-25 | Complete | Q4 2024-25 | System operation appreciation days given to 3rd parties including batteries, wind farms & their trading points, Shell, Octopus energy etc..
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Develop requirements for connectivity of training simulators | Q4 2023-24 | Delayed - Internal Reasons |  | Improvements to our training simulation environments depend on the delivery of Balancing Programme (OBP) and Network Control (NCMS) investment lines. The new training simulators will be based on the environments provided by OBP and NCMS. Due to revisions in their roadmaps, we've adjusted our training simulator roadmap to ensure alignment. This alignment has resulted in a delay, impacting the delivery of Future Training Simulator investments, which will now occur post-RIIO2. Consequently, the introduction of modern training facilities in our Control Training Unit (CTU) will be postponed, affecting efficiency. In the interim we will continue to use our existing training and simulation facilities, which remain fit for purpose to train staff to operate the control system. We remain committed to delivering this milestone against the new roadmap timeline. We will continue to work with DNOs and the wider industry on their future connectivity requirements. There is no impact on the consumer as this is purely industry training to ascertain what would happen if the DNOs were to become DSOs
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Trial training DNOs in simulators | Q4 2024-25 | Delayed - Internal Reasons |  | Due to the delay in delivery of enhanced training simulators we are unable to progress this action.
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Initial NCMS Training Simulator Stood Up | Q2 2023-24 | Complete | Q1 2024-25 | GE delivered a Training Simulator for NCMS into the AWS cloud environment in April 2024. This Training Simulator will now also be deployed to future On-Prem environments as and when they are deployed
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Complete Requirements for Joint Training Simulator | Q4 2023-24 | Delayed - Internal Reasons |  | Requirements gathering ongoing to fully define scope with NCMS, OBP (simulator integration) and CTU teams (training and scenario management tools); due Q2 25-26. Delays to the delivery of stand-alone simulators from the Network Control and Enhanced Balancing Capability projects has delayed completion in defining how to integrate the simulator capabilities. Revised roadmap to better align with NCMS and OBP deliveries to be presented in Q4 FY25
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Commence Dev/Test Phase | Q2 2024-25 | Delayed - Consumer Benefits |  | Re-baseline of plan against NCMS and OBP plans to align for delivery. GridOS pivot requires new milestone dates to be set for all corresponding Future Training Simulator milestones. Consumer benefit is realised by rebaselining our plan to include the adoption of the new GridOS platform from GE and this has been discussed and agreed with Ofgem through the CMF process. The provision of an enhanced training experience to reflect real-life operational scenarios and control room roles will reduce the time and associated costs of training Majority of project scope delivery deferred to align with OBP timescales for 2027
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Training Simulator Move to Implementation | Q4 2024-25 | Delayed - Consumer Benefits |  | Re-baseline of plan against NCMS and OBP plans to align for delivery. GridOS pivot requires new milestone dates to be set for all corresponding Future Training Simulator milestones. Consumer benefit is realised by rebaselining our plan to include the adoption of the new GridOS platform from GE and this has been discussed and agreed with Ofgem through the CMF process. The provision of an enhanced training experience to reflect real-life operational scenarios and control room roles will reduce the time and associated costs of training Majority of project scope delivery deferred to align with OBP timescales for 2027
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | An initial suite of learning packages built | Q1 2023-24 | Complete | Q1 2023-24 | A number of learning packages have been designed and developed with more planned for Q2. This includes an increase in on-line training material and the use of simulated scenarios for Energy Balancing training. Including technical role training for Transmission roles which have been difficult to recruit to.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | Learning packages tried and tested on trainees and amended where necessary | Q2 2023-24 | Complete | Q2 2023-24 | Training resources and material have been tried and tested on a number of new trainees with positive results. New training courses have been delivered for operational and non-operational staff. Feedback has been positive.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | All staff requiring access to the training packages have easy access 24/7 | Q4 2023-24 | Complete | Q4 2023-24 | Training packages created and stored in an area accessible to all staff. Used daily as part of the operational training courses.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | A full comprehensive suite of learning packages available and new ones added regularly | Q1 2024-25 | Complete | Q1 2024-25 | Work is complete on the learning suite and will be reviewed quarterly to ensure it is up to date and relevant
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | All staff requiring access to the training packages have easy access 24/7 and are able to use simulation training remotely | Q4 2024-25 | Delayed - Internal Reasons |  | The new training simulators will not have been delivered in time for this action. However it is anticipated that staff will be able to access offline training packages remotely.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Delivery of Automated System and Mobile App | Q1 2023-24 | Complete | Q1 2023-24 | Phase 3 is currently being assessed by internal and external IT providers with a number of future developments in the pipeline. The new automated system has now replaced the old manual system and the mobile app is being used by all operational staff.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Develop document management and rota improvements | Q4 2023-24 | Complete | Q4 2023-24 | Phase 3 of the automated rota and training system has been delivered and the project is completed.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Agile system that allows the user to register for training and receive training when it suits them | Q1 2024-25 | Delayed - Internal Reasons |  | Due to the prioritisation of operational training for both operational staff and training schemes, we have been unable to progress the development of Agile training systems. We don't expect to have created a new agile system by the end of BP2, however we are utilising the current training system where applicable.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Implement document management and rota improvements | Q4 2024-25 | Complete | Q2 2024-25 | Phase 3 of the automated rota and training system has been delivered and the project is completed.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Annual review of Training Plans | Q1 2023-24 | Complete | Q1 2023-24 | Annual review has been carried out on all the training plans associated to operational roles within the ENNC. They have been updated to include a skills matrix and links to newly delivered on-line learning.,
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Ad hoc review of training plans | Q2 2023-24 | Complete | Q2 2023-24 | All training plans and associated documents have been reviewed and updated to include links to online training and supporting documentation.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Ad hoc review of training plans | Q3 2023-24 | Complete | Q3 2023-24 | All operational training plans have been reviewed and updated with a detailed skills matrix and links to newly designed training packages.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Personalised training plans in place with continued gap analysis | Q4 2023-24 | Complete | Q4 2023-24 | Personal training plans issued to all trainees and a detailed skills matrix/ gap analysis carried out between trainee, trainer and line manager.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Created automation of training plans | Q1 2024-25 | Complete | Q2 2024-25 | Phase 3 of the automated rota and training system has been delivered and the project is completed.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | User testing of automation system for training plans | Q2 2024-25 | Complete | Q4 2024-25 | Our team embarked on a thorough investigation to determine if the new automated rota and training system could produce personalised training plans. We engaged in detailed discussions with the vendor, exploring the capabilities and limitations of the system. The vendor provided valuable insights into the system's functionalities, and we were hopeful that it would meet our requirements. To ensure a comprehensive evaluation, our team experimented with the system in the vendor's training environment. This hands-on approach allowed us to explore the system's features and understand its operational dynamics. However, despite our efforts, it became evident that the system was not capable of producing the personalised training plans we needed. After careful consideration and analysis, it was decided that the system would not be able to fulfil our requirements. This decision was based on the system's inability to provide the level of customisation we needed for personalised training plans. Our IT system architects have taken away the requirements and are now exploring other vendors' catalogues to find a suitable product. We are committed to finding a solution that meets our needs and enhances our operational training processes. There has been no impact on NESO or the consumers, as training has proceeded without interruption. The training plans have been manually customised and reviewed individually to ensure they meet the needs and objectives of each trainee.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Roll-out of automated training plans for Operational training | Q4 2024-25 | Delayed - Internal Reasons |  | Our team embarked on a thorough investigation to determine if the new automated rota and training system could produce personalised training plans. We engaged in detailed discussions with the vendor, exploring the capabilities and limitations of the system. The vendor provided valuable insights into the system's functionalities, and we were hopeful that it would meet our requirements. To ensure a comprehensive evaluation, our team experimented with the system in the vendor's training environment. This hands-on approach allowed us to explore the system's features and understand its operational dynamics. However, despite our efforts, it became evident that the system was not capable of producing the personalised training plans we needed. After careful consideration and analysis, it was decided that the system would not be able to fulfil our requirements. This decision was based on the system's inability to provide the level of customisation we needed for personalised training plans. Our IT system architects have taken away the requirements and are now exploring other vendors' catalogues to find a suitable product. We are committed to finding a solution that meets our needs and enhances our operational training processes. There has been no impact on NESO or the consumers, as training has proceeded without interruption. The training plans have been manually customised and reviewed individually to ensure they meet the needs and objectives of each trainee.
1 | Ongoing activities | D3.1.1 | Control Centre has fully tested skills, processes, plans and tools to support incident management and disaster recovery. | Fully meeting existing requirements. Future scope needs to be confirmed, following the publication of the Electricity System Restoration Standard. | Q4 2024-25 | Complete | Q4 2024-25 | Existing requirements are fully met.
1 | Ongoing activities | D3.1.2 | Restoration plans for GB with the necessary stakeholders, developed, maintained and validated. | Following the publication of the Electricity System Restoration Standard, first Assurance framework approved by Ofgem. Continue maintaining and validating fit for purpose Restoration Plans. | Q4 2024-25 | Complete | Q4 2024-25 | Continue to maintain fit for purpose Restoration Plans.
1 | Ongoing activities | D3.1.3 | Engage and collaborate with industry to plan and develop the new GB restoration standard, including the annual assurance framework, consistent with our licence obligations. | Code Admin Consultation sent out to industry Draft Final Modification Report and Issued to Ofgem | Q1 2023-24 | Complete | Q2 2023-24 | FMR issued to Ofgem in September
1 | Ongoing activities | D3.1.4 | Advice and oversight of Restoration and restoration strategy for the future provided. | Following the publication of the Electricity System restoration Standard, first Assurance Framework approved by Ofgem. | Q4 2024-25 | Complete | Q4 2024-25 | Assurance Framework submitted to Ofgem on 7th March 2025.
1 | Ongoing activities | D3.1.5 | Fully competitive Restoration procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | In 2023/24 technical evaluation and assessment of SE and Northern tenders. Award contracts for SE and Northern (and Wind) restoration services. | Q4 2023-24 | Complete | Q4 2023-24 | 4 Live Tenders in 2023 - 2024 (different stages): - South East Tender - Contracts awarded in December 2023. - Wind Tender - completed with no contracts awarded. - Northern Tender: final stages of evaluation progressing and contracts expected to be awarded by no later than Q1 2024-2025. - South West and Midlands Tender: launched in January 2024. Across all Tenders we have received a very wide range of technologies for all services that Restoration is seeking to procure from the market, namely: Primary Restoration Service Providers, Top Up Services and Distributed Restart Type Projects..
1 | Ongoing activities | D3.1.5 | Fully competitive Restoration procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | In 2024/25 new Tenders to meet requirements for ESRS implementation. | Q4 2024-25 | Complete | Q3 2024-25 | Northern tender process completed
1 | Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance framework for Electricity System Restoration | Review, update (if required) and submit for Ofgem's approval the annual Assurance Framework | Q1 2023-24 | Complete | Q1 2023-24 | Assurance Framework for 2023/24 was submitted to Ofgem on 14 April 2023
1 | Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance framework for Electricity System Restoration | Review, update (if required) and submit for Ofgem's approval the annual Assurance Framework | Q1 2024-25 | Complete | Q1 2024-25 | Assurance Framework for 2024/25 was submitted to Ofgem on 27 March 2024.
1 | Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. | Electricity System Restoration will become a much more agile process, featuring swift methodical power supply recovery and a whole system approach with the appropriate system control, simulation and decision making tools in place. | Q4 2024-25 | Complete | Q4 2024-25 | Restoration performance is quantified with the probabilistic model and details forms part of our annual assurance submissions
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Update regulatory framework following Ofgem's approval of regulatory changes | Q1 2023-24 | Complete | Q4 2023-24 | All approved regulatory framework are now up to date and published on ESO's website
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry to ensure progress with network changes. | Q2 2024-25 | Complete | Q2 2024-25 | There are ongoing engagements with industry to provide clarity on required changes to facilitate ESRS. Response from industry on delivery plans is slow and very low.
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry during tender process to secure restoration service providers | Q3 2023-24 | Complete | Q3 2023-24 | There has been extensive stakeholder engagement on the Tenders launched in 2023
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry for training and upskilling. | Q3 2024-25 | Complete | Q4 2024-25 | The ESRS and Restoration teams have provided continuous training to upskill SSE, SPT and ESO ENCC staff through workshops and practical sessions during September 2023 and May 2024. More training sessions are planned for spring of 2025 and engagement with NGET for inclusion in future sessions.
1 | Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations and licence obligations. | Tool available for integration with Network Control programme | Q3 2024-25 | Delayed - External Reasons |  | Risk 1: Due to resourcing issues, and Vodafone contract termination, delivery of the ICCP Links is delayed to backend of Q1 25/26. Vodafone was the original contractor installing the Inter Control centre Communication Protocol (ICCP) links; they have since been replaced with Magdalene as the contractor. Vodafone resourcing and attrition rate made it challenging at the project manager level and with continuous changing of resources they could not keep to original timelines. The 3 ICCP links are required in 2026 as the Distribution restoration plans have not yet gone live. The delivery date in late 2025 does not impact overall delivery. There is no impact on the overall deliverable. An update to the industry on new delivery dates for ICCP links has been made. Risk 2: NESO plan to progress RDST with GE by leveraging the platform GE are delivering as part of the NCMS project, GridOS Platform (Data Fabric). Using the same network data model across NCMS and RDST we want to align the user experience by positioning RDST as an extension to NCMS application suite as well as align architecture and realise cost benefits. RDST therefore has a dependency on the deployment of the GridOS platform and cannot be decoupled from NCMS Go Live (Q3FY26.) Identified challenges and gaps in GE's proposal for the RDST. The RDST will be launched under a unified platform along with NCMS and is reliant on NCMS delivery. The RDST is the deliverable, and it was to be delivered before the Electricity System Restoration Standard (ESRS) implementation date of 31 December 2026. It should not affect the overall date. Is it now expected to be implemented? Q3FY26 The industry expects that the RDST will be operational before ESRS implementation, and if confirmed, an update to the industry on new delivery dates would be required. There is no evidence that the RDST would impact restoration timings if not delivered on time.
1 | Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations and licence obligations. | Further tool testing and continuous development. | Q4 2024-25 | Delayed - External Reasons |  | Due to delays highlighted above in delivering the RDST and ICCP links, testing and continuous development will be delayed to FY26
1 | Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types in the Distributed ReStart innovation project. | Third Power Engineering live trial (including testing of Distributed Zonal Controller) | Q3 2023-24 | Complete | Q3 2023-24 | Third Power Engineering trial successfully delivered (Redhouse trial). https://www.nationalgrideso.com/document/289876/download
1 | Innovation project in restoration | D3.3.2 | Subject to industry adoption, Distributed ReStart proof of concept findings implemented and new system and communication methods implemented | We will fully understand Distributed ReStart's final recommendations and their implications. | Q1 2023-24 | Complete | Q1 2023-24 | Recommendations from Distributed ReStart are being implemented as part of ESRS
1 | Innovation project in restoration | D3.3.2 | Subject to industry adoption, Distributed ReStart proof of concept findings implemented and new system and communication methods implemented | We will have made decisions on which recommendations will be implemented in future (subject to industry adoption) | Q3 2023-24 | Complete | Q3 2023-24 | Selected recommendations from Distributed ReStart are being implemented as part of the tender process
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q1 2023-24 | Complete | Q2 2023-24 | Published 6 July 2023 after a short delay to ensure content is complete and up to date.
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q3 2023-24 | Complete | Q3 2023-24 | We have reviewed activities across the ESO to identify those which contribute to the ongoing delivery of transparency for the ESO and produced the revised ESO Transparency Roadmap, published 21st December.
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q1 2024-25 | Complete | Q1 2024-25 | An updated version of the transparency roadmap for FY24/25 was published on 28th June 2024.
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q3 2024-25 | Complete | Q3 2024-25 | An updated version of the transparency roadmap for FY24/25 published on our external website at: https://www.neso.energy/what-we-do/systems-operations .
1 | Ongoing activities | D17.6 | ESO Operational Transparency Forum (OTF) | Weekly OTF held to provide timely operational insight and an opportunity for question from industry. Positive stakeholder feedback received. | Q4 2024-25 | Complete | Q4 2024-25 | At the OTF we remain focused on understanding the needs of our customers in order to ensure the weekly forum meets their expectations by providing updated information and insight into the operational challenges. Back in December 2023, we conducted a comprehensive survey of the OTF. Using the feedback gathered, we identified and implemented necessary changes to enhance the value provided to participants. Following some delays due to preparations for NESO Day One, we integrated these improvements into the OTF in the third quarter of 2024/25. We then published a final update on our response to the survey on the OTF webpage in January 2025. In January 2025, we conducted an additional survey of participants. We received 91 responses, which is more than double the 40 we received for our last survey. This broader range of feedback represented a more diverse group of energy industry participants. We discovered that forum participants perform a variety of roles within their organisations, helping us to better understand our audience. Regular content and the focus topics/deep dives continue to score positively, and most comments were positive, showing that the industry highly values the forum. Further information and content from the OTF, including the OTF 2023 Survey Report - Updated Outcomes (January 2025), is available at: https://www.neso.energy/what-we-do/systems-operations/operational-transparency-forum
1 | Ongoing activities | D17.7 | Proactively driving transparency in ESO decision-making through identification, prioritisation and publication of more datasets and insight communicated through the Transparency Roadmap | Provides industry with greater transparency of our decisions in areas of high significance to stakeholders. | Q4 2024-25 | Complete | Q4 2024-25 | We continue to engage with stakeholders to explain how the ESO makes dispatch decisions and to respond to queries. In response to concerns raised by Battery Storage Coalition we have accelerated our activities to track, measure, report on and bring down the skip rate. We have held two CEO roundtables (10th October & 3rd December) with energy sector leader to discuss progress with our actions. We also held a Battery Forum event on 4th December, offering a platform for open discussion and collaboration, webinars on the LCP skip rate methodology and have been publishing skip rates datasets since 15th December from our new skip rate tool, based on the LCP methodology. This data is also share at the weekly Operational Transparency Forum (OTF). A further Battery storage and skip rate webinar was held on 27th February along with a skip rate data drop in on 12th March. We are continuing to engage with industry on our plans to increase transparency and bring down the level of skips.
1 | Ongoing activities | D17.8 | Digital Engagement Platform (DEP) continued phased deployment | The DEP will make the experience of engaging with the ESO more intuitive and user friendly by providing a single sign on for all ESO services and a personalised user experience with access to information, data and other services including markets, connections and codes. | Q4 2024-25 | Complete | Q4 2024-25 | Our approach has been to front-load work on our programme early on by increasing resources through standing up of an additional skilled team. This larger collaborative team created the ability to deliver foundational capabilities and features ahead of expected timelines but still in line with budget. Release 1: ESO website infrastructure (Acquia) made independent of National Grid website. Release 2: added user based authentication (CIAM single-sign-on) for ESO website (DXP). Plus, encouragement for user to sign on Release 3: Progressing vision of creating a more seamless customer experience across ESO digital properties. Data portal pages brought within DXP. Removal of front-end of data.nationalgrideso.com for CKAN data portal. CIAM integration with SMP for Markets registration and authentication. CIAM integration with Auctions users and APIs. CIAM integration with connections portal and added Multi Factor Authentication. CIAM integration with ENAMS and EGAMA. Improvements to Maps in terms of scope and functionality. Improvements to ESO back-end admin functionality. Search improvements for Data Portal and CMS. Release 4: personalisation of My ESO account and Data Portal Subscription enhancements. Personalisation of My News Carousel and My Events Carousel (select your topics of interest). Users able to filter My Events by type. As part of this release. we also upgraded our security around CIAM single-sign on, integrated with Connections 360, DCM and Operational Forms to bring about a more seamless UX with an iterative project on shared global components / web wrapper. Release 5 focused on re-branding the ESO website (design, content and URL changes) for the change to NESO and release of Help Centre. DEP was previously forecast to integrate with the Data and Analytics Portal. However DAP has been delayed until 2026. Therefore a change request has been raised to safeguard money intended for DEP/DAP integration this year. This work is now due to complete by Q1 FY26.
1 | Ongoing activities | D17.9 | Open Data Catalogue | Provides external users with a view of ESO Data and enables internal users to develop their own data products to benefit consumers. | Q4 2024-25 | Complete | Q4 2024-25 | Purview 1.0 data catalogue capability has been added to the Open Data Portal to provide valuable metadata, which can be accessed via the DEP user interface. Open Data Portal has been enabled with reporting and visualisation so external users can build data products.
1 | Ongoing activities | D18.1.1 | Daily analysis of Market activity and transaction data | Robust process for analysing data in a timely manner, which allows us to identify any suspicious behaviour. | Q4 2024-25 | Complete | Q4 2024-25 | The market monitoring team have a daily process established to review dynamic data, prices, and physical notifications of all balancing mechanism units. All potential suspicious activity or inconsistencies in data are logged and reviewed by the team to determine the next steps of an alert or investigation. Further capabilities have been built to detect and monitor the Inflexible Offers Licence condition, Transmission Constraint licence condition and grid code risks. These build on previous innovation projects implementing more sophisticated anomaly detection techniques and targeted models while refining existing ones. The team continue to update and improve analysis dashboards and data analytics to support identification of and reporting against potential breaches of REMIT whilst also increasing outward engagement with market participants to improve understanding of technical capabilities and reasons for anomalies whilst also increasing tool sophistication.
1 | Ongoing activities | D18.1.2 | Detection of suspicious behaviour and submission of Suspicious Transaction Reports (STR) to Ofgem | The continuous submission of detailed STRs to Ofgem, in a timely manner over the course of BP2 | Q4 2024-25 | Complete | Q4 2024-25 | Alongside the data based alerts via the automated tool assessing balancing mechanism data and Power BI dashboards, the team have established communication channels via email .box's to receive both internal to the ESO and external queries or tip-offs regarding potential suspicious activity. Every alert is assessed against REMIT and market rules and where there is reasonable grounds of suspicion of a breach of REMIT following an investigation, a suspicious transaction report (STR) will be created and shared with Ofgem's REMIT team. Similarly, where there is suspicion of a breach of market rules, a market incident report (MIR) is created. Across FY25 to date the team has submitted 6 STRs to Ofgem and 3 MIRs. This follows building increased complexity and data into reports adapting to feedback. All timings of STRs are tracked and are aimed to be submitted within ACER's 28 day guidance. Ongoing discussions are had across the year on process improvements for timely submission and new detection and reporting capabilities. The team has become significantly more proactive with challenging poor data directly to improve balancing service markets outside of the legal process. This includes a significant project delivered to improve the quality of wind data which has already realised significant error and cost reductions resulting from this.
1 | Ongoing activities | D18.1.3 | Undertake independent review of our Market Monitoring compliance activities against our PPAT and licence obligations alongside emerging market services. | This process includes a review of the original risk assessment and additional risk assessments of new market products and services. | Q4 2024-25 | Complete | Q4 2024-25 | The team commissioned an independent external review of the design and operating effectiveness of the team's processes to identify strengths and areas of improvement. The actions from this report are now complete. The market monitoring team undertakes a continual risk-based approach to the expansion of its monitoring processes and the services to which they apply, using a data driven assessment of ancillary services and prioritising higher risk products. This approach ensures that all ESO markets have proportionate monitoring with a yearly refresh to update for new products and services or changes to existing ones. The balancing services risk assessment process has been standardised, expanded to all new products and circulated to OFGEM and internal service owners for awareness of identified risks and monitoring approach.
1 | Ongoing activities | D19.1.1 | Data and Analytics (D&A) Operating Model | Our D&A operating model brings together people, process and technology to enable the continuous development and enhancement of D&A tools across the ESO & ongoing publication of data to external stakeholders via our Open Data Portal. The Operating Model is comprised of i) a "Hub" team, setting the "rules and tools" for data product development and includes Data Governance, Data Operations & Data Stewardship, and ii) business "Spoke" teams, who work with the Hub team on our DAP platform to create new data products in a self-serve manner. | Q4 2024-25 | Complete | Q4 2024-25 | The Hub and Spoke operating model has been implemented throughout NESO. Data Owership has been agreed within the Spokes (i.e. business areas) with central data capabilities, including DAP and data policy/best practice contained within the Hub. Data Services Portal went live on NESO intranet from Day 1 for colleagues to access data services provided by the Hub.
2 | Manage existing balancing services and markets | D4.1 | We manage an end-to-end process to ensure that balancing services are procured to deliver security of supply to lowest cost to consumers. | continued management of end-to-end processes | Q4 2024-25 | Complete | Q4 2024-25 | this is an ongoing activity
2 | Manage existing balancing services and markets | D4.1.1 | Frequency management strategy | Delivery of FRCR report with enhanced look-ahead. | Q4 2023-24 | Complete | Q1 2024-25 | Update on 28 Feb - Reviewed project delivery plan has been agreed within ESO. New completion date (and submission to Ofgem) is 28 June 2024. Industry consultation will be between 8 April to 16 May with a webinar proposed on 25 April. New plan will be communicated to SQSS Panel on 11 March. Ofgem will be communicated too. We will communicate to the industry when the consultation and webinar dates are approaching via OTF and emails to SQSS distribution list. Update on 25 March - Revised plan was presented to and agreed with Ofgem on 8 March 2024. Updated plan was communicated to SQSS Panel on 11 March 2024. No objections from Ofgem or SQSS Panel. Project is progressing well in line with revised schedule. Consultation is planned to launch on 8 April. Update on 08 May - FRCR 2024 report was launched for industrial consultation on 10 April with an aimed completion date of 17 May 2024. The ESO also ran a webinar on 1 May to go through the key recommendation of FRCR 2024 policy and answered live questions from industrial attendees. We will publish the webinar materials and Q&A document towards the end of the consultation period. We will further engage with Ofgem and SQSS Panel to update feedback from industry. Update on 20 June - FRCR 2024 is on track in line with the revised project delivery plan. The report is with SQSS panel for approval before submitting to Ofgem by end of June. Intensive engagement has been carried out this year to reach out to industry. FRCR 2024 final report submitted to Ofgem on 12 July 2024. 120 GVA.s min inertia policy was implemented on 19 June 2024. Update in mid Sep - await Ofgem approval of FRCR 2024. FRCR 2024 was approved by Ofgem on 27 September 2024. The policy is subsequently implemented in early October 2024.
2 | Manage existing balancing services and markets | D4.1.1 | Frequency management strategy | Delivery of FRCR report with enhanced look-ahead. | Q4 2024-25 | Delayed - External Reasons |  | The FRCR report has been issued for consultation on 3 March 2025. We have had significant engagement with the industry, Ofgem and the SQSS Panel on the approach and modelling of the FRCR25 report. This has included bespoke webinars and discussion forums on this complex technical topic. Following our engagement, the SQSS Panel's request edfor additional independent assurance of the report and methodlogy given its technical complexity This has placed an anticipated delay of submission of the report to the Authority, Ofgem by around 6 weeks.
2 | Power Responsive | D4.2.1 | Regular and specific metrics and publications across Distribution System Operator (DSO) development and co-development of local flexibility markets through a variety of innovation projects | Annual Report published | Q1 2023-24 | Complete | Q1 2023-24 | Report published
2 | Power Responsive | D4.2.1 | Regular and specific metrics and publications across Distribution System Operator (DSO) development and co-development of local flexibility markets through a variety of innovation projects | Annual report published | Q1 2024-25 | Complete | Q1 2024-25 | Published first week of July 2024.
2 | Power Responsive | D4.2.2 | Regular and specific metrics, and publications for multi sector approaches focusing on opportunities for household, community energy, small business participation, zero carbon technologies, and electrification of heat in Demand Side Flexibility (DSF). | Successful delivery of sector specific events and engagement to raise the awareness of ESO/DSO flexibility markets with the demand side community | Q4 2024-25 | Complete | Q2 2024-25 | Update Jan-25 We were proud to host the Flex Theatre at EMEX in Nov 24 and were pleased to publish our annual report in July-24. We attended BIgZero in July and hosted the first FlexAssure Roadshow in June. We held Operational metering working groups in June, September and then delivered a webinar on 08/01/2025 Looking forward we will continue to facilitate the Operational Metering Independent Review, deliver the growth of the LCM market, begin work on the Annual Report for 2025 and focus on the upcoming events for 2025 including the new FlexSummits. Update March 25 Progress on the Ops Metering Independent Review with an industry working group held early March. Plan is to share finding early June. 24/25 PR Annual Report first draft proof read and ready for final review and delivery in April/May Two day Energy Technology Live Event (DES) was a real success. 2nd Flex Summit held in Glasgow has been met with really positive feedback from the local DNOs, Aggregators and I&C customers. Focus is on those providers who haven’t yet made the step into flex services, discussing what is available and what the requirements are. LCM progress as we work to grow MWs in the market. Commercial Policy review should help this. March saw 242 MW of tendered volume, 16MW contracted. We are still seeing the market work on price discovery and hope to see dispatches increase over 2025.
2 | Deliver an efficient frequency market | D4.3.3 | New reserve products - development and introduction of a new suite of products to provide reserve to the Control Centre | Launch Firm market for nBM providers (dependency on D4.3.5) | Q3 2023-24 | Delayed - Internal Reasons |  | In April 2023, we delayed our Reserve products due to significant changes required in legacy balancing systems. We reconsidered implementing on these systems, opting instead for the Open Balancing Platform (OBP). Our strategy was to launch the Quick Reserve service via OBP with BM legacy system support, enabling delivery for BM parties in 2024 and creating a market route in 2025 for non-BM participants through future OBP releases. This approach was cost-effective for meeting ESO objectives while managing IT costs. Efforts to create dual market routes in 2024 faced limitations: • ASDP Development: Upgrading the ASDP dispatch platform was costly and time-consuming, not feasible before mid-2025. Its planned retirement in December 2025 would lead to a significant regret spend without accelerating market entry and would impact the OBP roadmap. • BM Development: Using EDL/EDT for non-BM participants impacted ESO development and provider integrations, requiring new interfaces and technology protocols, likely extending delivery timelines. ESO is committed to minimizing integration changes for new services and transitioning to the OBP. Delivering Quick Reserve to BM parties in winter 2024 via OBP and existing BM systems allows us to bring forward consumer value. The phased delivery is as follows: • Phase 1: BM participation in November 2024 (Delivered). • Phase 2: Non-BM participation in summer 2025 (On Track), with the non-BM market for Quick & Slow Reserve following the OBP Strategic non-BM functionality release, planned for Q2/Q3 2025-2026. This phased approach delivers Quick Reserve, expected to bring significant consumer value, with net savings estimated between £29.3 million and £32.7 million during seven months of participation through combined BM/OBP systems.
2 | Deliver an efficient frequency market | D4.3.3 | New reserve products - development and introduction of a new suite of products to provide reserve to the Control Centre | Launch Firm market for BM providers (dependency on OBP delivery) | Q4 2024-25 | Complete | Q4 2024-25 | Quick Reserve BM (phase 1) service went live on the 19th November with the first auction taking place on the 3rd December 2024. Engagement with industry on both the Quick Reserve phase 2 (enduring Service) and Slow Reserve has commenced and will continue throughout Q3 2024/25
2 | Deliver an efficient frequency market | D4.3.4 | Delivering an efficient frequency market | Created longer-term procurement strategy which spans response and reserve looking at how the products interact with each other operationally and commercially, and the wider market. | Q4 2024-25 | Complete | Q4 2024-25 | Jan 25 update: The launch of the Quick Reserve (Phase 1) Product in November 2024 saw the co-optimisation of Dynamic Frequency Response and a Reserve service. Market participants can submit baskets for both Quick Reserve and Frequency Response services, allowing the algorithm to co-optimise their bids. Co-optimisation is achieved when a market participant submits separate baskets for Quick Reserve and Frequency Response services on concomitant service windows. The algorithm selects the optimal combination of baskets while respecting splitting and capacity constraints. Co-optimsation of the services allows NESO to purchase both services at the lowest cost to consumer given the units available. Subject to consultation, future changes across Dynamic Response and Reserve will include locational procurement ensuring NESO can manage the operational challenges of service distribution and impact of network constraints as well as enabling units to stack (split) capacity across both services.
2 | Deliver an efficient frequency market | D4.3.5 | Auction capability | Implementation of the enduring auction capability and transition of the newly introduced services of BP1 onto the platform. | Q4 2024-25 | Complete | Q4 2024-25 | Balancing Reserve Service has been added to the Enduring Auction Platform. This service went live on the EAC platform early March 2024. Quick Reserve BM technical go live and re-branding activities also completed in Q3 2024 with full go live in November 2024.
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | In line with our new approach to annually consult on the new response services, we expect to formally engage with industry through the EBR Article 18 process in summer 2023-24. | Q2 2023-24 | Complete | Q2 2023-24 | Release 2 (2023-24) Electricity Balancing Regulation (EBR) consultation launched in Summer 2023 and was submitted to Ofgem end of September 23. Following challenges in the submission the ESO re-submitted and received approval in Mar-24. Key topics of focus for 2023-24 include removing barriers to Data-derived metering (baselining), clarity on topics such as State of Energy, updates to ramp rates, as well as a range of changes to tools and improvements to enable the Control Centre to operate the electricity transmission system securely.
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | We expect to publish updated service terms towards the end of Q3 2023-24. These changes will then feed into the C16 consultation process. | Q3 2023-24 | Complete | Q4 2023-24 | Service terms will be updated and published following Ofgem approval (expected in Q4). Delay due to amendments required in drafting of revised Release 2 - resubmitted and approved in Q4 23/24
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | Working on the assumption that the annual cycle is welcomed by industry we expect to be consulting via the EBR Article 18 process on response services in Q2 2024-25. | Q2 2024-25 | Complete | Q2 2024-25 | In Q2 we launched the Response Release 3 consultation. Key topics included the removal of the maximum ramp rate restriction, further clarity on the availability policy and significant changes to monitoring and reporting which will provide more robust performance management. All of these topics have been key service provider pain points identified through previous engagement. These changes remove barriers to participation, increasing liquidity and provider confidence in fair market. Following the consultation, the updated service terms were submitted to Ofgem in August 24.
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | If we consult in Q2 2024-25, we expect to publish updated service terms towards the end of Q3 2024-25. These changes will then feed into the C16 consultation process. | Q3 2024-25 | Complete | Q3 2024-25 | Updated service terms were published in November 2025.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Initial integration with Enduring Auction Capability | Q2 2023-24 | Complete | Q1 2023-24 | SMP has delivered initial integration with the Enduring Auction Capability in Q1 to facilitate market trials in September and go live of EAC in October 2023
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Query Management process aligned with wider ESO digital process | Q3 2023-24 | Complete | Q4 2024-25 | The Digital Engagement Platform (DEP) team have taken responsibility to developed a centralised query management process. This new process had a “technical” go live on 14 March 2025. In advance of this the SMP project has supported the development of the "Support Centre" that went live with the launch of NESO on 01 October 2024. SMP developed ~20 articles that are available on the Help Centre.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Integration with Settlements system | Q4 2023-24 | Complete | Q4 2024-25 | SMP has integrated at a high level with the new STAR system through the provision of direct contract information from November 2023. This milestone however was targeting greater integration from Q4 2023/24. In the SMP Show and Listen event on 07 September 23 we canvassed opinion from the industry on what they want NGESO to focus on initially. Access to invoice information on an enduring basis through STAR will not be achievable till the end of FY26, however SMP has delivered an interim solution that facilitates access to existing Sharepoint data that has been deployed on SMPs R3.11 release on 28 March 2025
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Enhance the wider BM registration process | Q2 2024-25 | Complete | Q4 2024-25 | BM Registration was migrated onto SMP from 14 February 2025. The initial release saw enabling data fields added to SMP and new functionality in support of creation of new BM Units. Existing active BM and Non-BM unit data was then migrated to SMP on 28 February alongside functionality to share data on SMP into downstream NESO systems. Interconnector and Supplier BMU data were covered in the SMP release on the 28 March. Further enhancements will then follow through FY26
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | All balancing services procured through SMP | Q4 2024-25 | Complete | Q4 2024-25 | All existing and enduring day ahead markets hosted on SMP (DC, DM, DR, Static FFR, BR, QR (BM)) with plans in place for future markets (QR NBM and SR). This is based on the strategy to focus on day ahead and enduring products that are consistent and repeatable that lend themselves to a self-serve digital experience. We believe that this represents an appropriate approach to service integration. SMP also hosts DFS and 2 x RDPs. SMP is currently not expecting to be involved in the procurement process for longer term contracts (pathfinders, Y-1, Y-4 for Stability, Voltage and Restoration) as these are more appropriately managed within wider procurement process; although we will seek to add value to the post award contract management process.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Supported the development of a proof of concept for industry asset register | Q2 2023-24 | Complete | Q3 2023-24 | SMP worked with UKPN and Electralink to develop a proof of concept that saw both SMP and the DNO share high level information with Electralink and they shared "risk of conflict" information to the opposite party where any MPAN match is found. This PoC proved that data of this type could be shared (albeit through a separate 3rd party) and helped to inform NESO could use data about assets pre-qualified for balancing services that may be committed elsewhere for a DSO service / behind a flexible DSO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. This PoC ran operationally in February 2024 and has informed DNO Reporting functionality delivered on SMP in November 2024 that will be used by the Flexibility Market Development Team and enhanced over time. Learnings will also feed into the wider "DER Visibility" project within NESO as well as our involvement in Ofgem FMAR and DESNZ AAR, CAR and FMU programmes.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Participation in proof of concept for industry asset register | Q4 2023-24 | Complete | Q4 2023-24 | SMP worked with UKPN and Electralink to develop a proof of concept that saw both SMP and the DNO share high level information with Electralink and they shared "risk of conflict" information to the opposite party where any MPAN match is found. This PoC proved that data of this type could be shared (albeit through a separate 3rd party) and helped to inform NESO could use data about assets pre-qualified for balancing services that may be committed elsewhere for a DSO service / behind a flexible DSO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. This PoC ran operationally in February 2024 and has informed DNO Reporting functionality delivered on SMP in November 2024 that will be used by the Flexibility Market Development Team and enhanced over time. Learnings will also feed into the wider "DER Visibility" project within NESO as well as our involvement in Ofgem FMAR and DESNZ AAR, CAR and FMU programmes.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Integrate SMP with industry asset register (subject to it being available) | Q2 2024-25 | Delayed - External Reasons |  | SMP has progressed significantly in asset registration but hasn't integrated with a separate register due to ongoing industry work lacking the certainty needed for integration whilst series of innovation projects play out such as Automated Asset Registration, Central Asset Registration and Flexibility Markets Unlocked. We have responded to Ofgem’s consultation Flexibility Market Asset Registration. Despite this, progress has been made, including a development backlog that delivered 24 releases in 24 months in BP2 and the following areas that will facilitate: 1. To enable future integration, we deliberately began with the MPAN as the foundation for asset registration in SMP. Since MPANs will be central to future asset registration approaches, we are well-prepared to meet future requirements. 2. We have prioritised developing our APIs to support system-to-system interactions, enabling the aggregation of multiple assets and improved handling of the heavy data load expected from future market integrations. 3. We’ve delivered a PoC alongside UKPN & Electralink that evidences how some aspects of market integration, specifically the “risk of conflict reporting and visibility”, could be delivered. This delivered 2 of the 4 BP2 milestones in this space. 4. SMP took learning from this PoC work and in Q3 delivered initial DNO reporting functionality that the Flexibility Market Development team will use in an adhoc manner (to share with DNOs to understand MPAN / balancing services pre-qualification risk of conflicts) and enhance over time. 5. We’ve also had direct interactions with all industry innovation projects and fed into the FMAR consultation response. We shared a sandbox environment and feedback on APIs to Arup and other project partners. We will now work with Elexon, as Market Facilitator, on wider industry integration and the requirements of Ofgem’s recent decisions on FMAR.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Improved DER asset visibility within SMP and / or wider NGESO platforms | Q4 2024-25 | Delayed - External Reasons |  | SMP has progressed significantly in asset registration but hasn't integrated with a separate register due to ongoing industry work lacking the certainty needed for integration whilst series of innovation projects play out such as Automated Asset Registration, Central Asset Registration and Flexibility Markets Unlocked. We have responded to Ofgem’s consultation Flexibility Market Asset Registration. Despite this, progress has been made, including a development backlog that delivered 24 releases in 24 months in BP2 and the following areas that will facilitate: 1. To enable future integration, we deliberately began with the MPAN as the foundation for asset registration in SMP. Since MPANs will be central to future asset registration approaches, we are well-prepared to meet future requirements. 2. We prioritised developing our APIs to support system-to-system interactions, enabling the aggregation of multiple assets and improved handling of the heavy data load expected from future market integrations. 3. We delivered a PoC alongside UKPN & Electralink that evidences how some aspects of market integration, specifically the “risk of conflict reporting and visibility”, could be delivered. This delivered 2 of the 4 BP2 milestones in this space. 4. SMP took learning from this PoC work and in Q3 delivered initial DNO reporting functionality the Flexibility Market Development team will use in an adhoc manner (to share with DNOs to understand MPAN / balancing services pre-qualification risk of conflicts) and enhance over time. 5. We’ve also had direct interactions with all industry innovation projects and fed into the FMAR consultation response. We shared a sandbox environment and feedback on APIs to Arup and other partners. There’s also a wider DER visibility project (TIDE) where SMP is central to a number of use cases. We’ll now work with Elexon as Market Facilitator on wider industry integration and the requirements of Ofgem’s recent decisions on FMAR.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.3 | Reforming markets to facilitate future growth of Distributed Flexibility technologies and models | Develop an ESO strategy to facilitate the growth of Distributed Flexibility. It will aim to understand the capabilities of distributed flexibility, their unique challenges in entering our markets, a defined vision for distributed flexibility in 2035, and a set of actions to reform our markets to facilitate their growth and participation. | Q4 2023-24 | Complete | Q4 2023-24 | Flexibility Strategy is under co-creation with industry parties. We have defined ESO’s vision, desired 2035 strategic objective and 2028 outcomes, as well as the roadmap of actions. The key focus of this quarter is testing our proposal with various industry colleagues via workshops and bilateral conversations. Based on the feedback received from industry, we changed our delivery approach. A Call for Input will be launched to make our engagement more effective and inclusive.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.3 | Reforming markets to facilitate future growth of Distributed Flexibility technologies and models | Align actions with Markets Roadmap and market reforms. Continue to refine the strategy, including further deep dives on specific issues as technologies and markets evolves. | Q4 2024-25 | Complete | Q4 2024-25 | Following an extensive industry Call for Input in June 2024, we have now published Enabling Demand side Flexibility in NESO markets It outlines the vision, outcomes and key objectives we aim to achieve by 2030 to support government CP30 ambition. Alongside this publication, we have also released stage 2 of our Demand Side Flexibility Routes to Market Review. This review aims to identify and prioritise barriers, setting out our approach to removing barriers and timeframes for doing so. In this second stage, we report on the outcomes of our engagement with industry and set our approach to prioritising the removal of barriers for demand-side flexibility to participate in flexibility markets.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.4 | Facilitating market access for Distributed Flexibility | Understand the key technical and commercial barriers to distributed flexibility today and deliver prioritised short-term changes as per ESO strategy. Progress towards the delivery of SMP (as per A4.4). | Q4 2023-24 | Complete | Q4 2023-24 | We continue to engage with the market and stakeholders and evolving our strategy around the development of flex markets including the delivery of SMP. The flexibility strategy will propose the direction we will be taking. Included in this is a review of stacking and key service requirements. We continue to progress this with industry stakeholders and have made some progress with the DNO's over a PoC for coordination/primacy rules.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.4 | Facilitating market access for Distributed Flexibility | Continue to identify and deliver changes required to faciliate distributed flexibility participation and coordinate with long-term Distributed Flexibiltiy Strategy. | Q4 2024-25 | Complete | Q4 2024-25 | SMP is actively involved in the discussions alongside DDT and Flexibility Market Development team. Positive progress has been made on reporting function to facilitate Primacy: SMP took learning from the PoC work and in Q3 has delivered initial DNO reporting functionality that the Flexibility Market Development team will use in an adhoc manner (to share with DNOs to understand MPAN / balancing services pre-qualification risk of conflicts) and enhance over time. SMP was also central to the ESO response to Ofgem’s Flexibility Market Asset Registration (FMAR) consultation and is feeding into DESNZ’s AAR (Automatic Asset Registration), CAR (Central Asset Registration) and FMU (Flexibility Markets Unlocked) programmes.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.5 | Ensure co-ordination of markets across the whole electricity system | Locational data available for all providers of flexibility services to facilitate DSO awareness. Further consideration on how flexibility should be coordinated across ESO-DSO for contractual and procurement processes. | Q1 2023-24 | Delayed - External Reasons |  | Impacted by wider Ofgem / DESNZ work on Industry Asset Registers. SMP is actively involved in the discussions alongside DDT and Flexibility Market Development team. SMP took learning from the PoC work and in Q3 has delivered initial DNO reporting functionality that the Flexibility Market Development team will use in an adhoc manner (to share with DNOs to understand MPAN / balancing services pre-qualification risk of conflicts to inform Primacy Rules) and enhance over time. SMP was also central to the ESO response to Ofgem’s Flexibility Market Asset Registration (FMAR) consultation and is feeding into DESNZ’s AAR (Automatic Asset Registration), CAR (Central Asset Registration) and FMU (Flexibility Markets Unlocked) programmes. SMP is also central to a series of use cases within NESO’s DER Visibility project.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.5 | Ensure co-ordination of markets across the whole electricity system | Continue to identify and deliver changes to support market coordination. | Q4 2024-25 | Complete | Q4 2024-25 | We have taken an active role in the Open Networks programme this year, leading on several workstreams to drive coordination. Our Flexibility Strategy Call for Input was launched in May with a dedicated workstream on DSO coordination, with a follow up document addressing feedback in December 2024 called 'Enabling Demand Side Flexibility'. There has been significant progress within the Stackability working group, reachign agreement on stakcing design principles to be implemented in new service designs, and with concerns raised by DNO's on the ability to stack the services with distribution services have been addressed by this year's DFS design directly.
2 | Balancing and ancillary services market reform | D4.6.1 | Development of competitive approaches to procurement of stability. | Long-term procurement: Implement the findings of innovation project and build on learnings from pathfinders, develop the details of implementing enduring long term market based on the output from BP1. Short-term market: Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2023-24 | Complete | Q4 2023-24 | • On progressing the mid-term (Y-1) Stability Market, we have now opened an Invitation to Tender (ITT) for market participants who wish to bid for the first Mid-term (Y-1) Stability Market delivery year, commencing 1st October 2025. The EOI closed on 26th January 2024 where providers expressed an interest and received an invitation to tender. Feedback from the informal consultation on service design, contract terms and technical eligibility criteria which we ran alongside the EOI process has been taken on board for the final design of the Mid-term (Y-1) market. Market participants are now preparing technical and commercial submissions for the first delivery year. The deadline for submitting these is 26th April 2024, following which ESO will assess bids against both technical and commercial criteria. We held two further industry webinars on Monday 5th and Tuesday 6th February 2024 to walk through the most important information as part of the ITT stage and offer an opportunity for industry to ask questions. We have also held 121 calls with every provider who is participating in the ITT for the first time. • In parallel, we are reviewing Y-4 and D-1 markets and engaging the relevant teams in ESO to understand what will be required to deliver these markets, and in what timescales this can be achieved. We are working closely with the Centralised Strategic Network Planning team to ensure that new system studies through CSNP are aligned and co-ordinated with the Long-term (Y-4) Stability Market, so this can be signalled accordingly when a requirement emerges. In our 2024 Markets Roadmap, we also shared plans to explore an optional Short-term (D-1) Stability Market in advance of the full delivery of an automated D-1 auction. We will be engaging with industry further on this. Our delivery plans will be updated through the recently introduced Markets Roadmap monthly delivery plan updates.
2 | Balancing and ancillary services market reform | D4.6.1 | Development of competitive approaches to procurement of stability. | Continuous improvement of long-term market design based on industry feedback. Run procurement process, if required depending on the system needs, so that the market participants have sufficient time to make informed business decisions on possible solutions and bidding approach. Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project | Q4 2024-25 | Complete | Q4 2024-25 | • We have now awarded contracts for the first Mid-term (Y-1) Stability Market delivery year, commencing 1st October 2025. Five contracts have been awarded for 5GVA.s inertia, delivering estimated consumer savings of £47.3m in 12 months. We have also launched the Invitation to Tender for the second delivery year (2026/27) of the Y-1 market where we are seeking to procure 15GVA.s inertia. • In parallel, we are continuing to finalise the Y-4 and D-1 initial market design and beginning to engage the relevant teams in NESO to understand what will be required to deliver these markets, and in what timescales this can be achieved. We have recently identified system requirements for stability from 2029 onwards and are considering how these could be met using the Long-term (Y-4) Stability Market. Furthermore, we are undertaking some analysis to derive the expected value through a Short-term (D-1) Stability Market to ensure it can be appropriately prioritised by NESO in the roadmap for ancillary service and system developments. Further updates will be provided in our 2025 Markets Roadmap publication and further delivery updates will be provided through Markets Roadmap monthly delivery plans.
2 | Balancing and ancillary services market reform | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Long-term procurement: Implement the findings of innovation project and build on learnings from pathfinders, develop the details of implementing enduring long term market based on the output from BP1. Short-term market: Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2023-24 | Complete | Q4 2023-24 | Following the reprioritisation activity ahead of winter 22/23, work on a Reactive Power market was paused. This work is now being re-started with a new timeline and deliverables being planned. The next steps for developing reactive markets were identified through the work in 2023 which is to prioritise the implementation of long term market, and continue review the benefit and impact for mid and short term markets.
2 | Balancing and ancillary services market reform | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Continuous improvement of long-term market design based on industry feedback. Run procurement process, if required depending on the system needs, so that the market participants have sufficient time to make informed business decisions on possible solutions and bidding approach. Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2024-25 | Complete | Q4 2024-25 | The long-term market is the succession to Voltage Pathfinders and will now form part of the Reactive Power Market as part of the Network Services programme. NESO have completed the system studies and identified system needs for locational voltage services across Great Britain from 2029 onwards. NESO are currently considering it's strategy options for how to meet these needs, considering the long-term market as an option. Once this strategy work is complete, more information will be provided to the market. In addition to the long-term market, as of March 2025 NESO have now completed our market design work for the mid-term reactive power market, reviewing the outstanding market design questions with industry. NESO have decided to proceed with the implementation of the mid-term market as part of the overall Reactive Power Market. NESO are now working on the detailed requirements and criteria as part of this market prior to launching the market, and more information will be shared with industry in the near future. We have started an innovation funded project to review the current methodology of ORPS (Obligatory Reactive Power Service), which is used to calculate a fixed rate to pay the utilisation of reactive power as an obligatory service. The methodology hasn’t been reviewed since it was initiated hence might not fit for the need now and future. The output might also play an impact on the potential value of a short term reactive market if it proposes a change, so the daily market review will be continued after the conclusion of this innovation project expected in Aug 2025.
2 | Balancing and ancillary services market reform | D4.6.3 | Maximise participation in ancillary services | Exploring barriers to entry across the ESO ancillary services markets, identifying mitigating actions and working with industry to implement the changes needed to facilitate routes to market, and increase participation and liquidity of our markets | Q4 2024-25 | Complete | Q4 2024-25 | This project is identifying barriers to entry for renewable generators and Interconnectors for Frequency Response and Reserve markets. The objective is to identify opportunities to remove barriers so that assets can join these markets when conditions allow. A new project team has been set up to lead on this. External engagement has been completed. As of Q2, the draft project report is also completed. The report was published in December 2025.
2 | Balancing and ancillary services market reform | D4.6.4 | Local Constraints Market reform | Assess whether LCM should be rolled out across other zones. Assess whether other services should be rolled out on the 3rd party flexibility platform | Q4 2023-24 | Complete | Q4 2023-24 | Assessment of LCM continues following commencement in 2023. Fixes to enable the market to encourage all types of participant will be the focus in shorter term.
2 | Balancing and ancillary services market reform | D4.6.4 | Local Constraints Market reform | Assess whether LCM should be rolled out across other zones. Assess whether other services should be rolled out on the 3rd party flexibility platform | Q4 2024-25 | Complete | Q4 2024-25 | We have concluded our C16 consultation to allow aggregators to be compensated for dispatches. Awaiting an Ofgem decision early Q3 24/25
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Publish co-created guidance covering any rule changes and system and operational improvements, in collaboration with Ofgem, BEIS and industry, within 4 weeks of rules being set. | Q1 2023-24 | Complete | Q1 2023-24 | CM: > Guidance is being updated with: > specific focus on areas of feedback > a new section of “new for this year” to assist parties with understanding Rules changes. > slides requested by DESNZ to aid in policy conversations to ensure consistent messaging cross-party in response to emerging focus of questions. > EMR DB have published the Operational Plan and circulated to over 3,000 parties on 12 June 2023 > EMR customer events are scheduled to take place on 19 July (in-person) and 25th July (online) to launch this year’s CM process, with a focus on prequalification and rule changes. > The EMR DB team have been working to update the process for query management to achieve quicker SLAs, and undertaken cross training of team to enable more rounded advice. CfD: > The EMR DB published CfD guidance prior the application window opening for Allocation Round 5. The guidance included: > How customers should complete the application form if applying for a private network CfD agreement > How Floating Offshore Wind applicants should provide the supply chain plan > How Solar PV applicants should entered their Initial Installed Capacity Estimate. > Clear steps on how applicants could view their Allocation results (e.g. examples were added of how applicants can check for confirmation of an action in the system being completed). > Overall formatting of the guidance documents were updated to ensure there was a clear flow through of each section related to the CfD Allocation process. > Guidance changes were refined in consultation with Delivery Partners, DESNZ and Ofgem and draft guidance documents were reviewed by a select group of customers. > The EMR DB also engaged through: > An auction scenarios video distributed to customers shortly after the budget notice being for Allocation Round being published > The CfD Launch Event and the EMR DB led applicant readiness webinar in early 2023.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Commence the pre-qualification process, with customers benefitting from enhanced guidance | Q2 2023-24 | Complete | Q3 2023-24 | CM: Prequalification application window closed on 19 September. The team is busy providing support to Applicants, including responding to queries. During 7/8 September, the Portal was running very slowly - the DB identified the root cause, correct it and issued comms to stakeholders on 8 September.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Conclude the pre-qualification and disputes processes and prepare for the auctions | Q3 2023-24 | Complete | Q3 2023-24 | CfD: Ofgem upheld the DB's decision on all of the disputes submitted to them. We recognise however that Ofgem did not uphold the DB's position on every matter included in the disputes. CM: The Tier 1 disputes process finished on 28 November 2023. The Tier 2 process is currently happening, with a small number of disputes raised to Ofgem for decision.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Deliver the auctions and post-auction activities, including capturing key learning points with industry | Q4 2023-24 | Complete | Q4 2023-24 | CfD: The DB has successfully completed the Auction Round 5 auction process. AR5 results were released to industry on 8 September 2023 CM: On 20 February 2024, the EMR DB ran the T-1 Auction and on 27 February 2024, the EMR DB ran the T-4 Auction. The Auction Monitor Reports for both auctions have been published by DESNZ, confirming that the Auctions were run in accordance with the CM Rules and Regulations. Following the Auction processes, the EMR DB has had lessons learned sessions internally and with DESNZ.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Publish co-created guidance covering any rule changes and system and operational improvements, in collaboration with Ofgem, BEIS and industry, within 4 weeks of rules being laid. | Q1 2024-25 | Complete | Q2 2024-25 | CfD: The CfD team published updated guidance in advance of AR6 opening, reflective of feedback following AR5 and other improvements identified by the team. These including moving to a Word format and reducing a very long guidance document by nearly half to make it more accessible to users. CM: We made significant improvements to guidance this year, including development of a separate integrated guidance website which is easier to search and navigate, and videos to help users navigate the new Portal. Stakeholder feedback has been positive about the changes.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Commence the pre-qualification process, with customers benefitting from enhanced guidance | Q2 2024-25 | Complete | Q2 2024-25 | CfD: This milestone has been completed. CM: the prequalification window opened on 6 August and the team is currently supporting Applicants with queries and addressing any Portal issues that occur. As part of the new Portal launch, the team created a new Integrated Guidance website, which we have received positive feedback on compared to our previous guidance site.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Conclude the pre-qualification and disputes processes and prepare for the auctions | Q3 2024-25 | Complete | Q4 2024-25 | CfD: This milestone has been completed. CM: This milestone has been completed.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Deliver the auctions and post-auction activities, including capturing key learning points with industry | Q4 2024-25 | Complete | Q4 2023-24 | CfD: AR6 Allocation process has been successfully completed with notices issued to Applicants on 3 September 2024. We have been engaging closely with DESNZ and Ofgem to develop Framework improvements to address issues encountered during AR6. CfD: The DB has successfully completed the Auction Round 5 auction process. AR5 results were released to industry on 8 September 2023 CM: On 20 February 2024, the EMR DB ran the T-1 Auction and on 27 February 2024, the EMR DB ran the T-4 Auction. The Auction Monitor Reports for both auctions have been published by DESNZ, confirming that the Auctions were run in accordance with the CM Rules and Regulations.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Develop a clear process for capturing and assessing policy, rule and process improvements which draws on operational experience and industry feedback and feed this into CMAG and other relevant BEIS and Ofgem processes. | Q1 2023-24 | Complete | Q1 2023-24 | The EMR DB has developed and shared with Ofgem a process for how they will identify and undertake initial assessment of proposals and then progress them through CMAG. Further work is being undertaken internally to develop a standardised approach for impact assessments, based on experience with changes to date, which will then be discussed with delivery partners for their input.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Q2-4: Once established, we will run the improvement process on an ongoing basis, with key outputs timed to meet BEIS, Ofgem and CMAG timelines. | Q4 2023-24 | Complete | Q4 2023-24 | The DB has identified potential changes that could be made to the CM Rules to improve clarity, processes and operations. However, in many cases the changes require greater clarity around the original policy intent and whether that continues to be appropriate, and so the DB is now working closely with other delivery partners to review these areas in more detail, before they become detailed change proposals. Now that REMA consultation 2 proposes to retain CM as an Optimised CM, the EMR DB are working with DESNZ and Ofgem to understand how this will influence potential operational and policy changes.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Undertake informal review of the improvement process with industry, BEIS and Ofgem to identify ways to refine the approach. | Q1 2024-25 | Complete | Q1 2024-25 | The improvement process has been successful in identifying 'pain points' through review of customer queries, operational experience and review of the Rules. However, as identified above, this is now being further developed through a holistic process across all delivery partners.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Q2 - Q4: Implement process refinements and run refined improvement process from Q2 onwards | Q4 2024-25 | Complete | Q4 2023-24 | CfD: following the completion of AR6, we have been engaging with DESNZ on improvements to the framework in preparation for AR7. CM: We are working with DESNZ and Ofgem on developing wider strategic changes to support Clean Power 2030, and Deliver Partners and CMAG on operational improvements in advance of the next prequalification round opening.
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Production of 2023 ECR | Q1 2023-24 | Complete | Q1 2023-24 | Report submitted to the Department of Energy Security and Net Zero on 31 May 2023.
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Develop further enhancements to security of supply modelling to support the transition to net zero (e.g. impact of weather, limited-duration technologies, DSR, and European modelling) | Q4 2023-24 | Complete | Q4 2023-24 | This milestone represents a well-established annual cycle of work. This year's projects are now complete and will be reported in the 2024 Electricity Capacity Report in line with the well-established process.
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Production of 2024 ECR | Q1 2024-25 | Complete | Q1 2024-25 | Report submitted to DESNZ on 31 May 2024
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Develop further enhancements to security of supply modelling to support the transition to net zero (e.g. impact of weather, limited-duration technologies, DSR, and European modelling) | Q4 2024-25 | Complete | Q4 2024-25 | This milestone represents a well-established annual cycle of work. We will report on the modelling improvements undertaken this year in the 2025 Electricity Capacity Report.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements following first study published in 2022 | Q1 2023-24 | Complete | Q1 2023-24 | We published our first 2035 resource adequacy study in December 2022 in collaboration with AFRY. We have since invited input and feedback from expert stakeholders via in-person / virtual round tables and bilateral discussions. We are now on track to set out our next steps for these studies and how feedback has informed this. This will be published on our Resource Adequacy website.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements following first study published in 2022 | Q4 2023-24 | Complete | Q4 2023-24 | We are committed to engaging with stakeholders in this work. We have already offered opportunity for stakeholders to provide input following the first study. We published an update in July 2023 and have set up an expert group to work with us on this. This represents continuous engagement activity.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Production of capacity adequacy study | Q1 2024-25 | Delayed - External Reasons |  | In BP2 we set out a milestone to deliver this by summer 2024. We then built a new internal team and reviewed this, in light of stakeholder feedback and delayed this until autumn 2024. This was delayed further due to our work on CP30 as we had to divert resource away from this to CP30. We also wanted clarity on the outcome of CP30 as an input for this study to ensure consistency. Following the publication of the Government's Clean Power Action Plan, we have now been able to progress with the modelling for this study. We now expect to publish this study in late spring / summer 2025, shortly after the end of the BP2 period. As CP30 has contributed the largest delay, we have flagged this as delayed - external reasons now. We consider the impact is negligible because (a) CP30 has helped accelerate deployment of new resources supported by support for a new CCUS power station and LDES Cap and Floor; (b) as we are intending to publish shortly after the BP2 period now, the delay of a few months has little impact on time horizons 10 – 15 years from now.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements | Q4 2024-25 | Complete | Q4 2024-25 | We are committed to engaging with stakeholders in this work. This milestone represents continuous activity. We have continued to engage with our expert stakeholder group on our modelling. We have also published 2 spotlights on our website in spring / summer 2024 that explore assumptions on demand-side response and adequacy metrics. A third spotlight was finalised in March 2025 setting out how we undertake our modelling ahead.
2 | Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of nationally driven regulatory change through the open governance process. | Other code changes identified by the ESO or raised by 3rd parties and RCRC | Q4 2023-24 | Complete | Q4 2023-24 | We have started analysing the refreshed RCRC data and plan to produce a recommendation in 2024. Grid Code: GC0117 - CBA is complete and in our view is positive for consumers. The workgroup vote is taking place in january. Expect to meet 2027 implementation timeframe CM088 - the STC modification that followed on from GC0141 (9th August Power Disruption) has now been approved. Completing all the post 9th August changes that were requested. CMP330/374/CM079 Contestable connections – sent to authority in Q3 2023 awaiting Ofgem decision Winter 2023/24 programme of work delivered to ensure appropriate changes are in place across the codes and frameworks where necessary (eg GC161) GC161 and GC162 have now been implemented. CUSC mods CMP413 - we continue to work proactively the workgroup to develop a solution and the WACMs that have been raised. CMP392 - this is currently with Ofgem for a decision. CMP376(Queue Management) – WACM7 has been approved and has been implemented. CMP330/374/414 (connection competition) – no change as awaiting Ofgem decision. Following stakeholder engagement the ESO identified a way to progress the change more quickly and has reflected this in its consultation response. CMP425 – we worked collaboratively with the workgroup and proposer to support developing a solution under urgent timescales and this is on track to be submitted to Ofgem at the time of writing. We have presented on an issue related to zoning at TCMF, and this has been raised as a formal CUSC modification (CMP419) and has started workgroups. A number of modifications have been raised in the past quarter and we continue to support development of these through the workgroup process.
2 | Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of nationally driven regulatory change through the open governance process. | Progress further code modification proposals as required in addition to wider programme projects | Q4 2024-25 | Complete | Q4 2024-25 | There are number of live code modification in flight, with a number of new Modifications expected through the year.
2 | Code management / market development and change | D6.1.1 | Enable major net zero programmes - Offshore Coordination | Delivery of code modifications associated with implementation of the offshore project dependent on progression of offshore coordination programme | Q4 2023-24 | Delayed - External Reasons |  | Throughout BP2, the code change process has progressed modifications to aid the wider offshore coordination programme, with further code modification work planned in BP3 and beyond: The Sub-group to support the Electricity System Operator (ESO, now NESO) in developing changes to the Transmission Network Use of System (TNUoS) charging methodology in relation to the OTNR was launched early 2023 and has now concluded. The overall focus of the group was to consider, discuss and provide input into developing the charging principles and subsequent methodology changes to support NESO in creating a set of code modifications to facilitate offshore coordination. There are 4 live modifications currently in the formal governance process, and this action will be closed once they concluded and the Authority has made their decision. CMP402, CMP419, CMP426 - currently at workgroup stage. CMP411 - approved by Ofgem and will be implemented at the end of BP2. In terms of the technical Codes, NESO is running approximately monthly meetings with stakeholders to explore potential Code changes required for the Holistic Network Design (HND) for offshore wind. The Technical Code Change team is also supporting the work of Ofgem and DESNZ on Offshore Hybrid Assets (OHA).
2 | Code management / market development and change | D6.1.2 | Enable major net zero programmes - Onshore Competition | Delivery of code modifications associated with implementation of onshore competition dependent on progression of onshore competition | Q4 2023-24 | Complete | Q4 2024-25 | CATO modifications are in flight and at an advanced stage. These modifications introduce the concept of Competitively Appointed Transmission Owners (CATOs) for the purposes of introducing Early Competition for the design, build and ownership of Onshore Transmission assets. Early competition CATO legislation was approved by Parliament in Autumn 2023 (which was initially threatening to cause delays to this deliverable). The intention is to bring all CATO mods to Ofgem for them to review in Q4 2024 (Grid Code, CUSC, STC, STCP and SQSS CATO mods). The Final Modification Reports (FMR) have been submitted to Ofgem for STC mods (CM086 and CM087), CUSC mods (CMP403 and CMP404) and SQSS (GSR031). The FMR for Grid Code mod GC0159 was submitted to Ofgem on 31/12/24.
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Delivery of code modifications to set equipment specifications | Q1 2023-24 | Complete | Q1 2023-24 | ESRS Modifications have now all been approved and are in the process of being implemented, this was complete by Q4 23/24 so behind schedule due to process taking slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - approved and being implemented STC modification - CM089 - CM089 : approved and being implemented.
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Completion of code changes | Q2 2023-24 | Complete | Q2 2023-24 | ESRS Modifications have now all been approved and are in the process of being implemented, this was complete by Q4 23/24 so behind schedule due to process taking slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - approved and being implemented STC modification - CM089 - CM089 : approved and being implemented.
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Code changes implemented for ESRS to facilitate licence compliance which is required by Dec 2026 | Q4 2024-25 | Complete | Q4 2023-24 | ESRS Modifications have now all been approved and are in the process of being implemented, this was complete by Q4 23/24 so behind schedule due to process taking slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - approved and being implemented STC modification - CM089 - CM089 : approved and being implemented.
2 | Code management / market development and change | D6.1.4 | Enable zero carbon operation - Stability | GC0137 'Grid Forming' Grid Code modification - guidance document delivery | Q1 2023-24 | Complete | Q1 2023-24 | The Grid Forming best practice guide is now on the ESO website.
2 | Code management / market development and change | D6.1.5 | Lead charging reform | Raise TNUoS modifications to facilitate charging reform | Q1 2024-25 | Complete | Q1 2024-25 | TNUoS Taskforce is currently working through a number of sub groups regarding identified issues. The 'sub groups' are now in the process of clearly articulating the defects and creating solutions. To date 2 Modifications have been raised with a further one to be raised in Q1 2024. It is expected that a number of further Modifications will follow throughout 2024. Scaling Factors was presented at the Taskforce and has now been raised as a formal CUSC modification (CMP424) which started workgroup in January 2024. Generation reference nodes has also been raised as a formal modification following development by the Taskforce, raised by SSE (CMP423). In addition CMP413, raised by EDF is progressing through workgroups and ESO are fully engaged in this process. The TNUoS 10year projection has also been developed alongside this modification to aid industry in making investment decisions. This was an extra piece of work that the ESO have done on top of the obligations within the CUSC.
2 | Code management / market development and change | D6.1.5 | Lead charging reform | Identify required code changes | Q4 2023-24 | Complete | Q4 2023-24 | This action is complete but a resulting CUSC modification is still in flight. CMP408 (amending the notice period) is awaiting a decision from Ofgem alongside CMP415 which looks at the fixed period following the analysis carried out through the CMP408 workgroup and the Enduring Fixed BSUoS subgroup. This sub-group is now on pause as it was agreed to wait for a decision on the aforementioned modifications and collect further data before raising any more modifications. This sub-group has received really positive feedback for the discussion it provided across industry, and the analysis that was shared. CMP420 was raised by industry and we are working with the workgroup to support the proposer developing a solution.
2 | Code management / market development and change | D6.1.6 | Support Market Wide Half Hourly Settlement | Code modifications concluded | Q1 2024-25 | Delayed - External Reasons |  | A revised MHHS Programme plan with associated milestones was approved by Ofgem following extensive industry consultation in 2023. This determined that code changes would be implemented in March 2025. On 20 September 2024, the MHHS Programme issued a proposed revision to the MHHS Programme Plan which will move industry milestones out by 5 months. Ofgem approved these changes to the industry plan under 'Change Request 55' which now means that industry code changes will be implemented in September 2025. Ofgem have confirmed that CUSC Modifications should be managed outside the scope of the MHHS Programme and Settlement Reform SCR. CUSC Modification CMP430 was approved by Ofgem in September 2024 with implementation in April 2025. This will make changes to TNUoS demand charging to support MHHS Implementation. It was raised by the ESO in February and progressed to an Urgent timetable to ensure any CUSC changes were made to accommodate the start of MHHS migration. ESO has fed back on code drafting under the BSC that impacts on ESO processes as part of the MHHS code drafting consultation process. All BSC drafting has been agreed under MHHS governance and Ofgem has raised the suite of Authority-led SCR Modifications to give effect to the MHHS design. These Modifications will progress in line with current MHHS industry milestones.
2 | Code management / market development and change | D6.1.6 | Support Market Wide Half Hourly Settlement | Produce required CUSC legal text and modifications raised | Q2 2023-24 | Complete | Q2 2024-25 | A revised MHHS Programme plan with associated milestones was approved by Ofgem following extensive industry consultation in 2023. CUSC Modifications have been progressed in line with the Ofgem approved MHHS Programme plan. Ofgem have confirmed that CUSC Modifications should be managed outside the scope of the MHHS Programme and Settlement Reform SCR. CUSC Modification CMP430 was raised in February and was progressed to an Urgent timeline to ensure Ofgem are able to make a decision by September 2024 for implementation in April 2025. Proposed CUSC legal text was produced and submitted to Ofgem for their decision as part of the Final Modification report at the end of August 2024.
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Regulatory priorities, system maintenance and functional backlog implemented | Q1 2023-24 | Complete | Q1 2023-24 | 22/6: Q1 regular system maintenance and backlog management in place
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Enduring team established to maintain new system (Q2), System maintenance and backlog management (Q3), Regulatory priorities and customer improvements implemented (Q4) | Q4 2023-24 | Complete | Q4 2023-24 | 22/3: BAU team established, Q4 regular system maintenance and backlog management in place, regulatory changes and enhancements implemented
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | System maintenance, regulatory priorities, customer enhancements and functional backlog management | Q1 2024-25 | Complete | Q1 2024-25 | 20/06 - The STAR business as usual team is set up to perform regular system maintenance activities. The STAR project teams works with relevant teams across ESO to track emerging regulatory changes and customer feedback alongside prioritising its functional backlog. Reprioritisation and review of the Roadmap and this backlog occurs on a regular basis.
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | System maintenance, regulatory priorities, customer enhancements and functional backlog management | Q2 2024-25 | Complete | Q2 2024-25 | 18/07 - The STAR business as usual team is set up to perform regular system maintenance activities. The STAR project teams works with relevant teams across ESO to track emerging regulatory changes and customer feedback alongside prioritising its functional backlog. Reprioritisation and review of the Roadmap and this backlog occurs on a regular basis.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | High Level Discovery | Q2 2023-24 | Complete | Q2 2023-24 | Impact Assessment completed for Market-wide Half Hourly Settlement (MHHS) changes required to the data file (TUoS Report or P0210) provided from Elexon to the ESO for TNUoS and BSUoS forecasting and billing.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Impact Assessment & Agree Approach | Q3 2023-24 | Complete | Q2 2024-25 | Approach to receipt of data for TNUoS Charging agreed under the sign-off of MHHS Change Request 32. Approach and timing of testing for this to be agreed between MHHS Programme, Elexon and ESO. Approach to process for management of disputes relating to BOAs agreed and solution will be reflected in MHHS BSC Legal Text. Impact Assessment for direct impacts of MHHS has been baselined. All ESO development work has been completed in line with the latest baselined MHHS Programme plan.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and implement | Q4 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q1 2024-25 | Delayed - External Reasons |  | On 20 September 2024, the MHHS Programme issued a proposed revision to the MHHS Programme Plan due to delays experienced with industry testing. Ofgem has approved the delay and a revised industry timeline has been baselined. NESO has carried out all activity necessary (design, code change) to achieve the original milestones. NESO is continuing to work with the MHHS Programme and Elexon under MHHS governance to support all required testing as and when scheduled, as per any revised timeline. Due to the approved delay, delivery will be pushed beyond BP2.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q2 2024-25 | Delayed - External Reasons |  | On 20 September 2024, the MHHS Programme issued a proposed revision to the MHHS Programme Plan due to delays experienced with industry testing. Ofgem has approved the delay and a revised industry timeline has been baselined. NESO has carried out all activity necessary (design, code change) to achieve the original milestones. NESO is continuing to work with the MHHS Programme and Elexon under MHHS governance to support all required testing as and when scheduled, as per any revised timeline. Due to the approved delay, delivery will be pushed beyond BP2.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q3 2024-25 | Delayed - External Reasons |  | On 20 September 2024, the MHHS Programme issued a proposed revision to the MHHS Programme Plan due to delays experienced with industry testing. Ofgem has approved the delay and a revised industry timeline has been baselined. NESO has carried out all activity necessary (design, code change) to achieve the original milestones. NESO is continuing to work with the MHHS Programme and Elexon under MHHS governance to support all required testing as and when scheduled, as per any revised timeline. Due to the approved delay, delivery will be pushed beyond BP2.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q4 2024-25 | Delayed - External Reasons |  | On 20 September 2024, the MHHS Programme issued a proposed revision to the MHHS Programme Plan due to delays experienced with industry testing. This proposes to delay the delivery of the industry-wide timeline by six months. This change request is currently with Ofgem who will need to provide their approval in order for the new timeline to be baselined. NESO has carried out all activity necessary (design, code change) to achieve the original milestones. NESO is continuing to work with the MHHS Programme and Elexon under MHHS governance to support all required testing as and when scheduled, as per any revised timeline. Due to the proposed delay, delivery may be pushed beyond BP2.
2 | Industry revenue management | D6.3.2 | TNUoS reform | High Level Discovery | Q1 2023-24 | Delayed - External Reasons |  | ESO Revenue team has shortlisted defects (considered by Task Force) for review, and have allocated these to categories (to progress as packages of work), we are aiming to create a workstream plan using the categories. The general delay against the business plan, is related to the complexity and volume of work contained within the Task Force, there is still on going analysis to determine if there are any further modifications that need to be raised to achieve the TNOUS Task Force objectives, until all modifications have been raised and significantly progressed through the code governance process, the ESO can not confidently conduct technical system discovery work to progress to plan.
2 | Industry revenue management | D6.3.2 | TNUoS reform | Impact Assessment & Agree Approach | Q2 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone High level Discovery (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q3 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q4 2023-24 | Delayed - External Reasons |  | On 20 September 2024, the MHHS Programme issued a proposed revision to the MHHS Programme Plan due to delays experienced with industry testing. Ofgem has approved the delay and a revised industry timeline has been baselined. NESO has carried out all activity necessary (design, code change) to achieve the original milestones. NESO is continuing to work with the MHHS Programme and Elexon under MHHS governance to support all required testing as and when scheduled, as per any revised timeline. Due to the approved delay, delivery will be pushed beyond BP2.
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q1 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q2 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q3 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q4 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in the overall delivery of this objective).
2 | Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | We are working on our internal capability to ensure we set ourselves up best to be a code manager. This includes: • Working on Code Digitalisation to improve the usability and navigation of our codes • Further proactive engagement with industry parties proposing changes to the codes we administer, seeking to ensure these are clear and value adding / raised at the optimum time" • Further enhancing our chairing and project management capability to ensure we maximise the value of all our stakeholder engagements notably at modification Workgroups and code Panels • Continuous improvements to our reporting, ensuring this is clear and understandable | Q4 2023-24 | Delayed - External Reasons |  | march 25 - we have recently responded to a consultation on the selection process of the Code Manager and are awaiting further feedback from Ofgem on the next steps. The consultation to discuss feedback on the content of the Strategic Direction Statement is also currently underway and will be submitted in March. We are supportive of the SDS providing guidance on prioritisation of modifications and projects of work however we have some reservations about how the prioritisation will be graded and scored to be able to monitor effectively. We have begun a programme to design a process for the ESO to fulfil the role of code manager. We have presented to OFGEM on our thoughts and ideas around the code manager process and how we feel we could facilitate this change. This includes - strategic road map of ideas and process flow -presentation to OFGEM -feedback requested on our thoughts, ideas and process -overlaying our new process with some previous modifications to demonstrate the difference that would have been made if followed -presentation to CUSC and GC panel on our thoughts and ideas of code manager -Specific relevant training courses for the team provided by external facilitators - Further embedding on the job training and internal processes - Breakdown of the current code and team process and review areas for further improvement - Customer and Stakeholder engagement and feedback to further improve communication. We await further guidance from Ofgem.
2 | Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | We are working on our internal capability to ensure we set ourselves up best to be a code manager. This includes: • Working on Code Digitalisation to improve the usability and navigation of our codes • Further proactive engagement with industry parties proposing changes to the codes we administer, seeking to ensure these are clear and value adding / raised at the optimum time" • Further enhancing our chairing and project management capability to ensure we maximise the value of all our stakeholder engagements notably at modification Workgroups and code Panels • Continuous improvements to our reporting, ensuring this is clear and understandable | Q4 2024-25 | Delayed - External Reasons |  | march 25 - we have recently responded to a consultation on the selection process of the Code Manager and are awaiting further feedback from Ofgem on the next steps. The consultation to discuss feedback on the content of the Strategic Direction Statement is also currently underway and will be submitted in March. We are supportive of the SDS providing guidance on prioritisation of modifications and projects of work however we have some reservations about how the prioritisation will be graded and scored to be able to monitor effectively. we have responded to two consultations led by Ofgem discussing the transition from code administrator to code manager and energy code reform. We have views on code consolidation and what the process would mean to be a code manager and have responded accordingly. we await further feedback from Ofgem on the next steps with our engagement around our thoughts and ideas on this subject.
2 | Work with all stakeholders to create a fully digitalised Whole System Technical Code by 2025 | D6.5 | Develop a single technical code for distribution and transmission that is focused on providing minimum standards to allow safe and secure operation of the electricity systems. | Prioritise and raise modifications as identified through example work | Q4 2023-24 | Complete | Q4 2023-24 | Grid code modification focused on the the simplification and rationalisation of section OC2 of the grid code has been submitted and is a live modification. The digitalisation side of the project is currently progressing to plan.
2 | Work with all stakeholders to create a fully digitalised Whole System Technical Code by 2025 | D6.5 | Develop a single technical code for distribution and transmission that is focused on providing minimum standards to allow safe and secure operation of the electricity systems. | Progress modifications | Q4 2024-25 | Complete | Q4 2024-25 | Following extensive engagement with stakeholders, a clear scope for the Grid Code (GC) simplification and rationalisation project was defined. A workstream (Alignment, Simplification & Rationalisation or ASR) commenced in December 2022. GC0164 (Simplification of Operating Code No.2) was proposed in October 2023. Since inception work has included 12 Workgroup meetings, 2 Industry surveys, 70 bilateral stakeholder sessions, 19 ASR workstream meetings and 25 dWSTC Steering Group meetings – noting that OC2 is approximately 2% of the GC. This exercise has led to the conclusion that rationalisation of technical sections (which form the majority of the GC) will be difficult to deliver using open governance and voluntary Industry resource. The Workgroup Consultation ran in June 2024 and received 3 responses. The Code Administration Consultation (CAC) closed in January 2025. The Mod is going back to Workgroup to consider some of the comments on the legal text from the CAC prior to Panel’s decision and implementation. GC0179 (Rationalising Balancing Code No.4 (BC4) and Balancing Code No.5 (BC5)) was submitted to the GC Administrator in March 2025. The dWSTC Steering Group, which provides strategic direction to this project on behalf of Industry, has proposed that further code simplification and rationalisation work could be embedded within business as usual (BAU) code modification work, except for the sections which require expert input. These could be handed over to the Code Manager programme proposed by the Energy Code Reform (ECR) work. NESO believes that, due to issues outlined above, further work beyond GC0164 and GC0179 should be handed over to the Code Manager programme. The GC0164 Workgroup has attempted to quantify the industry resources required to implement this type of change and a summary of its findings can be provided to the ECR team as part of a report on the lessons and findings on what further and wider code simplification work could entail.
2 | Fixed BSUoS tariff setting | D6.7 | Enhanced delivery of the recommendation from the BSUoS taskforce around reducing the volatility of BSUoS forecasting. | Continued investment in our forecasting capability and build on our existing capability for BSUoS forecasting. | Q4 2024-25 | Complete | Q4 2024-25 | Following on from the work that we did in 2023 with the Hartree Centre, to investigate whether state-of-the-art machine learning techniques could be employed to improve our forecast of balancing costs, we implemented the prophet model into the BSUoS forecasting system last April. We ran a webinar on the 17th April 2024 to present the changes and this was well attended and well received by a range of industry parties. We received positive feedback on both the changes being made and the webinar. Since those updates the only notable change has been to the way that we forecast the chargeable volume where we have extended the data set used to enable us to better map the relationship between national demand and BSUoS chargeable demand. We have analysed risks and opportunities with the current forecast model and work is underway to further automate the process to reduce the potential for manual errors when producing forecasts.
2 | Digitalisation of codes | D6.8 | Implementation of digital solutions | Implementation has commenced | Q4 2023-24 | Complete | Q4 2023-24 | March 25 - we are currently drafting a sanction request for further funding of the next phase of the internal workflow process (R5). Release 4 happened in February 2025 where we saw the release of the digital proposal form. Implementation of the digital code has commended and is up and running. There will be further enhancements to the system and further phased releases. Digital code is functioning and live and in use by internal and external users. There were slight delays to the project due to the project experiencing several challenges with correctly provisioning suitable testing environments within our chosen technology stack, Azure 2.0. To ensure that this con be resolved effectively we are therefore moving our go-live date to no later than 15th May 2024. Whilst these issues are being resolved we continue to work on Phase 2 of the project, including GenAI and Workflow management which in turn should help with the time delays in completing this early. The Digital Code management (DCM) project delivers the ESO the technology capability to make industry codes accessible and consumable for customers. It will transform customer experience for the code management process through: - Digitalisation of codes - Contextual guidance and relevance for customers - Provision of enhanced navigation capabilities - Greater clarity on relevant sections using metadata tagging, document and workflow management tools Project Progress to date: - Project setup/stakeholder engagement - Scoping - Industry Engagement & User Research - Requirement definition - Conceptual Solution Design
2 | Digitalisation of codes | D6.8 | Implementation of digital solutions | Implementation is complete | Q4 2024-25 | Delayed - Internal Reasons |  | March 25 - we are currently drafting a sanction request for further funding of the next phase of the internal workflow process (R5). Release 4 happened in February 2025 where we saw the release of the digital proposal form. MVP stage live as planned on the 15th May. now in the development phase of further enhancement releases. There are slight delays to the project due to the project experiencing several challenges with correctly provisioning suitable testing environments within our chosen technology stack, Azure 2.0. To ensure that this can be resolved effectively we are therefore moving our go-live date to no later than 15th May 2024. Whilst these issues are being resolved we continue to work on Phase 2 of the project, including GenAI and Workflow management which in turn should help with the time delays in completing this early. The Digital Code management (DCM) project delivers the ESO the technology capability to make industry codes accessible and consumable for customers. It will transform customer experience for the code management process through: - Digitalisation of codes -internal workflow for internal procedures and code updates to mitigate compliance risks - Contextual guidance and relevance for customers - Provision of enhanced navigation capabilities - Greater clarity on relevant sections using metadata tagging, document and workflow management tools Project Progress to date: - Project setup/stakeholder engagement - Scoping - Industry Engagement & User Research - Requirement definition - Conceptual Solution Design
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Full assessment delivery areas | Q2 2024-25 | Complete | Q4 2024-25 | Initial areas for assessment identified and early plans developed. We are seeking to align this work with key strategic industry objectives to drive most value from this process. Some areas of assessment are already being progressed based on alignment with other key priorities as part of BP2 e.g. DER Visibility and MHHS. Work in these areas are driven by individual separate project/programme timelines and have been prioritised accordingly.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Establish team to deliver assessment of frameworks | Q3 2023-24 | Complete | Q3 2023-24 | Team members started Nov-23 with one remaining vacancy to be filled in Q4 23-34 in line with resource requirements.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Detailed workplan and stakeholder engagement | Q4 2023-24 | Complete | Q4 2024-25 | Whilst we have established the Whole System Framework Team, the onboarding process took slightly longer than expected resulting in a delay to creating the detailed workplan and stakeholder engagement activities. Potential areas for assessment and inclusion in the team workplan have been identified and some high level information was shared at the Markets Forum in May. Further delays to more detailed stakeholder engagement activity has been caused by resource working on other urgent priorities under BP2. Work has already been delivered on some of the areas that will be set out in the detailed workplan, based on priorities in other areas of BP2.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Identify and raise or recommend changes | Q4 2024-25 | Complete | Q4 2024-25 | The team has successfully identified and recommended changes to the framework in several key strategic projects including Distributed Energy Resources (DER) visibility, Market suspension and restoration, and Notification for Demand Change projects. Ongoing assessment of framework areas will feed into the process for identifying and recommending changes, but this needs to consider (from a timing and content perspective) other key strategic industry activities, such as Energy Code Reform, Low Carbon Flexibility Road Map.
2 | Net zero market reform programme | D20.1 | Net Zero Market Reform programme | Be a trusted Partner to BEIS, Ofgem and the wider industry in this space. Ensuring the right market reforms to achieve net zero efficiently is a hugely complex challenge, with many interdependencies and a raft of future uncertainties. | Q4 2024-25 | Complete | Q4 2024-25 | We continue to be a trusted partner to DESNZ and Ofgem in the REMA process. We have undertaken two phases of analysis into dispatch, delivering a case for change and subsequently identifying and modelling the benefits of different packages of dispatch and wholesale market design. We engaged industry on both phases, including on the modelling methodology in phase 2. We presented our findings to the REMA Programme and DESNZ are minded to rule out any move to centralised dispatch. We continue to deliver analysis to the REMA Programme on how dispatch and balancing would work under a zonal and an enhanced national market package. We are also working alongside DESNZ and Ofgem on various aspects of zonal market design, including various new roles and responsibilities, as well as an implementation plan for zonal and enhanced national. We continue to support DESNZ in their analysis on reforms to the CFD and the CM.
2 | Setting the net zero cross border landscape | D21.1 | Cross-border strategy development | First phase of implementation fully initiated | Q2 2023-24 | Complete | Q2 2023-24 | By modelling the cross border conditions for a number of future scenarios, ESO better understands how the needs of the GB net zero power system can be supported by interconnection, which is expected to significantly increase in capacity. This analysis identified future risks and opportunities that create value specifically in term of adequacy, operability and system adequacy. These areas of work have been prioritised so the highest value items can be focused upon. The output includes the identification of further research and development work packages needed to further define the final solutions to implement. A final draft for comment was shared with Ofgem and DESNZ in September 2023.
2 | Setting the net zero cross border landscape | D21.1 | Cross-border strategy development | Conclusions and recommendations reviewed to check if they are still relevant | Q4 2024-25 | Complete | Q4 2024-25 | A final draft of the report has been produced that covers NESO activities that aims to optimise interconnection in the areas of flexibility, adequacy and operability. The last step is final, internal sign off which is imminent. From the cross-border strategy work, NESO have been able to strategically focus on the identified key areas for improvement and the steps required to achieve these improvements. NESO plans to share this with Ofgem later in 2025.
2 | Setting the net zero cross border landscape | D21.1.1 | Strategic Engagement with EU | UK/ EU TSO cooperation channels will be fully opened and functioning well | Q1 2023-24 | Complete | Q4 2024-25 | The Trade and Cooperation Agreement Working Arrangements have been approved in November 2024 by the EC and DESNZ via the Specialised Committee for Energy. The SCE have asked for implementation to be completed by ENTSO-E and UK TSOs – which is currently being completed. The Working Arrangements agreement allows formal re-engagement between GB TSOs and the EU TSOs. However, in the interim informal engagement is underway with ENTSO-E and EU TSOs in a number of key areas including North Sea Cooperation (inc Offshore and MPIs), interconnector ramping limits, operational harmonisation and IC flow control tools.
2 | Setting the net zero cross border landscape | D21.1.1 | Strategic Engagement with EU | Engagement established with new EU stakeholder groups | Q1 2024-25 | Complete | Q1 2024-25 | Outside ENTSO-E channels, EU engagement and cooperation channels have been established with a range of EU organisations such as CORESO and the Renewable Grid Initiative. Bilateral channels have been developed with interconnected TSOs such as EirGrid, Statnett, RTE, TenneT and 50 Hertz. ESO has also commenced active support for the North Sea Energy Cooperation via support for the Ostend Declaration works. Prior to formal approval is given for the TCA Working Arrangements, pre-emptive EU/ GB engagement has been undertaken by ESO via a number of ENTSO-E groups including Inter Synchronous Area sub group (GB - EU operational interactions) and the Regional Group North Sea (Offshore and onshore Network planning).
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Draft Interconnector Framework shared with industry | Q1 2023-24 | Complete | Q4 2024-25 | The ESO has released an RFI on interconnector frameworks. External engagement will take place ahead of industry consultation. This was re-prioritised to allow other work within the team take place earlier this year such as NTC and DFS derogation. NESO has shared the forward plans for the interconnector framework with industry via JESG in December 2024. These were consulted upon during January and February of 2025. NESO interconnector homepage successfully launched 4th march 2025. Re-purposed JSEG to develop policy positions, gone out to consultation to agree ToR and identify key topics to be brought for discussion, enabling better engagement with stakeholders. Consultation closing on 14th March with a number of positive responses already received.
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Ramping solution is SOGL compliant | Q2 2023-24 | Complete | Q4 2023-24 | The ESO has been working with an external consultant (Baringa) to carry out a CBA for interconnector ramping. This CBA has helped shape the ESO recommendation, which is to reduce interconnector ramp rates from 100MW/Min to 50MW/Min. This recommendation has been presented to the workgroup. The workgroup will propose an alternative. Process steps outlined below. Delay to original timeline is due to interconnector requests for other areas to be considered. Workgroup consultation July 2023 Workgroup report September 2023 Code Administrator Consultation October 2023 Modification Report December 2023. Report to be issued to Ofgem Dec 23- await a decision from Ofgem. Decision date to be confirmed and will update ticket to reflect this. Work group work is complete as it stands. Estimated decision date is 3rd March 2024> Decision date 15th March- Ofgem advised to implement 100MW/min - WACGM1. ESO is SOGL compliant
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Interconnector framework consulted upon | Q3 2023-24 | Complete | Q3 2023-24 | Interconnector Framework RFI is now out, closing 7th December. Reviewing responses and carrying out workshops internally and externally to develop scope
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Long-term ramping solutions are investigated | Q4 2023-24 | Delayed - Internal Reasons |  | To take account of feedback from Ofgem’s GC0154 decision letter, the Ramping task force took time to understand ramping issues with different technologies and evidence that there are operational issues with current ramp rates, particularly with new technologies and DER. The task force has held eight internal meetings since June 2024, one internal in-person workshop in October 2024, resulting in engagement with over 40 NESO internal colleagues to define security of supply challenges posed by ramping. External engagement has been held with ISA (the Inter Synchronous Area), TOs and the Wind Advisory Group. The task force has identified some interim measures that could be pursued, but an enduring solution will require detailed, technical studies to support any potential future Code Mod. There is no evidence of the required ramp rates for different (including new) technologies under various system conditions; a study would be needed to determine and evidence the required ramp rates for each technology. We’re taking the findings from the task force through internal governance and engaging with Ofgem, before developing the detailed specification of such studies. Task force will engage with Ofgem in Q2 2025 to share interim and long-term proposed solutions. The delay in delivery of this milestone is due to groundwork being undertaken, to better inform studies required to support the development of enduring solutions. In terms of investigating long-term ramping solutions – if there is agreement to proceed with studies, internal or external resources will need to be identified and procured. Ideally, studies could be underway within a year from internal agreement to proceed. Having supporting evidence for any future Code Mod on ramp rates is likely to result in a more efficient Code change (should one be required). A proposed Code Mod on ramp rates is likely to be based on customer savings due to reduced balancing actions required to manage current ramp rates.
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Interconnector Framework implementation plan agreed Long-term ramping solution implementation started | Q4 2024-25 | Complete | Q4 2024-25 | For Interconnector Framework implementation - see "Draft Interconnector Framework shared with industry". Following the GC154 workgroup we will continue to work with the interconnector owners and EU TSOs to identify longer term arrangements as well as investigating improvements to Ramping across the GB network. An internal ramping task-force has been evidence gathering and assessing ramping issues by technology type. The taskforce is recommending a number of next steps. These will be shared at the relevant internal governance forums in Q1 2025. Connected EU TSOs can be engaged with via the ISA EU harmonisation group.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Agreed UK Position on Day ahead, actively negotiating with EU TSOs Agreed Interim solution to cross border balancing at UK and EU level. Increased amount of engagement with EU TSOs | Q1 2023-24 | Delayed - External Reasons |  | Day Ahead Capacity Calculation (DACC) delayed due to limited engagement from EU TSOs on Capacity Calculation. EU TSOs likely to need a definitive steer from the Specialised Committee of Energy (SCE) in order to commit resources to DACC. The focus of the SCE steer during 2023 and 2024 was in relation to MRLVC (Multi Region Loose Volume Coupling), which is Day Ahead Capacity Allocation. The next round of work on MRLVC is a concept validation phase throughout 2025. MRLVC TCA project kicked off in January 2025 with steady progress being made across all four workstreams.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Draft UK Position on Intraday and Long Term. Continued development of Day Ahead arrangements | Q3 2023-24 | Delayed - External Reasons |  | Delayed due to prioritisation of Day Ahead timeframes over other timeframes (i.e. Intraday and Long Term) by UK and EU TSOs. No further work on the TCA has been directed by the SCE as of yet.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | UK position on enduring balancing options agreed with all relevant parties | Q4 2023-24 | Complete | Q4 2023-24 | Cost Benefit Analysis of CBB options completed. Agreed plan with DESNZ and Ofgem over summer 2023 for industry engagement to publish results. Held CBB industry webinar on 19th October 2023 to disseminate results, which was well attended. Finalising internal close-down reports on this activity.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Interim solution being implemented pending recommendation from the specialised committee on energy | Q1 2024-25 | Delayed - External Reasons |  | Interim Cross Border Balancing (CBB): CBA of CBB options showed low benefits for developing alternatives to TERRE / MARI. This was disseminated to industry following agreement between NESO, Ofgem, DESNZ that no further investigation was necessary. CBA reviewed in Q1 2025 - no change, as per previous position. Any CBB will need to be agreed as part of the TCA.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Noticeable step change in ESO to EU TSO relationships | Q2 2024-25 | Complete | Q2 2024-25 | Initiation of EU Harmonisation meetings (ISA or Inter-Synchronous Area) - monthly meetings alternately in-person and online, including Amsterdam in October 2023. Next planned in-person meeting in Brussels April 2024. These meetings provide a forum for ESO to raise issues of concern / interest from our side, and understand concerns and developments from connected EU TSOs. Feb 2024 ESO raised the issue of Grid Forming requirements on cross-border interconnectors; EU TSOs pleased that we raised this as an issue for mutual discussion. Bilateral meeting in Dublin between ESO and EirGrid in November 2023, following the UK-Ireland MOU on energy transition. Subsequent meeting took place online in March 2024. Recent EU-UK TSO cooperation on MRLVC (Multi Region Loose Volume Coupling) technical questions (Feb - June 2023). Awaiting further direction on MRLVC following Specialised Committee of Energy (SCE) meeting in November 2023. ESO representatives attended the 9th annual energy cross-border trading and balancing market forum in Berlin in Feb 2024.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Technical UK position agreed and negotiating with EU TSOs Enduring solution agreed at UK Level, ongoing negotiations with EU | Q4 2024-25 | Complete | Q4 2024-25 | Interim Cross Border Balancing (CBB): CBA of CBB options showed low benefits for developing alternatives to TERRE / MARI. This was disseminated to industry following agreement between NESO, Ofgem, DESNZ that no further investigation was necessary. CBA reviewed in Q1 2025 - no change, as per previous position. Any CBB will need to be agreed as part of the TCA.
2 | Enhancing cross border frameworks and markets | D21.2.3 | Enhancing interconnector operations and access to Great Britain markets | A review of existing interconnector operations in light of the transition to a highly interconnected system. Consider cross border roles within future GB ancillary services markets. | Q4 2024-25 | Complete | Q4 2024-25 | In October 2023, ESO ran an industry workshop looking at the results of a cost benefit analysis , completed by Compass Lexecon, for potential cross-border balancing solutions under a range of plausible future scenarios. In December 2024, NESO published the "Enabling Renewable and Interconnector participation in GB ancillary services" report, which examines the challenges for Interconnector market entry and how they can be solved as we move towards net zero operation.
3 | Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Undertake enhancements to ETYS Annual Report in response to stakeholder feedback. | Q1 2023-24 | Complete | Q1 2023-24 | The Annual ETYS consultation was completed on 15th May 2023 and we submitted the proposed Form of ETYS 2023 to Ofgem on 1st June 2023. This includes proposed improvements to the document based on feedback received over the past year.
3 | Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | ETYS Annual Report Published part of the Transitional Centralised Strategic Network plan Year-round Thermal needs published in ETYS Voltage screening results in ETYS | Q4 2023-24 | Complete | Q4 2023-24 | ETYS 2023 was successfully published on 29th August 2023. For the first time this year we have successfully brought forward publication of core content to allow our stakeholders more time to review system needs in advance of the Cost Benefit Analysis. The publication includes year-round thermal analysis and our voltage screening results in line with our commitment to expand our system needs. On 30th November we published ETYS appendix A (Existing Network diagrams), E (Fes charts), F (Contracted Generation), G (Nodal Demand), H (further information) and I (Transmission losses). Remaining elemnts were publicshed with the TCSNP2 in March 2023 - ETYS technical appendices B, C, D which contain future network data to align with the TCSNP2.
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | Start Engagement with Ofgem on the long-term requirement for Interconnector Analysis | Q1 2023-24 | Complete | Q1 2023-24 | We have started ongoing engagement with Ofgem in relation to our interconnector analysis for both the NOA and Cap & Floor Window 3.
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | Approval of Revised NOA Methodology | Q3 2023-24 | Complete | Q3 2023-24 | The draft methodology submitted to Ofgem on the 30th June 2023 has been has now been approved by Ofgem. This is now complete
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | NOA Annual Report Published, part of the Transitional Centralised Strategic Network plan | Q4 2023-24 | Complete | Q4 2023-24 | The NOA report has been subsumed within the Beyond 2030 report published on the 19th March 2024.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Review LOTI Process with Ofgem and Stakeholders to learn from the first two years of undertaking assessments | Q1 2023-24 | Complete | Q3 2023-24 | We have consulted with Ofgem and the Transmission Owners on how the first two years of LOTI cost-benefit analysis has gone. This yielded an average customer satisfaction score of 7.8 out of 10. Key commentary is summarised below. Positives: - The reports are clearly laid out, well presented and completed on time. Technical concepts, such as Least Worst Regret are well explained and outcomes are accompanied by suitable justification. This allows the TOs to comment in a meaningful way on the ESO report. - The ESO is open on analysis methodologies and approaches ensuring appropriate analysis is done for each study. Likewise the report is flexed to pull out study specific insights. Potential enhancements: - Expand the analysis to include social-economic and carbon benefits [ESO: This has been implemented for CNSP since the LOTI process was introduced] - A simpler exec summary as the technical content, while well explained, is still difficult for all readers to understand. - It is not clear from the report whether the ESO is challenging the TOs input. ESO could add text to the report on any engagement it had with the TOs where assumptions were challenged or changed.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q2 2023-24 | Complete | Q2 2023-24 | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q3 2023-24 | Complete | Q3 2023-24 | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q4 2023-24 | Complete | Q4 2023-24 | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q1 2024-25 | Complete | Q1 2024-25 | We continue to undertake LOTI cost-benefit analysis as and when required. This quarter we have been approached by the TOs in regards to a number of projects and have helped scope the studies. Economic analysis for these are expected in June, July and August.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q2 2024-25 | Complete | Q2 2024-25 | We continue to undertake LOTI cost-benefit analysis as and when required. A new process (Impact Assessment) has been established and will be applied to East and West Coast network reinforcement studies.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q3 2024-25 | Complete | Q3 2024-25 | We have continued to undertake LOTI and related cost-benefit analysis as and when required, and in agreement with Ofgem.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q4 2024-25 | Complete | Q4 2024-25 | Ongoing activity, continued throughout the quarter as required
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | EC5 tender run | Q3 2023-24 | Complete | Q4 2024-25 | Enduring tender concluded in December 24 with contract award due in Q4 24-25, for service to begin in July 26. The initial delay in launching the tender was due to the review of the service design to ensure we considered the range of possible solutions i.e. DNO connected and offshore assets, to increase competition and achieve best value for consumers. The details of the scale of works required to deliver a new OTS was finalised by NGET shared with bidders.
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | Constraint Management Pathfinder B6 year 3 tender | Q3 2023-24 | Milestone no longer valid |  | We have utilised an additional years' extension option from the B6 year 2 tender which will ensure that the current service will be in place until September 2027. This is as a result of the outcome of the tCSNP studies to determine any future constraint requirements, and focus on regions that will deliver most consumer benefit i.e. regions with high forecast constraint costs. The conclusion of these studies is that the optimal solution is a wider CMIS Scotland service (incorporating B6, B4, and part of B2) that will need design & implementation by one/both of the Scottish TO's. This will take some time to put into place, therefore the current target date is now Oct 27 for a new wider CMIS Scotland.
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | Constraint Management Pathfinder B6 year 2 service start date | Q3 2024-25 | Complete | Q3 2024-25 | This service is on schedule to start on time.
3 | Early Competition | D8.4 | Early Competition | Majority of commerical model elements delivered to Ofgem for approval (TRS, PPWCA) | Q1 2023-24 | Complete | Q2 2023-24 | Commercial model submitted to Ofgem.
3 | Early Competition | D8.4 | Early Competition | First generic tender documents and processes delivered to Ofgem to be approved | Q2 2023-24 | Delayed - External Reasons |  | Revised timetable agreed with Ofgem based on their inputs to the project.
3 | Early Competition | D8.4 | Early Competition | Early Competition contract completed and aligned with relevant licence obligations | Q3 2023-24 | Delayed - External Reasons |  | No longer required. agreed with Ofgem
3 | Early Competition | D8.4 | Early Competition | Implementation complete Project identified for first competition | Q4 2023-24 | Delayed - External Reasons |  | Revised timetable agreed with Ofgem based on their inputs to the project.
3 | Early Competition | D8.4 | Early Competition | Launch the first Early Competition tender | Q4 2024-25 | Delayed - External Reasons |  | Revised timetable agreed with Ofgem based on their inputs to the project.
3 | Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Integration with our network assessment tools | Q3 2023-24 | Complete | Q3 2023-24 | We have refreshed the economic assessment tools that we use to interact with our pan-European market dispatch model. This was done alongside the deployment of our new pan-European market dispatch model. The new model gave us new opportunities to enhance and integrate our tools, for example, by developing them in Python and integrating them with the pan-European dispatch tool via its API.
3 | Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Full integration with Data and analytics platform complete, enabling a joined- up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | Complete | Q4 2024-25 | We have started to update our economic assessment tool so that it can be used to undertake more types of analysis across the end to end strategic energy planning process. This includes data and model enhancements to allow the delivering of the Spatial Strategic Energy Plan the result of which will feed in to the Centralised Strategic Network Plan. By using a consistent economic assessment tool we will be able to use it for joined up analysis across different network needs and at multiple levels of granularity as appropriate for each NESO deliverable.
3 | Implement probabilistic modelling | D11.2 | Improved identification of network needs | Developed and implemented digital experience platform. This will provide an interactive platform to allow stakeholders to view network needs and see the impact selected generic options will have on addressing those needs from a technical perspective. | Q4 2023-24 | Complete | Q4 2023-24 | We have transformed the way we publish our probabilistic results. This year we have published our results on the ETYS portal with interactive plots and maps. We are continuously working to improve the way we publish our results and findings to engage our stakeholders more effectively.
3 | Implement probabilistic modelling | D11.2 | Improved identification of network needs | Full integration with Data and analytics platform complete, enabling a joined-up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | Delayed - Internal Reasons |  | We have started working with the DAP team for the full integration. It is delayed to align with the whole DAP program change.
3 | Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Implemented VO tool and identified further enhancements. | Q4 2023-24 | Complete | Q4 2023-24 | We have successfully launched the first version of the tool on cloud meeting all BP2 requirements. We have collected improvement idea and new requirements and are planning to release incremental updates with additional capabilities.
3 | Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Full integration with Data and analytics platform complete, enabling a joined- up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | Delayed - Internal Reasons |  | We have started working with the DAP team for the full integration. It is delayed to align with the whole DAP program change.
3 | Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Proof of concept for a stability screening tool | Q4 2023-24 | Complete | Q3 2023-24 | We have completed the POC on the stability screening tool.
3 | Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Implement stability screening tool | Q4 2024-25 | Complete | Q4 2024-25 | The solution is implemented in full and product is up and running. We are working on enhancements.
3 | Identify solutions | D12.2 | Potential solutions identified and direction established | Based on the prioritised list of issues, changes are initiated for the high-priority items and potential solutions are developed. | Q1 2023-24 | Complete | Q1 2023-24 | The list of SQSS changes have been reviewed and discussed with relevant stakeholders, new priorities have been established to all the topics.
3 | Identify solutions | D12.2 | Potential solutions identified and direction established | Based on the prioritised list of issues, changes are initiated for the low-priority items and potential solutions are developed. | Q3 2024-25 | Complete | Q3 2024-25 | Modification on system resilience has been approved. CATO GSR031 has been submitted to ofgem for approval. P2 alignment, MITS and offshore modification are ongoing, and potential solutions are being identified.
3 | Implement changes to the SQSS | D12.3 | Key changes to SQSS made or in progress | Based on the prioritised list of issues, changes are made or in progress for the high-priority items. | Q3 2023-24 | Complete | Q3 2023-24 | A few modifications are going, and potential solutions are being identified.
3 | Implement changes to the SQSS | D12.3 | Key changes to SQSS made or in progress | Based on the prioritised list of issues, changes are made or in progress for the low-priority items. | Q4 2024-25 | Complete | Q3 2024-25 | Modification on system resilience has been approved. CATO GSR031 has been submitted to ofgem for approval. P2 alignment, MITS and offshore modification are ongoing, and potential solutions are being identified.
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Summer Outlook Report Publication of Winter Review & Consultation | Q1 2023-24 | Complete | Q1 2023-24 | 2022 Summer Outlook Report published on 13 April. 2022/23 Winter Review and Consultation published 15 June alongside an early view of winter 2023/24
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of FES suite of documents (including data) | Q2 2023-24 | Complete | Q2 2023-24 | 2023 FES was published on the 10th July.
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Winter Outlook Report | Q3 2023-24 | Complete | Q2 2023-24 | 2023/24 Winter Outlook Report expected to be published on 28 Sep
2 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Summer Outlook Report Publication of Winter Review & Consultation | Q1 2024-25 | Complete | Q1 2024-25 | Summer Outlook published April 2024; Winter Review published June 2024
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of FES suite of documents (including data) | Q2 2024-25 | Complete | Q2 2024-25 | Analysis complete - FES suite of documents published on 15th July 2024 with live launch taking place in London
2 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Winter Outlook Report | Q3 2024-25 | Complete | Q3 2024-25 | 2024/25 Winter Outlook published in Q3 2024-25
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2 | Update pan-European and country level electricity and energy demand models | Update electricity our supply and demand data for several European countries to reflect the changes within the EU as they continue to evolve their economies to meet net zero decarbonisation. The European countries to model include those that are interconnected to the GB market in addition to a number of additional countries which, whilst further away, still have an impact on the GB market. Data to be benchmarked against the latest Ten Year Network Development Plan from ENTSO and incorporated within our pan-European dispatch model so that the FES, EMR and NOA analysis benefit from it. | Q4 2024-25 | Complete | Q4 2024-25 | Our electricity and hydrogen models require demand and supply scenarios that reflect our European neighbours pathway to low carbon economies at their own pace and in a way that is compatible with the underlying FES pathway narratives. We have updated these data and scenarios for FES25 in our pan European dispatch model and benchmarked against the Ten Year Network Development Plan from ENTSO. Quality assurance checks are ongoing and will be complete by the end of March 2025. These updates have also been reflected across different NESO teams including EMR and NOA.
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Starting to work with Local Authorities to understand the feedback loop between FES / Distribution scenarios / Local Area Energy Plans. Starting to work with gas networks to agree the granular breakdown of FES scenarios (Natural Gas and Hydrogen) | Q1 2023-24 | Complete | Q1 2023-24 | Work has started to understand the Feedback loop between FES / DFES and Local Area Energy Plans and the granular breakdown of FES scenarios (Natural Gas and Hydrogen) Engagement with the network companies has commenced through the network forum and bilateral discussions. The Call for Evidence for FES 2023 requested stakeholder views on the feedback loop and the regional breakdown of our gas and hydrogen pathways which included engagement with both network companies and local authorities. A project has been kicked off to understand the potential role for the FSO as Regional System Planner. This has included direct engagement with Local Authorities.
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Whole system regional data and insights provided alongside FES in July Enhanced visualisation launched. Regional data and visualisations added to our Website throughout the year as a appropriate and alongside the annual FES launch User configurable FES view available for Electricity supply and Demand | Q2 2023-24 | Complete | Q2 2023-24 | FES 2023 was launched on July 10th which included regional data and insights. Our visualisation platform was updated alongside the FES and included a user configurable interface for Electricity supply and demand.
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Whole system regional data and insights provided alongside FES in July Enhanced visualisation launched. Regional data and visualisations added to our Website throughout the year as a appropriate and alongside the annual FES launch User configurable FES view available for Electricity / Gas / Hydrogen supply and Demand | Q2 2024-25 | Delayed - External Reasons |  | Regional data and insights provided alongside FES 2024 including the building blocks and regional data used in our planning process. Regional building block data remains a key input in to downstream processes and will be published as part of FES 25. We are working with Ofgem and the RESP team to ensure that any regional insights from our Future Energy Scenarios modelling support/do not misalign with wider strategic energy planning processes. Due to additional work required on CP30 and the ongoing development of the RESP methodology, our regional insights have not yet been updated. This does not impact the inclusion of granular regional data within FES 25.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q1 2023-24 | Complete | Q1 2023-24 | Launch date communicated early with Ofgem and in line with previous years. Launched on 10 July as agreed.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES suite of documents (including data) | Q2 2023-24 | Complete | Q1 2023-24 | Complete - Launched 10th July 2023
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q3 2023-24 | Complete | Q3 2023-24 | On track and forms part of our ongoing engagement plan Published additional changes document in September.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q4 2023-24 | Complete | Q3 2023-24 | Complete - Stakeholder Feedback Document submitted to Ofgem and formal acceptance received that it meets licence condition. Minor updates agreed following further feedback.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q1 2024-25 | Complete | Q1 2024-25 | Published framework development document
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES suite of documents (including data) | Q2 2024-25 | Complete | Q2 2024-25 | Insights shared in FES publication launched on 15th July 2024. Four external webinars held to share insight and host Q&A
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q3 2024-25 | Complete | Q3 2024-25 | Updates included in NESO newsletter. Ran our Topic Table Talks event with over 100 stakeholders to hear feedback and insight from around the industry. Challenge and reviews for demand analysis taken place.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q4 2024-25 | Complete | Q4 2024-25 | Published FES 2025 methodology and Stakeholder Feedback Document. FES mailbox remains open and responding to queries
3 | FES: Bridging the gap to net zero | D13.4 | Bridging the Gap - produce evidence-based recommendations to support development of net zero policy | Delivery of a stakeholder informed report with recommendations for near term actions for net zero. | Q4 2023-24 | Complete | Q4 2023-24 | Focussing on enablers and dependencies for accelerating heat decarbonisation - closing webinar 28th Feb
3 | FES: Bridging the gap to net zero | D13.4 | Bridging the Gap - produce evidence-based recommendations to support development of net zero policy | Delivery of a stakeholder informed report with recommendations for near term actions for net zero. | Q4 2024-25 | Milestone no longer valid |  | Decision taken to focus on Advisory role over this activity in 24/25
2 | FES: Integrating with other networks and supporting DNOs to develop their own DFES processes | D13.5.3 | Enhance our energy modelling to reflect stakeholder feedback and changes to the credible pathways to net zero | Development plan in place | Q4 2023-24 | Complete | Q4 2023-24 | Our energy modelling has been updated for FES24 to enhance our ability to reflect H2 supply locations. We are continuing to work through the modelling requirements to support CSNP with internal and external stakeholders.
3 | Provide contractual expertise and management of connection contracts including provision of connection offers to customers | D14.1.1 | Managing an increasing volume of connection offers for customers | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | Complete | Q4 2024-25 | Ongoing activity
3 | Provide contractual expertise and management of connection contracts including provision of connection offers to customers | D14.1.2 | Contract management of connection agreements | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | Complete | Q4 2024-25 | Ongoing activity
3 | Ensure Grid Code compliance of new connections | D14.2.1 | Compliance monitoring of new connections in accordance with Grid Code provisions | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | Complete | Q4 2024-25 | Ongoing activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Run a new type of meeting as part of Connections process with DNOs and TOs focused on review of new connections still being processed by DNOs and suitability of DER as an option [at this point DER as a solution needs to be understood by all] | Q1 2023-24 | Complete | Q3 2023-24 | The ESO team is working seamlessly with the DNO community to push solutions forward for generation and demand sites that want to connect at a lower voltage level. We have a dedicated Demand team which has a sepcific account manager for each DNO, who is there to support in providing solutions to DER customers, in tandem with the relevant DNO. We have also increased resource to facilitate the work through the ENA led Strategic Connection Group, to help deliver greater capacity at a DNO level by assessing 'Technical limits' across the T/D interface. This is providing material benefit for DER applicants.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q2 2024-25 | Complete | Q2 2024-25 | As part of the ENA's 3-point plan to improve connections for embedded customers, we have worked with DNOs to develop Technical Limits at Grid Supply Points and implement revised Bilateral Connection Agreements through ESO's Connections Operational Demand Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Request feedback from Customers and DNOs | Q3 2023-24 | Complete | Q3 2023-24 | This has been done in tandem with DNO colleagues through the SCG work. Furthermore, we run monthly webinars with the industry, which offers an opportunity to discuss their experiences and questions around our activities in the Connection space. We also look to host twice yearly, customer seminars - which brings the wider industry together.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q4 2024-25 | Complete | Q3 2023-24 | Complete - As part of the ENA's 3-point plan to improve connections for embedded customers, we have worked with DNOs to develop Technical Limits at Grid Supply Points and implement revised Bilateral Connection Agreements through ESO's Connections Operational Demand Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously deliver on the use of DER, learn lessons and implement improvements | Q1 2024-25 | Complete | Q3 2023-24 | Complete - As part of the ENA's 3-point plan to improve connections for embedded customers, we have worked with DNOs to develop Technical Limits at Grid Supply Points and implement revised Bilateral Connection Agreements through ESO's Connections Operational Demand Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q3 2024-25 | Complete | Q3 2023-24 | Complete - As part of the ENA's 3-point plan to improve connections for embedded customers, we have worked with DNOs to develop Technical Limits at Grid Supply Points and implement revised Bilateral Connection Agreements through ESO's Connections Operational Demand Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q1 2023-24 | Complete | Q1 2023-24 | Complete - seminars held with over 200 attendees
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q2 2023-24 | Complete | Q2 2023-24 | Complete - seminars held with over 200 attendees
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q3 2023-24 | Complete | Q3 2023-24 | Complete - seminars held with over 200 attendees
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q4 2023-24 | Complete | Q4 2023-24 | Complete - seminars held with over 200 attendees.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q1 2024-25 | Complete | Q1 2024-25 | Complete - seminars held with over 200 attendees.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q2 2024-25 | Complete | Q2 2024-25 | Complete - seminars held with over 200 attendees.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q3 2024-25 | Complete | Q3 2024-25 | Complete - seminars held with over 200 attendees.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q4 2024-25 | Complete | Q4 2024-25 | Forum approach under review, to integrate key reform updates and progress on milestones
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Submit IT investment paper through internal governance process and obtain approval of scope and expenditure Engage with customers on ways to improve connections journey and ways of enhancing the portal | Q1 2023-24 | Complete | Q1 2023-24 | Future releases of the Connections portal are planned and the functionality backlog has been agreed. Sessions with industry stakeholders are ongoing with some smaller targeted sessions with specific groups of stakeholders already held and larger stakeholder events planned for the end of July 2023.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Further develop concept of new register, platform and connection with other systems [salesforce and customer portal]; Liaise with relevant internal stakeholders to verify concept and requirements | Q2 2023-24 | Complete | Q2 2023-24 | The functionality for the Connections portal is constantly being developed, with more functionality being added every 2-3 months throughout the BP2 period. The functionality being added is underpinned by stakeholder feedback.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Further development and testing - engage with relevant focus groups | Q3 2023-24 | Complete | Q3 2023-24 | This is an ongoing activity. We are currently carrying out feature development sessions with industry parties such as; consultants, DNOs and TOs to enhance portal functionality.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Implementation of updates to ESO Portal | Q4 2023-24 | Complete | Q4 2023-24 | Complete as phase 1 is delivered.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Obtain feedback on the new platform from internal and external stakeholders | Q1 2024-25 | Complete | Q1 2024-25 | Stakeholder feedback sessions planned for July 2023 and functionality being introduced directly into the portal to obtain customer feedback.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q2 2024-25 | Complete | Q2 2024-25 | Iterative change improvements catalogued, with effort and impact assessments continually reviewed. Recruitment for CX Lead role instigated to help support, optimise and improve customer service and experience.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q3 2024-25 | Complete | Q3 2024-25 | Iterative change improvements catalogued and being delivered, against supporting effort and impact assessments. Recruitment for CX Lead role completed and embedded within the Product Team.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q4 2024-25 | Complete | Q4 2024-25 | Ongoing Activity - CX & UX journey mapping supporting iterative improvement development. Additional PO's appointed to support delivery of activities
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.5 | Improving our internal processes | Improved customer feedback indicating customers welcome changes to connections processes | Q4 2024-25 | Complete | Q4 2024-25 | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.6 | Proposing future policy and code improvements | ESO has identified helpful policy and code changes, including ENA guidance and new ESO policies, which are supported by relevant stakeholders. Industry code modifications proposed. | Q4 2023-24 | Complete | Q4 2023-24 | We have completed all of our CAP (connections action plan) actions that were due before the end of Q4 2023-24. We continue to develop policies and tactical solutions to improve connections in line with the wider connections reform project. In addition we continue to support the policy and code changes that are being developed in conjunction with the ENA to help distribution projects
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.6 | Proposing future policy and code improvements | ESO has identified helpful policy and code changes, including ENA guidance and new ESO policies, which are supported by relevant stakeholders. Industry code modifications proposed. | Q4 2024-25 | Complete | Q4 2024-25 | Ongoing Activity - We continue to develop policies and tactical solutions to improve connections in line with the wider connections reform project. In addition we continue to support the policy and code changes that are being developed in conjunction with the ENA to help distribution projects
3 | Facilitate development of the customer connections portal | D14.4.1 | Implement first phase of the ESO connections portal, including online account management and integration with other network organisation websites | Deliver changes based on customer feedback | Q1 2023-24 | Complete | Q1 2023-24 | Two further releases have been implemented since the launch of MVP in March 2023 including new functionality for calculation of application fees as well as other front end and back end enhancements.
3 | Facilitate development of the customer connections portal | D14.4.1 | Implement first phase of the ESO connections portal, including online account management and integration with other network organisation websites | Deliver changes based on customer feedback | Q2 2023-24 | Complete | Q2 2023-24 | Complete as phase 2 is delivered. We released specific features based upon customer feedback.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Submit revised IT investment paper through internal governance process and obtain approval of scope and expenditure | Q1 2023-24 | Complete | Q1 2023-24 | IT investment paper submitted
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Further develop concept of phase 2 deliverables and identify different stages of deliverables along with key stakeholders to work with | Q2 2023-24 | Complete | Q2 2023-24 | Future releases of the Connections portal are planned and the functionality backlog has been agreed. Sessions with industry stakeholders are ongoing with some smaller targeted sessions with specific groups of stakeholders already held and larger stakeholder events planned for the end of July 2023.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Development of concept designs | Q3 2023-24 | Complete | Q3 2023-24 | Complete as phase 2 is delivered.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Development of concept designs | Q4 2023-24 | Complete | Q4 2023-24 | Complete as phase 2 is delivered.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Review and UAT for scheduled deliverables in Q3 & Q4 | Q1 2024-25 | Complete | Q1 2024-25 | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Continuous development of further elements for later delivery | Q2 2024-25 | Complete | Q2 2024-25 | Jira CR planning boards created to help quantify the 'effort' vs 'impact' and change priority.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Delivery of elements of the phase 2; Continuous development of further elements for later delivery | Q3 2024-25 | Complete | Q3 2024-25 | Product Team working through delivery of incremental improvements, utilising CX & UX journey maps to enhance successful delivery and adoption.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Delivery of elements of the phase 2; Continuous development of further elements for later delivery | Q4 2024-25 | Complete | Q4 2024-25 | Ongoing activity - no concerns. Additional and key CX/UX and PO roles appointed to support delivery.
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q1 2023-24 | Complete | Q1 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation and Grid Forming are ongoing, it will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q2 2023-24 | Complete | Q2 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, it will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q3 2023-24 | Complete | Q3 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q4 2023-24 | Complete | Q4 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q1 2024-25 | Complete | Q1 2024-25 | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q2 2024-25 | Complete | Q2 2024-25 | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q3 2024-25 | Complete | Q3 2024-25 | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q4 2024-25 | Complete | Q4 2024-25 | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.2 | Innovation projects developing new operability solutions – undertake innovation projects, as appropriate, to test operability solutions | Identify and initiate new innovation project | Q4 2023-24 | Complete | Q4 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.2 | Innovation projects developing new operability solutions – undertake innovation projects, as appropriate, to test operability solutions | New innovation project delivered and learning has been captured in developing of SOF | Q4 2024-25 | Complete | Q4 2024-25 | The NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, GFM interaction project was approved. D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. System strength on small signal stability was developed and IEEE paper was accepted. Guidance on system oscillation assessment was published. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Provide technical support to the connections process | D15.2.1 | Updates to customer offers and agreements – provide technical support to the connection offer process (as set out in activity A14.1) and assess offers to determine future operability need | As required and provide technical support to delivery of the connections hub in activity group A14 | Q4 2024-25 | Complete | Q4 2024-25 | Once the policy changes have been approved, they are reflected into the connection offers and agreements
3 | Provide technical support to the connections process | D15.2.1 | Updates to customer offers and agreements – provide technical support to the connection offer process (as set out in activity A14.1) and assess offers to determine future operability need | As required and provide technical support to delivery of the connections hub in activity group A14 | Q4 2024-25 | Complete | Q4 2024-25 | Once the policy changes have been approved, they are reflected into the connection offers and agreements
3 | Assess the technical implications of framework developments and implement changes into business procedures and systems | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. | Provide ongoing technical support to modifications as required (including those raised through open governance) – the level of resource required can vary hugely from one to another | Q4 2024-25 | Complete | Q4 2024-25 | Once the policy and framework changes have been approved, they are reflected into the business procedures and process
3 | Assess the technical implications of framework developments and implement changes into business procedures and systems | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. | Provide ongoing technical support to modifications as required (including those raised through open governance) – the level of resource required can vary hugely from one to another | Q4 2024-25 | Complete | Q4 2024-25 | Once the policy and framework changes have been approved, they are reflected into the business procedures and process
3 | Manage our operational data and modelling requirements | D15.4.1 | Data transfers between network organisations in accordance with current Grid Code and STC requirements – managing operational data flows across network companies to underpin offline network analysis in the ESO. | Delivery ETYS and NOA models | Q3 2023-24 | Complete | Q3 2023-24 | All 2023 ETYS Winter models completed (Years 1, 2, 4, 7, 9, 12) and released by 1st September 2023. Summer minimum Year 1 model released on 15/09/2023.
3 | Manage our operational data and modelling requirements | D15.4.1 | Data transfers between network organisations in accordance with current Grid Code and STC requirements – managing operational data flows across network companies to underpin offline network analysis in the ESO. | Delivery ETYS and NOA models | Q3 2024-25 | Complete | Q2 2024-25 | Prepare for new requirements needed in 2024 ETYS Model
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q1 2023-24 | Complete | Q1 2023-24 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q2 2023-24 | Complete | Q2 2023-24 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q3 2023-24 | Complete | Q3 2023-24 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q4 2023-24 | Complete | Q4 2023-24 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q1 2024-25 | Complete | Q1 2024-25 | All legislative requirements fulfilled to the required standard.
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q2 2024-25 | Complete | Q2 2024-25 | All legislative requirements fulfilled to the required standard
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q3 2024-25 | Complete | Q3 2024-25 | All legislative requirements fulfilled to the required standard
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q4 2024-25 | Complete | Q4 2024-25 | All legislative requirements fulfilled to the required standard
3 | Manage our operational data and modelling requirements | D15.4.3 | Automation of data exchange mechanism and preparation for CIM implementation | Identify initiative which will automate the data exchange mechanism Commence preparation for data exchange enhancements with network organisations | Q4 2023-24 | Complete | Q4 2023-24 | Woking on developing a new exchange node interface platform to facilitate interface points between Transmission Owner and DNO network data exchange with the help of DD & T. The extraction mechanism needs to be automated such that any change can be captured using an automated importing link into the offline toolsets.
3 | Manage our operational data and modelling requirements | D15.4.3 | Automation of data exchange mechanism and preparation for CIM implementation | Implementation of data exchange automation Prepared for data exchange enhancements with network organisations | Q4 2024-25 | Complete | Q4 2024-25 | Continue refine design solution in discussion with vendors and industry participants. Final solution to be optimised as soon as the legal text has been finalised and approved.
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Testing and commissioning of first GEMS pilot boundaries | Q1 2023-24 | Milestone no longer valid |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. At this point, the ESO and SPT explored alternative ways to achieve same benefit. Considering other developments in this space, the ESO identified functionalities delivered by Open Balancing Programme (OBP) are adequate to manage the system. A proposal for ESO to achieve dispatch automation via OBP and SPT to deliver network reconfiguration and operational tripping scheme at Kilmarnock South was agreed between ESO and SPT. The SPD ANM integration will be taken forward via a MW-Dispatch like project, mimicking the developments underway with NGED and UKPN DNOs in England. The new proposed way forward will deliver a more streamlined and lower risk and scalable solution for the consumer, providing consistency in approach GB wide, whilst not impeding new connections in this part of Southwest Scotland.
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Design and integration of GEMS functionality with SPD ANM scheme. | Q2 2024-25 | Milestone no longer valid |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. At this point, the ESO and SPT explored alternative ways to achieve same benefit. Considering other developments in this space, the ESO identified functionalities delivered by Open Balancing Programme (OBP) are adequate to manage the system. A proposal for ESO to achieve dispatch automation via OBP and SPT to deliver network reconfiguration and operational tripping scheme at Kilmarnock South was agreed between ESO and SPT. The SPD ANM integration will be taken forward via a MW-Dispatch like project, mimicking the developments underway with NGED and UKPN DNOs in England. The new proposed way forward will deliver a more streamlined and lower risk and scalable solution for the consumer, providing consistency in approach GB wide, whilst not impeding new connections in this part of Southwest Scotland. This is expected to be covered by RDP6
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Expansion of functionality to further boundaries on a system needs basis. | Q4 2023-24 | Milestone no longer valid |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. At this point, the ESO and SPT explored alternative ways to achieve same benefit. Considering other developments in this space, the ESO identified functionalities delivered by Open Balancing Programme (OBP) are adequate to manage the system. A proposal for ESO to achieve dispatch automation via OBP and SPT to deliver network reconfiguration and operational tripping scheme at Kilmarnock South was agreed between ESO and SPT. The SPD ANM integration will be taken forward via a MW-Dispatch like project, mimicking the developments underway with NGED and UKPN DNOs in England. The new proposed way forward will deliver a more streamlined and lower risk and scalable solution for the consumer, providing consistency in approach GB wide, whilst not impeding new connections in this part of Southwest Scotland.
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Commissioning of first DER onto combined GEMS and SPD ANM functionality. | Q4 2024-25 | Milestone no longer valid |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. At this point, the ESO and SPT explored alternative ways to achieve same benefit. Considering other developments in this space, the ESO identified functionalities delivered by Open Balancing Programme (OBP) are adequate to manage the system. A proposal for ESO to achieve dispatch automation via OBP and SPT to deliver network reconfiguration and operational tripping scheme at Kilmarnock South was agreed between ESO and SPT. The SPD ANM integration will be taken forward via a MW-Dispatch like project, mimicking the developments underway with NGED and UKPN DNOs in England. The new proposed way forward will deliver a more streamlined and lower risk and scalable solution for the consumer, providing consistency in approach GB wide, whilst not impeding new connections in this part of Southwest Scotland. This is expected to be covered by RDP6
3 | Develop Regional Development Programmes (RDPs) | D15.5.2 | RDP2 of RIIO-2 (MW dispatch, South East, UKPN) | IT implementation phase complete | Q2 2023-24 | Complete | Q4 2023-24 | All MWD enabling IT implementation complete.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Working with the DNO, continue to undertake IT requirements and design for new operability functionality | Q1 2023-24 | Complete | Q4 2023-24 | Product Backlog prioritisation, requirements gathering and design commenced.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete IT requirements and design | Q2 2023-24 | Complete | Q1 2024-25 | Complete - now in build.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete enhancements to new service and final implementation | Q4 2024-25 | Complete | Q4 2024-25 | All enhancements delivered to live and available for business use.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete IT development and testing; ongoing implementation of solution | Q1 2024-25 | Complete | Q3 2024-25 | This milestone did not complete in Q1 2024/25 due to delayed start of this RDP. This delay was a knock on from a delay to the completion of RDP 1 which was a precursor with the same DNO. The RDP 1 delay was due to issues with the implementation of a specific MPLS communication link allowing ESO / DNO secure communications rather than public internet communications as specified by the DNO Cyber Security protocols requirements. All core system IT development, testing and deliveries complete in NESO and NGED.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Assess enhancements to new service in accordance with operability needs and customer feedback | Q2 2024-25 | Complete | Q2 2024-25 | Service enhancements agreed and driven by stakeholder and customer input to ensure delivery of value add scope items.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Working with the DNO, continue to undertake IT requirements and design for new operability functionality | Q1 2023-24 | Complete | Q4 2023-24 | Product Backlog prioritisation, requirements gathering and design commenced.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete IT requirements and design | Q2 2023-24 | Complete | Q1 2024-25 | Complete - now in build.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete enhancements to new service and final implementation | Q4 2024-25 | Complete | Q4 2024-25 | MWD enhancements completed and full business go live achieved.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete IT development and testing; ongoing implementation of solution | Q1 2024-25 | Complete | Q3 2024-25 | This milestone did not complete in Q1 2024/25 due to the delayed start of this RDP. This delay was due to a delay in the delivery of RDP 2 which was a precursor to this RDP. The RDP 2 delay was due to ongoing and protracted discussions and negotiations with the DNO to agree the MW Dispatch scope and deliverables, specifically around service delivery expectations. All core system development, testing and IT deliveries complete in both NESO and UKPN.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Assess enhancements to new service in accordance with operability needs and customer feedback | Q2 2024-25 | Complete | Q2 2024-25 | Service enhancements agreed and driven by stakeholder and customer input to ensure delivery of value add scope items.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Establish enduring process to determine needs at GSPs | Q2 2023-24 | Complete | Q2 2023-24 | Factoring in our ongoing work through the ESO's Five Point Plan to Accelerate Connections, we have now drafted a process to determine a needs case at each GSP. This is currently undergoing final internal approval prior to being shared with stakeholders for review and feedback.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Rollout process and seek feedback from stakeholders | Q4 2023-24 | Complete | Q4 2023-24 | The RDP rollout process has been developed and feedback from stakeholders received and implemented. Process paper published in ESO external website.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Test application of process at one or more sites | Q2 2024-25 | Complete | Q1 2024-25 | We are working with SSEN to trial the process at their Abernethy network. CBA of the options complete with an operational solution recommended. Strategy paper has been finalised and awaiting sign off by SHEPD, SSEN-T and ESO.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Implement enduring ongoing process (BAU) | Q4 2024-25 | Complete | Q4 2024-25 | NESO are implementing a BAU compliance process for RDP5. The draft proposal is being discussed at the ENA Strategic connection group. 06/01/2024 update: The team have captured the learning points from the first Technical Limit project with NGED and have reflected this in the underlying documentation to standardise and streamline the process for other DNOs. This includes the Project Initiation Document, Joint Operating Procedure, and the Data Exchange Protocol. In addition to these standardised documents, NESO are leading the development of the Technical Limit compliance process, which will incentivise DNOs to ensure Technical Limits are not breached, and successive breaches are penalised appropriately (i.e. by temporary suspension of the Technical Limit) to ensure the security of the system and consumer value is maintained. While collaboration between NESO and the DNOs has been effective, there is a risk that parties may disagree with the proposed compliance process, which may take time to resolve. NESO are producing an overarching end to end process to provide clarity to both DNOs and NESO parties and will streamline the application and roll out of Technical Limits across the network. This process documentation will be made available to all DNOs once completed. This is anticipated to be completed by the end of February 2025. 28.03.2025 update: The process is now finalised and will be uploaded onto our quality management system.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Go / No go decision to progress RDP implementation; If yes, commence detailed RDP development | Q1 2023-24 | Complete | Q1 2023-24 | We have identified a number of opportunities where RDP5 can support the roll-out of functionality necessary to support the ESO's Five Point Plan to accelerate connections.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Complete IT requirements and design | Q2 2024-25 | Complete | Q2 2024-25 | Scoping discussion with all England and Wales DNOs are progressing. First external design Workshop with NGED completed. We are working to finalise design documents.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Complete detailed RDP development ahead of IT build. | Q3 2023-24 | Complete | Q3 2024-25 | This was delayed until ENA strategic connection group outcome was delivered. RDP 5 will now be implementing GSP technical limits as agreed by ENA Strategic Connections Group work. Project initiation documents (PIDs) are shared with all E&W DNOs. NGED and SSEN have signed their project initiation document. This will now allow us to start IT delivery activities. 06/01/2024 update: Detailed IT requirements completed and agreed with NGED, with other DNOs to follow. Completion of this milestone is linked to the successful implementation with a single DNO (NGED) as the all processes will be well defined enabling successive roll out to all other DNOs (noting that SSEN are close behind).
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Commence IT implementation in order to test new service solution. | Q4 2024-25 | Complete | Q4 2024-25 | IT project initiation documents signed off by NGED, NESO. Implementation has commenced. 06.01.2024 update: The Technical Limit roll out project with NGED is progressing well, with all IT development and testing complete. Go live is planned for 14th January 2025, which aligns with the BP milestone target date. ENCC infrastructure went live successfully on 14th January 2025 as planned.
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Go / No go decision to progress RDP implementation; If yes, commence detailed RDP development | Q1 2023-24 | Complete | Q1 2023-24 | We have identified a number of opportunities where RDP6 can support the roll-out of functionality necessary to support the ESO's Five Point Plan to accelerate connections.
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Complete IT requirements and design | Q2 2024-25 | Delayed - External Reasons |  | 13.03.2025 update: Following the successful deployment of MW Dispatch under RDP 3 and 4, NESO agreed to explore the use of a MW dispatch solution in the Dumfries and Galloway area of the SPD/SPT network to provide flexibility in the management of the local network constraints. The complexity of the Scottish transmission network, presence of Load Management Schemes, and other control schemes that were deployed historically have presented significant challenges and conflicts associated with the deployment of a MW Dispatch solution. NESO recommended a phased approach whereby only Generators that are party to a firm connection (in control of their own availability) under phase one, and explore the extension to non-firm Generators under phase 2 (subject to the primacy project outcome). NESOs internal review of the firm Generator capacity identified a total of 214MW, providing a clear business case for deploying MW dispatch (market competition and net zero). NESO have shared this approach with SPD, with whom there is a dependency on their response, who are conducting an independent review to confirm the forecasted benefit and enable signing of the PID to progress the project.
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Complete detailed RDP development ahead of IT build. | Q3 2023-24 | Delayed - Internal Reasons |  | ESO and SPD agreed to deliver a transmission constraint management service for DERs via RDP6 under the GEMS project. However, following stakeholder termination of the GEMS project, a replacement initiative was required to achieve the original intention of the constraint management service. NESO committed to implement a service similar to the MW dispatch intended to be provided by GEMS. Potential advantages to be gained by using similar design principle and put lessons learned to a good use. The proposed solution will scalable to enable national role out when required. 06.01.2024 update: Dependent on delivery of D15.5.7 IT requirements and design above. 13.03.2024 update: Dependent on delivery of D15.5.7 IT requirements and design above.
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Commence IT implementation in order to test new service solution. | Q4 2024-25 | Delayed - External Reasons |  | This RDP is anticipated to be a MW Dispatch type of solution for the Scotland region. Scope is currently being finalised to allow formal design and IT delivery phase to commence. 06.01.2024 update: Dependent on delivery of D15.5.7 IT requirements and design above. 13.03.2024 update: Dependent on delivery of D15.5.7 IT requirements and design above.
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q1 2024-25 | Complete | Q1 2024-25 | Completed drafting initial design for electricity modelling information data store to facilitate implantation CIM model exchange with DNOs
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q2 2024-25 | Complete | Q2 2024-25 | Development on interface for data exchange ongoing, vendor engaged in Proof of concept and in process of receiving full development offer and timelines.
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q3 2024-25 | Complete | Q3 2024-25 | All subgroup reviews and discussion on Grid Code legal text changes had been concluded. Planed for Work Group meeting to finalise consultation report. Continue with industry engagements to identify and agree early DNO adaptors.
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Grid Code mods progressed or submitted for approval | Q4 2023-24 | Complete | Q4 2023-24 | Progressing through sub group reviews on draft consultation report and legal text through industry engagements with intention to gather review feedbacks and finalise report and legal text in the next quarter. Reforecast required to align with latest information for final code authority sign off in Jan 2025
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q4 2024-25 | Complete | Q4 2024-25 | All subgroup reviews and discussion on Grid Code legal text changes had been concluded. Planed for Work Group meeting to finalise consultation report. Continue with industry engagements to identify and agree early DNO adaptors.
3 | Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. | Further upgrade to offline modelling tool software / service pack | Q2 2024-25 | Complete | Q2 2024-25 | Completed 2 service pack upgrades to users incorporating critical security / function enhancements & fixes to short circuit calculations as well as dealing with correct demand application / scaling in various operational planning studies
3 | Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. | Integration of offline modelling tools with Data and Analytics Platform | Q4 2024-25 | Complete | Q4 2024-25 | Finalised design on one process to convert & export electricity network data & model ready to be ingested into the Data and Analytics Platform. Detailed design completed, tested and validated.
3 | Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling | Feed findings from deliverable A16.3.2 and any Grid Code modifications into future modelling scoping and development | Q4 2023-24 | Complete | Q4 2023-24 | Through our recent engagement with DNOs and other industry participants via the GC0139 working group review panels, a number of planning code sections of the Grid Code needs modifying and changing to capture more detailed generation technical data within the DNO’s network, definitions and requirements have been reviewed in order to ensure these data meet the latest CGMES profile standards.
3 | Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling | Feed findings from deeper access work into offline network modelling development | Q4 2024-25 | Complete | Q4 2024-25 | Data exchange interface testing and delivery completed. Further additional scope / functionality to be delivered by vendors pending on the grid code legal text approval.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Learning from NIA projects (such as TOTEM) to define the requirements for EMT modelling work | Q1 2023-24 | Complete | Q1 2023-24 | NIA project TOTEM led by SSEN, provided base case EMT network component model based on ETYS 2021 Year 1. This will be used as base model for ESO to develop GB wide EMT model. The learnings such as dispatch tool requirement to analyse multiple scenarios, computational performance required will be taken forward to build future model building activities. DETECTS is another innovation project, where the SE Coast model with Users model integrated has been obtained. The main learning is on the integration of Users model to wider EMT model. More innovation projects, such as developing tools to analyse the system, are ongoing. Based on these learnings, ESO in discussion with wider industry, to build and maintain the GB wide EMT model for future.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Engage with wider industry and produce a roadmap to develop and maintain EMT models | Q2 2023-24 | Complete | Q2 2023-24 | ESO engaged with all onshore TOs through innovation project such as TOTEM to develop the base case GB wide EMT model. ESO is currently working with SSEN-T on EMT analysis. ESO is working in partnership with NGET on development of co-simulation NIA project. The JPC approved to form JPCMG subgroup on EMT modelling. ESO also having continuous engagement with wider industry (AEMO, G_PST, NERC, ESIG group) on learning and developing GB wide EMT model.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Identify the data requirements and develop process to collect required data and build initial EMT model. | Q4 2023-24 | Complete | Q4 2023-24 | Learnings from all NIA innovation projects are being used by ESO to define these requirements. ESO also engaged with wider industry (AEMO, NERC EMTTF, ESIG) in the world and their learnings also being used to develop these requirements. In addition to the above, CIGRE report and research papers have been used to define the data requirements. Data requirements for different analysis are presented to EMT Modelling JPCMG subgroup and received feedback from TOs.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To carry out initial EMT simulations for the GB network | Q1 2024-25 | Complete | Q1 2023-24 | ESO have already started to carry out EMT simulations for single plants/ HVDC. ESO obtain the initial model from DETECTS innovation project and started the regional analysis on GB.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To define the requirements for full GB system EMT simulation using learning from NIA projects (co-simulation analysis innovation project in D15.6.9) | Q2 2024-25 | Complete | Q2 2024-25 | After completing the feasibility of co-simulation analysis (between PowerFActory and PSCAD) through innovation projects, requirements will be defined. The project team is also looking into the possibility of having reduced EMT network model instead of co-simulation as well as specifying the required areas/ regions for the EMT simulation rather than considering full GB EMT model for simulations. The potential conversion from PF to PSSe and then co-simulation with PSCAD also being investigated. The requirements such as selecting suitable areas, reducing the wider network to the required regions to carry out wider system analysis are defined. Co-simulation is another method but requires more investigation, mainly from the tool suppliers.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To carry out EMT simulations to analyse control interactions, system oscillations and power quality studies. Developed plan for ongoing maintenance of EMT model(s). | Q4 2024-25 | Complete | Q3 2024-25 | ESO started to carry out EMT simulations for single plants/ HVDC. ESO obtain the initial model from DETECTS innovation project and developing the analysis skills. Different system analysis with wider GB model, obtained from TOTEM project, will be carried out. Different system analysis with wider GB model, obtained from TOTEM project, will be carried out. ESO started using TOTEM model to investigate the system behaviour, with the available Users models. The methodology such as impedance scan is also used to understand the behaviour of system during oscillation investigations. ESO developed the capabilities to carry out different analysis using EMT models.
3 | Transform our capability in modelling and data management | D15.6.9 | Co-simulation analysis innovation project | Engage with wider industry (different TOs) to start the potential innovation project for co-simulation works. | Q1 2023-24 | Complete | Q1 2023-24 | Engaged with NGET TO on requirements of co-simulation (between PowerFactory and PSCAD model). ESO is working with NGET to set up a new NIA project called Co-Simulation. Co-simulation NIA project is expected to start in 2 weeks. ESO also engaging with OPAL-RT and other academia on possible NIA projects as well.
3 | Transform our capability in modelling and data management | D15.6.9 | Co-simulation analysis innovation project | Evaluate the feasibility of co-simulation modelling between OLTA (PowerFactory) and PSCAD. | Q4 2023-24 | Complete | Q4 2023-24 | ESO is working with NGET on a NIA innovation project on co-simulation between PowerFactory and PSCAD. Through this innovation, at first the feasibility of co-simulation between PowerFactory and PSCAD has been evaluated. NIA project demonstrated the communication between two tools (PowerFactory and PSCAD) but due to communication delay, error introduced in the analysis. To investigate further on these issues, ESO is also currently exploring on the co-simulation feasibility analysis within PowerFactory (Both RMS and EMT within PowerFactory), through IT project. Engagement with DigSilent on co-simulation within PowerFactory tool is being explored through ONM investment.
3 | Deliver enhanced frequency control by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) first stage roll out. | Phase 1 (non-operational demonstration) implemented | Q3 2023-24 | Complete | Q2 2024-25 | Due to the long delay in getting contract signed between parties, the completion of non-operational demonstration date is expected to go beyond the current scheduled date. Currently change Request has been submitted and the expected completion of this milestone is Q2 2024-25. Through CMF process the revised milestone date has been updated. t is expected to be completed within BP2 period. With the Statement of Work has been agreed with GE Digital, the confidence level of completing this milestone is increased to HIGH. Installation of MCS system at Data Centre is completed. Local devices at Warwick office and GE Office location was completed. Establishing the flow of SPEN PMU data to non-prod PDC is ongoing. Non-operational demonstration, testing for number of scenarios have been carried out. Reports are being produced to capture the learnings from the trials.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Support ESO initiatives to remove technical barriers to ensure whole electricity system coordination & distributed flexibility market participation. | Q4 2023-24 | Complete | Q4 2023-24 | Actively engaged with Open Networks and DNO's. Co-leading a number of workstreams to facilitate Flex Market delivery including policy/code changes.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement on DSO transition to support ongoing developments and transition policy into the relevant codes and frameworks. | Q4 2023-24 | Complete | Q4 2023-24 | Actively engaged with Open Networks and DNO's. Co-leading a number of workstreams to facilitate Flex Market delivery including policy/code changes.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement in the Open Networks project to support ongoing developments and lead Work Stream 4 Whole Energy Systems | Q4 2023-24 | Complete | Q4 2023-24 | Actively engaged on workstreams on Open Networks, Currently co-leading on several to drive forward change and increase pace of change. we have a proposed way forward on Primacy rules and continue to engage with all stakeholders.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Support ESO initiatives to remove technical barriers to ensure whole electricity system coordination & distributed flexibility market participation. | Q4 2024-25 | Complete | Q4 2024-25 | Actively engaged on workstreams on Open Networks, Currently co-leading on several to drive forward change and increase pace of change.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement on DSO transition to support ongoing developments and transition policy into the relevant codes and frameworks . | Q4 2024-25 | Complete | Q4 2024-25 | Valuable feedback has been received from DNOs and FSPs in Flexibility Strategy Call for Input on DSO coordination. The team are iterating our strategy based on industry feedback. And we are leading on several groups within the Open Networks Programme, including leading the Market Development Workstream.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement in the Open Networks project to support ongoing developments and lead Work Stream 4 Whole Energy Systems | Q4 2024-25 | Complete | Q4 2024-25 | Actively engaged with Open Networks and DNO's. Co-leading a number of workstreams to facilitate Flex Market delivery including policy/code changes.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Initiate project scoping with external stakeholders to enable operational visibility of DER | Q1 2023-24 | Complete | Q1 2023-24 | We have initiated Project scoping with internal stakeholders to identify DER visibility use cases. Identified relevant external stakeholders. Next step to engage externally to produce a high level view of External stakeholders expectations.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Complete project scoping with external stakeholders to enable operational visibility of DER | Q2 2023-24 | Complete | Q3 2023-24 | We have completed work to produce a DER Visibility Roadmap strategy. We undertook a cross functional view to produce detailed user requirements across ESO & external stakeholders as well considering regulatory, data and technology architecture aspects needed to deliver DER visibility. This holistic approach is expected to reduce risk & maximise consumer benefit.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Initiate IT discovery phase to understand impacts on required changes to systems and define change strategy | Q3 2023-24 | Complete | Q3 2023-24 | Digital, Data & Technology (DD&T) Discovery kicked off on 25th March, having been delayed by 2.5 months due to internal scoping. Expected timescales have increased from 3 to 13 months, leading to delays to associated milestones and the wider programme. The programme has been replanned to be rebaselined, which will be approved at the DER Visibility Steering Committee on 5th April 2024 to return to green.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Complete IT discovery phase and identify costs of implementation | Q4 2023-24 | Complete | Q4 2024-25 | Digital, Data & Technology (DD&T) DER Visibility and Access Discovery has now concluded, which include an expanded scope of also improving the network operator’s access to DERs, leading to delays to associated milestones and the wider programme. The initial Discovery looking at DER assets was completed in September 2024, delayed from July 2024. A separate Discovery looking at Consumer Energy Resources (CER) will follow. due to the nature of the programme and its scope of transformational change in NESO and industry, assessing impact and viability of requirements will need to be iterative as the programme progresseThe NESO DER Tech Impact Assessment is complete. This milestone encompasses both ESO/NESO scope only and excludes any technical impact assessment required of the DNO's, DNO Tech Capability Assessment activity has not started due to delay in DNO support, Whole impact assessment (Tech, Policy, Business) approach work with DNO's via Open Networks DER Technical Working Group is planned from 17th January 2025 for 10 weeks.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Commencement of requirements and design phase to develop detailed IT solution to enable DER visibility | Q1 2024-25 | Complete | Q3 2024-25 | The initial DD&T Discovery looking at DER assets has completed in September, delayed from July, with delivery of captured changes being sanctioned in January 2025. This is due to assumptions within the ESO Tech Impact Assessment highlighting areas that require further confirmation ahead of sanctioning. Enabling work on the detailed IT solution for DER assets will kick off in October 2024, meaning that this milestone will be delayed by c 6 months.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Commence building the storage and transfer capability to utilise bigger volumes of data associated with a larger number of operational metering data points | Q4 2024-25 | Milestone no longer valid |  | Updated: Milestone as articulated in milestone description is no longer appropriate within scope of the TIDE (prev. DER Visibility) programme for BP2 and will not be completed. Decisions on the expansion of data storage infrastrucure will need to be led by NESO IT and informed by the ongoing work to understand data requirements, volumes and storage as well as DER/CER asset data usage across NESO & Industry & consequent solution implementation roadmaps. This work has been progressing as planned in BP2 as described in milestones for IT Discovery above. Specific IT solution(s) that have been identified in the discovery phase will be progressed in the current design phase and ultimately implemented in line with IT infrastructure capability .
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Initiate IT discovery phase for primacy implementation to understand impacts on required changes to systems and define change strategy | Q1 2023-24 | Complete | Q4 2024-25 | We have completed the discovery phase for the implementation of primacy rules. Through this, we have identified the impacted digital infrastructure, scoped key data we'll require, and considered system changes we must make. It provides us with a high level solution for how we'll implement primacy along with indicative costs and timelines. It informs the next more detailed design phase which we'll do in coordination with detailed market design work and continued engagement with the DNOs on data and data exchange.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Complete IT discovery phase and identify costs of implementation | Q2 2023-24 | Complete | Q4 2024-25 | Discovery phase complete
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Commencement of requirements and design phase to implement primacy rules into operational IT systems | Q3 2023-24 | Delayed - Internal Reasons |  | Rules have been developed in collaboration with the DNO's, which has allowed us to progress with the IT discovery phase. This is due to be completed in March-25, and the commencement of the design will follow in April-25.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Continue to lead on Open Networks work to deliver primacy rules | Q3 2023-24 | Complete | Q4 2024-25 | Rules have been developed by Baringa for day ahead services. Whole system CBAs has been developed to determine the best whole system outcome.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Initial operational systems developed for primacy co-ordination based on outputs of requirements and design phase | Q3 2024-25 | Complete | Q4 2024-25 | Rules have been developed by Baringa for day ahead services. Whole system CBAs has been developed to determine the best whole system outcome. Discovery phase for enduring operational systems complete; processes and data exchanges in place in interim.
3 | Net zero operability | D15.9.5 | Provide Early engagement with stakeholders on implementation of technologies required for net zero carbon operation | ESO is supporting stakeholders in implementing new technology developments. Positive feedback from policy makers as applicable | Q4 2024-25 | Complete | Q4 2024-25 | 19/3/25 Throughout 2024-25 we have continued to develop opportunities for new technologies to provide system and energy services as we progress towards net zero. We have developed new markets and services to meet future system needs, whilst opening these up to new technologies and benefitting the end consumer. We have introduced new ways to manage thermal constraints, meet system stability needs, and gain access to wider reactive power capability. We have sought new providers of restoration services on distribution networks and delivered a further response and reserve products suitable for new technologies. We have progressed innovation projects and code changes to provide greater visibility and insight into a system dominated by inverter based resources, and found new ways to access further asset capability. We have worked with DESNZ and industry stakeholders to develop standards for EVs and other Energy Smart Appliances that will ensure they can provide flexibility to the electricity system whilst not creating excessive security risks.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.1 | Year ahead regional outage programmes developed in liaison with network parties. | Deliver regional outage programmes | Q4 2023-24 | Complete | Q4 2023-24 | This is the Year Ahead Plan which is delivered on an annual basis. Its part of plan build process. The plan is an iterative process throughout the year at year ahead timescales and is locked down at week 49 then handed over at week 6 the following year.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.1 | Year ahead regional outage programmes developed in liaison with network parties. | Deliver regional outage programmes | Q4 2024-25 | Complete | Q3 2024-25 | This is the Year Ahead Plan which is delivered on an annual basis. Its part of plan build process. The plan is an iterative process throughout the year at year ahead timescales and is locked down at week 49 then handed over at week 6 the following year.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.2 | Detailed week and day ahead operational documentation produced for National Control | Weekly / Day ahead outage plans | Q4 2023-24 | Complete | Q4 2023-24 | Continuous Activity - this is business as usual planning in the Network Access Planning department. We are obliged to adhere to the STCP 11-1 mandated timescales for communication with customers if they are impacted. We are also obliged to produce an operational plan for our control room. We have provided this operational plan on 100% of the days that we are obliged to.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.2 | Detailed week and day ahead operational documentation produced for National Control | Weekly / Day ahead outage plans | Q4 2024-25 | Complete | Q4 2024-25 | Continuous Activity - this is business as usual planning in the Network Access Planning department. We are obliged to adhere to the STCP 11-1 mandated timescales for communication with customers if they are impacted. We are also obliged to produce an operational plan for our control room. We have provided this operational plan on 100% of the days that we are obliged to.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Stakeholder mapping activities commenced | Q1 2023-24 | Complete | Q1 2023-24 | Started Stakeholder mapping exercise
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Stakeholder mapping activities continued and context communicated to stakeholders | Q2 2023-24 | Complete | Q3 2023-24 | Stakeholder mapping exercise completed. Stakeholders invited to OC2 forum in March, where ESO will present initial concept for discussion.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Organisation of cross industry forum with OC2 attendees to present and hear thoughts | Q3 2023-24 | Complete | Q3 2023-24 | We remain on track for scoping a whole electricity system decision making process. As per the milestone, we delivered an interim OC2 forum in September 2023 and will host a full one in 2024
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | CBA and summary paper written for presentation to industry and ESO senior management | Q4 2023-24 | Complete | Q4 2023-24 | Summary paper written and circulated to ESO Senior Leaders. Provisional CBA produced. To be shared externally in early April.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q1 2024-25 | Complete | Q1 2024-25 | Started Stakeholder mapping exercise.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q2 2024-25 | Complete | Q2 2024-25 | Started stakeholder mapping exercise- 1st milestone complete
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q3 2024-25 | Complete | Q3 2024-25 | Started stakeholder mapping exercise- 1st milestone complete
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Agree framework to facilitate decision making | Q4 2024-25 | Delayed - External Reasons |  | Holistic Decision making template produced and shared with DNOs first. Feedback received from DNOs. in principle, they are supportive of the framework however would require further engagement to refine and implement the process.
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in D16.3.1 and D16.3.2 | Proposals for draft modifications completed | Q4 2023-24 | Complete | Q4 2023-24 | Scoping and proposal documented.
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in D16.3.1 and D16.3.2 | Code modifications finalised for approval | Q4 2024-25 | Delayed - External Reasons |  | Partner DNOs onboard and future process design sessions underway. Risk to full completion due to delay of GC0139 Code Modifications approval.
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | Proposals for frameworks, models and processes completed | Q4 2023-24 | Complete | Q4 2023-24 | Scoping and proposal completed.
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | Frameworks, models and processes completed to facilitate deeper access planning. | Q4 2024-25 | Delayed - Consumer Benefits |  | Partner DNOs onboard and outage and planning data sharing process designs agreed and in development. Development and implementation time slightly longer than anticipated in order to provide a robust, scalable solution. This was originally scoped as a manual data share solution between NESO and DNOs which has already been delivered, however, we collectively are looking to further deliver an automated API supported data exchange solution which will be more robust, enduring and scalable. The API solution development is the reason this deliverable has extended beyond the original March 2025 delivery date with a new expected delivery of the enduring solution in Q1 2025-2026. The initial manual data sharing process has been delivered in March 2025 as proof of concept. This delay will not negatively impact consumers, NESO or DNOs as we have delivered manual data exchanges already and are feeding this development into our ongoing strategic outage planning improvements discussions with DNOs and industry partners.
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Dependent on outcomes of A16.3 deliverables | Q3 2023-24 | Complete | Q4 2023-24 | Work supported by PODE workstream 1. API links between eNAMS outage management app and NGET's NCIS app commissioned both reading and writing data. Delivers resource planning and efficiency savings for the TO. Working with Scottish Power TO on API proof of concept. Exiting Proof of Concept for Conga, an enhanced reporting tool which may enable users to self serve outage queries and analyse outage planning performance. TOs have been provided with access to an ESO outage tracker, the "ROB" (Regional Outage Board) enabling TOs to track the progress of their outage requests through the ESO outage planning process. Activity completed 16 June 2023. Scoping document completed.
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Scoping complete | Q4 2023-24 | Complete | Q4 2023-24 | Duplicate Milestone
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Dependent on outcomes of A16.3 deliverables | Q4 2024-25 | Complete | Q4 2024-25 | Work supported by PODE workstream 1. Activity to deliver ongoing eNAMS improvements ongoing. Scoping complete and design in progress for improved industry-wide outage notifications via eNAMS - delivered in March 2025 release.
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Dependent on outcomes of A16.3 deliverables | Q4 2023-24 | Complete | Q4 2023-24 | Duplicate Milestone.
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Dependent on outcomes of A16.3 deliverables | Q3 2024-25 | Complete | Q3 2024-25 | Work supported by PODE workstream 1. Activity underway and ongoing. Multiple eNAMS improvements and enhancements have been delivered in conjunction with industry third party participants to improve user and customer experience.
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Whole System Outage Notifications in use | Q4 2024-25 | Complete | Q4 2024-25 | The Whole System view and outage alignment is available now via the MWD solution which allows DNOs to take precedence under the Primacy rules and in line with Flex Markets. We are working with partner DNOs to build on and enhance this solution further and have delivered eNAMS functionality to facilitate reporting and visibility on Flex Markets impact on outage placement and management.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q1 2023-24 | Complete | Q1 2023-24 | SANDBOX environment is up and running and in continuous use.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q2 2023-24 | Complete | Q2 2023-24 | SANDBOX environment is up and running and in continuous use.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q3 2023-24 | Complete | Q3 2023-24 | SANDBOX environment is up and running and in continuous use.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q4 2023-24 | Complete | Q4 2023-24 | SANDBOX environment is up and running and in continuous use.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q1 2024-25 | Complete | Q1 2024-25 | We have provided secure, and controlled experimental Sandbox environments. Business users continuously use the platforms for development and testing.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q2 2024-25 | Complete | Q2 2024-25 | Sandbox environment is up and running.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q3 2024-25 | Complete | Q3 2024-25 | Sandbox environment is up and running.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q4 2024-25 | Complete | Q4 2024-25 | Sandbox environment is up and running.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Project delivery timelines and full project plan identified for delivery of contingency analysis automation and automation of multiple cardinal point analysis | Q1 2023-24 | Complete | Q1 2023-24 | We have collaborated with subject matter experts and documented user stories to capture the requirements. Additionally, we have developed a project plan to ensure the delivery of these requirements.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Proof of concept for agreed automation commenced | Q2 2023-24 | Complete | Q2 2023-24 | This part of work is completed.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Proof of concept for automation completed | Q3 2023-24 | Complete | Q3 2023-24 | We have completed the scoping and are preparing for delivery.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training programme for teams in NAP developed and delivery schedule planned | Q4 2023-24 | Complete | Q4 2023-24 | Training has already started with multiple session organised across networks. This will be a continuous activity as planned.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools underway. | Q1 2024-25 | Complete | Q1 2024-25 | Training has already started with multiple session organised across networks. This will be a continuous activity as planned.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q2 2024-25 | Complete | Q2 2024-25 | We have already organised multiple training sessions across networks. This will be a continuous activity.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q3 2024-25 | Complete | Q3 2024-25 | Training has already started with multiple session organised across the business. This will be a continuous activity.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q4 2024-25 | Complete | Q4 2024-25 | Training has already started with multiple session organized across networks. This will be a continuous activity.
3 | Network Planning Review | N/A | Network Planning Review | Development of a centralised strategic network planning methodology is complete. | Q4 2024-25 | Delayed - External Reasons |  | Development of the CSNP methodology, continues in collaboration with Ofgem and other key stakeholders continued throughout this period with the commencement of the working groups. Revised completion date agreed with Ofgem (and set out in licence conditions), due to interactions with other spatial plans and connection reforms. Consultation on draft methodology will be published by end of June 2025
3 | Offshore Coordination | N/A | Offshore Coordination | ESO activities in the Offshore Transmission Network Review timeline are delivered to the agreed timescales and quality. | Q4 2024-25 | Complete | Q3 2024-25 | On Track based on the plan
2 | Deliver an enhanced platform for EMR | D5.2 | Deliver an enhanced platform for EMR | User familiarisation completed for initial release, with system go live for CM Process. Using portal and data to increase automation of ESO processes to improve efficiency and information available to industry. Guidance to rule changes are incorporated into Portal. The EMR Portal will allow disputes to be linked directly to relevant Applications | Q1 2024-25 | Complete | Q1 2024-25 | The New Portal was fully implemented for Capacity Market processes on 17th June. User familiarisation was run between mid March to mid April. 63 users representing nearly 300 different companies participated. An integrated guidance platform has been implemented alongside the new portal with guidance accessible via direct links from the system or via a guidance website.. Prioritised improvements have been designed in processes to enable increased automation and enhanced customer journeys. The Prequalification Disputes process has been designed and implemented to enable an improved customer journey for Disputes to be raised and tracked against associated Prequalification Application.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Regulatory changes implemented for annual processes in current EMR Portal. | Q2 2023-24 | Complete | Q2 2023-24 | Changes from the DESNZ consultation were implemented in the portal prior to the Prequalification round opening in July 2023.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Regulatory changes implemented for annual processes. | Q2 2024-25 | Complete | Q2 2024-25 | We worked with the DESNZ team to assess and agree changes required to deliver items of work included in the scope of their CM2023 Phase 2 consultation. The change scope was updated based on the impact of the election on regulatory approval processes, with the agreed changes Implemented in August 2024. We also implemented functionality to deliver changes to metering processes in accordance with CP373 from the Ofgem CM consultation. Ofgem published their approved decision on 14th June.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Deliver planned integration of EMR within the Digital Engagement Platform, considerate of any licensed business separation requirements. Additional improvements to EMR portal to enhance customer experience, following customer feedback. Assessment of delivery options for the Contracts for Difference (CfD) scheme delivery in accordance with REMA proposals. | Q4 2024-25 | Complete | Q4 2024-25 | DEP Integration has been enabled for EMR via implementation of the Customer Identity Access Management (CIAM) solution on 18th March 2025. The Delivery Body have designed a prioritisation approach with the dedicated customer user group, to support recommendations for enhanced customer experience and are publishing a customer improvement backlog on our website. Improvements focus areas for Q4 were presented in the January user group and implemented on 18th March, largely focused on improvements to application validations for CM Prequalification The first formal customer feedback point was completed post PQ application phase in November 2024. 36 customers responded to the survey with a median score of 7.5/10 in their rating of overall experience in using the new portal. A further feedback point is expected to be run in Q1 FY26. The Delivery Body have worked with DESNZ to monitor REMA proposals to support decisions on future CfD system landscape. In their REMA Autumn update DESNZ confirmed that there would be no material change to the CfD mechanism until at least AR9, with REMA options focused on enhanced pot structures and participation rather than wholesale change to the application and allocation framework. AR7/8 and 9 are crucial rounds for supporting governments Clean Power 2030 policy objectives, therefore in BP3 we have proposed delivery of enhancements to the current CfD portal to ensure stability and avoid diverting resources or disrupting the industry with a new system solution. The closure of this assessment will be reported within the Cost Monitoring Framework (CMF) for March 2025.
3 | Connections Reform | D14.5.1 | Five Point Plan | TEC Amnesty implement terminations. Queue management CUSC mod with Ofgem for a decision. CPA review and non firm offers for storage in progress, working with the TO's to deliver this. | Q2 2023-24 | Complete | Q2 2023-24 | As part of ESO's 5 point plan for connections, we have issued 4.1 GW of contract terminations / TEC reductions in response to customer expression of interest. We submitted CMP376 to Ofgem for decision (recommending adopting queue management milestones to connection contracts).
3 | Connections Reform | D14.5.1 | Five Point Plan | Queue Management: Issue Notice to Industry to start implementation phase. Accelerated non-firm offers for storage: Revised offers issued to 10GW (phase1) | Q3 2023-24 | Complete | Q3 2023-24 | Notice issued 27 November 2023 to all customers with connection dates of November 2025 or later. Customers have 6 months to respond and request a Mod App to delay their connection date or queue management milestones will be applied to their existing agreement. Phase 1 accelerated non-firm offers issued to 20 storage projects (9.3GW) in England & Wales which submitted an expression of interest.
3 | Connections Reform | D14.5.1 | Five Point Plan | Two-step offers: 2nd step offers issued to all participating customers in England & Wales Queue management: Share outcome of CMP376 6-month notice to industry (number of projects / GW seeking to delay connection date versus number of projects / GW to have milestones added to their existing connection agreement. Accelerated non-firm offers for storage: Tranche 2 communicated plan with industry. | Q1 2024-25 | Complete | Q1 2024-25 | All two-step offers were issued by the end-of May to affected customers in England & Wales. Queue management implementation in progress: customers had until 27 May to confirm whether they want to mod app to delay their connection date or have queue management milestones applied to their existing connection date. The number of customers within each of these categories is being shared at the June CDB and CPAG meetings. ESO is working with NGET and SSENT to confirm the customer projects to be included within Phase 2 for delivery by September. SSENT has confirmed the details of the projects to be included. SPT has advised that no projects that submitted an EoI can be accelerated on a non-firm basis.
3 | Connections Reform | D14.5.1 | Five Point Plan | CPAs and Transmission Work Review: revised offers issued to customers seeking acceleration (where studies identify this is possible) Accelerated non-firm offers for storage: Revised offers issued to Phase 2 customers | Q2 2024-25 | Complete | Q2 2024-25 | Set as Low confidence as the revised offers have not been issued for the projects expressing interest in accelerated connection dates following adoption of revised modelling assumptions. For acceleration of storage projects through the use of non-firm offers, Phase 2 projects in England and Wales have not been issued. We are working with the Transmission Owners on both of these projects to propose plans to complete/close these projects.
3 | Connections Reform | D14.5.1 | Five Point Plan | Quantification of the initial impact of CMP376 (queue management) implementation | Q3 2024-25 | Complete | Q3 2024-25 | We are tracking implementation of queue management milestones. We report progress monthly via the connections data book and through Connections Delivery Board's monthly reporting pack. This includes the number of projects with queue management milestones applied and the number of projects where queue management milestones have not yet been applied.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | High-level design options developed and consultation launched including recommended reform option | Q1 2023-24 | Complete | Q1 2023-24 | Connections Reform Phase 2 high level design developed and consultation published in June.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | Consultation closed and stakeholder feedback reviewed to refine reform proposal | Q2 2023-24 | Complete | Q2 2023-24 | Consultation closed as scheduled and responses collated and reviewed to refine the reform proposal.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | Complete Phase 2 - Final recommendations and indicative implementation plan published | Q3 2023-24 | Complete | Q3 2023-24 | Final recommendations published in December 2023.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Mobilise ESO Connections Change Delivery activity to align with Connections Action Plan. Implement voluntary Letter of Authority Develop transparent/faster process to assess and convey the transmission impacts of distribution connections Flexible connections and management of distribution connections within agreed 'technical limits' across all GSPs Detailed reporting of connections data | Q3 2023-24 | Complete | Q3 2023-24 | Following November publication of the Ofgem/DESNZ Connections Action Plan we mobilised the team and assigned responsibilities for each ESO-assigned action within CAP. We implemented a voluntary Letter of Authority into the Connection Application process. We continued engagement with DNOs through the Strategic Connections Group on the development of a Distribution Forecasted Transmission Capacity approach. Technical Limits Phase 1 completed and a Connection Databook developed for reporting detailed connections data.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Establish plans, instigate workstreams for ESO-led actions. Consult industry stakeholders through CPAG and CDB Deliver CAP Q1 2024 milestones: Letter of Authority Code Mod proposal Further proposals to raise entry requirements Recommendations to improve certainty and progression of customers holding capacity Recommendations to optimise existing network capacity Review scope for improvements in CPAs for optimised planning Review scope of enabling works Recommendations to effectively allocate network capacity released in the short term Signposting a single digital view of network data for connection customers Detailed reporting of connections data. | Q4 2023-24 | Complete | Q4 2023-24 | Workstream established for ESO-assigned actions within CAP with progress updates and papers for review submitted to CPAG and CDB. CPAG met 5 times in Q4 and CDB 3 times. The Letter of Authority code mod was submitted and approved. Options to raise entry requirements and to improve certainty of progression of customers holding capacity both addressed through recommending extending Gate 2 of reformed process to the existing queue. Recommendations for improvements to CPAs for optimised planning and to review the scope of enabling works presented to CPAG as part of Package 2 recommendations. Recommendation for capacity reallocation developed and presented to CPAG and CDB. ESO's 'Connections 360' tool to provide a single digital view of the network for connections customers developed and shared at CPAG and CDB. Detailed reporting of connections data continues on a monthly basis. Detailed reporting of connections data continued through the monthly Databook.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Deliver CAP Q2 2024 milestones: Consider further letter of authority actions Recommendations for longer-term approach to allocate capacity complementing strategic network planning Detailed reporting of connections data Develop delivery plans and mobilise activity according to outcome of the Q4 (2023-34) milestones and recommendations | Q1 2024-25 | Complete | Q1 2024-25 | Connections Reform and Change Delivery activity continues to deliver CAP milestones. The Letter of Authority Phase 2 proposal went to Connections Delivery Board in May, who provided a steer and next steps are in delivery. We continue to work with Ofgem, DESNZ and TOs to consider recommendations for 2025 and beyond that go beyond TMO4+ and look to align more closely with strategic network planning. Monthly connections data reporting continues. We have worked with ENA, Ofgem and DESZ to revise the CAP delivery plan in light of the outcome of the March 2024 milestones. The revised plan was presented to the May CDB meeting.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Detailed reporting of connections data Continued delivery of activity according to outcome of Q4 (2023-24) milestones and recommendations | Q2 2024-25 | Complete | Q2 2024-25 | Monthly connections data reporting continues. We continue to report progress against all of ESO's remaining Connections Action Plan Actions within the monthly CDB reporting pack.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Detailed reporting of connections data Continued delivery of activity according to outcome of Q4 (2023-24) milestones and recommendations | Q3 2024-25 | Complete | Q3 2024-25 | Monthly connections data reporting continues. We continue to report progress against all of ESO's remaining Connections Action Plan Actions within the monthly CDB reporting pack. This includes agreeing with CDB a revised approach to tracking CAP actions that are now being progressed through the TMO4+ connection reform proposals.
3 | Connections Reform | D14.5.3 | Connections Action Plan - ESO delivery | Detailed reporting of connections data Continued delivery of activity according to outcome of Q4 (2023-24) milestones and recommendations | Q4 2024-25 | Complete | Q4 2024-25 | Monthly connections data reporting. March submission (with data to the end of February 2025, submitted 14 March 2025). We have continued to report progress against all of ESO's remaining Connections Action Plan Actions within the monthly CDB reporting pack. This includes agreeing with CDB a revised approach to tracking CAP actions that are now being progressed through the TMO4+ connection reform proposals.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Indicative implementation plan developed | Q2 2023-24 | Complete | Q2 2023-24 | Indicative implementation plan developed and published within consultation document.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Implementation Phase begins. Process mapping and detailed design underway | Q3 2023-24 | Complete | Q3 2023-24 | We mobilised the Implementation Phase as soon as the Phase 2 Final Recommendations were published in December 2023.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Identify licence and code changes required for agreed reforms. | Q4 2023-24 | Complete | Q4 2023-24 | Code Changes identified for the agreed reforms. We also shared our recommended strategy for the structure of the required code modifications with the Connections Process Advisory Group. Licence change assessment ongoing into Q1 2024-25
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Complete detailed design and process mapping for the reforms to be implemented Raise code changes at Code Panel(s) | Q1 2024-25 | Complete | Q1 2024-25 | End-to-end process mapping developed for the reformed connections process and under internal review. Code changes for TMO4+ raised in May and Ofgem has granted use of the urgency process.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Code changes progressing through working groups. | Q2 2024-25 | Complete | Q3 2024-25 | We submitted the code modifications and related methodologies to Ofgem 20 December, closing this milestone
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Code changes progressing through working groups. Licence changes complete | Q3 2024-25 | Delayed - External Reasons |  | No confidence on completion this BP as Ofgem's latest view is that their decision on Licence changes will be made in mid April 2025. 14 February 2025 Ofgem published its minded to decision with a consultation running until 14 March before it will consider responses and reach a decision. Following that a 56 day stand-still is required before licence changes go-live.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 3 | Reformed connections process goes-live. First connection application window opens. | Q4 2024-25 | Delayed - External Reasons |  | No confidence in Go-Live in Q4 as Ofgem has indicated its decision on the code mods, licence changes and methodologies will now happen in mid April 2025. 14 February 2025 Ofgem published its minded to decision with a consultation running until 14 March before it will consider responses and reach a decision. Following that a 56 day stand-still is required before licence changes go-live. The first application window can only open following the 56 day period