## CUSC Prioritisation
CUSC Prioritisation Criteria |  |  |  | Prioritiy Category (Modifications are listed in numerical order within their priority category)
Section 8: 8.19.1.(e) makes the following provision for the Panel and states “Having regard to the complexity, importance and urgency of particular CUSC Modification Proposals, the CUSC Modifications Panel may determine the priority of CUSC Modification Proposals and may (subject to any objection from the Authority taking into account all those issues) adjust the priority of the relevant CUSC Modification Proposal accordingly” |  |  |  | High
Complexity | The modification is viewed as being resource intensive and will most likely require a higher than average number of workgroups to conclude the process. Additionally, the modification defect is viewed to have implications for many different areas of the energy market which need to be taken into consideration throughout the process. |  |  | Medium to High Medium
Importance | The perceived value & risk associated with the proposed modification. The value / risk could be considered from a number of different perspectives i.e. financial / regulatory / licence obligations both directly for customer and end consumers more generally. |  |  | Low to Medium Low
Urgency | A modification which requires speedy consideration within the code governance process, both complexity and importance should be factors considered in evaluating urgency as well as the timescales for implementation within the respective code.
Priority Category | Mod Number | Title | Previous Priority Category (changes highlighted in blue) | Panel Comments on Prioritisation as of 28 July 2023 | Proposer Organisation
High | CMP315 and CMP375 | TNUoS: Review of the expansion constant and the elements of the transmission system charged for (CMP315) Enduring Expansion Constant & Expansion Factor Review (CMP375) | High | • Panel recognised there is a material impact here; however, argued that need to understand the TCR outcome before progressing further This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. November 2020 Panel agreed to move CMP315 from “Low to Medium” to “High” in light of recent developments re: the Expansion Constant. ESO's modification re: the wider solution on the Expansion Constant (CMP375) was presented to the June 2021 Panel. Panel agreed that CMP315 will be progressed in parallel with CMP375 (rather than be formally amalgamated) with Workgroups on the same day. Panel noted that CMP375 is a complex change and agreed that it is better to commence this as soon as possible and provide clarity for stakeholders on the future of the Expansion Constant and placed this “High” in the prioritisation stack. Given the interaction with CMP315, CMP315 will remain high in the prioritisation stack. Workgroups recommenced on 10 August 2021. | PeakGen (CMP315) ESO (CMP375)
High | CMP408 | Allowing consideration of a different notice period for BSUoS tariff settings | High | Given the high materiality and industry interest, Panel believed a High priority was appropriate. | ESO
High | CMP415 | Amending the Fixed Price Period from 6 to 12 months | High | Given the intrinsic links to CMP408 Panel placed this in the High Priority Category | ESO
Medium to High | CMP328 | Connections Triggering Distribution Impact Assessment | Medium to High | Although this was prioritised as "High" when originally progressed, there was challenge that the materiality is not as high as when originally progressed. However, as the Workgroup are reconvening following an Authority send-back, Panel on balance was felt that this should have a Medium to High priority. | Scottish and Southern Energy Power Distribution Limited
Medium to High | CMP396 | Re-introduction Of BSUoS on Interconnector Lead Parties | Medium to High | August 2022 Panel placed as “Medium to High” in the prioritisation stack because there appears to be direct impact on competition and the end consumer. However, the Panel agreed that independent legal advice needs to be commissioned first as important to determine whether or not this proposed change is legally permissible. Panel also set a revised Terms of Reference on this basis and requested that the 1st Workgroup develop and agree the request for legal opinion which would then be issued to an independent QC. Once the QC opinion has been finalised, this will be issued to Panel, who would then revise Terms of Reference and review current “Medium to High” priority | Saltend Cogeneration Company Ltd
Medium to High | CMP402 | Introduction of Anticipatory Investment (AI) principles within the User Commitment Arrangements | Medium to High | Given the high materiality and that this is the first of a number of changes in this area, this was placed as “Medium to High” in the prioritisation stack | ESO
Medium to High | CMP411 | Introduction of Anticipatory Investment (AI) within the Section 14 charging methodologies. | Medium to High | Panel believed this should be prioritised alongside CMP402 (as this also relates to Anticipatory Investment) and therefore a Medium to High priority was agreed | ESO
Medium to High | CMP413 | Rolling 10-year wider TNUoS generation tariffs’ | Medium to High | Panel recognised the materiality for TNUoS bill payers and complexity and the Proposer's desire for as early implementation date as possible (ideally 1 April 2024). However, Panel did recognise that 1 April 2025 was the earliest realistic implementation date, which means more time potentially available to assess, and there are other areas looking at similar topics. Therefore, on balance, Panel agreed to place as "Medium to High" in the prioritisation stack. | EDF Energy
Medium to High | CMP417 | Extending principles of CUSC Section 15 to all Users | Medium to High | Panel agreed to place within the 'Medium to High' priority category due to being part of the Connections reform package and the potential benefits to demand customers. | ESO
Medium to High | CMP419 | Generation Zoning Methodology Review | New modification | Given the complexity of the defect, the potential for several alternative solutions and the advantage of an early decision on re-zoning for investors, this was placed as “Medium to High” in the prioritisation stack | ESO
Medium | CMP286/ CMP287 | Improving TNUoS Predictability through Increased Notice of the Target Revenue (CMP286) and Inputs (CMP287) used in the TNUoS Tariff Setting Process | Medium | Ofgem sent back on 30 June 2023, at the July 2023 CUSC Panel, it was agreed to return the modification to the same priority it was given prior to submission of the FMR. | E.ON
Medium | CMP304 | Improving the Enhanced Reactive Power Service by making it fit for purpose | Medium | • Modification seeks to apply a different timescale to the provision on reactive power – Panel divided though on whether this is a simple change as solution still needs to be clarified • Ofgem cannot make a final decision on CMP305 until CMP304 is completed • Decreased cost to consumers if more competition This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. Workgroups recommenced on 8 November 2021. Prioritisation was discussed at October 2022 Panel and priority was not changed, as there remains a need for reactive services. However, the Panel (and Proposer) agreed that work on CMP304 is paused until such time that the ESO team, who are leading on the Reactive Reform (Market Design), have completed their Feasibility studies, which in turn will help to inform the Proposer's solution. July 2023 - Proposer and ESO Panel Rep to review the output of Phase 1 of the ESO's feasibility studies ahead of reconvening the Workgroup | SSE Generation
Medium | CMP392 | Transparency and legal certainty as to the calculation of TNUoS in conformance with the Limiting Regulation | Medium | Panel agreed that CMP392 will be placed as “Medium” in the prioritisation stack noting there is a potential compliance risk but some Panel Members argued that materiality is low and therefore on balance agreed a "Medium" priority. | SSE Generation
Medium | CMP393 | Using Imports and Exports to Calculate Annual Load Factor for Electricity Storage | Medium | Panel agreed that CMP393 will be placed as “Medium” in the prioritisation stack as although there could be a high materiality and complexity (given the analysis required), some Panel Members noted it may be prudent to wait for the TNUoS Taskforce to meet and agree high-level principles. On balance, Panel agreed a "Medium" priority. | Zenobe
Low | CMP291 | The open, transparent, non discriminatory and timely publication of the harmonised rules for grid connection (in accordance with the RfG, DCC and HVDC) and the harmonised rules on system operation set out within the Bilateral Agreements | Low | • Complex change • Enduring requirement but no compliance date set This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At June 2021 Panel, Panel discussed the interaction with GC0117 and Code Admin confirmed with the Grid Code Review Panel ESO representative confirmed that progression of GC0117 is not dependent on CMP291 progressing . Therefore, CMP291 will remain “Low” in the prioritisation stack. At the last quarterly prioritisation deep-dive (October 2022 Panel), no case was presented to change the priority. | SSE Generation
Medium | CMP405 | TNUoS Locational Demand Signals for Storage | Medium | As this is being developed in parallel with CMP393, Panel placed CMP405 at the same “Medium” priority as CMP393 | SSE Generation
Medium | CMP418 | Refine the allocation of Static Var Compensators (SVC) costs at OFTO transfer | New modification | Whilst some Panel Members thought that based on the complexity, importance and urgency of the modification it should be considered as ‘Medium to High’ or ‘High’. The majority agreed that it should be placed as ‘Medium’ in the prioritisation stack. | Ocean Winds
Low | CMP341 | CUSC Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions | Low | • Complex • Although a CACOP and Ofgem driven initiative, there does not appear to be any current industry appetite to progress This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At the last quarterly prioritisation deep-dive (October 2022 Panel), no case was presented to change the priority. | ESO