## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | DG | Provide views to ESO on potential anomalies in charging methodology | Update provided within slides 7/8 of the Workgroup Meeting 3 Papers | WG3 | Closed | WG3
2 | WG1 | NP | Investigate with Revenue as to whether implementation date can be moved forward, or provide justification if not | Implementation agreed to be moved to 01 April 2026. | WG2 | Closed | WG2
3 | WG1 | NP | Investigate who is responsible for Governance of ETYS boundaries and how many new boundaries have been created in the past 10 years | No specific no codes or formal governance for ETYS boundaries but: - JPC discuss ETYS boundaries with the TO, which has subgroups including Investment Planning, Modelling and ETYS - STC governs the discussions and the relationship between the ESO and the TOs. In the last 10 years one boundary has been created approximately every 2 years. | WG2 | Closed | WG2
4 | WG1 | NP | Investigate potential effect on boundaries if constraints are removed by the bootstrap. Also look into expected trajectory of constraints. | Update provided within slides 9 of the Workgroup Meeting 3 Papers | WG2 | Closed | WG3
5 | WG1 | NP | Circulate a document which provides an overview of the ETYS Boundaries and ETYS Zones | Shared within Workgroup Meeting 2 Papers - Document provides detail in pages 4 and 6 | WG2 | Closed | WG2
6 | WG1 | ML | Create Microsoft Form for Workgroup members to feed interactions into | Link shared in WG1 Summary | WG2 | Closed | WG2
7 | WG2 | NP | Clear usable map illustrating ETYS zones (Shape file, zoomable, more interactive the better). | Update provided within slide 9 of the Workgroup Meeting 3 Papers | WG3 | Closed | WG3
8 | WG2 | NP | ETYS boundaries and zones on one map. | Update provided within slide 9 of the Workgroup Meeting 3 Papers | WG4 | Closed | WG3
9 | WG2 | AH | Circulate CMP324/325 documentation links with Workgroup. | CMP324/325 Modification page | WG5 | Closed | WG3
10 | WG2 | AH | Circulate “Approach to understanding generation rezoning” document link | “Approach to understanding generation rezoning” document link | WG6 | Closed | WG3
11 | WG2 | NP | ESO Revenue team to attend WG4 and present analysis. |  | WG5 | Closed | WG5
12 | WG2 | NP | Look at CUSC 14.15.12 and investigate if this could be used. | Update provided within slide 10 of the Workgroup Meeting 3 Papers | WG8 | Closed | WG3
13 | WG3 | PA | Confirm the Authority position around policy and workgroup work |  | WG5 | Closed | WG5
14 | WG3 | NP/RP | ESO to liaise with the TOs to obtain coordinates for each transmission node | SSEN Data shared with workgroup previously, awaiting update on SP Energy Networks | WG4 | Open
15 | WG3 | NP | Share list of the transmission nodes and the ETYS zone they sit in with the Workgroup | Will be provided before the next workgroup in March. | WG5 | Closed | WG5
16 | WG3 | NP | Confirm with Revenue Team that the analysis will: - Be inclusive of data until the end of RIIO3 - show the existing generation zone and the new generation zone as per the proposal under CMP419 for each generator (including a table similar to CMP324 on the TEC Register) - show how the reactance has been calculated for HVDC circuits - demonstrate the changes to the model required for CMP419 (to allow replication) | Update provided on slide 12 of the Workgroup Meeting 4 Papers | WG4 | Closed | WG4
17 | WG3 | NP | Confirm that alongside the published analysis a copy of the transport and tariff model will be provided to WG members | This was followed up directly with members after WG5. A Licence Agreement is required to be signed (once per company) to access transport and tariff model. Licence Agreement has been included with WG6 documents for anyone who is yet to gain access | WG4 | Closed | WG6
18 | WG3 | NP | Confirm whether it is possible to share a list of nodal prices for all generators by generation zone, or whether the ESO only have a price per ETYS zone | Update provided on slide 13 of the Workgroup Meeting 4 Papers | WG4 | Closed | WG4
19 | WG3 | NP | Confirm whether the methodology and assumptions being used as part of the analysis will be available to share with the Workgroup ahead of the analysis taking place | Will be provided before the next workgroup in March. | WG5 | Closed | WG5
20 | WG3 | All | Share any potential alternative requests | There are currently no potential alternative requests | 2024-01-09 | Closed | WG4
21 | WG4 | TE/SC | After receiving examples of inconsistencies between the July and December Transport Models (TE) provide feedback on changes (SC) |  | WG5 | Closed | WG5
22 | WG4 | SC | Look into interactive nodal 10-year map |  | WG5 | Closed | WG5
23 | WG4 | SC | Confirm whether requested elements can be included in analysis: - Connectivity matrix - Year and non year-round split - Cost reflectivity |  | ASAP | Closed | WG5
24 | WG5 | MC/SC | Confirm whether there is still a requirement for Transport Model access to be monitored via an NDA process | NESO position is that this is still required | WG6 | Closed | WG6
25 | WG5 | SC | To share the map they created as part of Action 19 | Included in WG6 documents | WG6 | Closed | WG6
26 | WG5 | SC | Add key and numbering to zones on the Connection Map | Included in WG6 documents | WG6 | Closed | WG6
27 | WG5 | SC | Complete a comparison of zone profiles based on the average difference year round versus average difference peak security | Comparison included in WG6 slides | WG6 | Closed | WG6
28 | WG5 | SC | Include generational technology impact | Need to understand request for this in more detail | WG6 | Closed | WG6
29 | WG5 | MC | Confirm to Workgroup the scope of the modification on onshore and offshore | Will be covered in WG6 discussions | WG6 | Closed | WG6
30 | WG5 | MC | Confirm to whether changing the T’n’T model is in scope for this modification | This is currently not in scope | WG6 | Closed | WG6
31 | WG6 | MC | Provide additional analysis incl most affected Generators and what effect it has, and impact on zones and range of nodal prices. |  | WG7 | Open
32 | WG6 | MC | Investigate ETYS changes with HND and whether this is forward looking |  | WG7 | Open
33 | WG6 | MC/NL | Catch up regarding analysis issues and investigate subjectivity in connectivity matrix |  | WG7 | Open