## LLFC Transfers
TCR Implementation Plan: Timeline for MDD Changes and LLFC Migration Activity | [6 empty] | Last updated: 28/01/2022 |  | Nov '20 |  |  |  |  | Dec |  |  |  | Jan '21 |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan
[9 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 5
ID | LDSO | Activity | Contact | Start Date (Publish) | End date (Go-live) | WD | Rate | Status | 2020-11-02 | 2020-11-09 | 2020-11-16 | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08 | 2021-02-15 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31
M1 | ENWL | MDD Version 303: NORW and ETCL | Sarah Ross | 2020-10-14 | 2020-10-21 | 1 | N/A | Complete
M2 | BUUK | MDD Version 304: IPNL | Sarah Ross | 2020-11-11 | 2020-11-18 | 1 | N/A | Complete
M3 | NPG,WPD,UKPN,SPEN,SSEN | MDD Version 306: All DNO regions | Sarah Ross | 2021-01-13 | 2021-01-20 | 1 | N/A | Complete
M4 | N/A | MDD Version 307: likely no TCR MDD Changes | Sarah Ross | 2021-02-10 | 2021-02-17 | 1 | N/A | Complete
M5 | N/A | MDD Version 308: likely no TCR MDD Changes | Sarah Ross | 2021-03-10 | 2021-03-17 | 1 | N/A | Complete
M6 | TBD | MDD Version 310: likely no TCR MDD Changes | Sarah Ross | 2021-04-14 | 2021-04-21 | 1 | N/A | Complete
M7 | TBD | MDD Version 311: likely no TCR MDD Changes | Sarah Ross | 2021-05-12 | 2021-05-19 | 1 | N/A | Complete
M8 | TBD | MDD Version 312: likely no TCR MDD Changes | Sarah Ross | 2021-06-09 | 2021-06-16 | 1 | N/A | Complete
M9 | TBD | MDD Version 313: likely no TCR MDD Changes | Sarah Ross | 2021-07-14 | 2021-07-21 | 1 | N/A | Complete
M10 | TBD | MDD Version 314: likely no TCR MDD Changes | Sarah Ross | 2021-08-11 | 2021-08-18 | 1 | N/A | Complete
M11 | TBD | MDD Version 315: FORB, UKPD, PENL, INDI, UDNL, VATT, HARL | Sarah Ross | 2021-09-15 | 2021-09-22 | 1 | N/A | Complete
M12 | TBD | MDD Version 316: GGEN, GUCL, INDI, FORB, HARL | Sarah Ross | 2021-10-13 | 2021-10-20 | 1 | N/A | Complete
M13 | TBD | MDD Version 317: LENG, MPDL, HYDE, SOUT, FEAL, LENG E63 end-dated | Sarah Ross | 2021-11-10 | 2021-11-17 | 1 | N/A | Complete
M14 | TBD | MDD: Version 318: FORB, LENG (end-dating remaining) | Sarah Ross | 2021-12-15 | 2021-12-22 | 1 | N/A | Complete
Elexon led testing of Central Systems, Industry Systems and Internal Applications
C1 | N/A | Central System Testing: Testing of enlarged MDD files to ensure Settlement process are not impacted | Karen Lavelle | 2021-01-06 | 2021-03-28 | 58 | N/A | Complete
C2 | N/A | Industry/Participant Testing: Testing of enlarged MDD files to ensure Settlement process are not impacted | Karen Lavelle | 2021-02-10 | 2021-02-23 | 10 | N/A | Complete
Elexon IT changes to Central Systems and Internal Applications
C3 | N/A | IT development: System improvements to Central Systems | Elexon | 2021-04-01 | 2021-07-01 | 17 weeks | N/A | Complete
Indicative LLFC Transfers |  |  |  | Start Date | End date
T1 | ENWL | ENWL LLFC Transfers (NORW) | Tony McEntee | 2021-01-11 | 2021-02-15 | 26 days to transfer | 3k/day | Complete
T2 | BUUK | BUUK LLFC Transfers (IPNL and ETCL) | Tom Cadge | 2021-03-05 | 2021-03-14 | 2 working days to transfer 10 calendar days | 15k / day | Complete
T3 | ENWL | ENWL LLFC Transfers (NORW) | Tony McEntee | 2021-04-01 | 2021-04-08 | 6 working days | 3k/day | Complete
T4 | ENWL | ENWL LLFC Transfers (NORW) | Tony McEntee | 2021-04-21 | 2021-04-21 | 1 working day | 3k/day | Complete
T5 | NPG | NPG LLFC Transfers (NEEB/YELG) | Leanne Yates | 2021-04-05 | 2021-05-11 | 20 days to transfer +5 days to avoid billing | 14k / day | Complete
T6 | WPD | WPD LLFC Transfers (EMEB/MIDE/SWEB/SWAE) | Dave Wornell | 2021-05-12 | 2020-05-26 | 6 days to transfer + 5 days to avoid billing | 80k/day (20k/day per region) | Complete
T7 | UKPN | UKPN LLFC Transfers (EELC/SEEB/LOND) | Chris Ong | 2021-06-14 | 2021-07-09 | 15 days to transfer +5 days to avoid billing | 60k/day for first 10 days (20k/day per region) 20k/day for final 10 days | Complete
T8 | SPEN | SPEN LLFC Transfers (SPOW/MANW) | Elaine Carr | 2021-05-27 | 2021-06-11 | 7 days to transfer +5 days to avoid billing | 40k / day x 5 (20k/day per region) 31k /day x 1 17k/day x 1 | Complete
T9 | SSEN | SSEN LLFC Transfers (HYDE/SOUT) | Donald Preston | 2021-07-05 | 2021-08-16 | 26 days to transfer + 5 days to avoid billing | 15k / day | Complete
T10 | Last Mile | Last Mile LLFC Transfers (GUCL) | Morven Hunter | 2021-12-01 | 2022-02-04 | 15 days to transfer | 18.5 k / day | On track
T11 | Vattenfall | Vattenfall LLFC Transfers (VATT) | Darren Reeve | 2021-10-04 | 2021-10-20 | 1 working day + 3 for contingency | Up to 100s / day | Complete
T12 | Energy Assets | Energy Assets LLFC Transfers (UDLN) | Donna Townsend | 2021-10-04 | 2021-10-29 | 1 Working Day |  | Complete
T13 | UK Power Dist | UK Power Distribution LLFC Transfers (UKPD) | Alistair Johnson | 2021-11-01 | 2021-11-12 | 1 working day |  | Complete
T14 | Eclipse | Eclipse LLFC Transfers (GGEN) | Sarah Owen | 2021-11-01 | 2021-12-03 | 15 | 150 total | Complete
T15 | Forbury Assets | Forbury Assets LLFC Transfers (FORB) | Alan Fradley | 2021-10-25 | 2021-12-31 | 15 |  | Complete
T16 | Espug | ESP Electricity LLFC Transfers (LENG) | Amy Penny | 2021-12-20 | 2021-12-31 | 5 working days + 3 for contingency | 8100 total | Complete
T17 | Harlaxton | Harlaxton LLFC Transfers (HARL) | Edward Hardy | 2022-02-01 | 2022-02-01 | 2 | 260 total | On track
T18 | Leep Utilities | Leep Utilities LLFC Transfers (PENL) | Will Ellis | 2021-09-22 | TBD | 5 | 7k total | On track
T19 | Indigo | Indigo LLFC Transfers (INDI) | Megan Goss | 2021-10-21 | 2021-11-09 | 5 | TBD | Complete
T20 | Fulcrum | Fulcrum LLFC Transfers (FEAL) | Kevin Mukuzvazva | 2022-01-04 | 2022-01-26 | 5 | TBD | Complete
T21 | Murphy G. | Murphy Group LLFC Transfers (MPDL) | Stuart Monk | 2022-01-24 | 2022-02-04 | 10 | Up to 100s / day | On track

## Assumptions
TCR Implementation Plan: Assumption List
Plan Notes | 1. The dates in the plan are subject to change; 2. The dates of the LLFC transfers are highly dependent on the MDD changes being processed, approved, and released to the dates set out in the plan; 3. This plan will be monitored and updated as required, updated plans will be issued by LDSOs on a 4 weekly basis from January onwards, up until the LLFC transfers are complete.
ID | Planning Assumptions | Status
A1 | Transfer volumes and rates per day are being finalised and so are subject to change
A2 | BSC Panel will approve all DNO MDD CRs in December, for implementation in January (MDD V306). If this decision is deferred then we will undertake a replan with the LDSOs and Elexon. | Closed
A3 | Elexon are working with their Service Providers and industry to confirm the plan and timeline for the testing activity. The dates in this plan are therefore subject to change. Elexon are anticipating publishing a testing timeline in early December. | Closed
A4 | Elexon Central System Testing and Industry Testing would need to complete in March with no outstanding issues in order for the IDNO changes to be published in MDD Version 310. | Closed
A5 | SVG / BSC Panel will begin to approve the IDNO MDD CRs in April, in time for publication in MDD V310. | Closed
A6 | The IDNO CRs can be processed and released within five MDD releases or less (c MDD 310-314) | Closed
A7 | This plan assumes the DNOs can process LLFC transfers for multiple DNO regions in parallel. | Closed
A8 | The plan also assumes that supplier systems can process LLFC transfers at the rate set out in the plan - currently a max rate of 80k/day. If this assumption is proven inaccurate we will replan to reduce the rates. | Closed
A9 | Unless otherwise stated the IDNOs can process their LLFC transfers in 5 working days. Engagement with the remaining IDNOs is underway to validate this assumption. | Open
A10 | The DTN has the capacity to communicate the number of LLFC transfers expected to be triggered per day - currently a max rate of 80k/day. The LDSOs will work with ElectraLink to validate this assumption. | Closed
A11 | Each DNO has been allocated five contingency days to avoid making LLFC transfers on the same days as billing runs | Closed
A12 | The Switching Programme, and other industry change, will not prevent the transfer of LLFCs between January - September 2021. This assumption has been made following engagement with Ofgem's Switching Programme PMO. | Closed
A13 | If the BSC Panel do not approve the DNO MDD CRs in December, Elexon will re submit these to the April SVG/BSC Panel for approval. It is anticipated this will cause a one month delay to the delivery of the LLFC transfers (they will be completed in October rather than September). | Closed