## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | CH | To clarify with Ofgem: • The possible impact of the change if it proposed to be applied retrospectively • Information on the end of tender revenue stream | Meetings planned prior to WG2 | WG2 | Closed | WG2
2 | WG1 | AH | Invite Terry Baldwin (ESO) to present overview of CM085 clarify and any interaction with CMP418 at WG2. | TB presented to WG2 | WG2 | Closed | WG2
3 | WG1 | GL | Investigate boundaries that could be applied to the solution. | GL clarified that discussed internally and Dynamic Reactive Compensation Equipment always required regardless of boundary distance. | WG2 | Closed | WG2
4 | WG1 | JL | Explanation of what constitutes Dynamic Reactive Compensation Equipment, with a diagram if possible. | Definition shared with workgroup. Couple of slides to be presented in WG3 and for inclusion in WG report. JL gave presentation during WG3. | WG3 | Closed | WG3
5 | WG2 | HT | To confirm TO payment of ORPS with a slide on asset clarification. | Slide shared at WG3 that clarified that TO's do not recieve ORPS as already paid for Transmission Sevices | WG3 | Closed | WG3
6 | WG2 | GL | Provide details of the impact on TNUoS if the proposed change was approved by the Authority. | N/A | WG3 | Closed | WG3
7 | WG2 | GL | If DRCE were treated as generation assets what would the ESO pay in balancing services. | N/A | WG3 | Closed | WG3
8 | WG2 | All | Investigate how retrospectively could be applied to this modification without reopening tariffs. | GL/PM Investigate retrospectivity feasibility without reopening tariffs and write into the solution if appropriate | WG4 | Open
9 | WG3 | HT | Should documentation for CMP418 have ‘Wider Tariff’ capitalised or not (if so a definition for Wider Tariff is needed as a part of the legal text changes). |  | WG4 | New
10 | WG3 | HT | To ask the revenue team if they have any capacity to analyse the operating figures used by Ocean Winds in WG3 within the timeframes of the modification. |  | WG4 | New
11 | WG3 | GL | Consultation document, where HND is mentioned that the proposed solution, if approved, will apply to all radially connected offshore windfarms within the HND or not. The reason is because the defect is stemming from the allocation of cost of DRCE at OFTO transaction related to the requirements in the Grid Code for radially connected offshore windfarms. |  | WG4 | New
12 | WG3 | GL | Consultation document, Price controls are not codified – that has been the case so far and NGESO agrees. We think it’s outside the scope of the defect and we do not require for that process to be codified for the defect to be addressed anyway. |  | WG4 | New
13 | WG3 | GL | BC Report, clarity around 45 years asset life in the BC report and assessment of wider tariff impact – should it be 25 years and align with OFTO TRS? |  | WG4 | New
14 | WG3 | GL | BC Report, clarity around targets post 2030 and implication for assessment on wider tariff impact– beyond 2030? |  | WG4 | New
15 | WG3 | GL | BC Report, clarity around discount rates being applied in the– NGESO 4% discount rate not relevant if OFTO (7.5%?) |  | WG4 | New
16 | WG3 | GL | BC Report, add operation and maintenance cost of 1.5% to SVC wider tariff impact (should increase the benefit of the proposal) |  | WG4 | New
17 | WG3 | GL | BC Report, explain that the OFTOs get paid via the base transmission revenue. The purpose is not for OFTO's to get paid. |  | WG4 | New
18 | WG3 | GL | BC Report, wording to reflect this is a commercial defect. |  | WG4 | New
19 | WG3 | GL | BC Report, impact on wind farm development cost – better define that the 1.09 is a saving on CfD bids for offshore wind generators. |  | WG4 | New
20 | WG3 | GL | BC Report, 37.35 is in 2012 and this figure needs to be updated. |  | WG4 | New
21 | WG3 | GL | BC Report, make clear that this is only applying in the future and does not work retrospectively. |  | WG4 | New
22 | WG3 | GL | Clarification required on final paragraph of Annex 8 |  | WG4 | New
23 | WG3 | GL | Annex 9 – clarify that offshore wind does not get ORPS |  | WG4 | New
24 | WG3 | CG | Add HT slide RE Condition E15 as Annex to consultation |  | WG4 | Closed | WG5
25 | WG3 | PM | Confirm whether the “overhead factor” for onshore TO kit in RIIO-T2 is still the 1.8% that it was in RIIO-T1 and TPCR5. | ​​Post meeting update overhead factor in the present price control has been confirmed as 1.5%.​ | WG4 | Closed | WG5