## Cover
Navigation
How to use this document
System Wide View of Recommendations
Region Key

## How to use this document
How to use this document
This appendix provides a list of all works identified as part of the Beyond 2030 network planning process.
The appendix can be navigated by clicking on the workbook tabs below.
The System-Wide view provides a comprehensive list of the onshore and offshore works that have been considered in this network planning process, including our recommendations where approprate. This sheet also shows the optimal delivery dates for these works where appropriate, and can be filtered as required.
The Key of Regions shows the outline boundaries of the regions of Great Britian used in this document.
The recommendations outlined this appendix reflect our current and best view, based on information available today. As the development of these projects progresses towards delivery, more details will emerge and variations to the designs or delivery considerations may occur due to supply chain, network access, or other constraints. Further development will also be undertaken by relevant bodies and alternative options considered as appropriate. Therefore, these recommended delivery dates may be subject to change in future.
Our recommendations for wider works are as follows:
“Proceed - Critical”: This option is critical to our future planning. Investment should be made in the next financial year to ensure the option’s earliest in-service date remains on course.
“Proceed – Maintain”: This option is important and recommended soon after its earliest-in-service date. Investment can be made in the next financial year to maintain project momentum and ensure its earliest-in-service date is delayed by at most one year.
“Hold”: This option is important and recommended for the future, however it is not on the earliest-in-service date submitted to NOA. Therefore, the delivery date of this option can be delayed by at least one year and the option can be reviewed in the next NOA cycle.
“Stop”: This option is not currently recommended within the optimal path of any scenario; delivery should be stopped and not be continued.
“Do not start”: This option is not currently recommended within the optimal path of any scenario; delivery work should not begin.
More information on specific reinforcements can be found in the Beyond 2030 report and Beyond 2030 technical report.

## System-Wide View
System-Wide View
New Infrastructure and Upgrades
Short Description of Works | Type of Work | Reinforcement Type | Code | Earliest In Service Date (EISD) | Optimal Delivery Date | Recommendation | Maturity Level | Notes | Regions
Upgrade the existing network to a higher voltage between Blackhillock and Kintore | Wider | Existing network upgrade | BKUP | 2034 | 2034 | Proceed - Critical | 3 - Design/development and consenting |  | North of Scotland
Upgrade the existing circuits between Brinsworth and Thorpe Marsh to allow for more capacity | Enabling & Wider Works | Existing network upgrade | BTR2 | 2027 | 2034 | Hold | 1 - Scoping | This project is also currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | Yorkshire and Humber, East Midlands
New circuit across North West England | Enabling & Wider Works | New onshore circuit | CLN2 | 2036 | 2036 | Proceed - Critical | 1 - Scoping | Superseded previously recommended CLNC, this project is also currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North West England
New circuit between South East Scotland and North West England | Wider | New onshore circuit | CMN3 | 2033 | 2035 | Proceed - Maintain | 1 - Scoping | Superseded previously recommended CMNC | North West England, Central and Southern Scotland
Upgrade the existing network to a higher voltage between Clydes Mill and Strathaven | Wider | Existing network upgrade | CVUP | 2031 | 2033 | Hold | 1 - Scoping |  | Central and Southern Scotland
Replace the conductors on the existing circuits between Carrington and Daines with higher capacity conductors | Enabling | Existing network upgrade | DCR4 | 2027 | N/A | N/A | 1 - Scoping | This project is currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North West England
Establish further connection capacity between Dounreay, Banniskirk (Spittal), and Thurso | Enabling | Existing network upgrade | DSUP | 2034 | N/A | N/A | 3 - Design/development and consenting | This project is currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North of Scotland
Refine one of the proposed offshore HVDC link planned between Scotland and Eastern England with a third connection into Lincolnshire | Enabling | New offshore circuit | E4L6 | 2033 | N/A | N/A | 1 - Scoping | This project is currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | East Midlands, East of England
Replace the conductors on a short section of the existing circuit between Errochty and Clunie with higher capacity conductors | Wider | Existing network upgrade | ECRE | 2029 | 2032 | Proceed - Maintain | 3 - Design/development and consenting |  | North of Scotland
Installation of series compensation on the existing circuit between East Anglia Coastal Node and Tilbury | Wider | Existing network upgrade | ECSC | 2027 | 2034 | Proceed - Maintain | 1 - Scoping | Subject to recommendations of East Anglia Network Study and OCSS recommendation | East of England
Replace the conductors on the existing circuits between Brinsworth and Thorpe Marsh, Brinsworth and Chesterfield, and Chesterfield and Ratcliffe with higher capacity conductors | Wider | Existing network upgrade | EDN3 | 2032 | 2037 | Hold | 1 - Scoping |  | Yorkshire and Humber, East Midlands
Reconfigure the network between Stalybridge and Thorpe Marsh | Wider | Existing network upgrade | ESCF | 2033 | 2033 | Proceed - Critical | 1 - Scoping |  | North West England, Yorkshire and Humber
Upgrade the existing circuits between Eggborough and Thorpe Marsh to allow for more capacity | Enabling & Wider Works | Existing network upgrade | ETRE | 2029 | 2031 | Proceed - Critical | 1 - Scoping | This project is also currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | Yorkshire and Humber
Upgrade the existing network to a higher voltage between Harker and Stella West | Enabling & Wider Works | Existing network upgrade | FSU1 | 2035 | 2035 | Proceed - Critical | 1 - Scoping | This project is also currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North East England, North West England
New circuit between Harburn and Gala North | Wider | New onshore circuit | HGNC | 2036 | 2038 | Proceed - Maintain | 1 - Scoping |  | Central and Southern Scotland
Replace the conductors on the existing circuits between Hawthorn Pit and Norton with higher capacity conductors | Enabling | Existing network upgrade | HNRE | 2029 | N/A | N/A | 1 - Scoping | This project is currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North East England
New HVDC link between North West England and North Wales | Wider | New offshore circuit | LPDC | 2037 | N/A | STOP | 1 - Scoping |  | North West England, Wales
New transmission capacity between the South Lincolnshire, Cambridgeshire and North West Norfolk boundary to Hertfordshire | Enabling & Wider Works | New onshore circuit | LRN6 | 2034 | 2034 | Proceed - Critical | 1 - Scoping | This project is also currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | East Midlands, East of England
Upgrade the existing circuits between Lackenby and Thornton to allow for more capacity | Enabling & Wider Works | Existing network upgrade | LTRE | 2030 | 2031 | Proceed - Critical | 1 - Scoping | This project is also currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North East England, Yorkshire and Humber
Upgrade the existing Mersey ring of circuits and substations to allow for more capacity (Phase 1 of 2) | Wider | Existing network upgrade | MRU1 | 2031 | 2036 | Hold | 1 - Scoping |  | North West England
Upgrade the existing Mersey ring of circuits and substations to allow for more capacity (Phase 2 of 2) | Wider | Existing network upgrade | MRU2 | 2033 | 2037 | Hold | 1 - Scoping |  | North West England
New circuit from north east Scotland to the Central Belt | Enabling & Wider Works | New onshore circuit | NHNC | 2038 | 2038 | Proceed - Critical | 1 - Scoping | This project is also currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North of Scotland, Central and Southern Scotland
New circuit between New Deer and Greens (New Deer 2) | Enabling | New onshore circuit | NNNC | 2030 | N/A | N/A | 4 - Planning/consenting | This project is currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North of Scotland
Replace the conductors on the existing circuit between Norton and Osbaldwick with higher capacity conductors | Wider | Existing network upgrade | NOR6 | 2029 | 2031 | Proceed - Critical | 1 - Scoping |  | North East England, Yorkshire and Humber
Carry out thermal upgrading on the existing circuit between Osbaldwick and Thornton | Enabling | Existing network upgrade | OTHW | 2027 | N/A | N/A | 1 - Scoping | This project is currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | Yorkshire and Humber
Replace the conductors on the existing circuits between Carrington and Penwortham and Penwortham and Padiham with higher capacity conductors | Wider | Existing network upgrade | PCR1 | 2030 | 2036 | Hold | 1 - Scoping |  | North West England
Upgrade and/or rebuild the circuits and equipment between Longside (Peterhead 2), Peterhead, Persley, Kintore, Fetteresso, Alyth, and Kincardine | Enabling & Wider Works | Existing network upgrade | PKUP | 2033 | 2033 | Proceed - Critical | 3 - Design/development and consenting | This project is also currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | North of Scotland
Replace the conductors on the existing circuit between Pentir and Trawsfynydd with a higher capacity then was previously recommended | Wider | Refine previous option | PTC2 | 2028 | 2031 | Proceed - Critical | 1 - Scoping | Supersedes previously recommended PTC1 | Wales
New circuit in North Wales with a higher capacity then was previously recommended | Wider | Refine previous option | PTN2 | 2028 | 2037 | Proceed - Critical | 1 - Scoping | Supersedes previously recommended PTNO | Wales
New circuit within South East England | Enabling | New onshore circuit | RANC | 2036 | N/A | N/A | 1 - Scoping | This project is currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | South East England
Offshore network cable connecting wind farms in Shetland to the Scottish mainland | Interface Point | New offshore circuit | Shetland Hub | N/A | N/A | N/A | 2 - Strategic Optioneering | 1800 MW: DC 525 kV Bipole (2 Cables) | North of Scotland
Offshore network cable from a coordinated series of wind farms connecting to the Branxton area | Interface Point | New offshore circuit | SW_E1a | N/A | N/A | N/A | 2 - Strategic Optioneering | 1500 MW: DC 525 kV Bipole (2 Cables) | Central and Southern Scotland
Offshore network cable from a coordinated series of wind farms connecting to Lincolnshire Connection Node | Interface Point | New offshore circuit | SW_E1c_1 | N/A | N/A | N/A | 2 - Strategic Optioneering | 2000 MW: DC 525 kV Bipole (2 Cables) | East Midlands
Offshore network cable interconnecting platforms within the SW_E1c wind farm | Interface Point | New offshore circuit | SW_E1c_1 to SW_E1c_2 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1000 MW: AC 275 kV (2 Cables) | East Midlands
Offshore network cable from a coordinated series of wind farms connecting to Weston Marsh | Interface Point | New offshore circuit | SW_E1c_2 | N/A | N/A | N/A | 2 - Strategic Optioneering | 2000 MW: DC 525 kV Bipole (2 Cables) | East Midlands
Offshore network cable interconnecting the SW_E1c and SW_E1a wind farms | Interface Point | New offshore circuit | SW_E1c_2 to SW_E1a | N/A | N/A | N/A | 2 - Strategic Optioneering | 2000 MW: AC 275 kV (4 Cables) | East Midlands
Offshore network cable interconnecting platforms within the SW_E2a wind farm | Interface Point | New offshore circuit | SW_E2a_1 to SW_E2a_2 | N/A | N/A | N/A | 2 - Strategic Optioneering | 2500 MW: AC 275 kV (5 Cables) | Central and Southern Scotland
Offshore network cable from a coordinated series of wind farms connecting to Richborough | Interface Point | New offshore circuit | SW_E2a_2 | N/A | N/A | N/A | 2 - Strategic Optioneering | 2000 MW: DC 525 kV Bipole (2 Cables) | South East England
Offshore network cable interconnecting the SW_E2a and SW_E1c wind farms | Interface Point | New offshore circuit | SW_E2a_2 to SW_E1c_1 | N/A | N/A | N/A | 2 - Strategic Optioneering | 2000 MW: AC 275 kV (4 Cables) | South East England
Offshore network cable from a coordinated series of wind farms connecting to Longside (Peterhead 2) | Interface Point | New offshore circuit | SW_E2b | N/A | N/A | N/A | 2 - Strategic Optioneering | 2000 MW: AC 275 kV (4 Cables) | North of Scotland
Offshore network cable interconnecting the SW_E2b and SW_E2a wind farms | Interface Point | New offshore circuit | SW_E2b to SW_E2a_1 | N/A | N/A | N/A | 2 - Strategic Optioneering | 2000 MW: AC 275 kV (4 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Hurlie (Fiddes) | Interface Point | New offshore circuit | SW_E3 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1050 MW: AC 275 kV (3 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Dounreay | Interface Point | New offshore circuit | SW_N2 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1500 MW: AC 275 kV (3 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Lewis | Interface Point | New offshore circuit | SW_N3 | N/A | N/A | N/A | 2 - Strategic Optioneering | 500 MW: AC 275 kV (1 Cable) | North of Scotland
Offshore network cable from a single wind farm connecting to Shetland | Interface Point | New offshore circuit | SW_NE1a | N/A | N/A | N/A | 2 - Strategic Optioneering | 500 MW: AC 275 kV ( 2 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Shetland | Interface Point | New offshore circuit | SW_NE1b | N/A | N/A | N/A | 2 - Strategic Optioneering | 1800 MW: AC 275 kV (4 Cable)) | North of Scotland
Offshore network cable from a single wind farm connecting to Shetland | Interface Point | New offshore circuit | SW_NE1c | N/A | N/A | N/A | 2 - Strategic Optioneering | 500 MW: AC 275 kV (2 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Banniskirk (Spittal) | Interface Point | New offshore circuit | SW_NE2 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1050 MW: AC 275 kV (3 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Greens (New Deer 2) | Interface Point | New offshore circuit | SW_NE3 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1000 MW: AC 275 kV (2 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to the New Deer area | Interface Point | New offshore circuit | SW_NE4 | N/A | N/A | N/A | 2 - Strategic Optioneering | 550 MW: AC 275 kV (2 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Longside (Peterhead 2) | Interface Point | New offshore circuit | SW_NE6 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1000 MW: AC 275 kV (2 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Longside (Peterhead 2) | Interface Point | New offshore circuit | SW_NE7 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1500 MW: DC 525 kV Bipole (2 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Peterhead | Interface Point | New offshore circuit | SW_NE8 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1000 MW: AC 275 kV (2 Cables) | North of Scotland
Add power control devices to the existing circuit between Drax and Thornton | Enabling | Existing network upgrade | TDP4 | 2030 | N/A | N/A | 1 - Scoping | This project is currently required to enable the development of a robust and reliable offshore network connection and will be reappraised in the detailed design stage | Yorkshire and Humber
East Coast Anglo-Scottish onshore reinforcement | Wider | New onshore circuit | TLNO | 2040 | N/A | STOP | 1 - Scoping |  | North East England, Central and Southern Scotland
Reconfigure the network between Keadby and Thorpe Marsh | Wider | Existing network reconfiguration | TMC2 | 2032 | 2037 | Hold | 1 - Scoping |  | Yorkshire and Humber
Reconfigure Thorpe Marsh substation | Wider | Existing network reconfiguration | TMCF | 2032 | 2034 | Proceed - Maintain | 1 - Scoping |  | Yorkshire and Humber
Add power control devices to the existing circuit between Thorpe Marsh and West Melton ​ | Wider | Existing network upgrade | TMPC | 2030 | 2031 | Proceed - Critical | 1 - Scoping |  | Yorkshire and Humber
New circuit between Wymondley and Waltham Cross and increase operating voltage of the network within the area | Wider | New onshore circuit | TWNC | 2033 | 2034 | Proceed - Maintain | 1 - Scoping |  | East of England, London
Increase the capacity of the proposed HND1 West Coast offshore HVDC link between Scotland and Wales | Wider | New offshore circuit | WCD4 | 2036 | 2037 | Proceed - Maintain | 1 - Scoping |  | Central and Southern Scotland, Wales
New circuit between south west Scotland and North West England | Wider | New onshore circuit | WCN2 | 2037 | 2037 | Proceed - Critical | 1 - Scoping | Supersedes previously recommended WCNC | North West England, Central and Southern Scotland
Revised recommendations
Short Description of Works | Type of Work | Reinforcement Type | Code | Earliest In Service Date (EISD) | Optimal Delivery Date | Recommendation | Maturity Level | Notes | Regions
New circuit across North West England | Wider | New onshore circuit | CLNC | 2036 | N/A | Stop | 1 - Scoping | Superseded by option CLN2 | North West England
New circuit between South East Scotland and North West England | Wider | New onshore circuit | CMNC | 2033 | N/A | Stop | 1 - Scoping | Superseded by option CMN3 | North West England, Central and Southern Scotland
Replace the conductors on the existing circuit between Elvanfoot and Harker with higher capacity conductors | Wider | Existing network upgrade | EHRE | 2030 | 2031 | Proceed - Critical | 1 - Scoping | This project had an HND Essential recommendation and is now recommended as Proceed - Critical. | North West England, Central and Southern Scotland
Replace the conductors on the existing circuit between Feckenham and Minety with higher capacity conductors | Wider | Existing network upgrade | FMR2 | 2029 | 2031 | Proceed - Critical | 1 - Scoping | This project was previously recommened as part of Pathway to 2030. | West Midlands, South West England
Carry out thermal upgrading on the existing circuit between Thurcroft and West Melton | Wider | Existing network upgrade | JTHW | 2027 | 2034 | Proceed - Maintain | 1 - Scoping | This project was previously recommened as part of Pathway to 2030. | Yorkshire and Humber
Adjust the existing network to form a circuit from Kincardine North towards Strathaven and Smeaton using existing pylon routes | Wider | Existing network reconfiguration | LCU2 | 2033 | 2037 | Hold | 1 - Scoping | This project had a Hold recommendation in the NOA2021/22 Refresh and continues to be recommended as Hold. | Central and Southern Scotland
New offshore circuit between North West England and North Wales | Wider | New offshore circuit | LPDC | 2037 | N/A | Stop | 1 - Scoping | This project had a Hold recommendation in the NOA2021/22 Refresh and continues to be recommended as Stop. | North West England, Wales
New circuit between North Wales and South Wales | Wider | New onshore circuit | PSNC | 2037 | 2037 | Proceed - Critical | 1 - Scoping | This project had an HND Essential recommendation and is now recommended as Proceed - Critical. | Wales
Replace the conductors on the existing circuit between Grendon and Sundon with higher capacity conductors | Wider | Existing network upgrade | SGRE | 2029 | 2031 | Proceed - Critical | 2 - Strategic Optioneering | SGRE also has the HND reinforcement code PT2030-CW34 | East of England
Replace the conductors on the existing circuit between Spennymoor to Norton with higher capacity conductors | Wider | Existing network upgrade | SNRE | 2029 | 2035 | Hold | 1 - Scoping | This project had a Hold recommendation in the NOA2021/22 Refresh and continues to be recommended as Hold. | North East England
Replace the conductors on the existing circuit between Spennymoor to Stella West with higher capacity conductors | Wider | Existing network upgrade | SPRE | 2029 | 2035 | Hold | 1 - Scoping | This project had a Hold recommendation in the NOA2021/22 Refresh and continues to be recommended as Hold. | North East England
Replace the conductors on the existing circuits between Hinkley Point, Taunton and Exeter with higher capacity conductors | Wider | Existing network upgrade | THRE | 2029 | 2031 | Proceed - Critical | 1 - Scoping | This project had a Hold recommendation and is now recommended as Proceed - Critical. | South West England
New circuit between South East Scotland and North East England | Wider | New onshore circuit | TLNO | 2040 | N/A | Stop | 1 - Scoping | This project had a Proceed - Critical recommendation in the NOA2021/22 Refresh and continues to be recommended as Stop. | Central and Southern Scotland, North East England
Replace the conductors on the existing circuit between Strathaven and Elvanfoot with higher capacity conductors | Wider | Existing network upgrade | VERE | 2030 | 2031 | Proceed - Critical | 1 - Scoping | This project had an HND Essential recommendation and is now recommended as Proceed - Critical. | Central and Southern Scotland
New circuit between South West Scotland and North West England | Wider | New onshore circuit | WCNC | 2037 | N/A | Stop | 1 - Scoping | Option superseded by WCN2 | Central and Southern Scotland, North West England
Offshore network cable from a single wind farm connecting to Birkhill Wood | Interface Point | New offshore circuit | R4_1 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1440 MW: DC 320 kV Monopole (2 Cables) | Yorkshire and Humber
Offshore network cable from a single wind farm connecting to Birkhill Wood | Interface Point | New offshore circuit | R4_2 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1440 MW: DC 320 kV Monopole (2 Cables) | Yorkshire and Humber
Offshore network cable from a single wind farm connecting to Birkhill Wood | Interface Point | New offshore circuit | PA_1 | N/A | N/A | N/A | 2 - Strategic Optioneering | 1440 MW: DC 320 kV Monopole (2 Cables) | Yorkshire and Humber
Offshore network cable from a coordinated series of wind farms connecting to Lincolnshire Connection Node | Interface Point | New offshore circuit | SW_E1A_3 | N/A | N/A | N/A | 2 - Strategic Optioneering | 2000 MW: DC 525 kV Bipole (2 Cables) | East Midlands, North of Scotland
Previously Recommended
Short Description of Works | Type of Work | Reinforcement Type | Code | Maturity Level | Notes | Regions
New circuit in north East Anglia | Wider | New onshore circuit | AENC | 3 - Design/development and consenting |  | East of England
New circuit in south East Anglia | Wider | New onshore circuit | ATNC | 3 - Design/development and consenting |  | East of England
New circuit between Beauly and Coachford (Blackhillock 2) | Wider | New onshore circuit | BBNC | 4 - Planning/consenting |  | North of Scotland
Upgrade the existing network to a higher voltage between Beauly and Denny | Wider | Existing network upgrade | BDUP | 4 - Planning/consenting |  | North of Scotland
Replace the conductors on the existing circuit between Bramley and Fleet with higher capacity conductors | Wider | Existing network upgrade | BFRE | 2 - Strategic Optioneering |  | South East England
New circuit between Carnaig (Loch Buidhe) and Beauly | Wider | New onshore circuit | BLN4 | 4 - Planning/consenting |  | North of Scotland
New circuit between Coachford (Blackhillock 2) and Peterhead | Wider | New onshore circuit | BPNC | 4 - Planning/consenting |  | North of Scotland
New circuit between Bramford and Twinstead | Wider | New onshore circuit | BTNO | 4 - Planning/consenting |  | East of England
Replace the conductors on the existing circuit between Barking and West Ham with higher capacity conductors | Wider | Existing network upgrade | BWRE | 2 - Strategic Optioneering |  | London
Add power control devices to the existing circuit between Cellarhead and Drakelow | Wider | Existing network upgrade | CDP1 | 2 - Strategic Optioneering |  | North West England, West Midlands
Increase rating of power control devices installed on the existing circuit between Cellarhead and Drakelow | Wider | Existing network upgrade | CDP2 | 2 - Strategic Optioneering |  | North West England, West Midlands
Further increase rating of power control devices installed on the existing circuit between Cellarhead and Drakelow | Wider | Existing network upgrade | CDP3 | 2 - Strategic Optioneering |  | North West England, West Midlands
New circuit between Creyke Beck and High Marnham | Wider | New onshore circuit | CGNC | 3 - Design/development and consenting |  | Yorkshire and Humber, East Midlands
Add power control devices to the existing circuits between Creyke Beck, Keadby and Killingholme | Wider | Existing network upgrade | CKPC | 2 - Strategic Optioneering |  | Yorkshire and Humber
Replace the conductors on the existing circuit between Drax and Fenwick Tee with higher capacity conductors | Wider | Existing network upgrade | DFRE | 2 - Strategic Optioneering |  | Yorkshire and Humber
Upgrade the existing network between Windyhill, Lambhill and Denny North, including increasing elements to a higher voltage | Wider | Existing network upgrade | DLUP | 1 - Scoping |  | Central and Southern Scotland
Upgrade existing circuits and establish a new route between Bonnybridge and Glenmavis | Wider | Existing network upgrade | DWNO | 3 - Design/development and consenting |  | Central and Southern Scotland
Upgrade the circuit between Kincardine to Wishaw, including increasing elements to a higher voltage | Wider | Existing network upgrade | DWUP | 3 - Design/development and consenting |  | Central and Southern Scotland
New offshore HVDC link between Torness and Hawthorn Pit (Eastern Green Link 1) | Wider | New offshore circuit | E2DC | 4 - Planning/consenting |  | North East England, Central and Southern Scotland
New offshore HVDC link between Peterhead and Drax (Eastern Green Link 2) | Wider | New offshore circuit | E4D3 | 4 - Planning/consenting |  | Yorkshire and Humber, North of Scotland
New offshore HVDC link between Peterhead and the East Coast of England (Eastern Green Link 3) | Wider | New offshore circuit | E4L5 | 4 - Planning/consenting |  | East Midlands, North of Scotland
Replace the conductors on the existing circuit between Enderby and Patford Bridge and East Claydon with higher capacity conductors | Wider | Existing network upgrade | EBRE | 2 - Strategic Optioneering |  | East Midlands, London
Upgrade the existing network to a higher voltage between Brinsworth and Chesterfield and Chesterfield and High Marnham. Develop new High Marnham and Chesterfield high voltage substations | Wider | Existing network upgrade | EDEU | 2 - Strategic Optioneering |  | Yorkshire and Humber, East Midlands
New circuit between Chesterfield and Ratcliffe-on-Soar | Wider | New onshore circuit | EDN2 | 2 - Strategic Optioneering |  | East Midlands
Replace the conductors on the existing circuit between Elvanfoot and Harker with higher capacity conductors | Wider | Existing network upgrade | EHRE | 1 - Scoping | EHRE is also listed under the revised recommendations above. | North West England, Central and Southern Scotland
New circuit between Elstree and St John’s Wood | Wider | New onshore circuit | ESC1 | 2 - Strategic Optioneering |  | East of England, London
Replace the conductors on the existing circuit between Feckenham and Hams Hall with higher capacity conductors | Wider | Existing network upgrade | FHRE | 1 - Scoping |  | West Midlands
Replace the conductors on the existing circuit between Feckenham and Minety with higher capacity conductors | Wider | Existing network upgrade | FMR2 | 1 - Scoping | FMR2 is also listed under the revised recommendations above. | West Midlands, South West England
Replace the conductors on the existing circuit between Feckenham and Walham with higher capacity conductors | Wider | Existing network upgrade | FWRE | 1 - Scoping |  | West Midlands, South West England
Carry out thermal upgrading on the existing circuit between Cottam and Market Harborough and Grendon | Wider | Existing network upgrade | GCHW | 2 - Strategic Optioneering |  | East Midlands
New circuit between North Lincolnshire and South Lincolnshire border | Wider | New onshore circuit | GWNC | 2 - Strategic Optioneering |  | Yorkshire and Humber, East Midlands, East of England
Upgrade the existing network to a higher voltage at Bridgewater and replace the conductors on the existing circuit to Hinkley with higher capacity conductors | Wider | Existing network upgrade | HBUP | 1 - Scoping |  | South West England
Upgrade the existing network to a higher voltage between Waltham Cross to Hackney | Wider | Existing network upgrade | HWUP | 2 - Strategic Optioneering |  | East of England, London
Replace the conductors on the existing circuit between Feckenham and Ironbridge with higher capacity conductors | Wider | Existing network upgrade | IFR1 | 1 - Scoping |  | West Midlands
Carry out thermal upgrading on the existing circuit between Thurcroft and West Melton | Wider | Existing network upgrade | JTHW | 1 - Scoping | JTHW is also listed under the revised recommendations above. | Yorkshire and Humber
Carry out thermal upgrading of the existing circuits between Creyke Beck, Keadby and Killingholme | Wider | Existing network upgrade | KCEU | 2 - Strategic Optioneering |  | Yorkshire and Humber
Replace the conductors on the existing circuit between Cottam and Keadby with higher capacity conductors | Wider | Existing network upgrade | KCRE | 2 - Strategic Optioneering |  | Yorkshire and Humber, East Midlands
Carry out thermal upgrading on the existing circuit between Keadby and West Burton | Wider | Existing network upgrade | KWHW | 2 - Strategic Optioneering |  | Yorkshire and Humber, East Midlands
Increase rating of power control devices installed on the existing circuit between Keadby and West Burton | Wider | Existing network upgrade | KWP2 | 2 - Strategic Optioneering |  | Yorkshire and Humber, East Midlands
Add power control devices to the existing circuit between Keadby and West Burton | Wider | Existing network upgrade | KWPC | 2 - Strategic Optioneering |  | Yorkshire and Humber, East Midlands
Adjust the existing network to form a circuit from Kincardine North towards Strathaven and Smeaton using existing pylon routes | Wider | Existing network reconfiguration | LCU2 | 1 - Scoping | LCU2 is also listed under the revised recommendations above. | Central and Southern Scotland
Replace the conductors on the existing circuit between Lackenby and Norton with higher capacity conductors | Wider | Existing network upgrade | LNRE | 1 - Scoping |  | North East England
Build a new substation north of Kincardine and connect this to Denny North | Wider | New network upgrade | LWUP | 3 - Design/development and consenting |  | Central and Southern Scotland
Carry out thermal upgrading on the existing circuit between Bramley and Melksham | Wider | Existing network upgrade | MBHW | 2 - Strategic Optioneering |  | South East England, South West England
Replace the conductors on the existing circuit between Bramley and Melksham with higher capacity conductors | Wider | Existing network upgrade | MBRE | 2 - Strategic Optioneering |  | South East England, South West England
Carry out thermal upgrading to Bramford and Norwich substations | Wider | Existing network upgrade | NBEU | 2 - Strategic Optioneering |  | East of England
Install voltage support equipment within the North East region | Wider | Existing network upgrade | NEMS | 2 - Strategic Optioneering |  | North East England
Add power control devices to the existing circuits between Blyth and Tynemouth and Blyth and South Shields | Wider | Existing network upgrade | NEP1 | 2 - Strategic Optioneering |  | North East England
Add power control devices to the existing circuit to the North of Tilbury | Wider | Existing network upgrade | NTP1 | 2 - Strategic Optioneering |  | East of England
New circuit between Osbaldwick and Poppleton | Wider | New onshore circuit | OPN2 | 4 - Planning/consenting |  | Yorkshire and Humber
Offshore network cable from a single wind farm connecting to Blyth | Interface Point | New offshore circuit | PA_2 | 2 - Strategic Optioneering | 1800 MW: DC 525 kV XLPE pair with metallic return | North East England
Replace the conductors on the existing circuits between Carrington and Penwortham and Penwortham and Padiham with higher capacity conductors | Wider | Existing network upgrade | PCR1 | 1 - Scoping | PCR1 is also listed under the revised recommendations above. | North West England
Install further voltage support equipment at Pelham | Wider | Existing network upgrade | PEM1 | 2 - Strategic Optioneering |  | East of England
Install voltage support equipment at Pelham | Wider | Existing network upgrade | PEM2 | 2 - Strategic Optioneering |  | East of England
New offshore circuit between Banniskirk (Spittal) and Longside (Peterhead 2) | Wider | New offshore circuit | PSDC | 4 - Planning/consenting |  | North of Scotland
New circuit between North Wales and South Wales | Wider | New onshore circuit | PSNC | 1 - Scoping | PSNC is also listed under the revised recommendations above. | Wales
Connect the existing circuit between Connah's Quay and Pentir directly into Bodelwyddan | Enabling | Existing network reconfiguration | PT2030-CW01 | 2 - Strategic Optioneering |  | Wales
Add power control devices to the existing circuit between Rugeley and Drakelow | Enabling | Existing network upgrade | PT2030-CW02 | 2 - Strategic Optioneering |  | East Midlands, West Midlands
Replace the conductors on the existing circuit between Rugeley and Drakelow with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW03 | 2 - Strategic Optioneering |  | East Midlands, West Midlands
Replace the conductors on the existing circuit between Rugeley and Ironbridge with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW04 | 2 - Strategic Optioneering |  | East Midlands
Replace the conductors on the existing circuit between Hams Hall and Drakelow with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW05 | 2 - Strategic Optioneering |  | East Midlands, West Midlands
Replace the conductors on the existing circuit between Bodelwyddan and Connah's Quay with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW06 | 2 - Strategic Optioneering |  | Wales
Replace the conductors on the existing circuit between Connah's Quay, Legacy and Trawsfynydd with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW09 | 2 - Strategic Optioneering |  | Wales
Install voltage support equipment at Ironbridge | Enabling | Existing network upgrade | PT2030-CW10 | 2 - Strategic Optioneering |  | West Midlands
Install voltage support equipment at Drakelow | Enabling | Existing network upgrade | PT2030-CW11 | 2 - Strategic Optioneering |  | East Midlands
Add power control devices to the existing circuit between Bodelwyddan and Connah's Quay | Enabling | Existing network upgrade | PT2030-CW14 | 2 - Strategic Optioneering |  | Wales
Replace the conductors on the existing circuit between Drakelow and Willington with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW15 | 2 - Strategic Optioneering |  | East Midlands
Replace the conductors on the existing circuit between Drakelow and Ratcliffe on Soar with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW16 | 2 - Strategic Optioneering |  | East Midlands
Change the configuration of the existing network in the Midlands and increase the voltage of the existing circuit between Drakelow and Rugeley | Enabling | Existing network reconfiguration | PT2030-CW19 | 2 - Strategic Optioneering |  | East Midlands, West Midlands
Change the configuration of the existing circuits between Blyth and Stella West | Enabling | Existing network reconfiguration | PT2030-CW20 | 2 - Strategic Optioneering |  | North East England
Install power flow control devices on the Keadby-West Burton circuit | Enabling | Existing network upgrade | PT2030-CW21 | 2 - Strategic Optioneering |  | East Midlands
Replace the conductors on the existing circuit between Lackenby and Thornton with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW22 | 2 - Strategic Optioneering |  | North East England
Replace the conductors on the existing circuit between Sundon and Wymondley with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW23 | 2 - Strategic Optioneering |  | East of England
Change the configuration of the network between Drakelow and Ratcliffe on Soar | Enabling | Existing network reconfiguration | PT2030-CW24 | 2 - Strategic Optioneering |  | East Midlands
Change the configuration of the existing network in northern Lincolnshire | Enabling | Existing network reconfiguration | PT2030-CW25 | 2 - Strategic Optioneering |  | Yorkshire and Humber
Carry out thermal upgrading on the existing circuit between Creyke Beck and Keadby | Enabling | Existing network upgrade | PT2030-CW26 | 2 - Strategic Optioneering |  | Yorkshire and Humber, East Midlands
Install voltage support equipment to support the existing circuit between Keadby and Fenwick Tee | Enabling | Existing network upgrade | PT2030-CW27 | 2 - Strategic Optioneering |  | Yorkshire and Humber
Replace the conductors on the existing circuit between the Fenwick Tee and Thorpe Marsh with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW28 | 2 - Strategic Optioneering |  | Yorkshire and Humber
Replace the conductors on the existing circuit between Drax and Thorpe Marsh with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW29 | 2 - Strategic Optioneering |  | Yorkshire and Humber
Add power control devices to the existing circuit between Creyke Beck, Keadby and Humber Refinery | Enabling | Existing network upgrade | PT2030-CW30 | 2 - Strategic Optioneering |  | Yorkshire and Humber, East Midlands
Replace the conductors on the existing circuit between Ratcliffe on Soar and Enderby with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW31 | 2 - Strategic Optioneering |  | East Midlands
Add power control devices to the existing circuit between Cottam and West Burton | Enabling | Existing network upgrade | PT2030-CW32 | 2 - Strategic Optioneering |  | East Midlands
Replace the conductors on the existing circuit between Cowley and East Claydon with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW33 | 2 - Strategic Optioneering |  | South East England
Replace the conductors on the existing circuit between Grendon and Sundon with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW34 | 2 - Strategic Optioneering | PT2030-CW34 has the NOA code SGRE and is also listed under the revised recommendations above. | East of England
Replace the conductors on the existing circuit between Ryhall, Eaton Socon and Wymondley with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW35 | 2 - Strategic Optioneering |  | East of England
Carry out thermal upgrading on the existing circuit between Drax and Eggborough | Enabling | Existing network upgrade | PT2030-CW36 | 2 - Strategic Optioneering |  | Yorkshire and Humber
Carry out thermal upgrading on the existing circuit between Burwell Main and Pelham | Enabling | Existing network upgrade | PT2030-CW37 | 2 - Strategic Optioneering |  | South East England
Add power control devices to the existing circuit between Spalding and Weston Marsh | Enabling | Existing network upgrade | PT2030-CW38 | 2 - Strategic Optioneering |  | East Midlands
Install voltage support equipment to support the existing circuit Yorkshire and Humber region | Enabling | Existing network upgrade | PT2030-CW39 | 2 - Strategic Optioneering |  | Yorkshire and Humber
Replace the conductors on the existing circuit between Norton and Osbaldwick with higher capacity conductors | Enabling | Existing network upgrade | PT2030-CW40 | 2 - Strategic Optioneering |  | North East England, Yorkshire and Humber
Install voltage support equipment at Penwortham | Wider | Existing network upgrade | PWMS | 2 - Strategic Optioneering |  | North West England
Offshore network cable from a single wind farm connecting to Weston Marsh | Interface Point | New offshore circuit | R4_3 | 2 - Strategic Optioneering | 1500 MW: AC 275 kV (3-4 Cables) | East Midlands
Offshore network cable from a single wind farm connecting to Bodelwyddan | Interface Point | New offshore circuit | R4_4 | 2 - Strategic Optioneering | 1500 MW: AC 275 kV (3-4 Cables) | Wales
Offshore network cable from a single wind farm connecting to Penwortham | Interface Point | New offshore circuit | R4_5 | 2 - Strategic Optioneering | 480 MW: AC 275 kV (1 Cable) | North West England
Offshore network cable from a single wind farm connecting to Penwortham | Interface Point | New offshore circuit | R4_6 | 2 - Strategic Optioneering | 1500 MW: AC 275 kV (3 Cables) | North West England
Install voltage support equipment at Rye House | Wider | Existing network upgrade | RHM1 | 2 - Strategic Optioneering |  | East of England
Install further voltage support equipment at Rye House | Wider | Existing network upgrade | RHM2 | 2 - Strategic Optioneering |  | East of England
New offshore circuit between Suffolk and Kent | Wider | New offshore circuit | SCD1 | 3 - Design/development and consenting |  | South East England
Replace the conductors on the existing circuit between Elstree and Sundon with higher capacity conductors | Wider | Existing network upgrade | SER1 | 2 - Strategic Optioneering |  | East of England
Replace the conductors on the existing circuit between Elstree and Sundon with higher capacity conductors and connect into the Elstree Substation | Wider | Existing network upgrade | SER2 | 2 - Strategic Optioneering |  | East of England
New substation in the South Humber area | Wider | New network upgrade | SHNS | 3 - Design/development and consenting |  | Yorkshire and Humber
New circuit between Banniskirk (Spittal) and Carnaig (Loch Buidhe) | Wider | New onshore circuit | SLU4 | 4 - Planning/consenting |  | North of Scotland
Replace the conductors on the existing circuit between Spennymoor to Norton with higher capacity conductors | Wider | Existing network upgrade | SNRE | 1 - Scoping | SNRE is also listed under the revised recommendations above. | North East England
Replace the conductors on the existing circuit between Spennymoor to Stella West with higher capacity conductors | Wider | Existing network upgrade | SPRE | 1 - Scoping | SPRE is also listed under the revised recommendations above. | North East England
Carry out thermal upgrading on the existing circuit between Stella West and Spennymoor | Wider | Existing network upgrade | SSHW | 2 - Strategic Optioneering |  | North East England
Offshore network cable from a coordinated series of wind farms connecting to Hawthorn Pit | Interface Point | New offshore circuit | SW_E1A_1 | 2 - Strategic Optioneering | 1800 MW: DC 525 kV Bipole (2 Cables) | Yorkshire and Humber, North of Scotland
Offshore network cable from a coordinated series of wind farms connecting to Hurlie (Fiddes) | Interface Point | New offshore circuit | SW_E1A_2 | 2 - Strategic Optioneering | 2000 MW: AC 275 kV (3-4 Cables) | North of Scotland
Offshore network cable from a coordinated series of wind farms connecting to Lincolnshire Connection Node | Interface Point | New offshore circuit | SW_E1A_3 | 2 - Strategic Optioneering | 2000 MW: DC 525 kV Bipole (2 Cables) | East Midlands, North of Scotland
Offshore network cable from a single wind farm connecting to Banniskirk (Spittal) | Interface Point | New offshore circuit | SW_N1 | 2 - Strategic Optioneering | 2250 MW: AC 275 kV (4-6 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Lewis | Interface Point | New offshore circuit | SW_N4 | 2 - Strategic Optioneering | 740 MW: AC 275 kV (2-3 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to the New Deer area | Interface Point | New offshore circuit | SW_NE4 | 2 - Strategic Optioneering | 1500 MW: AC 275 kV (3-4 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting to Longside (Peterhead 2) | Interface Point | New offshore circuit | SW_NE7 | 2 - Strategic Optioneering | 1500 MW: DC 525 kV Bipole (2 Cables) | North of Scotland
Offshore network cable from a single wind farm connecting in south west Scotland, to enable power flow on two coordinated cables to Kilmarnock South and Pentir | Interface Point | New offshore circuit | SW_W1_1 | 2 - Strategic Optioneering | 2000 MW: DC 525 kV Bipole (2 Cables) | Central and Southern Scotland
Offshore network cable allowing power flow between Kilmarnock South and Pentir, while coordinating with a wind farm connecting in south west Scotland | Interface Point | New offshore circuit | SW_W1_2 | 2 - Strategic Optioneering | 2000 MW: DC 525 kV Bipole (2 Cables) | Central and Southern Scotland
Offshore network cable allowing power flow between Kilmarnock South and Pentir, while coordinating with a wind farm connecting in south west Scotland | Interface Point | New offshore circuit | SW_W1_3 | 2 - Strategic Optioneering | 2000 MW: DC 525 kV Bipole (2 Cables) | Central and Southern Scotland
New offshore HVDC link between East Scotland and the East of England (Eastern Green Link 4) | Wider | New offshore circuit | TGDC | 2 - Strategic Optioneering |  | East of England, Central and Southern Scotland
Add power control devices to the existing circuit between Tilbury and Grain | Wider | Existing network upgrade | TGP1 | 2 - Strategic Optioneering |  | East of England, London
Replace the conductors on the existing circuits between Hinkley Point, Taunton and Exeter with higher capacity conductors | Wider | Existing network upgrade | THRE | 1 - Scoping | THRE is also listed under the revised recommendations above. | South West England
Add power control devices to the existing circuit between Tilbury and Kingsnorth | Wider | Existing network upgrade | TKP1 | 2 - Strategic Optioneering |  | East of England, London
Carry out thermal upgrading on the existing circuits between Tilbury to Grain and Tilbury to Kingsnorth | Wider | Existing network upgrade | TKRE | 2 - Strategic Optioneering |  | East of England, London
New circuit from Kintore to Emmock (Tealing) and upgrade elements of the existing Emmock to Westfield and Alyth to Emmock circuits | Wider | New onshore circuit | TKUP | 4 - Planning/consenting |  | Central and Southern Scotland
Replace the conductors on the existing circuit between Strathaven and Elvanfoot with higher capacity conductors | Wider | Existing network upgrade | VERE | 1 - Scoping | VERE is also listed under the revised recommendations above. | Central and Southern Scotland
Replace the conductors on the existing circuit between Strathaven and Smeaton with higher capacity conductors | Wider | Existing network upgrade | VSRE | 1 - Scoping |  | Central and Southern Scotland
Install voltage support equipment at Walpole | Wider | Existing network upgrade | WAM1 | 2 - Strategic Optioneering |  | East of England
Install further voltage support equipment at Walpole | Wider | Existing network upgrade | WAM2 | 2 - Strategic Optioneering |  | East of England
New offshore circuit between the Western Isles and Beauly | Other | New offshore circuit | Western Isles – Beauly HVDC link | 4 - Planning/consenting |  | North of Scotland
Replace the conductors on the existing circuit between West Burton and Ratcliffe-on-Soar with higher capacity conductors | Wider | Existing network upgrade | WRRE | 2 - Strategic Optioneering |  | East Midlands
Connect the existing circuit between Pelham and Sundon that passes Wymondley substation into the substation | Wider | Existing network reconfiguration | WYTI | 2 - Strategic Optioneering |  | East of England