## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | NP | Consider if a definition for HND is required as part of the modification | Provided in update to legal text in Workgroup 2 | WG2 | Closed | WG2
2 | WG1 | NP | To determine how the wider cancellation charge would be calculated for the affected offshore Generators, to take into account relevant onshore works plus those offshore works that have been classified as wider under CMP428, including whether a specific zone needs to be created for the offshore Generators. | Further information required regarding offshore Generators, and further clarity on wider cancellation charge calculation | WG3 | Closed | WG3
3 | WG2 | NP | Provide further clarification on the modification and how it works alongside methodologies already in place. | NA | WG3 | Closed | WG3
4 | WG2 | NP | Provide examples for the Workgroup to go through. | NA | WG3 | Closed | WG3
5 | WG3 | NP | Consider the defect wording to align to the worked example shown to members | NA | ASAP | Closed | WG4
6 | WG3 | DJ | Confirm the timelines the Authority will publish the asset classification on the HND follow up exercise | NA | ASAP | Closed | WG4
7 | WG3 | NP | Amend the typographical error in the proposed legal text | NA | ASAP | Closed | WG4
8 | WG3 | Proposer | Consider if any Users have any fixed liabilities associated with the HND. | The Proposer confirmed that there are no Users with fixed liabilities associated with the HND. | WG4 | Closed | WG5
9 | WG5 | Proposer | Amends to the Executive Summary for the Workgroup Report to note that this modification is considering Attributable Works and the application of the wider cancellation charge will be subsequently considered by the ESO. | Circulated within Workgroup Report draft on 27/03. | WG6 | Closed | WG6
10 | WG5 | Proposer | To check with ESO legal team proposed legal text amendment to the Attributable Works definition; this was further amended to include the addition of ‘(a) and (b)’ to make it clearer. | NA | WG6 | Closed | WG6
11 | WG5 | Chair | Engagement with the Authority required to ensure their Asset Classification definition can be aligned with CMP428 in any future Authority published documentation. | No imminent plan to change terminology, advised a Fast Track modification could be used for future decisions if necessary | WG6 | Closed | WG6
12 | WG5 | Proposer | Excepted Works was not completely clear; the Proposer agreed to review this with the ESO legal team and investigate the possibility of updating the guidance note on User Commitment. | NA | WG6 | Closed | WG6
13 | WG6 | Proposer | Review the following legal text definitions with ESO legal based on feedback from the Workgroup: • Centralised Strategic Network Plan • Excepted Works • HND • OTNR | NA | WG7 | Closed | WG7