## CUSC Prioritisation
CUSC Prioritisation Criteria | [8 empty] | Prioritiy Category (Modifications are listed in numerical order within their priority category)
Section 8: 8.19.1.(e) makes the following provision for the Panel and states “Having regard to the complexity, importance and urgency of particular CUSC Modification Proposals, the CUSC Modifications Panel may determine the priority of CUSC Modification Proposals and may (subject to any objection from the Authority taking into account all those issues) adjust the priority of the relevant CUSC Modification Proposal accordingly” | [8 empty] | High
Complexity | The modification is viewed as being resource intensive and will most likely require a higher than average number of workgroups to conclude the process. Additionally, the modification defect is viewed to have implications for many different areas of the energy market which need to be taken into consideration throughout the process. | [7 empty] | Medium to High Medium
Importance | The perceived value & risk associated with the proposed modification. The value / risk could be considered from a number of different perspectives i.e. financial / regulatory / licence obligations both directly for customer and end consumers more generally. | [7 empty] | Medium to Low Low
Urgency | A modification which requires speedy consideration within the code governance process, both complexity and importance should be factors considered in evaluating urgency as well as the timescales for implementation within the respective code.
Priority Category | Mod Number | Title | Discussed | Stage in Process | TNUoS Task Force / Storage TNUoS Sub Group / BSUoS /REMA | CAP/ OTNR/ HND | Proposed Implementation Date | Previous Priority Category (changes highlighted in blue) | Panel Comments on Prioritisation as of 12 April 2024 | Proposer Organisation | Outside WG stage
High | CMP424 | Amendments to Scaling Factors used for Year Round TNUoS Charges | N | Workgroup Report to April Panel | TNUos Task Force | N | 2025-04-01 | New modification | Given the potential risk to the model and the mitigation which would come from the solution the Panel considered modification should be prioritised as ‘High’. | ESO
High | CMP426 | TNUoS charges for transmission circuits identified for the HND as onshore transmission | High | Previously paused, the analysis is expected in a couple of weeks | N | OTNR | 2025-04-01 | New modification | Panel agreed that given the profile and required timescales of the modification it should be placed as High | ESO
High | CMP430 | Adjustments to TNUoS Charging from 2025 to support the Market Wide Half Hourly Settlement (MHHS) Programme | High | Workgroup Consultation end of April | N | N | 2025-04-01 | New modification | Panel agreed that as they had recommended 'Urgency' it should be placed as 'High' | ESO
High | CMP428 | User Commitment liabilities for Onshore Transmission circuits in the Holistic Network Design | High | DFMR to April Panel | N | HND | 2024-06-14 | High | Panel agreed that as they had recommended 'Urgency' it should be placed as 'High' January 2024: Panel agreed that due to the risk to customer liability and CMP426's prioritisation it should be placed as 'High' | ESO | x
High | CMP431 | Adjustments to TNUoS Charging from 2025 to support the Market Half Hourly Settlement (MHHS) Programme (Non-Charging) | High | Workgroup Consultation end of April | N | N | 2025-04-01 | New modification | Panel agreed that as they had recommended 'Urgency' it should be placed as 'High' | ESO
Medium to High | CMP402 | Introduction of Anticipatory Investment (AI) principles within the User Commitment Arrangements | Medium to High | Paused awaiting solution amendment | N | OTNR/ HND | Q3 2024 | Medium to High | Given the high materiality and that this is the first of a number of changes in this area, this was placed as “Medium to High” in the prioritisation stack | ESO
Medium to High | CMP419 | Generation Zoning Methodology Review | Medium to High | Workgroup Consultation in April | N | OTNR | 2026-04-01 | Medium to High | Given the complexity of the defect, the potential for several alternative solutions and the advantage of an early decision on re-zoning for investors, this was placed as “Medium to High” in the prioritisation stack | ESO
Medium | CMP344 | Clarification of Transmission Licensee revenue recovery and the treatment of revenue adjustments in the Charging Methodology |  | Send Back 2 Workgroups Meetings planned | N | N | 2025-04-01 | High | Panel agreed it should be placed as 'High' to support a quick resolution and based on the work required to address the deficiencies within the latest send back. Special April 2024 Panel: Due to the complexity, importance and the required timescales of the other modifications in the stack the Panel reprioritised the modification from ‘High’ to ‘Medium’ | RWE
Medium | CMP417 | Extending principles of CUSC Section 15 to all Users |  | Workgroup Consultation in June | N | N | 2025-07-01 | Medium to High | Panel agreed to place within the 'Medium to High' priority category due to being part of the Connections reform package and the potential benefits to demand customers. Special April 2024 Panel: Due to the complexity, importance and the required timescales of the other modifications in the stack the Panel reprioritised the modification from ‘Medium - High’ to ‘Medium’ | ESO
Medium | CMP420 | Treatment of BSUoS Revenue Recovery, and potential creation of a BSUoS Fund | Medium | Workgroup Report to June Panel | BSUoS | N | 2025-04-01 | Medium to High | Due to the complexity of the defect, the potential value of an unofficial fund, interactions with the Future System Operator and the timing of its set up, this was placed as “Medium to High” in the prioritisation stack. December 2023: The Panel agreed that when rationalised against the other modifications in the stack this should be placed as 'Medium' | SSE Generation
Medium | CMP423 | Generation Weighted Reference Node | Medium | Workgroup Meeting 2 in April | TNUos Task Force | N | 2026-04-01 | Medium to High | Due to the complexity and technical aspects of the defect, alongside the amount of time the TNUoS Task Force had already contributed to the development of the solution, the Panel considered modification should be prioritised as ‘Medium to High’ December 2023: The Panel agreed that whilst the modification was complex, when rationalised against the other modifications in the stack this should be placed as 'Medium' | SSE
Medium | CMP432 | Improve “Locational Onshore Security Factor” for TNUoS Wider Tariffs | Medium | Workgroups starting in June | TNUos Task Force | N | 2026-04-01 | New Modification | The Panel placed the new modification as Medium on the prioritisation stack based on its complexity, importance and the required timescales. | SSE
Medium to Low | CMP288 | CMP288 - Explicit charging arrangements for customer delays and backfeeds | Medium to Low | Send Back - 2nd Workgroup Consultation April- May | N | N | 10 BD post Authority Decision | Medium | Due to the consideration required by the Ofgem send back letter of 14 September 2023, the September 2023 CUSC Panel agreed to return the modification to the same priority it was given prior to the initial submission of the FMR. December 2023: The Panel agreed that when rationalised against the other modifications in the stack this should be placed as 'Medium to Low' | ESO
Low | CMP304 | Improving the Enhanced Reactive Power Service by making it fit for purpose |  | No Workgroups scheduled | N | N | TBC | Medium to Low | • Modification seeks to apply a different timescale to the provision on reactive power – Panel divided though on whether this is a simple change as solution still needs to be clarified • Ofgem cannot make a final decision on CMP305 until CMP304 is completed • Decreased cost to consumers if more competition This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. Workgroups recommenced on 8 November 2021. Prioritisation was discussed at October 2022 Panel and priority was not changed, as there remains a need for reactive services. However, the Panel (and Proposer) agreed that work on CMP304 is paused until such time that the ESO team, who are leading on the Reactive Reform (Market Design), have completed their Feasibility studies, which in turn will help to inform the Proposer's solution. July 2023 - Proposer and ESO Panel Rep to review the output of Phase 1 of the ESO's feasibility studies ahead of reconvening the Workgroup. December 2023: The Panel agreed that when rationalised against the other modifications in the stack this should be placed as 'Medium to Low' Special April 2024 Panel: Due to there being no Workgroup scheduled the Panel reprioritised the modification from ‘Medium – Low’ to ‘Low’ | SSE Generation
Low | CMP328 | Connections Triggering Distribution Impact Assessment |  | No Workgroups scheduled | N | N | TBC | Medium to Low | Although this was prioritised as "High" when originally progressed, there was challenge that the materiality is not as high as when originally progressed. However, as the Workgroup are reconvening following an Authority send-back, Panel on balance was felt that this should have a Medium to High priority. December 2023: The Panel agreed that until there is further Proposer engagement, and, when rationalised against the other modifications in the stack this should be placed as 'Medium to Low' Special April 2024 Panel: Due to there being no Workgroup scheduled the Panel reprioritised the modification from ‘Medium – Low’ to ‘Low’ | Scottish and Southern Energy Power Distribution Limited
Low | CMP341 | CUSC Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions | Low | No Workgroups scheduled | N | N | TBC | Low | • Complex • Although a CACOP and Ofgem driven initiative, there does not appear to be any current industry appetite to progress This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At the last quarterly prioritisation deep-dive (October 2022 Panel), no case was presented to change the priority. | ESO
Low | CMP405 | TNUoS Locational Demand Signals for Storage |  | Paused awaiting Subgroup data | N | N | 2026-04-01 | Medium | As this is being developed in parallel with CMP393, Panel placed CMP405 at the same “Medium” priority as CMP393 Special April 2024 Panel: Due to there being no Workgroup scheduled as the modification is being paused until the outcome of the Storage Subgroup the Panel reprioritised the modification from ‘Medium’ to ‘Low’ | SSE Generation