## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | Workgroup 1 | Chair | Amend timeline to run workgroup consultation after the Christmas period | Chair amended timeline | Workgroup 2 | Closed | WG2
2 | Workgroup 1 | All | Consider the terms of reference | Point 4 was amended to "Assess the implications of interest being applied to over/under recovery" | Workgroup 2 | Closed | WG2
3 | Workgroup 1 | Proposer | Present solution | Proposer presented solution in WG2 | Workgroup 2 | Closed | WG2
4 | Workgroup 2 | Proposer | Proposer to design a timetable to assist with cross referencing when certain charges are set and forecasted to align and provide clarity when under and over recovery applies to which period. | No longer relevant |  | Closed | WG4
5 | Workgroup 2 | Proposer | Proposer to work with ESO to draft Legal Text and share with the Workgroup |  | Workgroup 5 | Closed | WG5
6 | Workgroup 4 | Chair | Amend the implementation date to April 2025 with CMP420 requesting special consideration from Ofgem | No longer required | Workgroup 6 | Closed | WG6
7 | Workgroup 4 | AT | Produce a guidance note with an obligation on ESO to provide a weekly report on fixed tariff revenue vs cost and take to TCMF for their input . | Will be progressed within a CUSC Section 3 modification instead. | Workgroup 6 | Closed | WG6
8
9
10
11
12
13
14
15
16
17