## LIVE
Risk Register for Enquiries and Projects Template v14
Enquiry/Project Number: |  | 021700
Project Title: |  | SIF Scenarios of Extreme Events - Alpha Phase | [5 empty] | Mandatory Field
Client: |  | National Grid ESO | [5 empty] | Optional Field
Update Date: |  | 2023-12-11
Version: |  | 2
|  |  |  | Inherent Risk Assessment |  |  |  | Risk Control Information | [5 empty] | Risk Treatment Plan |  |  | Post-Treatment Risk Assessment |  |  |  |  | Risk Register Control
Risk ID | Risk Title | Risk Description (If… then…) | Risk Impact (Time, Cost, Quality / Performance) | Probability | Impact | Risk Score | Proximity (when is risk likely to occur) | Risk Owner | Risk Type | Risk Category | Raised By | Date raised | Status | Risk Treatment | Treatment Actions | Action Owner | Post-Treatment Probability | Post-Treatment Impact | Post-Treatment Risk Score | Fallback Plan | For Beta? | Last Updated | Comments / Notes
6 | Insufficient Support for Beta Phase from Partners | If we do not demonstrate value to potential gas and electricity transmission / distribution partners then we may not get necesary support for a beta phase application. | Cost - no funding for Beta. | 3 | 4 | 12 | 1st quarter 2024 | ESO | Threat | Strategic | ESO | 2023-12-20 | Open | Reduce | LE - Ask UKRI for Innovation Challenge Documentation so we know which partners we require. MP - Ask for what wider partners would benefit from in workshops. (Specifically Including Scottish Gas and Electricity Transmission and Distribution). LE - Ensure Alpha deliverables include relevant information that supports wider partners, e.g. capturing gas - elec interdependencies, and scenarios. MP - Communicate our plans for the point above to partners and reiterate at partner updates. | Luke Edelston Megan Pearce | 2 | 4 | 8 |  |  | 2023-12-20 | From SIF Governance Document v2 2.9. "Eligibility Criterion 6: "Projects must include participation from a range of stakeholders. The Project Partners involved in the Project must satisfy the requirements set out in the Innovation Challenge and Innovation Challenge Documentation."
11 | Insufficient robustness of outputs | The model outputs cannot be relied on for relevant decision-making or risk assessments due to a lack of trustworthy data. | Quality | 3 | 4 | 12 | Throughout | ESO | Threat | Technical | ESO | 2024-01-24 | Open | Reduce | Quality assess outputs by end of alpha, mitigating probability. ESO to request internal modelling SME to assess model. Validate model outputs against past events (quantitative). | ESO | 1 | 3 | 3 |  |  | 2024-01-24
16 | Competing Alpha projects under same organisation | Frazer-Nash is running SfEE and another similar SIF Alpha project, which may raise a conflict of interest if both are competing for Beta phase funding | Either or both projects may breach CoI conditions for Beta applications, potentially resulting in failure to obtain Beta funding | 2 | 5 | 10 | Toward end of Alpha phase, until Beta application deadline (May 22) | FNC | Threat | Governance | DPO/DM | 2024-02-08 | Open | Reduce | Declare any potential conflicts of interest to UKRI and implement any recommendations they make. Limit overlap of staff between governance positions on affected projects. | DM | 1 | 4 | 4 |  | Y | 2024-02-08
1 | Lack of data | There is a lack of technical data provided by project partners resulting in a constrained scope of modelling. | Quality: Model capabilities or accuracy may be reduced | 3 | 3 | 9 | Throughout | ESO | Threat | Performance | DPO | 2023-12-11 | Open | Reduce | Gather relevant data using our academic partners. Ensure early communication of requirement and dates for interviews. Define Resilience Metrics early to understand required outputs from model (which guides inputs too). Regular liaison between modelling team and Met office to ensure they are aligned. Define required model inputs in more detail, e.g. scenarios, data. | Chris Williams | 2 | 2 | 4 | Work with available data to produce best possible model, and plan for inclusion of further data at a later stage (e.g. in beta phase). |  | 2023-12-20
17 | Retention of SQEP resource through Beta | If there is a delay in awarding Beta project funds, SQEP resource currently utilised in Alpha or planned for Beta may become unavailable | Quality of Beta outputs could be reduced by not having access to sufficient SQEP resource, or delivery of outputs could be delayed while other resource is secured | 3 | 3 | 9 | Early stages of Beta project | FNC/ESO | Threat | Performance | DM | 2024-08-02 | Open | Reduce | Include project in resource forecasts. Use diverse team | All partners | 2 | 3 | 6 |  |  | 2024-03-11
5 | Stakeholder engagement | Stakeholder engagement activities may not run to schedule due to partner availability. | Time: May delay future project tasks | 4 | 2 | 8 | Dec 2023 - Jan 2024 | ESO | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Active engagement with project partners and other work packages to ensure they have key inputs when required | Megan Pearce | 2 | 2 | 4 | Proceed with available partners to maximise information gain while minimising impact on other work packages. |  | 2023-12-11
7 | Similar projects with overlapping scope apply and compete for Beta Phase. | If we do not differentiate SfEE from other SIF projects, e.g. CREDO+, then we may be unsuccessful in Beta application. | Cost - no funding for Beta. | 2 | 4 | 8 | 1st quarter 2024 | ESO | Threat | Technical | ESO | 2023-12-20 | Open | Reduce | ESO will have worshops with CREDO+ project to understand their scope, understand where there are overlaps and potential collaboration opportunities. At midpoint review, ask UKRI what other relevant Alpha projects are and stakeholder details. Find out if there is a mapping / potential model interfaces. Then follow up with stakeholders to find out more. | Luke Edelston | 1 | 3 | 3 |  |  | 2023-12-20
2 | Teamworking | The project brings together team members from multiple different organisations and sectors. There may be difficulties ensuring effective communication between people with varied technical backgrounds. | Time: Inefficencies in communication or organisation may result in delays to project tasks | 2 | 3 | 6 | Throughout | ESO | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Early engagement with project partners to ensure everyone understands their role and contribution to the project; project manager to ensure jargon-free communications where possible and ensure difficult issues are explained clearly. | Luke Edelston | 1 | 1 | 1 | Revisit project communication arrangements to find more efficient/effective methods |  | 2023-12-11
4 | Complexity of interrelated events | The categorisation and clasification of events and scenarios, both in terms of causes and effects, has the potential to escalate beyond the scope of this discovery phase. | Time: May delay future project tasks Cost: May require more effort than originally planned | 2 | 3 | 6 | Throughout | ESO | Threat | Performance | DPO | 2023-12-11 | Open | Reduce | Maintain focus on the structure of the event register, prioritising a framework that will provide a basis to be built upon in subsequent phases, rather than achieve an exhaustive summary of events | Daniel O'Brien | 1 | 2 | 2 | Proceed with simplified representations of complex events/scenarios, and plan for inclusion of fuller events/scenarios at a later stage. |  | 2023-12-11
15 | Impact data limitations | General limitations of the impact data, duplicate entries etc, assumptions that need to be made. | Quality: decisions have to be made based on expert elicitation, which can be valuable, but not always support by quantitative analysis. | 2 | 3 | 6 | Throughout, but especially with final breakdown of meterological scenarios at beta phase. |  | Threat | Technical | Joe Osborne | 2024-01-24 | Open | Reduce | Working with partners on the project, ensure that we have access to all distribution/transmission impact data and we can make pragmatic choices about handling of duplicates/contradictory information. | All partners | 1 | 3 | 3 |  |  | 2024-03-01
3 | Resource availability | Key project personnel are unable to dedicate the required time due to holidays, unplanned leave or other project commitments. | Time: Staff unavailability may result in delays to project tasks | 2 | 2 | 4 | Throughout | ESO | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Draw up project plan with resource allocation at the start. Have a large pool of resource available to backfill roles where necessary. Consider impact of national holidays (e.g. spring holidays) during project planning and allow for reduced availability during these periods. | Daniel O'Brien | 1 | 2 | 2 | Draw on Frazer-Nash and partner resource pools to add additional project team members. |  | 2023-12-11
8 | Model outputs of vulnerabiliies becomes classified / sensitive. | If model outputs / inputs are sensitive / classified then we need to change how we manage this information and where the model is held. | Quality: reputational damage, or leaks of vulnerabilities to nefarious actors. Cost: sensitive information limits ability to generate academic publications, which could impact university funding. | 1 | 4 | 4 | 1st quarter 2024 | Chris | Threat | Governance | Daniel O'Brien | 2023-12-20 | Open | Avoid | Confirm security treatment for Alpha and Beta (check with Neil). Communicate our strategy for mitigating security risks of handling data from DNOs etc, to partners / UKRI. Option to limit /data that goes into the model to reduce the sensitivity of outputs. Could also remove details of vulnerabilities from reports to remove classifications. | Daniel O'Brien | 1 | 2 | 2 |  |  | 2024-01-17
9 | Not accessing the right people at ESO / external stakeholders | Unable to get the right expertise to make timely decisions and ensure the metoerological extremes for testing are as appropriate and flexible as they can be, especially where impact data doesn't give us as much insight as expert ellicitation could. | Quality: Meteorological information that isn't as tailored as it could be. | 2 | 2 | 4 | Throughout | Met Office / ESO | Threat | Governance | Joe Osborne | 2024-01-24 | Open | Reduce | Mitigated through ESO commitment and willingness to get extra data if requested. | Joe Osborne | 1 | 2 | 2 |  |  | 2024-01-17
10 | Being able to access wide range of commercial and academic work. | If insights exist in other projects / commissioned research there are insights that we could miss out on. | Quality: Covering old ground, not building on existing science and novel applications. | 2 | 2 | 4 | Throughout | Met Office / ESO | Threat | Technical | Joe Osborne | 2024-01-24 | Open | Reduce | Mitigated through ESO and external stakeholders sharing any work they're able to share, or at least a summary of this. | Joe Osborne | 1 | 2 | 2 |  |  | 2024-01-17
12 | Scalability | Methodologies can't accurately scale to be used in wider geographical areas of input scenarios | Performance | 1 | 3 | 3 | Throughout | Chris | Threat | Technical | ESO | 2024-01-24 | Open | Avoid | Record decisions and assumptions (with rationale) and state where they are / are not valid. Validate assumptions with wider group regularly (e.g. every two weeks). | Chris Williams | 1 | 3 | 3 |  |  | 2024-03-01
13 | Continuity | previous stages/decisions/assumptions have not been recorded properly for project continuity, causing issues if colleagues change or project evolves. | Performance | 1 | 3 | 3 | Throughout | ESO | Threat | Performance | ESO | 2024-01-24 | Open | Avoid | Record assumptions / decisions and state where they are / are not valid. | ESO | 1 | 2 | 2 |  |  | 2024-03-01
14 | Obsolescence | Inappropriate modelling results due to GB energy system changing faster than model/data can keep up with. | Quality | 1 | 3 | 3 |  | Chris | Threat | Technical | ESO | 2024-01-24 | Open | Avoid | Asset owners to ensure that their infrastructure / asset database is kept up to date and fed into the model. Record assumptions and decisions about model scope, grouping of assets/nodes. | All partners | 1 | 3 | 3 |  | y | 2024-03-01
18 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
19 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
20 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
21 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
22 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
23 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
24 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
25 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
26 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
27 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
28 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
29 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
30 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
31 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
32 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
33 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
34 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
35 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
36 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
37 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
38 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
39 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
Date of Last Review
Name of Last Reviewer
Note on A9: Risk ID A shorthand means of naming risks. The Risk ID must not change once allocated.
Note on B9: Risk Title A 2-3 word concise title to summarise e.g. Resource constraints
Note on C9: Risk Description A succinct and specific description of the risk and what might cause or trigger it. Either: "If… then…" or "There is a risk that… if…" e.g. If more than 40mm of rain falls within 24hrs then the river will burst its banks. or There is a risk that the river will burst its banks if it rains more than 40mm of rain falls in 24hrs.
Note on D9: Risk Impact If the event occurs, describe the immediate impacts of the risk on the project. These should be identified in terms of time or schedule delay, project cost increase, quality of the output / performance of the service / reputation of the company. Not all of the risks will impact in all three areas. The description of the impact should take the form of: "The town will flood"
Note on E9: Probability 1 - Very Low 5 - Very High
Note on F9: Impact 1 - Very Low 5 - Very High Use the worst case from the Time, Cost or Quality risk impact box.
Note on G9: Risk Score Auto-calculates the risk score. Risk Score = Probability x Impact
Note on H9: Proximity (when is the risk likely to occur) Date / phase / milestone in the schedule when the impact will take effect. If multiple impacts, state earliest date / phase / milestone.
Note on I9: Risk Owner Who is accountable if the risk event occurs? This must be a person or specific role, not an organisation.
Note on J9: Risk Type Is the risk identified a threat, opportunity or an issue? This field helps to filter different types of risk on a project.
Note on K9: Risk Category What area of risk does the risk title relate to? This field helps to filter different categories of risk on the project.
Note on L9: Raised By Who identified the risk in the first place. This helps to trace the origin of a risk in case more information is needed.
Note on M9: Date Raised When was the risk first identified. This helps to understand how much time has elapsed in treating the risk.
Note on N9: Status Identify if risk is open, closed or transferred off this risk register to someone else (e.g. onto the company Business Systems risk register for company-wide risks to do with D365).
Note on O9: Risk Treatment If 'Accept', then no further action is required. For all other treatments, continue to explain your plan.
Note on P9: Treatment Actions Specifically, what do you need to do to mitigate the threat or exploit the opportunity?
Note on Q9: Action Owner Who is responsible for treating the risk. This must be a person or specific role, not an organisation.
Note on R9: Post Treatment Probability 1 - Very Low 5 - Very High This is only true if the treatment plan is effective.
Note on S9: Post-Treatment Impact 1 - Very Low 5 - Very High This is only true if the treatment plan is effective.
Note on T9: Post-Treatment Risk Score: Auto-calculates the risk score. Risk Score = Probability x Impact This is only true if the treatment plan is effective.
Note on U9: Fallback Plan What will you do if the risk event still occurs, even after treating it?
Note on W9: Last Updated When was this risk last reviewed and updated?

## 2023-12-20 (hidden)
Risk Register for Enquiries and Projects Template v14
Enquiry/Project Number: |  | 021700
Project Title: |  | SIF Scenarios of Extreme Events - Alpha Phase | [5 empty] | Mandatory Field
Client: |  | National Grid ESO | [5 empty] | Optional Field
Update Date: |  | 2023-12-11
Version: |  | 2
|  |  |  | Inherent Risk Assessment |  |  |  | Risk Control Information | [5 empty] | Risk Treatment Plan |  |  | Post-Treatment Risk Assessment |  |  |  | Risk Register Control
Risk ID | Risk Title | Risk Description (If… then…) | Risk Impact (Time, Cost, Quality / Performance) | Probability | Impact | Risk Score | Proximity (when is risk likely to occur) | Risk Owner | Risk Type | Risk Category | Raised By | Date raised | Status | Risk Treatment | Treatment Actions | Action Owner | Post-Treatment Probability | Post-Treatment Impact | Post-Treatment Risk Score | Fallback Plan | Last Updated | Comments / Notes
1 | Lack of data | There is a lack of technical data provided by project partners resulting in a constrained scope of modelling. | Quality: Model capabilities or accuracy may be reduced | 3 | 3 | 9 | Throughout | PM | Threat | Performance | DPO | 2023-12-11 | Open | Reduce | Gather relevant data using our academic partners. Ensure early communication of requirement and dates for interviews. Define Resilience Metrics early to understand required outputs from model (which guides inputs too). Regular liaison between modelling team and Met office to ensure they are aligned. Define required model inputs in more detail, e.g. scenarios, data. | Chris Williams | 2 | 2 | 4 | Work with available data to produce best possible model, and plan for inclusion of further data at a later stage (e.g. in beta phase). | 2023-12-20
2 | Teamworking | The project brings together team members from multiple different organisations and sectors. There may be difficulties ensuring effective communication between people with varied technical backgrounds. | Time: Inefficencies in communication or organisation may result in delays to project tasks | 2 | 3 | 6 | Throughout | PM | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Early engagement with project partners to ensure everyone understands their role and contribution to the project; project manager to ensure jargon-free communications where possible and ensure difficult issues are explained clearly. | Luke Edelston | 1 | 0 | 0 | Revisit project communication arrangements to find more efficient/effective methods | 2023-12-11
3 | Resource availability | Key project personnel are unable to dedicate the required time due to holidays, unplanned leave or other project commitments. | Time: Staff unavailability may result in delays to project tasks | 2 | 2 | 4 | Throughout | PM | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Draw up project plan with resource allocation at the start. Have a large pool of resource available to backfill roles where necessary. Consider impact of national holidays (e.g. spring holidays) during project planning and allow for reduced availability during these periods. | Daniel O'Brien | 1 | 2 | 2 | Draw on Frazer-Nash and partner resource pools to add additional project team members. | 2023-12-11
4 | Complexity of interrelated events | The categorisation and clasification of events and scenarios, both in terms of causes and effects, has the potential to escalate beyond the scope of this discovery phase. | Time: May delay future project tasks Cost: May require more effort than originally planned | 2 | 3 | 6 | Throughout | PM | Threat | Performance | DPO | 2023-12-11 | Open | Reduce | Maintain focus on the structure of the event register, prioritising a framework that will provide a basis to be built upon in subsequent phases, rather than achieve an exhaustive summary of events | Daniel O'Brien | 1 | 2 | 2 | Proceed with simplified representations of complex events/scenarios, and plan for inclusion of fuller events/scenarios at a later stage. | 2023-12-11
5 | Stakeholder engagement | Stakeholder engagement activities may not run to schedule due to partner availability. | Time: May delay future project tasks | 4 | 2 | 8 | Dec 2023 - Jan 2024 | PM | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Active engagement with project partners and other work packages to ensure they have key inputs when required | Megan Pearce | 2 | 2 | 4 | Proceed with available partners to maximise information gain while minimising impact on other work packages. | 2023-12-11
6 | Insufficient Support for Beta Phase from Partners | If we do not demonstrate value to potential gas and electricity transmission / distribution partners then we may not get necesary support for a beta phase application. | Cost - no funding for Beta. | 3 | 4 | 12 | 1st quarter 2024 | PM | Threat | Strategic | Katerina Foka Sandoval | 2023-12-20 | Open | Reduce | LE - Ask UKRI for Innovation Challenge Documentation so we know which partners we require. MP - Ask for what wider partners would benefit from in workshops. (Specifically Including Scottish Gas and Electricity Transmission and Distribution). LE - Ensure Alpha deliverables include relevant information that supports wider partners, e.g. capturing gas - elec interdependencies, and scenarios. MP - Communicate our plans for the point above to partners and reiterate at partner updates. | Luke Edelston Megan Pearce | 2 | 4 | 8 |  | 2023-12-20 | From SIF Governance Document v2 2.9. "Eligibility Criterion 6: "Projects must include participation from a range of stakeholders. The Project Partners involved in the Project must satisfy the requirements set out in the Innovation Challenge and Innovation Challenge Documentation."
7 | Similar projects with overlapping scope apply and compete for Beta Phase. | If we do not differentiate SfEE from other SIF projects, e.g. CREDO+, then we may be unsuccessful in Beta application. | Cost - no funding for Beta. | 2 | 4 | 8 | 1st quarter 2024 | PM | Threat | Technical | Katerina Foka Sandoval | 2023-12-20 | Open | Reduce | ESO will have worshops with CREDO+ project to understand their scope, understand where there are overlaps and potential collaboration opportunities. At midpoint review, ask UKRI what other relevant Alpha projects are and stakeholder details. Find out if there is a mapping / potential model interfaces. Then follow up with stakeholders to find out more. | Luke Edelston | 1 | 3 | 3 |  | 2023-12-20
8 | Model outputs of vulnerabiliies becomes classified / sensitive. | If model outputs / inputs are sensitive / classified then we need to change how we manage this information and where the model is held. | Quality: reputational damage, or leaks of vulnerabilities to nefarious actors. | 1 | 4 | 4 | 1st quarter 2024 | Modelling | Threat | Governance | Daniel O'Brien | 2023-12-20 | Open | Avoid | Confirm security treatment for Alpha and Beta (check with Neil). Communicate our strategy for mitigating security risks of handling data from DNOs etc, to partners / UKRI. Option to limit / obscure data that goes into the model to reduce the sensitivity of outputs. | Daniel O'Brien | 1 | 2 | 2 |  | 2023-12-20
9
10
11 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
12 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
13 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
14 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
15 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
16 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
17 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
18 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
19 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
20 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
21 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
22 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
23 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
24 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
25 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
26 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
27 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
28 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
29 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
30 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
31 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
32 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
33 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
34 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
35 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
36 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
37 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
38 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
39 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
Date of Last Review
Name of Last Reviewer
Note on A9: Risk ID A shorthand means of naming risks. The Risk ID must not change once allocated.
Note on B9: Risk Title A 2-3 word concise title to summarise e.g. Resource constraints
Note on C9: Risk Description A succinct and specific description of the risk and what might cause or trigger it. Either: "If… then…" or "There is a risk that… if…" e.g. If more than 40mm of rain falls within 24hrs then the river will burst its banks. or There is a risk that the river will burst its banks if it rains more than 40mm of rain falls in 24hrs.
Note on D9: Risk Impact If the event occurs, describe the immediate impacts of the risk on the project. These should be identified in terms of time or schedule delay, project cost increase, quality of the output / performance of the service / reputation of the company. Not all of the risks will impact in all three areas. The description of the impact should take the form of: "The town will flood"
Note on E9: Probability 1 - Very Low 5 - Very High
Note on F9: Impact 1 - Very Low 5 - Very High Use the worst case from the Time, Cost or Quality risk impact box.
Note on G9: Risk Score Auto-calculates the risk score. Risk Score = Probability x Impact
Note on H9: Proximity (when is the risk likely to occur) Date / phase / milestone in the schedule when the impact will take effect. If multiple impacts, state earliest date / phase / milestone.
Note on I9: Risk Owner Who is accountable if the risk event occurs? This must be a person or specific role, not an organisation.
Note on J9: Risk Type Is the risk identified a threat, opportunity or an issue? This field helps to filter different types of risk on a project.
Note on K9: Risk Category What area of risk does the risk title relate to? This field helps to filter different categories of risk on the project.
Note on L9: Raised By Who identified the risk in the first place. This helps to trace the origin of a risk in case more information is needed.
Note on M9: Date Raised When was the risk first identified. This helps to understand how much time has elapsed in treating the risk.
Note on N9: Status Identify if risk is open, closed or transferred off this risk register to someone else (e.g. onto the company Business Systems risk register for company-wide risks to do with D365).
Note on O9: Risk Treatment If 'Accept', then no further action is required. For all other treatments, continue to explain your plan.
Note on P9: Treatment Actions Specifically, what do you need to do to mitigate the threat or exploit the opportunity?
Note on Q9: Action Owner Who is responsible for treating the risk. This must be a person or specific role, not an organisation.
Note on R9: Post Treatment Probability 1 - Very Low 5 - Very High This is only true if the treatment plan is effective.
Note on S9: Post-Treatment Impact 1 - Very Low 5 - Very High This is only true if the treatment plan is effective.
Note on T9: Post-Treatment Risk Score: Auto-calculates the risk score. Risk Score = Probability x Impact This is only true if the treatment plan is effective.
Note on U9: Fallback Plan What will you do if the risk event still occurs, even after treating it?
Note on V9: Last Updated When was this risk last reviewed and updated?

## 2023-12-13 (hidden)
Risk Register for Enquiries and Projects Template v14
Enquiry/Project Number: |  | 021700
Project Title: |  | SIF Scenarios of Extreme Events - Alpha Phase | [5 empty] | Mandatory Field
Client: |  | National Grid ESO | [5 empty] | Optional Field
Update Date: |  | 2023-12-11
Version: |  | 2
|  |  |  | Inherent Risk Assessment |  |  |  | Risk Control Information | [5 empty] | Risk Treatment Plan |  |  | Post-Treatment Risk Assessment |  |  |  | Risk Register Control
Risk ID | Risk Title | Risk Description (If… then…) | Risk Impact (Time, Cost, Quality / Performance) | Probability | Impact | Risk Score | Proximity (when is risk likely to occur) | Risk Owner | Risk Type | Risk Category | Raised By | Date raised | Status | Risk Treatment | Treatment Actions | Action Owner | Post-Treatment Probability | Post-Treatment Impact | Post-Treatment Risk Score | Fallback Plan | Last Updated | Comments / Notes
1 | Lack of data | There is a lack of technical data provided by project partners resulting in a constrained scope of modelling. | Quality: Model capabilities or accuracy may be reduced | 3 | 3 | 9 | Throughout | PM | Threat | Performance | DPO | 2023-12-11 | Open | Reduce | Gather relevant data using our academic partners. Ensure early communication of requirement and dates for interviews. | PM | 2 | 2 | 4 | Work with available data to produce best possible model, and plan for inclusion of further data at a later stage (e.g. in beta phase). | 2023-12-11
2 | Teamworking | The project brings togeher team members from multiple different organisations and sectors. There may be difficulties ensuring effective communication between people with varied technical backgrounds. | Time: Inefficencies in communication or organisation may result in delays to project tasks | 2 | 3 | 6 | Throughout | PM | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Early engagement with project partners to ensure everyone understands their role and contribution to the project; project manager to ensure jargon-free communications where possible and ensure difficult issues are explained clearly. | PM, Partners | 1 | 2 | 2 | Revisit project communication arrangements to find more efficient/effective methods | 2023-12-11
3 | Resource availability | Key project personnel are unable to dedicate the required time due to holidays, unplanned leave or other project commitments. | Time: Staff unavailability may result in delays to project tasks | 2 | 2 | 4 | Throughout | PM | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Draw up project plan with resource allocation at the start. Have a large pool of resource available to backfill roles where necessary. Consider impact of national holidays (e.g. spring holidays) during project planning and allow for reduced availability during these periods. | PM | 1 | 2 | 2 | Draw on Frazer-Nash and partner resource pools to add additional project team members. | 2023-12-11
4 | Complexity of interrelated events | The categorisation and clasification of events and scenarios, both in terms of causes and effects, has the potential to escalate beyond the scope of this discovery phase. | Time: May delay future project tasks Cost: May require more effort than originally planned | 2 | 3 | 6 | Throughout | PM | Threat | Performance | DPO | 2023-12-11 | Open | Reduce | Maintain focus on the structure of the event register, prioritising a framework that will provide a basis to be built upon in subsequent phases, rather than achieve an exhaustive summary of events | PM | 1 | 2 | 2 | Proceed with simplified representations of complex events/scenarios, and plan for inclusion of fuller events/scenarios at a later stage. | 2023-12-11
5 | Stakeholder engagement | Stakeholder engagement activities may not run to schedule due to partner availability. | Time: May delay future project tasks | 4 | 2 | 8 | Dec 2023 - Jan 2024 | PM | Threat | Schedule | DPO | 2023-12-11 | Open | Reduce | Active engagement with project partners and other work packages to ensure they have key inputs when required | PM, Partners | 2 | 2 | 4 | Proceed with available partners to maximise information gain while minimising impact on other work packages. | 2023-12-11
6 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
7 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
8 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
9 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
10 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
11 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
12 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
13 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
14 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
15 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
16 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
17 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
18 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
19 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
20 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
21 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
22 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
23 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
24 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
25 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
26 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
27 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
28 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
29 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
30 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
31 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
32 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
33 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
34 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
35 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
36 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
37 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
38 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
39 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
40 | [5 empty] | 0 |  |  |  | Please select | [8 empty] | 0
Date of Last Review
Name of Last Reviewer
Note on A9: Risk ID A shorthand means of naming risks. The Risk ID must not change once allocated.
Note on B9: Risk Title A 2-3 word concise title to summarise e.g. Resource constraints
Note on C9: Risk Description A succinct and specific description of the risk and what might cause or trigger it. Either: "If… then…" or "There is a risk that… if…" e.g. If more than 40mm of rain falls within 24hrs then the river will burst its banks. or There is a risk that the river will burst its banks if it rains more than 40mm of rain falls in 24hrs.
Note on D9: Risk Impact If the event occurs, describe the immediate impacts of the risk on the project. These should be identified in terms of time or schedule delay, project cost increase, quality of the output / performance of the service / reputation of the company. Not all of the risks will impact in all three areas. The description of the impact should take the form of: "The town will flood"
Note on E9: Probability 1 - Very Low 5 - Very High
Note on F9: Impact 1 - Very Low 5 - Very High Use the worst case from the Time, Cost or Quality risk impact box.
Note on G9: Risk Score Auto-calculates the risk score. Risk Score = Probability x Impact
Note on H9: Proximity (when is the risk likely to occur) Date / phase / milestone in the schedule when the impact will take effect. If multiple impacts, state earliest date / phase / milestone.
Note on I9: Risk Owner Who is accountable if the risk event occurs? This must be a person or specific role, not an organisation.
Note on J9: Risk Type Is the risk identified a threat, opportunity or an issue? This field helps to filter different types of risk on a project.
Note on K9: Risk Category What area of risk does the risk title relate to? This field helps to filter different categories of risk on the project.
Note on L9: Raised By Who identified the risk in the first place. This helps to trace the origin of a risk in case more information is needed.
Note on M9: Date Raised When was the risk first identified. This helps to understand how much time has elapsed in treating the risk.
Note on N9: Status Identify if risk is open, closed or transferred off this risk register to someone else (e.g. onto the company Business Systems risk register for company-wide risks to do with D365).
Note on O9: Risk Treatment If 'Accept', then no further action is required. For all other treatments, continue to explain your plan.
Note on P9: Treatment Actions Specifically, what do you need to do to mitigate the threat or exploit the opportunity?
Note on Q9: Action Owner Who is responsible for treating the risk. This must be a person or specific role, not an organisation.
Note on R9: Post Treatment Probability 1 - Very Low 5 - Very High This is only true if the treatment plan is effective.
Note on S9: Post-Treatment Impact 1 - Very Low 5 - Very High This is only true if the treatment plan is effective.
Note on T9: Post-Treatment Risk Score: Auto-calculates the risk score. Risk Score = Probability x Impact This is only true if the treatment plan is effective.
Note on U9: Fallback Plan What will you do if the risk event still occurs, even after treating it?
Note on V9: Last Updated When was this risk last reviewed and updated?

## Risk Help
Definitions & Information
Risk Identification and Assessment Guidance | Risk ID | A shorthand means of naming risks. The Risk ID must not change once allocated.
| Risk Title | A 2-3 word concise title to summarise e.g.. Resource constraints
| Risk Description | A succinct and specific description of the risk and what might cause or trigger it. Either: "If… then…" or "There is a risk that… if…" e.g. If more than 40mm of rain falls within 24hrs then the river will burst its banks. or There is a risk that the river will burst its banks if it rains more than 40mm of rain falls in 24hrs.
| Risk Impact | If the event occurs, describe the immediate impacts of the risk on the project. These should be identified in terms of time or schedule delay, project cost increase, quality of the output / performance of the service / reputation of the company. Not all of the risks will impact in all three areas. The description of the impact should take the form of: "The town will flood".
| Probability | The probability that the cause or trigger will occur. 1 - Very Low; 5 - Very High See Risk Assessment Criteria tab.
| Impact | The impact the risk event will have on the project. Use the worst case from the Time, Cost or Quality risk impact box. 1 - Very Low; 5 - Very High See Risk Assessment Criteria tab.
| Risk Score | Auto-calculates Probability x Impact.
| Proximity (when is the risk likely to occur) | Date / phase / milestone in the schedule when the impact will take effect. If multiple impacts, state earliest date / phase / milestone.
Risk Control Information | Risk Owner | Who is accountable if the risk event occurs? This must be a person or specific role, not an organisation.
| Risk Type | Choices: Threat, Opportunity, Issue. | Threat | A negative risk.
| Risk Category | What area of risk does the risk title relate to? This field helps to filter different categories of risk on the project. (see below) | Opportunity | A positive risk.
| Raised By | Who identified the risk in the first place. This helps to trace the origin of a risk in case more information is needed. | Issue | A risk that has occurred, or is certain to, that exceeds the PM’s ability or tolerance to deal with it.
| Date Raised | When was the risk first identified. This helps to understand how much time has elapsed in treating the risk.
| Status | Identify if risk is open, closed or transferred off this risk register to someone else (e.g. onto the company Business Systems risk register for company-wide risks to do with D365).
Risk Treatment Plan | Risk Treatment | Choices: Accept, Avoid, Transfer, Reduce. | Accept | A response to a threat where no course of action is taken.
| Treatment Actions | Specifically, what do you need to do to mitigate the threat or exploit the opportunity?
| Action Owner | Who is responsible for treating the risk. This must be a person or specific role, not an organisation. | Avoid | A response to a threat that eliminates its probability or impact on the project.
Post-Treatment Risk Assessment | Post-Treatment Probability | The probability that the cause or trigger will occur after treating the risk. 1 - Very Low; 5 - Very High See Risk Assessment Criteria tab.
| Post-Treatment Impact | The impact the risk event will have on the project after treating the risk. Use the worst case from the Time, Cost or Quality risk impact box. 1 - Very Low; 5 - Very High See Risk Assessment Criteria tab. | Transfer | A response to a threat that reduces its probability, impact or both by transferring the risk to a third party.
| Post-Treatment Risk Score | Auto-calculates Probability x Impact after treating the risk. | Reduce | A response to a threat that reduces its probability, impact or both.
| Fallback Plan | What will you do if the risk event still occurs, even after treating it?
| Last updated | When was this risk last reviewed and updated?
| Comments / Notes | Space for the PM to record any other pertinent information.

## Risk Assessment Criteria
Project Risk Assessment Criteria
Scoring |  | Probability | Impact
|  |  | Time | Cost* | Quality / Performance
5 | Very High | >85% | > 1 month | > 10% | Failure to deliver key output. Impact to future phases.
4 | High | >60%; <85% | > 2 weeks | > 5%, <=10% | Failure to deliver high priority output / reduced quality of key output. Impact to future phases.
3 | Medium | >40%; <60% | > 1 week | > 2%, <=5% | Failure to deliver optional output / reduced quality of high priority output. Impact to future phases.
2 | Low | >15%; <40% | > 1 day | > 1%, <= 2% | Failure to deliver low priority output
1 | Very Low | <15% | < 1 day | <= 1% | Marginal impact on outputs
*Percentage of project works cost limit.
The Project Manager can tailor this example threat assessment scoring criteria grid to the context and requirements of their specific project before undertaking a risk assessment. | [5 empty] | Probability Impact Grid for this Risk Register
Impact
[6 empty] | 5 | 5 | 10 | 15 | 20 | 25
[6 empty] | 4 | 4 | 8 | 12 | 16 | 20
[6 empty] | 3 | 3 | 6 | 9 | 12 | 15
[6 empty] | 2 | 2 | 4 | 6 | 8 | 10
[6 empty] | 1 | 1 | 2 | 3 | 4 | 5
[7 empty] | 1 | 2 | 3 | 4 | 5 | Probability