## Index
Index for Strategic Innovation Fund Discovery Round 3 Application
Guidance
This tab is for information only.
Question | Worksheet in this template
General Information | Key Info
Question 1 | N/A
Question 2 | Investment worksheet
Question 3 | N/A
Question 4 | N/A
Question 5 | N/A
Question 6 | N/A
Question 7 | Key Info Project Plan Risk Register (This is where you upload the completed Project Management Book Template)
Question 8 | N/A
Question 9 | N/A
Question 10 | N/A
Question 11 | N/A
Question 12 | N/A
Question 13 | N/A

## Key Info
Key Information
Guidance
This is a mandatory worksheet to be completed for all project partners.
Key
To be populated
Automated populated
Drop down to be populated
Project Name | FractalFlow
| Company Name | Contact name (One per partner) | Email | Website URL
Lead partner | Northern Powergrid | Chris Goodhand | chris.goodhand@northernpowergrid.com | https://www.northernpowergrid.com
Partner 1 | Frazer-Nash Consultancy | Fraser Pearson | f.pearson@fnc.co.uk | https://www.fnc.co.uk
Partner 2 | National Grid ESO | Claudia Centazzo | claudia.centazzo@nationalgrideso.com | https://www.nationalgrideso.com
Partner 3
Partner 4
Partner 5
Partner 6
Partner 7
Partner 8
Partner 9
Partner 10
Partner 11
Partner 12
Partner 13
Partner 14
Partner 15
| Company Name | Contact name | Email | Website URL
Subcontractor 1
Subcontractor 2
Subcontractor 3
Subcontractor 4
Subcontractor 5

## Investment
Investment
Guidance
This is a mandatory worksheet. It is aimed at understanding what other funded/ proposed projects have contributed to this proposal.
List out any other sources of UK Government funds or innovation funds which has informed this application. Examples may include but are not limited to NIA, NIC, UKRI, European funding, IFI, private investment etc. This should also include applications pending approval.
Type of funding (drop down) | Total if known (£) | Name of Project | Description of Project / fund

## Project Plan
Project Plan
Guidance
This is an mandatory tab which is designed to accompany a project Gantt chart (which should be added to the Gantt chart tab) in order to provide a description of the overall objectives of each work package, key tasks, deliverables and milestones (together with success criteria). It also forms a register of approved due dates for your deliverables and milestones which if successful in achieving funding, your Monitoring Officer will track your progress against. It is required in addition to a Gantt chart in order to provide a description of these items rather than just a schedule. The Gantt chart must show the work packages, their relationships and dependencies hence the project’s critical path. Within the context of this document: 1. Tasks are the activities that will be carried out. 2. Deliverables are the outputs of these (e.g. document, spec, piece of software etc) 3. Milestones are significant points of achievement, these may be the point at which several deliverables have been achieved to reach an outcome. Note that dependencies between tasks, deliverables and milestones should be shown on your Gantt Chart and are therefore not referenced within the 2nd level plan to avoid un-necessary duplication.
Summary of Work Packages
Ref | Work Package Title | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per Work Package | Actual Spend to date per Work Package
WP1 | Feasibility Assessment | National Grid ESO | 2024-04-19 | 79824 | 89016
WP2 | Cost Benefit Assessment | Frazer-Nash Consultancy | 2024-04-19 | 28539 | 31721
WP3 | FractalFlow Roadmap | Northern Powergrid | 2024-05-09 | 33286 | 42329
|  |  | Total: | 141649 | 163066
Work Package Description (Repeat for each Work Package)
Work Package Number | WP1 | Work Package Title | Feasibility Assessment | Lead Partner | National Grid ESO
Overall Work Package Objectives | 1. Complete a detailed requirements definition for the project scope, including interfaces and constraints. The requirements will be gathered from each of the project stakeholders, and will include barriers, resources and opportunities relating to technical, commercial and regulatory aspects. 2. The requirements that are considered to fundamentally impact the feasbility of this project will be assessed in further detail to characterise the issues, challenges, and opportunities in order to determine the viability of continuing this project into the alpha phase. |  | Key Tasks | 1. Requirements definition, including engagement with key stakeholders. 2. Requirements review to assess importance and determine ease of implementation. 3. Review of the feasibility of requirements against their importance and ease of implementation
Significant equipment, materials or subcontractors utilised |  |  | All spend on this work package is labour.
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M1.1 | WP1 - Feasibility Assessment - Complete | Technical requirements and feasibility findings summarised and reviewed by all partners (in review meeting). | National Grid ESO | 2024-04-19 | 15335 | 17335
M1.1 | WP1 - Feasibility Assessment - Complete | Technical requirements and feasibility findings summarised and reviewed by all partners (in review meeting). | Frazer-Nash Consultancy | 2024-04-19 | 64489 | 71681
|  |  |  | Total: | 79824 | 89016
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D1.1 | ESO - Requirements Capture for FractalFlow Capability and Interfaces | ESO requirements identified in workshop output shared with all stakeholders (written format) | National Grid ESO | 2024-03-22 | Complete
D1.2 | NPg - Requirements Capture for FractalFlow Capability and Interfaces | NPg requirements identified in workshop output shared with all stakeholders (written format) | Northern Powergrid | 2024-03-22 | Complete
Work Package Description (Repeat for each Work Package)
Work Package Number | WP2 | Work Package Title | Cost Benefit Assessment | Lead Partner | Frazer-Nash Consultancy
Overall Work Package Objectives | 1. Assess the cost of delivering the FractalFlow capability in accordance with the SIF cost template, including software, hardware, Application Programming Interface, and ongoing maintenance/support costs. 2. Evaluate the benefits provided by the FractalFlow capability in accordance with SIF cost template. |  | Key Tasks | 1. Identify the inputs needed as part of the cost/benefit assessment 2. Collect input data to support the cost/benefit assessment 3. Undertake cost/benefit assessment in accordance with SIF template
Significant equipment, materials or subcontractors utilised |  |  | All spend on this work package is labour.
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M2.1 | WP2 - CBA - Complete | Cost benefit assessment produced and verified by FNC, feedback received from all partners (in review meeting) | Frazer-Nash Consultancy | 2024-04-19 | 28539 | 31721
|  |  |  | Total: | 28539 | 31721
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D2.1 | CBA and Populated SIF Template | Cost Benefit Assessment completed and SIF Template populated | Frazer-Nash Consultancy | 2024-04-18 | Complete
Work Package Description (Repeat for each Work Package)
Work Package Number | WP3 | Work Package Title | FractalFlow Roadmap | Lead Partner | Northern Powergrid
Overall Work Package Objectives | 1. Undertake a roadmap identifying the technical and commerical developments required and a timeline for delivery of the FractalFlow capability. |  | Key Tasks | 1. Analysis of requirements, barriers, resources and opportunities 2. Gap analysis to define development roadmap and implementation strategy, including timeline
Significant equipment, materials or subcontractors utilised |  |  | All spend on this work package is labour.
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M3.1 | WP3 - Technology Roadmap - Complete | Roadmap produced and feedback received from all partners (in review meeting) | Northern Powergrid | 2024-04-19 | 6000 | 12000
M3.1 | WP3 - Technology Roadmap - Complete | Roadmap produced and feedback received from all partners (in review meeting) | Frazer-Nash Consultancy | 2024-04-19 | 15439 | 17161
M3.2 | All WP Outputs Consolidated | WP outputs consolidated into a single summary with feedback from all partners integrated | Frazer-Nash Consultancy | 2024-05-09 | 6502 | 7227
M3.3 | Show and tell webinar | Show and tell webinar completed | Frazer-Nash Consultancy | 2024-06-03 | 5345 | 5941
|  |  |  | Total: | 33286 | 42329
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D3.1 | Technology Roadmap | Technology Roadmap produced | Northern Powergrid | 2024-04-19 | Complete
D3.2 | Final deliverable: Feasibility, CBA and roadmap synthesis | All WP outputs consolidated into a single summary presenting the technical and commercial development case for FractalFlow | Frazer-Nash Consultancy | 2024-05-09 | Complete
D3.3 | Webinar presentation slides | Slides prepared and ready for dissemination | Frazer-Nash Consultancy | 2024-06-03 | Complete
106:152D23106:127106:177D23106:127106:196D23106:12106:332
Work Package Description (Repeat for each Work Package)
Work Package Number | #REF! | Work Package Title | #REF! | Lead Partner | #REF!
Overall Work Package Objectives |  |  | Key Tasks | 1. Describe the high level tasks to achieve the work package objectives. 2. 3. 4. 5. 6. 7. 8. 9. 10.
Significant equipment, materials or subcontractors utilised |  |  | This is used to help us understand how your plan relates to spend in these areas
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M1 | [5 empty] | To be populated in delivery
M2 | [5 empty] | To be populated in delivery
M3 | [5 empty] | To be populated in delivery
M4 | [5 empty] | To be populated in delivery
M5 | [5 empty] | To be populated in delivery
M6 | [5 empty] | To be populated in delivery
M7 | [5 empty] | To be populated in delivery
M8 | [5 empty] | To be populated in delivery
M9 | [5 empty] | To be populated in delivery
M10 | [5 empty] | To be populated in delivery
|  |  |  | Total: |  | 0
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D1
D2
D3
D4
D5
Work Package Description (Repeat for each Work Package)
Work Package Number | #REF! | Work Package Title | #REF! | Lead Partner | #REF!
Overall Work Package Objectives |  |  | Key Tasks | 1. Describe the high level tasks to achieve the work package objectives. 2. 3. 4. 5. 6. 7. 8. 9. 10.
Significant equipment, materials or subcontractors utilised |  |  | This is used to help us understand how your plan relates to spend in these areas
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M1 | [5 empty] | To be populated in delivery
M2 | [5 empty] | To be populated in delivery
M3 | [5 empty] | To be populated in delivery
M4 | [5 empty] | To be populated in delivery
M5 | [5 empty] | To be populated in delivery
M6 | [5 empty] | To be populated in delivery
M7 | [5 empty] | To be populated in delivery
M8 | [5 empty] | To be populated in delivery
M9 | [5 empty] | To be populated in delivery
M10 | [5 empty] | To be populated in delivery
|  |  |  | Total: |  | 0
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D1
D2
D3
D4
D5
Work Package Description (Repeat for each Work Package)
Work Package Number | #REF! | Work Package Title | #REF! | Lead Partner | #REF!
Overall Work Package Objectives |  |  | Key Tasks | 1. Describe the high level tasks to achieve the work package objectives. 2. 3. 4. 5. 6. 7. 8. 9. 10.
Significant equipment, materials or subcontractors utilised |  |  | This is used to help us understand how your plan relates to spend in these areas
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M1 | [5 empty] | To be populated in delivery
M2 | [5 empty] | To be populated in delivery
M3 | [5 empty] | To be populated in delivery
M4 | [5 empty] | To be populated in delivery
M5 | [5 empty] | To be populated in delivery
M6 | [5 empty] | To be populated in delivery
M7 | [5 empty] | To be populated in delivery
M8 | [5 empty] | To be populated in delivery
M9 | [5 empty] | To be populated in delivery
M10 | [5 empty] | To be populated in delivery
|  |  |  | Total: |  | 0
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D1
D2
D3
D4
D5
Work Package Description (Repeat for each Work Package)
Work Package Number | #REF! | Work Package Title | #REF! | Lead Partner | #REF!
Overall Work Package Objectives |  |  | Key Tasks | 1. Describe the high level tasks to achieve the work package objectives. 2. 3. 4. 5. 6. 7. 8. 9. 10.
Significant equipment, materials or subcontractors utilised |  |  | This is used to help us understand how your plan relates to spend in these areas
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M1 | [5 empty] | To be populated in delivery
M2 | [5 empty] | To be populated in delivery
M3 | [5 empty] | To be populated in delivery
M4 | [5 empty] | To be populated in delivery
M5 | [5 empty] | To be populated in delivery
M6 | [5 empty] | To be populated in delivery
M7 | [5 empty] | To be populated in delivery
M8 | [5 empty] | To be populated in delivery
M9 | [5 empty] | To be populated in delivery
M10 | [5 empty] | To be populated in delivery
|  |  |  | Total: |  | 0
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D1
D2
D3
D4
D5
Work Package Description (Repeat for each Work Package)
Work Package Number | #REF! | Work Package Title | #REF! | Lead Partner | #REF!
Overall Work Package Objectives |  |  | Key Tasks | 1. Describe the high level tasks to achieve the work package objectives. 2. 3. 4. 5. 6. 7. 8. 9. 10.
Significant equipment, materials or subcontractors utilised |  |  | This is used to help us understand how your plan relates to spend in these areas
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M1 | [5 empty] | To be populated in delivery
M2 | [5 empty] | To be populated in delivery
M3 | [5 empty] | To be populated in delivery
M4 | [5 empty] | To be populated in delivery
M5 | [5 empty] | To be populated in delivery
M6 | [5 empty] | To be populated in delivery
M7 | [5 empty] | To be populated in delivery
M8 | [5 empty] | To be populated in delivery
M9 | [5 empty] | To be populated in delivery
M10 | [5 empty] | To be populated in delivery
|  |  |  | Total: |  | 0
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D1
D2
D3
D4
D5
Work Package Description (Repeat for each Work Package)
Work Package Number | #REF! | Work Package Title | #REF! | Lead Partner | #REF!
Overall Work Package Objectives |  |  | Key Tasks | 1. Describe the high level tasks to achieve the work package objectives. 2. 3. 4. 5. 6. 7. 8. 9. 10.
Significant equipment, materials or subcontractors utilised |  |  | This is used to help us understand how your plan relates to spend in these areas
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M1 | [5 empty] | To be populated in delivery
M2 | [5 empty] | To be populated in delivery
M3 | [5 empty] | To be populated in delivery
M4 | [5 empty] | To be populated in delivery
M5 | [5 empty] | To be populated in delivery
M6 | [5 empty] | To be populated in delivery
M7 | [5 empty] | To be populated in delivery
M8 | [5 empty] | To be populated in delivery
M9 | [5 empty] | To be populated in delivery
M10 | [5 empty] | To be populated in delivery
|  |  |  | Total: |  | 0
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D1
D2
D3
D4
D5
Work Package Description (Repeat for each Work Package)
Work Package Number | #REF! | Work Package Title | #REF! | Lead Partner | #REF!
Overall Work Package Objectives |  |  | Key Tasks | 1. Describe the high level tasks to achieve the work package objectives. 2. 3. 4. 5. 6. 7. 8. 9. 10.
Significant equipment, materials or subcontractors utilised |  |  | This is used to help us understand how your plan relates to spend in these areas
Summary of Milestones
Ref | Milestone Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | SIF funding request per milestone (£) | Actual Spend to date per Milestone
M1 | [5 empty] | To be populated in delivery
M2 | [5 empty] | To be populated in delivery
M3 | [5 empty] | To be populated in delivery
M4 | [5 empty] | To be populated in delivery
M5 | [5 empty] | To be populated in delivery
M6 | [5 empty] | To be populated in delivery
M7 | [5 empty] | To be populated in delivery
M8 | [5 empty] | To be populated in delivery
M9 | [5 empty] | To be populated in delivery
M10 | [5 empty] | To be populated in delivery
|  |  |  | Total: |  | 0
Summary of Deliverables
Ref | Deliverable Title | Success Criteria | Partner Responsible (drop down) | Due Date (dd/mm/yyyy) | Status (Drop down
D1
D2
D3
D4
D5
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F173: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F202: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F231: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .
Note on F260: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please note that total of SIF funding requested per milestones should equal the total approved amount for SIF funding .

## Risk Register
Risk Register
Guidance
This is an mandatory tab for a risk register.
Ref | Risk Description | Likelihood (Low/Medium/High) | Impact (Low/Medium/High) | Migitation | Related Work Package (drop down) | Risk Owner (drop down) | Status (drop down)
Technical
R1 | Conflicting requirements from different stakeholders | Medium | Medium | Requirements will be assessed to determine which are mandatory and which are desireable. Any conflicting requirements will be discussed with key stakeholders to identify the requirement which will provide maximum benefit to the output. This will be performed by understanding the key use cases associated with requirements. The DNO stakeholder engagement plan means that we will also capture common use cases across DNOs helping focus on a set of requirements that maximum benefits across DNOs (as well as the NGESO) in the Alpha phase. | WP1 | Frazer-Nash Consultancy | Closed
R2 | Solution fails to identify key constraints/barriers which impacts project feasibility | Low | Medium | A stakeholder requirements workshops is planned with ESO, NPG and is to include different teams from these organisations to fully characterise requirements, constraints, barriers etc. Frazer-Nash are highly experience at capturing and developing requirements for novel technology solutions and digital tools. The workshop will combine both a systems engineering and software development approach to ensure we have explored and captured the development envolope. | WP1 | Frazer-Nash Consultancy | Closed
R3 | Policy or regulations change during the delivery of the project which impacts the scope and/or feasibility of the proposed solution | Low | Low | Horizon scanning to be undertaken on an ongoing basis for early identification of any relevant changes. Impact assessments will be conducted in the event of any policy or regulatory changes to confirm the ongoing viability of the project. The project kick-off will include a horizon scanning exercise. | WP1 | Frazer-Nash Consultancy | Closed
R4 | Provision of a fully DNO/supplier-agnostic solution is not achievable with existing equipment. | Medium | Medium | DNO/supplier-agnostic solutions will be sought where possible. NPG is considered to be representative of other DNOs for this initial stage but wider DNO engagement may be needed during the alpha phase. | WP1 | Frazer-Nash Consultancy | Closed
R5 | It takes time to get up to speed with the new OFGEM CBA tool and CBA requirements. | Low | Low | FNC have experience in a range of CBA analysis methods and tools within a power transmission and distribution setting. Time has been built into WP2 to enable familiarisation of the tool and how this affects the CBA. | WP2 | Frazer-Nash Consultancy | Closed
Project Managament
R5 | Key project personnel are unable to dedicate time to delivery, due to unplanned leave or other project commitments. | Low | Medium | Resources have be notified and a FNC have had an internal kick-off with the project team and informed both NPg and ESO partners. Key resources have notified of avaliablity throughout the discovery phase and this has been accounted for in planning. Short-notice resource issues will be managed by resource managers. Frazer-Nash have a large and diverse resource pool which will support mitigation of this risk. | All | All | Closed
R6
R7
R8
R9
R10
R11
R12
R13
R14
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25

## Lists (hidden)
Status
Advanced Propulsion Centre (APC)
Completed |  | BEIS (Define in description)
In Progress |  | Department For Transport
European Commission
International Funding
Risk |  | NIA - Network Innovation Allowance
NIC - Network Innovation Competition
Low |  | Other (Define in description)
Medium |  | UKRI (Define in description)
High
Yes
No | Open
Closed