## Sheet1
Ref | Risk Description | Mitigation | Related Work Package (drop down) | Risk Owner | Status
|  |  |  | (drop down) | (drop down)
R1 | NGESO resource availability to support the essential workshops planned during WP1 | Placeholder invites for the workshops have provisionally been sent to key personnel already | WP1 | ESO | Closed
R2 | Key project partner personnel are unable to dedicate time to delivery, due to holidays, unplanned leave or other project commitments. | Have considerable strength-in-depth in our team that we could draw on if we lose key project members. | All | All | Closed
R3 | Lack of clarify regarding the scope to be delivered by partners results in rework, duplication of effort or a breakdown in working relationship. | The scope which is to be delivered by the various project team members has been formally agreed during the initial project scoping stages. Strong communications channel between partners already exists and these have been used effectively to clarify delivery scope and project tasking. | All | All | Closed
R4 | Inconsistency of Deliverables due to multiple authors. | Mitigated through the Quality Management System requiring verification and approval prior to distribution. Partner will agree a structure before starting and getting everyone to present progress during weekly meetings. | All | Frazer-Nash | Closed
R5 | Different stakeholders have different priorities for focus on most suitable technique to develop during Alpha Phase. | Multicriteria Decision Analysis will be used to help decide the most appropriate technique to be used, with criteria established with stakeholders. | WP4 | ESO; Frazer-Nash | Closed
R6 | Difficulty mobilising as project partners haven't yet agreed contract terms or collaborations agreements | Frazer-Nash and NGET have agreed terms with ESO on previous SIF projects so this should mitigate teh risk. Also Collaboration agreement negotiations will commence early in the new year. | All | ESO | Closed
R7 | Potential of scope creep, due the size of the challenge we are addressing | Project Manager and Technical Lead will be in regular communication about progress, making sure the project maintains focussed on the Discovery Phase objectives and scope. Scope bounds will be drawn during the KO meeting and vision statement tasks | All | ESO; Frazer-Nash | Closed