## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | ​​Martin Cahill​ | ​​Develop a table or flowchart to illustrate various scenarios for how generators will be treated under the proposed threshold change. This will provide clarity and will be reviewed by the Workgroup to help to refine the proposed solution.​ To include different MW sized generators, new vs change to capacity, and demand connections with generation attached. | Provided in WG3 | 2025-01-30 | Closed | WG3
2 | WG1 | ​​Martin Cahill | ​​Consider potential future risks and mitigations. for discussion at the next Workgroup meeting. Specifically, to consider: - What work is already in place to assess cumulative impact of smaller generators - Is there a need to be able to roll back increase if too many projects in 1-5MW range apply - What other mitigations are, or will be in place | Discussed in WG2 | 2025-01-30 | Closed | WG2
3 | WG1 | ​​Martin Cahill | ​​With regards to data presented to illustrate the total England and Wales accepted DER by technology, the Proposer took an action to provide up to date data and further clarity on what the data represents.​ | Discussed in WG2 | 2025-01-30 | Closed | WG2
4 | WG1 | ​​Martin Cahill | ​​Send out the draft legal text to Workgroup members to review​ | Completed following WG1 | 2025-01-30 | Closed | WG2
5 | WG1 | ​​Martin Cahill | ​​The Proposer took an action to develop the implementation timelines for CMP446 in relation to CMP434 and CMP435 further, considering different decision outcomes.​ | Provided in WG3 | 2025-01-30 | Closed | WG3
6 | WG1 | ​​Martin Cahill | ​​The Proposer took an action to keep the Workgroup of Modification GC0139 updated on the progress of this Modification in case there is any cross over.​ | Completed following WG1 | 2025-01-30 | Closed | WG2
7 | WG1 | ​​Martin Cahill | ​​Clarify the definition of MW capacity to be used, as different terms such as installed capacity, export capacity, and developer capacity are used inconsistently.​ | Discussed in WG3 | 2025-01-30 | Closed | WG3
8 | WG1 | ​​Martin Cahill | ​​Provide a clear explanation and documentation on why Scotland codification is excluded from the defect, including legal, strategic, and practical reasons​ | Discussed in WG2 | 2025-01-30 | Closed | WG2
9 | WG1 | ​​Milly Lewis | ​​The Chair took an action to remove item J from the Terms of Reference. There was also a minor amendment to item (i).​ | Completed following WG1 | 2025-01-30 | Closed | WG2
10 | WG1 | Martin Cahill | Provide explanation of CP30 interaction at TI and DNO level | Discussed in WG2 | 2025-01-30 | Closed | WG2
11 | WG2 | Daniel Clarke | Workgroup members discussed GSPs that have no fault level headroom and therefore would be subject to current processes. A Workgroup member took an action to investigate whether a list of these GSPs could be provided. | Discussed in WG4 | 2025-02-03 | Closed | WG4
12 | WG2 | Brian Hoy | A Workgroup member took an action to update the table of different scenarios with columns for existing and requested capacities. This table will include columns for installed and export capacity and whether a TIA would be required for each capacity type per scenario. | Discussed in WG3 | 2025-02-03 | Closed | WG3
13 | WG2 | Martin Cahill | The proposer took an action to send an up-to-date pie chart confirming total accepted DER by technology in MW to Workgroup members and to ensure the up-to-date figures are added into the Workgroup consultation. | Discussed in WG3 | 2025-02-03 | Closed | WG3
14 | WG2 | Martin Cahill | The Proposer took an action to make it clear that implementation refers to legal text implementation, to add some example timings, and to make it clear that removal of existing REPs only refers to yet to be connected | Discussed in WG3 | 2025-02-03 | Closed | WG3
15 | WG2 | Martin Cahill | Confirm the plan for communications for existing projects, whether they do or do not have to do apply for Gate 2. It was noted that this could be the responsibility of DNOs, however this will be confirmed. | Discussed in WG6 | 2025-02-03 | Closed | WG6
16 | WG2 | Martin Cahill | The Proposer took an action to update the wording in the proposed legal text to change “it is agreed that” to “it is acknowledged that”... “only an Embedded Small Power Station which is 5MW or above is a Relevant Embedded Power Station requiring the submission of an Evaluation of Transmission Impact to The Company in accordance with Paragraph 5.1(a)” | Discussed in WG3 | 2025-02-03 | Closed | WG3
17 | WG2 | Martin Cahill | Following feedback from Workgroup 2, NESO to determine whether the proposal should include a definition of capacity to be used in the legal text and whether this should be based on Registered Capacity, Developer Capacity or anything different. | Discussed in WG3 | 2025-02-03 | Closed | WG3
18 | WG2 | Kate Teubner | A Workgroup Member took at action to create a list of scenarios where there could be a cross over between this Modification and Clean Power 2030 to look at in the next Workgroup meeting. | Discussed in WG3 | 2025-02-03 | Closed | WG3
19 | WG3 | ​​Drew Johnstone​ | ​​Workgroup Members noted that example scenario 12 on the table for ‘Action 12 – Version 2’ should be ‘No’ for ‘Installed Capacity’ and ‘Same’ for ‘Outcome check’. A Workgroup Member will update the table accordingly.​ | Discussed in WG4 | 2025-02-05 | Closed | WG4
20 | WG3 | ​​Zivanayi Musanhi​ | ​​A Workgroup Member has agreed to update the table for ‘Action 12 – Version 2’ to include scenarios where the ‘Export capacity’ is at zero in both the ‘Existing’ and ‘New’. ​ | Discussed in WG4 | 2025-02-05 | Closed | WG4
21 | WG3 | ​​Garth Graham​ | ​​A Workgroup Member has agreed to raise a WACM where export capacity is used as the underlying measure, as opposed to registered/installed capacity as in the Original Proposal. ​ | Raised in WG4 | 2025-02-05 | Closed | WG4
22 | WG3 | ​​Martin Cahill​ | ​​Proposer agreed to update the timeline slide (“TM04 & CMP Timing”) to ensure the dates used are consistent across each example timeline and are clearly marked as for information/indicative only.​ | Discussed in WG4 | 2025-02-05 | Closed | WG4
23 | WG3 | ​​Martin Cahill​ | ​​Proposer will check the wording of the proposed legal text, to ensure it does not inadvertently exclude medium sized power stations.​ | Discussed in WG4 | 2025-02-05 | Closed | WG4
24 | WG4 | Martin Cahill | The Proposer took an action to ensure that the fault level headroom considerations are clearly documented in the Workgroup consultation, including any necessary legal text adjustments. | Discussed in WG8 | 2025-03-07 | Closed | WG8
25 | WG4 | Martin Cahill / Dan Clarke | It was confirmed by NGET that a list of GSPs that have no fault level headroom will be made available next week, and that the Proposer will consider what the enduring solution will be for the list to be made available publicly. | Discussed in WG6 | 2025-03-07 | Closed | WG6
26 | WG4 | Garth Graham | The Proposer of Alternative 1 took an action to consider changing the terminology within this proposal from “MVA” to ”MW”. | Discussed in WG8 | 2025-03-07 | Closed | WG8
27 | WG4 | Martin Cahill | The Proposer took an action to speak to Ofgem to clarify the statement within the Workgroup consultation regarding the review by TOs of thresholds in Scotland. This is to ensure a clear understanding of whether a review is currently underway or planned for the future. | Closed following WG5 | 2025-03-07 | Closed | WG5
28 | WG4 | Martin Cahill | The Proposer agreed to review and adjust wording in describing the governance process for the threshold changes. This specifically relates to references to the CDB and CPAG, which don’t have a governance regime in place. | Closed following WG5 | 2025-03-07 | Closed | WG5
29 | WG4 | Martin Cahill | The Proposer took an action to revise the DNO application process section to number the steps and indicate where the process stops for projects under 5 MW. | Closed following WG5 | 2025-03-07 | Closed | WG5
30 | WG4 | Martin Cahill | The Proposer took an action to add a bullet point to the capacity definitions section to explain the rationale behind using installed capacity versus export capacity. | Closed following WG5 | 2025-03-07 | Closed | WG5
31 | WG4 | Alex Markham | With regards to tracking cumulative impact, the NESO Representative took an action to clarify the wording in the Workgroup consultation. | Closed following WG5 | 2025-03-07 | Closed | WG5
32 | WG4 | Alex Markham | The NESO Representative took an action to revise the wording to make the explanation of technical limits clearer and to include a link to the public-facing rule book. A further discussion will be held with Workgroup members on this post-consultation. | Discussed in WG6 | 2025-03-07 | Closed | WG6
33 | WG6 | Martin Cahill | Proposer to consider the inclusion of Trade Associations in the Communications Plan. | Discussed in WG6 | 2025-03-07 | Closed | WG9
34 | WG6 | Martin Cahill | Proposer to share a table with the Workgroup that clarifies the treatment of projects under differing Fault Level Headroom scenarios and to include this in the Workgroup Report. | Discussed in WG8 | 2025-02-24 | Closed | WG8
35 | WG6 | Martin Cahill | Proposer to share updated draft Legal Text with Fault Level Headroom considerations. | Discussed in WG8 | 2025-02-24 | Closed | WG8
36 | WG6 | Martin Cahill | In relation to the 5 MW threshold in the Original Proposal, the Proposer will issue updated Legal Text that clarifies the decimal point issue. | Discussed in WG6 | 2025-03-07 | Closed | WG9
37 | WG6 | Martin Cahill | In relation to the definition of ‘Registered Capacity’, the Proposer will share a table that shows the Distribution Code and Grid Code definitions side-by-side along with their impact on the MW thresholds. | Discussed in WG8 | 2025-02-24 | Closed | WG8
38 | WG8 | Martin Cahill | Adjust the table of scenarios to clearly define the MW ranges, specifically changing the middle row to "1 to less than 5 MW" and the bottom row to "equal to or greater than 5 MW" | Discussed in WG8 | 2025-02-26 | Closed | WG9
39 | WG8 | Martin Cahill / Brian Hoy | Consider including a note in the report about the possibility of quicker responses for 1 to 5 MW connections if no works are required, as suggested by a Workgroup member, who will provide wording. | Discussed in WG8 | 2025-02-26 | Closed | WG9
40 | WG8 | Daniel Clarke | Check if the definition of fault level headroom at the T to D boundary is captured in Appendix G or if it needs to be included in the legal text. | Discussed in WG8 | 2025-02-26 | Closed | WG9
41 | WG8 | Martin Cahill | Review the wording "it is acknowledged that" to ensure that wording is clear and concise | Discussed in WG8 | 2025-02-26 | Closed | WG9
42 | WG8 | Martin Cahill | Double-check the definitions to ensure the correct use of "relevant embedded small power station." | Discussed in WG8 | 2025-02-26 | Closed | WG9
43 | WG8 | Martin Cahill | Ensure the legal text does not conflict with CMP434/435 and consider a tidy-up exercise if needed. | Discussed in WG8 | 2025-02-26 | Closed | WG9
44 | WG8 | Martin Cahill | Add a footnote or additional text to the scenarios table to clarify the processes around fault level headroom and the requirement for a TIA if there is not sufficient headroom. | Discussed in WG8 | 2025-02-26 | Closed | WG9
45 | WG8 | Martin Cahill | Update the scenarios table in the Workgroup Report to reflect the WACM1 approach, which uses export capacity, as well as the Original Proposal. | Discussed in WG8 | 2025-02-26 | Closed | WG9
46 | WG8 | Garth Graham | Include a definition for export capacity within section 6.5.1 to avoid confusion with the existing definition of maximum export capacity. | Discussed in WG8 | 2025-02-26 | Closed | WG9
47 | WG8 | Kate Teubner | The Workgroup requested further rationale of how the 25 MW cap was calculated. The Proposer of WACM3 and WACM4 took an action to confirm this. | Discussed in WG8 | 2025-02-26 | Closed | WG9
48 | WG8 | Kate Teubner | Draft legal text, ensuring it clearly defines the cap and its application. | Discussed in WG8 | 2025-02-26 | ​​Closed post meeting​ | WG10
49 | WG9 | Kate Teubner | Proposer of WACM 3 and 4 to update their proposed Legal Text incorporating Workgroup feedback. | Discussed in WG9 | 27/02/2025 | ​​Closed post meeting​ | WG10