## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | Proposer | The Proposer to share the assumptions for the analysis produced for CMP444 and clarify if there were any assessment for forecast error. |  | 2024-12-04 | Closed | WG2
2 | WG1 | Chair | TORs to be updated at the November CUSC Panel |  | 2024-12-11 | Open | WG2
3 | WG2 | Proposer | Consider the impact of circuits flipping between the peak and year-round backgrounds | Presented thoughts at WG3 - as we are averaging multiple years NESO don't think the issue of circuit flipping needs to be accounted for in the proposal | 2024-12-11 | Closed | WG3
4 | WG2 | Proposer | What major infrastructure assets are included in the 5-year forecast |  | 2024-12-11 | Open
5 | WG2 | Proposer | Explain the degree of alignment with CP30 that is included into the forecast |  | 2024-12-11 | Open
6 | WG3 | Proposer | Consider additional modelling | Presented in WG 9 | 2025-01-09 | Open | WG9
7 | WG4 | Proposer | Map the Original solution to the alternatives submitted for comparison as this will make it easier when voting | comparison chart/table included in wg consultation doc | 2025-01-09 | Closed | WG 6
8 | WG4 | Proposer | Check the output of the workbook to ensure it is not still looking at the wrong floor. | corrected example tariff output calculation to look at the percentile methodology | 2025-01-09 | Closed | WG 6
9 | WG4 | Proposer | Create a diagrammatic explanation of the methodology for the potential alternative solution. | Will address post consultation | 2025-01-09 | Open
10 | WG4 | Proposer | Reach out to the proposers to agree on a common format for presenting the results of the analysis. | Results of the analysis are included in th workgroup consultation | 2025-01-09 | Closed | WG6
11 | WG7 | Chair | Liaise with Authority and Chair of CMP432 to clarify expectations and alignment with CMP444 | Clairified in WG8 | 2025-02-06 | Closed | WG8
12 | WG7 | Alternative Proposers | Provide the initial CAP and floor values for each component to Niall for analysis. | The proposer presented in WG8 | 2025-02-06 | Closed | WG8
13 | WG7 | Proposer | Provide clarity on defect and scope of CMP444 | The proposer presented in WG8 | 2025-02-06 | Closed | WG8
14 | WG9 | Proposer WACM 3 (Mark Smeed) | Clarify the impacts of the data set change in WACM 3 |  | 2025-02-17 | Open | WG10
15 | WG10 | Chris White | Adjust the graph to show the data in absolute values instead of percentages, and in pounds per kilowatt. |  | 2025-02-17 | Open | WG11
16
17
18
19
20