## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | ND | Share the SECULF model with the work group to enable replication of the calculation. | NESO are unable to share as the data contained within the SECULF methodology is NESO intellectual Property and contains commercially sensitive information. Legal Position NESO is unable to release the infro,ation requested due to confidentiality issues and supported in CUSC and Utiilities Act: CUSC 6.15- and associated License condition to comply with CUSC. Utilities Act Section 105 | WG2 | Closed | WG3
2 | WG1 | Proposer & PJ | Submit written arguments detailing the implications of the security factor on network reinforcement and incremental cost, including perspectives on whether it implies an ever-growing N minus number. | This was covered in presentations given by the Proposer and the Workgroup member in Workgroup 2 | WG2 | Closed | WG2
3 | WG1 | ND | NESO to speak to teams internally to request industry access to VBA code within the Transport and Tariff Model | See comments in Action 1 | WG2 | Closed | WG3
4 | WG1 | Proposer | Share the SSE Consultant’s report | Circulated to Workgroup members and presented on 14 February 2025 | WG2 | Closed | WG3
5 | WG1 | Chair | Liaise with the Chair of CMP444 to ensure modifications are running in alignment. | Spoke to the chair and the modifications are aligned, with HH from OFGEM also confirming this | WG2 | Closed | WG2
6 | WG2 | Chair | Loop in with the Chair of CMP444 regarding an Ofgem call | Spoke to CG but I wasn't needed for the call as they are two separate modifications with different timelines The FMRs will be submitted to Ofgem with a few weeks difference and will align for the authority decision We will record the interactions in our report | WG3 | Closed | WG3
7 | WG2 | Chair | Reach out to suggested members to join the Workgroup | Email sent on 07/02 to NGET | WG3 | Closed | WG3
8 | WG2 | Chair | Send invites with the amended time for the next Workgroup | Actioned | WG3 | Closed | WG3
9 | WG2 | ND | Keep Workgroup Updated on whether an SME from NESO can attend the next Workgroup | NESO SME was unable to attend the Workgroup on 18/02 and was therefore cancelled | WG3 | Closed | WG3
10 | WG3 | ND | Circulate the Workgroup members email and ask NESO for a response to the data request | See comments in Action 1 | WG4 | Closed | WG4
11 | WG3 | ND | Request legal opinion from NESO to support why certain data cannot be shared | See comments in Action 1 | WG4 | Closed | WG4
12 | WG3 | ND | Request written response from NESO regarding blockers and why certain data cannot be shared | See comments in Action 1 | WG4 | Closed | WG4
13 | WG3 | ND | Confirm internally with NESO if independent auditing is an option |  | WG4 | Open | Ongoing
14 | WG3 | Chair | Follow up with suggested members to invite them to the Workgroups | An email was sent and received a reponse advising 'they will consider if they can provide any useful input ahead of these meetings and might reach out'. | WG4 | Closed | WG4
15 | WG3 | ND | Organise a Teach-in with a NESO SME to explain the Security Factor calculation |  | WG4 | Open | Ongoing
16 | WG3 | Chair | Collate the Workgroup members list of questions for NESO to provide detailed responses to each question listed. | Questions have been collated and are now with NESO to respond to. | WG4 | Open
17 | WG4 | ND | Obtain draft tariff demand and generation to include in the consultation | An email was sent to Workgroup members on 24/02 attaching analyisis showing the impact of CMP432 on current tarrifs. | WG5 | Closed | WG5
20 | WG5 | ND | Assess possibility of modelling mod impacts on tariffs for the workgroup consultation document. | It was agreed that it was too late to ask for this data ahead of the Workgroup Consultation and could be something to be considered for the Workgroup Report if members think it is necessary | WG6 | Closed | WG6
21 | WG6 | Chair | Add a discussion about the impact of the proposed modification on existing Generators at both ends of the country to the agenda for the next meeting. | Discussion took place on WG7 | WG 7/8 | Closed | WG7
22 | WG7 | Chair | Review the 'applicable objectives' section on the Workgroup Consultation where the responses was No or NA and feedback Workgroup members | Data captured and will be added to the Workgroup Report | WG8
23 | WG7 | ND | Analysis on the longer term impact on tariffs and modelling | Have emailed ND the 'ask' | WG8/9
24 | WG7 | Chair | Capture the comment from the Battery company on impact on different technologies in the Workgroup Consultation | Comment captured and will be added to the Workgroup Report | WG8
25 | WG7 | Chair | Re share the questions collated for NESO to gather any additional requests before they are answered | Emailed Workgroup members on 17/03/2025 and reshared the updated list with ND 18/03/25 | WG8 | Closed
26 | WG7 | Chair | Send a new Workgroup member the legal text amendments that were sent to the Workgroup last week | Sent - 13/03/25 | WG8 | Closed
27 | WG7 | Proposer/SSE | Remote Island links- Investigate why they are not built with redundancy, unlike onshore to onshore. (Legal text) |  | WG9 | Open