## Slide 1: Stability Phase 1
Provider Availability Notifications
July 2025

## Slide 2
Background
Providers need to notify us of any periods where they will have an outage, planned maintenance, or they will be unavailable to provide their contacted service for a period of time, as per the Commercial Contractual arrangement for Stability Phase 1 (Stability Pathfinder Agreement – Phase 1)
Overview of the provider notification process
Providers are required to follow different processes dependant on the amount of notice being given to the NESO
This is summarised in slides 3-5
12 months ahead
Less than 24 hours ahead
12 months to 24 hours ahead
Providers are required to submit a Planned Maintenance Programme
The Network Planning team will review
This is explained further in slide 3
Providers are required to submit any details of Unplanned Outages or Reduction in Capability
The forms can be submitted to the Control Room via email
This is explained further in slide 5
Providers are required to submit any details of Planned Outages or Reduction in Capability
This information can be submitted via eNAMS or by populating a standardised template/proforma and returning it to the NESO via email
This is explained further in slide 4
Overview
Notice period prior to Delivery

## Slide 3: Planned Outages (Maintenance Programme)
Summary
As per section 3 of the Stability Pathfinder Agreement – Phase 1 – providers are required to submit a Planned Maintenance Programme prior to the start of each contract year.
Contractual Information
3.1.2 - In accordance with the timescales and provisions of the Grid Code, the Provider shall notify the Company of all planned maintenance and inspection periods applicable to the Facility (“Maintenance Plan”) for the forthcoming year (except that for the last year of this Agreement, the Maintenance Plan shall be applicable only for the relevant portion of the forthcoming year). Within fourteen (14) days of such notification, the Company shall notify the Provider of its agreement (which shall not be unreasonably withheld) with or objections to the Maintenance Plan and, if the Company shall make no notification within such time, it shall become binding on the Parties. The Parties shall act in good faith and use reasonable endeavours to resolve any objections notified by the Company taking into account maintenance practices consistent with Good Industry Practice and the Maintenance Plan shall be amended accordingly
3.1.3 - The Provider shall be entitled to payment for Availability in respect of any period specified in the Maintenance Plan in which the Facility will be Unavailable to the extent of (unless the Parties agree otherwise) a maximum of fifteen (15) days in any period of twelve (12) calendar months (to be reduced on a pro rata basis where the Maintenance Plan covers a period of less than twelve (12) calendar months.
Process for Provider Notifications
Providers can send a Maintenance Plan to the following email addresses at the start of each Contract Year
    England & Wales: tranreq@neso.energy
    Scotland: TRScotland@neso.energy
  Within fourteen (14) day`s NESO will notify the provider of agreement or any objections/feedback to the Maintenance Plan. If no response is received within 14 days the provider can assume that the plan has been accepted
  The NESO Network Planning team will utilise the information provided to update the eNAMS system accordingly
12 months ahead

## Slide 4: Planned Outages/Reduction in Capability
Summary
As per section 3 of the Stability Pathfinder Agreement – Phase 1 – providers are required to make the NESO aware of any outages or reductions in capability as soon as possible
Contractual Information
3.4 - Each Notice of Unavailability shall be accompanied by an explanation in reasonable detail of the reasons for the Facility being Unavailable, which, in relation to the Summer Period in any Contract Year may relate to technical issues concerning the Facility.
Process for Provider Notifications
  Providers have 2 options for submitting this information to NESO :-​
Via eNAMS – providers can request access to eNAMS (a NESO planning tool) and add information about their outages​
Via email – alternatively, providers are required to complete a template/proforma and send it to the following email addresses​
    England & Wales: tranreq@neso.energy
    Scotland: TRScotland@neso.energy
  With option 2 – the completed template/proforma will be reviewed by NESO’s Network Planning team and the information will be added to eNAMS on the providers behalf
  To understand the impact of reductions in capability providers should refer to Schedule F – Payments of their Stability Pathfinder Agreement
12 months to 24 hours ahead

## Slide 5: Unplanned Outages / Reduction in Capability
Summary
As per section 3 of the Stability Pathfinder Agreement – Phase 1 – providers are required to make the NESO aware of any notification of unavailability as soon as possible
Contractual Information
3.3 - If at any time the Provider becomes aware that the Facility is no longer, or will no longer be, Available, it shall promptly notify the Company that the Facility is Unavailable by facsimile in the form set out in Form A in Schedule H (‘Notice of Unavailability’), including where the Facility is Unavailable because it is either: (i) exporting Active Power or (ii) importing Active Power otherwise than for the sole purpose of operating in Synchronous Compensation mode (or, in the case of a pumped storage plant, importing Active Power for operation of the pumps).
3.4 - Each Notice of Unavailability shall be accompanied by an explanation in reasonable detail of the reasons for the Facility being Unavailable, which, in relation to the Summer Period in any Contract Year may relate to technical issues concerning the Facility.
3.5- Following a Notice of Unavailability, (other than where the Facility is Unavailable by reason of (i) exporting Active Power or (ii) importing Active Power for the purpose of operating in Synchronous Compensation mode (or, in the case of a pumped storage plant, importing Active Power for operation of the pumps)), the Provider shall take all reasonable steps to restore the capability of the Facility to provide the Stability Compensation Service (and keep the Company reasonably informed of progress in restoring such capability) and shall notify the Company by notice by facsimile in the form set out in Form B Schedule H (“Availability Restoration Notice”) when that capability has been restored.
Process for Provider Notifications
In this instance, given the short timescales, provider notifications have to be sent directly to NESO’s Control Room and Network Planning Team
2 forms are available to cover the different scenarios (these are all available in Schedule H of the Stability Pathfinder Contract)
FORM A - DECLARATION OF UNAVAILABILITY
FORM B - RESTORATION OF AVAILABILITY
Once completed the relevant form needs to be sent via email as per the below :-
    Email address: ctr1.ccta@neso.energy AND
    England & Wales - tranreq@neso.energy OR Scotland - TRScotland@neso.energy
Provider will also need to place a phone call to the relevant control room desk if they become partially or fully unavailable in control timescales.
  The NESO Network Planning team will review the forms, and utilise the information provided to update the eNAMS system accordingly
  To understand the impact of reductions in capability providers should refer to Schedule F – Payments of their Stability Pathfinder Agreement
Less than 24 hours ahead