## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
​​18​ | WG 20 | TP | ​​Chair to clearly label and organise folders within SharePoint​ |  | WG21 | Closed | WG21
​​19​ | ​​WG 20​ | ​​TP​ | ​​Chair to send out WG invites for November ​ |  | WG21 | Closed | WG21
​​20​ | ​​WG 20​ | ​​AC​ | WG member to circulate proposed P2/9 draft revised definitions |  | WG21 | Closed | WG21
21 | WG21 | SML, PT, GV, AB | ToR a) Implementation and costs - Further work required on this to understand full extent of impact and cost. NESO - SM and PT GV - SPEN AB - TO Scot |  | WG22 | Closed
22 | WG21 | IP | Flag to INA when Workgroup consultation will be |  | WG22 | Closed
23 | WG21 | IP and GV | ToR g) Consider the Ofgem Letter of 10 January 2022 Looks at this in more detail | This has been considered and will just need noting in WG cons | WG22 | Closed
24 | WG21 | GL/SM | Discuss GSR029 with proposor to ensure alignment of 'Group Demand' definition | The Proposer confirm the definition ‘Group Demand’ aligns. Discussions and agreement took place in a subgroup with the Proposer of GSR029 | WG22 | Closed | WG25
25 | WG21 | All | Review legal text and provide final comment |  | WG22 | Closed
26 | WG21 | SML, IP | Legal text to be amended post 13 Dec and final version added to most up to date baseline |  | WG22 | Closed
27 | WG21 | TP | Amend and update Workgroup Consultation document and send to IP for further review |  | WG22 | Closed
28 | WG22 | IP | Look at wordinf of TORs item (i) |  | WG23 | Closed
29 | WG22 | PT / SML | Supply update on costs around implementation. |  | WG23 | Closed
30 | WG22 | TP | Circulate document and legal text |  | WG23 | Closed
31 | WG22 | IP/TP | to look at introductory text for introducing any changes to the DRC and Schedules |  | WG23 | Closed
32 | WG22 | ALL | To review documents and legal text by lunchtime 29 Nov |  | WG23 | Closed
33 | WG22 | SMC | To finalise baseline to a final point. |  | WG23 | Closed
34 | WG22 | TP | To share links and or documents |  | WG23 | Closed
35 | WG22 | PT | To identify any consequential changes to STC/STCP | SML confirmed this could be closed. This will be looked at once after completion of this modification and network models are solidified. |  | Closed | WG25
36 | WG23 | PT | WG23 - Provide INA with the slide pack related to option 4 and invite them to reach out with any concerns. |  | WG24 | Closed
37 | WG23 | SA | Schedule a meeting with NGED (SW) & the Proposer (IP) to address the concerns raised by UK Power Networks. The meeting will include a detailed discussion on the GAP analysis and the maturity of the CIM format to ensure alignment and confidence in the implementation approach. |  | WG24 | Closed
38 | WG23 | IP | Discuss with Graham from Scottish Power to clarify the details required to determine whether additional costs would be incurred to implement the proposal | This will be captured in 39 | WG24 | Closed
39 | WG23 | IP/TP | Create a pro-forma for the DNOs to estimate the costs associated with implementing the proposal |  | WG24 | Closed
40 | WG23 | TP | TP to inform the Panel of the revised timeline, indicating that the Workgroup Report is anticipated to be ready by July 2025. | Going to May Panel | WG24 | Closed
41 | WG24 | IP | IP to share slides from NESO event with INA | Email Sent on 27 May | WG25 | Closed | WG25
42 | WG24 | All | SML to share with TP. TP to share with the WG for completion before 06 June | SML shared the proforma. | WG25 | Closed | WG25
43 | WG24 | IP/PT/AC | Arrange further discussion regarding the need for NESO led group for governance and process for reporting to BSI | IP confirmed discussions took place in the ENA subgroup and will be handed over to VSI. | WG25 | Closed | WG25
44 | WG25 | SML | Review the DRC Schedule Excel spreadsheet and make suggested changes. | The SME confirmed amendments to the DRC Schedule including the aggregated energy source dropdown on the Spreadsheet had been made. | WG26 | Closed | WG26
45 | WG25 | SML/ Code Team | Confirm whether NESO is able to publish the DRC Schedule Excel spreadsheet online | SML to speak to Legal | WG26 | Open | WG28
46 | WG25 | Code team | Consider how the DRC Schedule will be governed in the future | SML to speak to Legal | WG26 | Open | WG28
47 | WG25 | SML | Investigate confidentiality and potential NDA's between NESO/ TOs/ DNOs. | The Chair circulated NESO’s legal team’s response to Workgroup Members stating that the Grid Code already has existing confidentiality provisions at GC.12. GC.12.1 signposts to the confidentiality provisions contained in CUSC. As a result, there is no need for additional confidentiality clauses in the Planning Code or an NDA/Data Sharing Agreement. A Workgroup Member confirmed that this is not covered by the Electricity Act, so hence the current/future data sharing would be the same. | WG26 | Closed | WG26
48 | WG25 | SML | Consider how to reference PC Data Exchange Timeline in legal text for PC9 and PC10 with disclaimer | The SME confirmed that the existing reference for PC data exchange timeline and legal text for PC 9 and 10 with disclaimer, was already in place since before December 2024. | WG26 | Closed | WG26
49 | WG25 | SML | Review DRC Schedule Word document tables and that it aligns with Excel version | The DCR Schedules were reviewed following amendments made as required by Action 44. | WG26 | Closed | WG26
50 | WG25 | SML/AC/IP | Consider Term or Reference f) and how it will be met. Review GC0106 and the SOGL Observability Area | The Chair confirmed a Workgroup member had provided Annex 10 to deal with Terms of Reference (f) point | WG26 | Closed | WG26
51 | WG25 | IP | Review GAP analysis in Workgroup Report | The Proposer confirmed the ‘Gap Analysis’ section in the Workgroup Report has been removed as the new defined terms are correctly detailed in the Section titled ‘GB SQSS Review – GSR029’. | WG26 | Closed | WG26
52 | WG25 | IP | Review CIM background in Workgroup Report | The Proposer confirmed they had amended the Workgroup Report to include more text around CIM background. | WG26 | Closed | WG26
53 | WG25 | SML | Reword how Term of Reference a) is being met and how to split the average cost out | The SME confirmed Terms of Reference (a) had been discussed in the subgroup and amended the wording in the Workgroup Report. | WG26 | Closed | WG26
54 | WG25 | All | Review legal text and Workgroup report with comments and tracked changes prior to next Workgroup meeting on 12 August | The NESO Representative confirmed the legal text changes and wording in the Workgroup Report had been amended to clarify NESO cost breakdown and year one versus ongoing costs on setup and annual costs for Network Operators | WG26 | Closed | WG28
55 | WG25 | SML | Review interactions with CMP434 | The SME confirmed they were satisfied that consideration had been given to CMP434. Discussions were held in the subgroup, in particular around Schedule 28, and confirmed TOs were satisfied with the changes made. | WG26 | Closed | WG26
56 | WG25 | IP/AC/SML | The implications associated with IDNOs and the PSM | The SME confirmed that approval had been given to the Legal Text by the subgroup. | WG26 | Closed | WG26
57 | WG26 | SML | Reword or restructure the section on NESO cost breakdown and year one versus ongoing costs, ensuring clarity on setup and annual costs for Network Operators. | The NESO Representative confirmed the legal text changes and wording in the Workgroup Report had been amended to clarify NESO cost breakdown and year one versus ongoing costs on setup and annual costs for Network Operators | WG27 | Closed | WG28
58 | WG26 | GV, Chair | Discuss minor amendments to Annex 10 with AC offline. | The Workgroup were happy that Annex 10 addressed terms of reference f). | WG27 | Closed | WG28