## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
9 | WG2 | MG | Provide detail on bipole / rigid bipole faults |  | ​​WG5 | ​​Closed | WG6
13 | WG3 | BA | A sentence should be added to an appropriate existing guidance note to ensure faults on metallic returns are addressed. Suggested sentence and suggested guidance note where this will sit to be provided | A Proposer action for post-decision if GSR030 is approved | ​Post-GSR030 approval | ​​Closed | WG6
​​15​ ​ | ​​4​ ​ | ​​All​ ​ | ​​Review use of CBRA for cable installation to discuss at the next meeting​ ​ | ​​NA ​ ​ | 19.10 ​ | Closed | WG7
16 | 4 | BA | Send amended wording for the definitions slide from today's presentation |  | 25.09 | Closed | WG6
17 | 4 | BA | Consider other possible impacting factors, such as compass deviation | Factors noted in document and WG consultation question considered | 29.09 | Closed | WG6
18 | 4 | JG | Share slides from today's WG presentation (after checking for commercially sensitive information) |  | 25.09 | Closed | WG5
​​19​ ​ | ​​4​ ​ | ​​BA​ ​ | ​​Share overhead circuit risk tolerances, calculations and rationale behind what's deemed an acceptable level of risk (and relevance to cable scenarios)​ ​ | ￼ ​ | ​​29.09​ ​ | Closed | WG7
​​20​ ​ | ​​4​ ​ | ​​BA, FW​ ​ | ​​Compile text to cover ToR 3 - Consider retrospective impact on existing cables.​ ​ | 11/06/2025 - Workgroup agreed to come back to this as part of Workgroup Consultation discussion. Need to consider question in consultation. Action can be closed should no further feedback be received. | WG15 | Open​
​​21​ | ​​4​ | ​​LC ​ | ​​Consider what acceptable levels of risk are, what could be included in the SQSS & BA's suggested units involved for assessing risk​ | BA to follow up with LC 22/03/2024 - Propose to close | ​​05.10​ | Closed | WG10
​​22​ | ​​4​ | ​​NN, BA, LC​ | ​​To discuss offline - risk and associated costs (investment in reinforcing the network and build/maintenance). BA to send a written narrative to help Orsted understand this ahead of a discussion​ | 23.02 - Need cost implications for lower risk, (higher cost). Review again in WG8. 22/03/2024 - Still not had cost data from Orsted and co. This is now a blocker 05/12/2024 - Ongoing 11/03/25 - Discussions around risks and associated costs are no longer relevant to this. | ​​05.10​ | Closed | WG12
​​23​ | ​​4​ | ​​All​ | ​​Consider details of the above once shared and provide a proposal for discussion at the next WG​ | 05/12/2024 - Ongoing 11/03/2025 - proposer decision to close this action due to the report now requiring review for any missed detail | ​​05.10​ | Closed | WG12
24 | 5 | BA | Put together the wording for the intentional damage/terrorism risk | In report | 17.11 | Closed | WG7
25 | 5 | BA | Add more examples to the Mechanical Common Modes of Failure section | No examples to be added | 17.11 | Closed | WG7
26 | 5 | BA | To redraft page 10 section, reach out to SMEs | Done | 17.11 | Closed | WG7
27 | 5 | BA/ NN | Offline discussion to see if previous CBA will fit into this mod | Outcome tbc | 17.11 | Closed | WG7
28 | 6 | FW | Consult the ESO’s FRCR team to update the Chair on timings for the sensitivity analysis | Impacting other timeline adjustments 22/03/2024 - Propose to Close | 45296 | Closed | WG9
29 | 6 | NN, LC | Slides from WG 5 were to be reviewed and updated before sharing with the Workgroup for publication. | 24/07/2025 NN to confirm once emails have been checked. | WG15 | Open​
30 | 6 | BA | Revise wording (and diagrams) in the Workgroup Consultation as per the Workgroup discussions and comments in the document, including copying Workgroup discussions into the Workgroup Considerations section. | 22/03/2024 - Propose to close. BA has updated some of this as per WG | WG 7 | Closed | WG9
31 | 6 | BA | Review what analysis can sit separately to the Consultation document in an Annex. | 22/03/2024 - This can now be move 03/09/2024 - All now sat in workgroup discussion | WG 7 | Closed | WG10
32 | 6 | All | Share any environmental and/or economic benefits of this solution to the Chair/Proposer | This will be added as a question in the consultation 11/03/2025 - Proposer agreed to close this action, however asked the workgroup to send any additional environmental or economic benefits of the solution if they had any. | WG13 | Closed | WG12
33 | 6 | Chair | Review permissions access for Workgroup members to the shared workspace. | 22/03/2024 - Proposer to close | 45647 | Closed | WG9
34 | 7 | BA | Proposer to review whether Chapter 9 is affected by the code changes. | 22/03/2024 - Ongoing | WG8 | Closed | WG10
35 | 7 | BA | Proposer to check for missing text in the Issue 2 section of the consultation document. | 22/03/2024 - Ongoing - TP to support | WG8 | Closed | WG14
36 | 7 | BA | Titles and information sources needed for tables/figures included in documentation. | 22/03/2024 - Ongoing | WG8/9 | Closed | WG10
37 | 7 | BA, Workgroup | Decision needed about a reasonable number of links to include in the event frequency analysis and diagrams to be checked by BA | 22/03/2024 - BA needs support on this from Richard Proctor? 05/12/2024 - Ongoing 11/03/2025 - Proposer advised diagrams have been reviewed however still decision required on reasonable number of links required. | WG13 | Closed | WG12
38 | 7 | BA | Event frequency/probability analysis to be updated with 2GW and 2.5GW links, cases with wind and consideration of interconnected connections. | 22/03/2024 - Ongoing | WG8 | Closed | WG10
39 | 7 | BA, SQSS Panel | Offshore Transmission Owners to be contacted about the likelihood of mechanical failures (which can be handled confidentially) for the Proposer to assess. | 24/07/2024 aligns with action 20, to be close together | WG8/9 | Open
40 | 7 | BA, FW | Proposer to look into why HND costs for landing points haven’t been available and to look for missing text for this section. | 22/03/2024 - FW had orig and then got new ones. Are these ok? BA - Can use if pub available? FW to send to BA to check 05/12/2024 - Text updated but need numbers - Ongoing 11/03/2025 - Proposer to review the reprot to ensure there is substantial justification. | WG13 | Closed | WG12
41 | 10 | All | Mitigating risk - impact of clause 7.8.4 retrospectivity to exisiting projects and projects in late development execution | 05/12/2024 - Action missing as highlighted from NN 11/03/2025 - TP and BA to review the narrative aroung the retrospective application of clause 7.8.4 | WG13 | Closed | WG12
42 | 10 | BA,TP | Discuss scope with Panel and confirm | 24/07/2025 Proposer confirmed this has been actioned and Panel were keen for the Workgroup to proceed. Offline discussion to be had with AU | WG17 | Open​
43 | 10 | All | Provide feedback on details discussed in WG10 on scope creep by email | No update provided - propose to close 11/03/2025 - TP/BA discussed feedback of WG 10, and agreed to capture the notes provided by NN and seek panel view. This required Panel view- BA to draft email to Panel | WG11 | Closed | WG14
44 | 12 | BA | Develop text regards loss of reactive capability and ensure accuracy | Actions Completed. | WG13 | Closed | WG13
45 | 12 | BA | Create and share with Workgroup a diagram explaining worst-case scenario related to voltage limits and reactive capability | 11/06/2025 - text added to cover this so now closed | WG13 | Closed | WG14
46 | 12 | All | Workgroup to review and decide if Annex 3 (including draft proposal for STC) should be deleted from the report. | 24/07/2025 Proposer to check Workgroup Consultation to see if question has been added, can then be closed | WG15 | Open​
47 | 12 | TP | Add a section in the report for Workgroup Consultation questions and gather suggestions from responses | Actions Completed. | WG13 | Closed | WG13
48 | 12 | All | Review the Workgroup Report, focussing on the justification of the 1800MW section and provide feedback | 2025-06-11 | WG13 | Closed | WG14
49 | 12 | BA/NN | Nicola expressed concerns about the process of reclassifying and declassifying cables based on risk assessments. Consider how to develop a more structured approach to the assessment process. | 24/07/2025 Proposer and NN agree this hase been actioned and the Workgroup Consultation reflects both views. | WG13 | Closed | WG16
50 | 12 | BA | To email Panel to gain their views on the representation within the Workgroup to avoid issues on the day of submission. | 24/07/2025 Proposer confirmed emails sent to Ofgem and he is satisfied with representation | WG15 | Closed | WG16
51 | WG13 | TP/BA | Chair and Proposer to have an offline conversation with DB on the modification process. |  | WG14 | Closed | WG14
52 | WG13 | BA/All | Proposer to revise specific workgroup consultation questions and amend as discussed in the Workgroup. | 24/07/2025 Proposer confirmed this has been actioned | WG15 | Closed | WG16
53 | WG14 | TP | Circulate the 'Cyber and Physical Security Threats' presented to JESG to the Workgroup | Circulated on 12/06/2025 - https://www.neso.energy/document/362591/download | WG15 | Closed | WG16
54 | WG15 | BA/SB/GG | To discuss the 5 options included on the Workgroup Consultation Report |  | WG17 | Open
55 | WG15 | BA/SB | Check with legal team regarding the definition of "shared subsea cable route" and its implications |  | WG17 | Open
56 | WG15 | BA/SB | Confirm with legal team the classification of offshore transmission circuits and their compliance with Chapter 2 of the SQSS. |  | WG17 | Open
57 | WG16 | BA/AU | To arrange a meeting to develop a table that outlines the impacts on various circuit types |  | WG17 | Open
58 | WG16 | BA | To draft wording Re: "DC High Speed isolator" |  | WG17 | Open
59 | WG16 | BA/LJ/Ross | To arrange a meeting to discuss "Offshore Transmission Circuit" definition |  | WG17 | Open
60 | WG16 | SB/DS | To update legal text from the Workgroup and forward to DS to circulate to Workgroup members |  | WG17 | Open​

## Sheet2
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status
​​20​ ​ | ​​4​ ​ | ​​BA, FW​ ​ | ​​Compile text to cover ToR 3 - Consider retrospective impact on existing cables.​ ​ | 24/07/2025 agreed this would be closed once Proposer has reviewed the updated ToR with Workgroup members at the next meeting 02/09 | WG15 | Propose to close WG17
29 | 6 | NN, LC | Slides from WG 5 were to be reviewed and updated before sharing with the Workgroup for publication. | 24/07/2025 NN to confirm once emails have been checked. | WG15 | Propose to close WG17
39 | 7 | BA, SQSS Panel | Offshore Transmission Owners to be contacted about the likelihood of mechanical failures (which can be handled confidentially) for the Proposer to assess. | 24/07/2024 aligns with action 20, to be close together | WG8/9 | Propose to close WG17
42 | 10 | BA,TP | Discuss scope with Panel and confirm | 24/07/2025 Proposer confirmed this has been actioned and Panel were keen for the Workgroup to proceed. Offline discussion to be had with AU | WG13 | Propose to close WG17
46 | 12 | All | Workgroup to review and decide if Annex 3 (including draft proposal for STC) should be deleted from the report. | 24/07/2025 Proposer to check Workgroup Consultation to see if question has been added, can then be closed | WG15 | Propose to close WG17
54 | WG15 | BA/SB/GG | To discuss the 5 options included on the Workgroup Consultation Report | 24/07/2025 Proposer to discuss with GG | WG17 | Open
55 | WG15 | BA/SB | Check with legal team regarding the definition of "shared subsea cable route" and its implications | 24/07/2025 Proposer check with legal | WG17 | Open
56 | WG15 | BA/SB | Confirm with legal team the classification of offshore transmission circuits and their compliance with Chapter 2 of the SQSS. | 24/07/2025 Proposer check with legal | WG17 | Open
57 | WG16 | BA/AU | To arrange a meeting to develop a table that outlines the impacts on various circuit types |  | WG17 | Open
58 | WG16 | BA | To draft wording Re: "DC High Speed isolator" |  | WG17 | Open
59 | WG16 | BA/LJ/Ross | To arrange a meeting to discuss "Offshore Transmission Circuit" definition |  | WG17 | Open
60 | WG16 | SB/DS | To update legal text from the Workgroup and forward to DS to circulate to Workgroup members |  | WG17 | Open​