## Slide 1: Stability Phase 3
Provider Availability Notifications
July 2025

## Slide 2: Overview
Background
As per the Commercial Contractual arrangements for Stability Phase 3 (Stability Compensation Service – Phase 3) – providers are required to notify the NESO of any :-
  Outages; OR
  Periods where a Facility is no longer, or will no longer be, capable of providing the full Contracted Capability
High Level overview of the provider notification process
Providers are required to follow different processes dependant on the amount of notice being given to the NESO
This is summarised in the diagram below but further detail regarding each point is covered across slides 3-6
12 months ahead
Less than 24 hours ahead
12 months to 24 hours ahead
Providers are required to submit a Planned Maintenance Programme
The Network Access Planning team will review
This is explained further in slide 3
Providers are required to submit any details of Unplanned Outages or Reduction in Capability
The forms can be submitted to the Control Room via email
This is explained further in slide 5
Providers are required to submit any details of Planned Outages or Reduction in Capability
This information can be submitted via eNAMS or by populating a standardised template/proforma and returning it to the NESO via email
This is explained further in slide 4
Notice period prior to Delivery

## Slide 3: Planned Outages (Maintenance Plan)
Summary
As per section 4.10 of the Stability Compensation Service – Phase 3 agreement – providers are required to submit a Maintenance Plan prior to the start of each contract year (Apr – Mar).
This Maintenance Plan can include up to a maximum of 15 days of planned outage for a single contract year
Contractual Information
Maintenance of the Facility
4.10 - The Provider shall, prior to the commencement of each Contract Year, notify the Company in writing by such means as the Company may reasonably require of the dates and times of all planned maintenance and inspection periods applicable to the Facility (“Maintenance Plan”) for the forthcoming Contract Year (except that for the first Contract Year, the Maintenance Plan shall be applicable for the purposes of this Agreement only for that part of the Contract Year commencing on the Service Commencement Date). The Provider may propose modifications to the Maintenance Plan from time to time during the Contract Year on no less than twenty-eight (28) days notice. The Maintenance Plan may include up to a maximum of fifteen (15) days of planned outages in any Contract Year (to be reduced on a pro rata basis if the Maintenance Plan covers a period of less than twelve (12) calendar months).
Process for Provider Notifications
Providers can send a Maintenance Plan to the following email addresses at the start of each Contract Year
    England & Wales: tranreq@neso.energy
    Scotland: TRScotland@neso.energy
  Within fourteen (14) day`s NESO will notify the provider of agreement or any objections/feedback to the Maintenance Plan. If no response is received within 14 days the provider can assume that the plan has been accepted
  The NESO Network Planning team will utilise the information provided to update the eNAMS system accordingly
12 months’ ahead

## Slide 4: Planned Outages / Reduction in Capability
Summary
As per section 4.3 of the Stability Compensation Service – Phase 3 agreement – providers are required to make the NESO aware of any outages or reductions in capability as soon as possible
There are different processes for this depending on the level of notice being provided. If a provider is giving NESO less that 24 hours notice – please see the following slide
Contractual Information
4.3. - The Provider shall, without delay on becoming aware that the Facility is no longer, or will no longer be, capable of providing to the full extent the Contracted Inertia Capability, Contracted Reactive Capability and the Contracted SCL Capability (including by reason of Force Majeure or, in the case of a Modified Facility, by reason of the Facility being Unavailable due to the provision of a Permitted Service) promptly notify the Company in the form set out in Forms A - C (as applicable) in Schedule E (“Redeclaration”).
Process for Provider Notifications
Providers have 2 options for submitting this information to NESO :-
Via eNAMS – providers can request access to eNAMS (a NESO planning tool) and add information about their outages
Via email – alternatively, providers are required to complete a template/proforma and send it to the relevant email addresses
    England & Wales: tranreq@neso.energy
    Scotland: TRScotland@neso.energy
  With option 2 – the completed template/proforma will be reviewed by NESO’s Network Planning team and the information will be added to eNAMS on the providers behalf
  To understand the impact of reductions in capability providers should refer to Schedule D – Payments of their Stability Pathfinder Agreement
From 12 months+ to 24 hours ahead

## Slide 5: Unplanned Outages / Reduction in Capability
Summary
As per section 4.3 of the Stability Compensation Service – Phase 3 agreement – providers are required to make the NESO aware of any outages or reductions in capability as soon as possible
This slide covers the scenario where a provider is unable to give NESO a minimum of 24 hours notice
Contractual Information
4.3. - The Provider shall, without delay on becoming aware that the Facility is no longer, or will no longer be, capable of providing to the full extent the Contracted Inertia Capability, Contracted Reactive Capability and the Contracted SCL Capability (including by reason of Force Majeure or, in the case of a Modified Facility, by reason of the Facility being Unavailable due to the provision of a Permitted Service) promptly notify the Company in the form set out in Forms A - C (as applicable) in Schedule E (“Redeclaration”).
Less than 24 hours ahead
Process for Provider Notifications
In this instance, given the short timescales, provider notifications have to be sent directly to NESO’s Control Room
4 forms are available to cover the different scenarios (these are all available in Schedule E of the Pathfinder Agreement)
FORM A - STABILITY COMPENSATION SERVICE FAX FORM FOR REDECLARATION OF INERTIA CAPABILITY​
FORM B - STABILITY COMPENSATION SERVICE FAX FORM FOR REDECLARATION OF SCL CAPABILITY​
FORM C - STABILITY COMPENSATION SERVICE FAX FORM FOR REDECLARATION OR RESTORATION OF REACTIVE CAPABILITY​
FORM D - STABILITY COMPENSATION SERVICE FAX FORM FOR RESTORATION NOTICE
Once completed the relevant form needs to be sent via email as per the below :-
    ctr1.ccta@neso.energy AND
    England & Wales - tranreq@neso.energy OR Scotland - TRScotland@neso.energy
  To understand the impact of reductions in capability providers should refer to Schedule D – Payments of their Stability Pathfinder Agreement