## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | FK | Update legal text based on Workgroup feedback |  | WG2 | Closed | WG2
2 | WG1 | SS | Consider whether the Legal Text in OC6.9.5. is applicable within the bounds of the existing licence rather than through primary legislation |  | WG2 | Closed | WG3
3 | WG1 | LT | Discuss possible changes to the timeline with Proposer and Ofgem |  | WG2 | Closed | WG2
4 | WG2 | RS | Provide update on System Defence Plan | To be amended following conclusion of GC0176 | WG3 | Closed | WG3
5 | WG2 | AM/AC | Liaise to ensure that there were no misunderstandings about the ability to meet the 2-5 minute requirement with fast load blocks in OC6.5.3 |  | WG3 | Closed | WG3
6 | WG2 | FK | Confirm Grid Code defined terms in OC6.5.3 and OC6.9.7 |  | WG3 | Closed | WG3
7 | WG3 | All | Network Operators to provide a list of the licence requirements that are likely to need a derogation if DCRP is used, and the reasons why. |  | WG4 | Closed | WG4
8 | WG3 | JZH | Provide ETG with updates in OC6.5.5 and investigate whether OC6.2.2 is still required. |  | WG6 | Closed | WG6
9 | WG3 | RS | Provide OC7 legal text on correct Baseline document without Fax option in tables. |  | WG4 | Closed | WG4
10 | WG3 | All | Workgroup members to think of Specific Workgroup Consultation questions prior to next Workgroup meeting |  | WG4 | Closed | WG5
11 | WG3 | LT | Chair to contact Ofgem Representative regarding the outcome of discussions on Action 7. |  | WG5 | Closed | WG5
12 | WG4 | RS | NESO SME to update the Legal Text following WG4 discussions, including a timeline diagram in OC6. |  | WG5 | Closed | WG5
13 | WG4 | LT | Updated Workgroup Consultation document to be shared for review. |  | WG5 | Closed | WG5
14 | WG4 | All | Network Operators to confirm they’re content with timings in OC6.9.4 and NESO SME to take this point to next ETG. |  | WG5 | Closed | WG5
15 | WG4 | LT | Chair to provide Workgroup with update on revisions to the timeline. |  | WG5 | Closed | WG5
16
17