## Sheet1
Action number | Workgroup Raised | Owner | Action | Comments | Due by | Status | Workgroup Closed
1 | WG1 | GG/AJ/GL/HN | Offline discussion to be arranged to make amendments to the draft legal text following WG1 comments |  | WG2 | Closed | WG2
2 | WG1 | CG | Draft the Workgroup Consultation for members to review prior to WG2 | Drafted and placed in the collaboration space. | 2025-08-07 | Closed | WG2
3 | WG1 | CG | Create a GC0183 Collaboration Space for Workgroup members to review the documents |  | 2025-08-07 | Closed | WG2
4 | WG1 | CG | Clarify the role of a Workgroup Observer |  | WG2 | Closed | WG2
5 | WG2 | CG | Send updated legal text (G&D, OC2, OC7) and Workgroup consultation for final review |  | TBC | Closed | WG3
6 | WG2 | AJ/GL | NESO Legal Team to review draft legal text |  | TBC | Closed | WG3
7 | WG2 | HN | Create a flow diagram to demonstrate the time sequence of the notifications |  | TBC | Closed | WG3
8 | WG2 | HN/JZH | Discuss KC comments on legal text sections OC2 2.5.1 b) and OC2 2.5.2 b) |  | TBC | Closed | WG3
9 | WG2 | CG | Update ToR and take slide to GCRP |  | 2025-08-21 | Open
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32