## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | RP | Provide a view on TNUoS/BNUoS ongoing work relating to constraints (see slide 22, WG1). Including Risk and mitigation and modelling | Ongoing waiting update from Balancing team | WG3 | Closed | WG4
2 | WG1 | RP | Provide view on Electrolysers - Is this within Final Demand? Subject to locational signals? | Ongoing waiting on update from revenue team | WG3 | Closed | WG4
3 | WG1 | LJ | Share Fronteir slides with WG |  | WG2 | Closed | WG2
4 | WG1 | LJ | Provide worked numbers as per slide 29 (WG1) | This will be included in later reports. Still waiting on data from revenue team | WG3 | Closed | WG5
5 | WG1 | LJ and RP | Look at party profiles ahead of next WG | The Proposer and NESO Representative to look at examining different profile shapes of possible customer types. | WG3 | Closed | WG2
6 | WG2 | MC | To gain data from the Revenue team for actual NHH for 4-7pm and NHH for all periods | NESO were requested to provide the data for this action, but it will now use estimated data and go through the methodology. | WG4 | Closed | WG5
7 | WG2 | LJ and RP/ PM | To review 14.16.2 Legal text | The proposer and NESO Representative are reviewing section 14.16.2 of the legal text. This would be closed following workgroup discussions. | WG4 | Closed | WG5
8 | WG3 | LJ | To work through equation for understanding of example for 20 million by the 4 to 7 demands, splitting up into 4 to 7 for peak and year-round using different volume. | The Proposer has worked through the equation of understanding examples for 20 million by the four to seven demands and splitting up into four to seven for peak and year-round using different volumes. | WG4 | Closed | WG7
9 | WG3 | DH | Provide confirmation of the charging year the data was analysed from. | DH confimed that the data given to the Workgroup was from 23. | WG4 | Closed | WG5
10 | WG3 | TP/LJ+C11:H11 | Schedule time for proposer and TP to review document Workgroup Consultation Document | Initial review done. | WG4 | Closed | WG5
11 | WG4 | LJ | The Proposer took an action to add percentage changes into the impact tables showing the impact on bills for better clarity. | All tariffs and customer bill tariff tables were added. | WG5 | Closed | WG8
12 | WG4 | LJ/ All | The Proposer took an action to clearly define the original proposal for discussion at the next meeting. Workgroup members to discuss whether any alternatives should then be proposed ahead of the Workgroup Consultation. | The Proposer advised defining the original proposal and discussing alternatives, was completed. | WG5 | Closed | WG7
13 | WG5 | DH / AS | Workgroup members discussed the need for additional data analysis, particularly focusing on the impact of the charging year forecast on the pound per MW hour and pence per kWh. A follow up action was taken to look into providing a forecast of the consumption for the 2029/30 year and to apply the necessary ratios for later years. A Workgroup member to provide historic wholesale prices to compare with the 10 years component | A Workgroup member provided an update, which involved providing additional data on the impact of the charging year forecast. They mentioned they had pulled together data from Elexon and shared it with the Chair and the Proposer. | WG6 | Closed | WG6
14 | WG5 | DH | Workgroup members identified anomalies in the data for certain zones, particularly Zone 1. A Workgroup member agreed to investigate further to ensure accurate data representation. | The Proposer noted that the anomalies have been resolved with updated data, but further review is needed, and the calculation tables will need to be updated. | WG6 | Closed | WG6
15 | WG6 | TP/SW | Update the timeline and circulate it to the Workgroup for review before sending it to the panel. | SW circulated the timlined to Workgroup members. | WG7 | Closed | WG7
16 | WG6 | All | Review and edit the Workgroup consultation document, adding comments and changes as necessary. | Consultation document reviewed, and comments added. | Ongoing | Closed | WG8
17 | WG6 | AS | Develop the WACCM proposal and share it with the work group for review before the next Workgroup. | This was shared with the Workgroup ahead of Workgroup 7 | WG7 | Closed | WG7
18 | WG6 | LJ/PM | Develop the legal text on the current CUSC section 14 baseline | The Proposer and PM acknowledged that they had not yet completed this task, and advised it was ongoing and would be important in the autumn. | Ongoing | Open
19 | WG7 | RH | Check If the alternative solution raised by GD is within scope of this modification | The Chair informed that NESO legal had advised the alternative solution proposed by a Workgroup member was out of scope. | WG8 | Closed | WG8
20 | WG8 | SW | ​​Send an offline version of the updated consultation report to all Workgroup members for review before publication.​ | The Workgroup Consultation was circulated for review before submission | 2025-07-07 | Closed | 2025-07-07
21 | WG10 | RH/SW | Send out options for the next workgroup meeting date, via a Doodle poll. |  | WG11 | Open