## Pre-Hiatus
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | EW | Provide data on the difference between amount secured under CMP192 and actual cancellations | Proposer gave update on presentation | WG2 | Closed | WG3
2 | WG1 | EW | Provide information on the amount of connections triggering transmission works | Agreed to close as no longer necessary. Question too wide. | WG2 | Closed | WG3
3 | WG1 | EW/TC | Catch up offline regarding new works triggering Final Sums |  | WG2 | Closed | WG2
4 | WG1 | AP | Investigate potential STC changes |  | WG2 | Closed | WG2
5 | WG1 | EW | Investigate the potential for negative costs if Demand is applied to wider works |  | WG2 | Closed | WG2
6 | WG1 | EW | Provide update on interim arrangements | Proposer gave update on presentation | WG2 |  | WG3
7 | WG1 | AP | Look into definitions for attributable works for Demand and TIC |  | WG2 | Closed | WG3
8 | WG1 | EW | Provide justification for Workgroup Consultation that extending Section 15 is the correct solution | Previous action: Provide justification for Workgroup Consultation that extending Section 15 is the correct solution | WG2
9 | WG1 | AP | Provide draft legal text |  | WG2
10 | WG1 | LT | Provide Terms of Reference update to CUSC Panel |  | 45190 | Closed | WG2
11 | WG2 | AP | Provide an update of status of the term ‘Seven Year Statement’ within the CUSC
12 | WG2 | RM/AP | Provide wording in ConsAg (Construction Agreement) for key consents
13 | WG2 | RM | Provide update on implementation date for existing Users
14 | WG2 | RM | Investigate whether a guidance note can be provided for FSM
15 | WG2 | EW | Check figures provided for pre-trigger and circulate UCM guidance document to the Workgroup | Figures provided were from the current UCM guidance document
16
17

## Post-Hiatus
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG6 | Chair/ Proposer | Add new Terms of Reference to cover off demand and generation Users connecting and needing the same projects and investments. | The Chair confirmed Panel approved the new Terms of Reference (g) ‘Consider the interaction between Demand and Generation Securities’. | WG7 | Closed | WG7
2 | WG6 | Proposer | Consider which principles of UCM are being transferred and any that aren't, include justifications. | The Proposer confirmed no changes were needed regarding the SIF and LARF applications and will continue to apply as proposed. | WG7 | Closed | WG8
3 | WG6 | Proposer | Consider if FSM will still be applicable to some Users or if it will be removed altogether | The Proposer confirmed final sums will be removed altogether and the solution will apply to everyone not covered by the current Section 15. | WG7 | Closed | WG7
4 | WG6 | Proposer | Consider how combined capacity is calculated for hybrid sites to avoid double counting. | The Proposer updated the Workgroup that consideration for calculation for hybrid sites had been given concluding that, under the CUSC, TO assigns works to each technology/stage, calculating securities based on relevance. If a work applies to both generation and demand, it is attributed to the technology with the higher factor (e.g., demand if its capacity is greater). | WG7 | Closed | WG7
5 | WG6 | Proposer | Provide stage approach examples | The Proposer advised this action was no longer relevant as CMP417 aims to align generation and demand. Any change to SIF scaling across all schemes would require a broader modification to CMP192 and believed this was out of scope for CMP417. Examples of attribute cancellation charge were provided to the Workgroup. | WG7 | Closed | WG7
6 | WG6 | Proposer | Consider impacts on Grid Code and on changes to security statement timings and the impact this will have. | The Proposer met with the NESO Customer Solutions and Engineering Team to discuss impacts of changes to security statement timings. The Team believed there are no impacts on the Grid Code. | WG7 | Closed | WG7
7 | WG7 | SN/MC | Look into model allocation of capex to investigate whether zonal allocation is cost reflective for both Generation and Demand | The SME explained their approach, where total CapEx (including both generation and demand-driven works) is reduced by User Risk and Global Asset Reuse Factors before apportioning to ETYS zones using Boundary information. This will then be divided by expected MW connections to set a £/MW tariff. They advised that the method will be an approximation and not based on actual wider spend per zone. | WG8 | Closed | WG8
8 | WG7 | SN/MC | Provide example on wider liability and cancellation charge | The SME explained the user risk factor splits liability 50/50 between generation and consumers, but only generation faces wider liability currently. Under the proposed change, both Generation and Demand would share this liability, which is expected to reduce securities for Demand sites, especially those with high liabilities | WG8 | Closed | WG8
9 | WG7 | SN/MC | Consider in more detail what happens with SIF for Generation, particularly for connection sites and one off works. Update: Proposer to look into examples which show financial impact at a future workgroup | Worked examples provided and discussed by the Workgroup (see action 16). | WG8 | Closed | WG12
10 | WG7 | SN/MC | Consider and finalise solution for DNOs | The Proposer met with the DNOs and feedback that most DNO works are driven by large embedded demand projects, but rare cases exist where reinforcement is required due to general load growth. The group agreed on the need for high-level guidelines for such scenarios | WG8 | Closed | WG10
11 | WG7 | SN/MC | Discuss use of TORIs with TOs and whether this is required in the solution. Update: Proposer to provide a more detailed example for the next Workgroup. | It is proposed to still have two security statements as the calculation inputs are still different for Generation and Demand | WG8 | Closed | WG10
12 | WG7 | SN/MC | Provide summary of solution within Workgroup Consultation document | Solution summary provided | WG8 | Closed | WG11
13 | WG10 | MC | Further consider how embedded customer information will be collected and provide an example. | Multiple embedded demand projects are not grouped in the same DNO Mod App. If a project triggers a Mod App, a single construction agreement covers all required Transmission Works—no need to split liabilities further. For CMP417, a one-to-one mapping is recommended. | WG10 | Closed | WG11
14 | WG10 | MC | Consider whether Demand customers will be included into the Statement of Works document, Appendix G table or other documentation/list. | Allowing multiple embedded projects would require a Generation-like process (e.g.Statement of Works, Appendix G). Applying this to Generation would greatly expand the modification’s scope. Broader process changes should be considered separately as demand grows. | WG10 | Closed | WG11
15 | WG11 | MC | Develop a detailed implementation plan for reissuing Construction Agreements | Update provided in Workgroup 13 however further work is still required | WG13 | Open
16 | WG12 | MC | Worked examples: Investigate whether DNO examples can be provided Add MW values Include Scottish assets Include drop in post-trigger security requirements | Proposer presented the updated worked examples within the Workgroup. | WG13 | Closed | WG13
17 | WG12 | MC | Workgroup Consultation: Clarify 10% security requirement Include CMP192 diagrams to illustrate changes over project lifetime Clarify wider liability calculations Include implementation arrangements | The Workgroup members agreed the final points within the Workgroup Consultation. | WG13 | Closed | WG13
18 | WG12 | MC | Make adjustments to the legal text and review with NESO legal prior to Workgroup Consultation | The Proposer received comments from Legal but were unable to review in time for the Workgroup. The Proposer presented the Legal Text and agreed these during WG13 and confirmed they would be annexed to the Workgroup Consultation | WG13 | Closed | WG13
19 | WG13 | MC | Query with NESO Representative whether a guidance note was produced for CMP447. |  | WG14 | Open
20 | WG13 | All | Workgroup to review how the impact of DNOs effet their contracts |  | WG14 | Open