## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed | Notes
2 | WG1 | SN/SD | Draft the legal text for the modification and share it with work group members for review. | Preceeding actions raised - actions 8 and 9 | WG2 | Closed | WG2
4 | WG1 | SN/SD | Check for any interaction with this modification on the STC. | No observed interation with the STC. | WG2 | Closed | WG3
5 | WG1 | SN/SD | Review CUSC Section 3 for any interaction relating to invoicing and reconciliations from this modification which would require a consequential CUSC non-charging modification being raised. | The Commercial codes team have done an initial review and believe there is likely a consequential modification required to amend some wording in Section 3 to align with the proposal. | WG2 | Closed | WG3
6 | WG2 | SN | Review Section 3.10.5 and provide update to the Workgroup | Update provided in WG3 | WG3 | Closed | WG3
7 | WG2 | DC | Draft a question for the Workgroup Consultation. | Completed and included in the Workgroup Consultation document | WG3 | Closed | WG3 | CUSC section 3.10.5 has a sentence that needs replacing with a requirement to give a required TEC monthly profile. So a twin mod is needed. The rest of CUSC section 3, including the section about generation TNUoS reconciliations, looks fine to me as it is. Dan, Al and Camille had a chat about it, we could share NESO's initial views but then add something like 'we'd encourage the proposer to investigate this as well' .. so that the proposer takes some ownership of the action (if a second mod is needed)
8 | WG2 | KH | Add legal text and consultation documents to the collaboration space for review. | Draft Legal Text and consultaion document shared on collaboration space. | WG3 | Closed | WG3 | This is being reviewed by Paul Mott in Commercial Codes
9 | WG2 | SN/SD | Update the legal text for both sections 3 and 14 on to the latest CUSC baseline and share it with the Workgroup for review. | Section 14 has been drafted and shared with WG Members. Section 3 will require a twin mod if it needs changing. Propose to close. | WG3 | Closed | WG3
10 | WG2 | SD | Discuss and potentially raise an alternative modification that includes both the initial connection and disconnection scenarios. | Alternative request form raised and being reviewed by Code admin | WG4 | Closed
11 | WG2 | SD | Review and refine the wording for the Workgroup Consultation question regarding the end phase, ensuring clarity on terms like disconnection and de-energisation. | Wording has been refelected in the Workgroup Consultation document. | WG3 | Closed | WG3
12 | WG2 | SD | Update the diagram to reflect the changes under this modification, so it can be included in the Workgroup Consultation document. | Diagram to be provided to Workgroup members for review prior to including as an annex to the workgroup consultation | WG3 | Closed | WG3 | Positive so far, still in discussions
13 | WG3 | SD/SN | Consult with the revenue team to confirm the preferred approach for daily versus monthly pro rata charging. | The revenue team have no strong preference between daily or monthly pro rata charging - Daily is fine from the revenues point of view. | WG4 | Closed | WG4
14 | WG3 | SD/SN | Consult with the revenue team to confirm the appropriate wording for Question 7 regarding negative charging zones. | We will hold off until Chiamaka shares her view. Workgroup to review in WG4 and share following the meeting | WG4 | Closed | WG4
15 | WG3 | SD/SN | Consult with the revenue team to determine if immediate tariff changes are necessary and update the work group consultation document accordingly. | Revenue forecast however this doesnt change the current process. Revenue beleive current process should continue. | WG4 | Closed | WG4
16 | WG3 | KH | Change the wording in the legal text to "a relevant charging date" and share it back on the collaboration space. | Completed. | WG4 | Closed | WG4
17 | WG3 | DC | Ensure the work group report covers the discussion on over and under recovery and its impact. | Ongoing | WG4 | Closed
18 | WG4 | SD | Consult with the Revenue Team to clarify the reconciliation approach for both positive and negative charging zones, including how charges would be calculated if peak output data is unavailable. | Ongoing | WG5 | Closed
19 | WG4 | SD | Confirm definition of a "chargeable day" and confirm how this should be interpreted for charging purposes. | Ongoing | WG5 | Closed
20 | WG4 | GP | Update the wording in the workgroup consultation to accurately reflect the treatment of negative charging zones and ensure clarity for readers. | Ongoing | WG5 | Closed
21 | WG4 | SD/AA | Refine and finalise the Legal Text for the daily charging section. | Ongoing | WG5 | Closed
22 | WG4 | SD/AA | Ensure the Alternative Request (WACM) Legal Text is developed in line with the baseline, with further review and input from the legal team before circulation | Ongoing | WG5 | Closed
23 | WG4 | KH | Update the Workgroup Consultation document with the agreed changes and circulate it to members for review, with a deadline for feedback and updates by Friday 18 July 2025. | Ongoing | WG5 | Closed
24 | WG5 | SD/SN | Draft and circulate the Legal Text for WACM 1 |  | WG6 | Closed
25 | WG5 | RB/GM | Draft Legal Text for WACM 2 (if voted in), ensuring alignment with WACM 1 except for retrospectivity. |  | WG6 | Closed
26 | WG5 | KH | Share Workgroup Consultation responses with new Workgroup Members. |  | WG6 | Closed
27 | WG5 | SD/SN | Catch up with the revenue team to provide numbers on how many plants would be affected by retrospective application. |  | WG7 | Open
28 | WG5 | KH | Propose dates and schedule an extra meeting for the WACM 2 vote |  | WG6 | Closed
29 | WG5 | SD | Raise consequential change in Section 6 and include as part of WACM 1 |  | WG6 | Open
30 | WG6 | SD | Review and consolidate the three sets of Legal Texts |  | WG7 | Open
31 | WG6 | KH | Share the aligned Legal Text on the Collaboration space |  | WG7 | Open
32 | WG6 | GM | Review and update the summary for WACM 2 in the Workgroup Report and add a one-liner describing the Legal Text difference. |  | WG7 | Open
1 | WG1 | KH | Amend Terms of Reference c) to include consideration of increases in TEC and d) to include the consideration of over-recovery. | Will be updated at CUSC Panel in May | WG2 | Closed | Workgroup 2
3 | WG1 | SN/SD | Provide further information on the cash flow and money trail related to asset connection and revenue recovery. | We have spoken with NESO revenue and believe we have a HL view of the charging model and payments to TO's. We intend to get this validated by the TO's to confirm our understanding. | WG2 | Closed | Workgroup 2
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We are not the proposer so we were are reviewing the proposed legal text not drafting the legal text.
Note on D36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was there a discussion about consideration to reductions in TEC as well ?