## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 (24) | CG/JR | Send out updated slides and remaining invites |  | WG2 (25) | Closed | WG2 (25)
2 | WG1 (24) | CG | Raise concerns regarding voting expressed by members internally |  | WG2 (25) | Closed | WG2 (25)
3 | WG1 (24) | AJ | Engage with CBA team to ensure any of the CAC responses are reflected in the CBA (raised by AC) |  | TBC | Closed | WG2 (25)
4 | WG1 (24) | AJ | Regarding consequential changes to other code, provide further information and timelines |  | TBC | Closed | WG2 (25)
5 | WG1 (24) | AJ | Research BELLA versus BEGA numbers | NESO is actively working to obtain the data | TBC | Open
6 | WG1 (24) | PD | Ofgem to confirm if the new CBA is only to be done on the ‘Original Proposal (OP)’ solution (ie 10MW) or OP and Alternative |  | WG2 (25) | Closed | WG2 (25)
7 | WG1 (24) | AJ | CBA Representative to attend the Workgroup meeting to explain the process clearly |  | TBC | Closed | WG2 (25)
8 | WG1 (24) | MS (TIDE Project) | Presentation on TIDE to discuss the relationship with GC0117 |  | WG2 (25) | Closed | WG2 (25)
9 | WG1 (24) | CG | Adding in to the report a simple table showing the total level of embedded generation in 2019, 2025 and forecast to be in 2030 (Suggested by GG) |  | TBC | Open
10 | WG1 (24) | PD | Confirm whether all the additional items mentioned in the Ofgem letter need to be explicitly added to the ToR, or if they are implicitly covered |  | WG2 (25) | Closed | WG2 (25)
11 | WG2 (25) | AJ | Investigate if there are any comments made on the original CBA in the CAC responses |  | WG3 (26) | Open
12 | WG2 (25) | CG/SK | Circulate previous CBA comments (Annex sent by email) |  | WG3 (26) | Open
13 | WG2 (25) | MT | Forecast Embedded Generation Levels data –Figure 6 to be provided as a table on the CG0117 data thresholds for 10 MW and 100 MW |  | WG3 (26) | Open
14 | WG2 (25) | PY/IN | Investigate whether a market facilitator should be present in these discussions |  | WG3 (26) | Open
15 | WG2 (25) | JB/CG | To email concerns regarding connection to Chair to circulate with connection colleagues |  | WG3 (26) | Open
16 | WG2 (25) | AJ | Set out a table breaking down Ofgem send back letter and how these will be addressed – clear direction (BS request) |  | WG3 (26) | Closed
17 | WG2 (25) | AJ | Ensure any consequential code changes are identified as follow-on work if GC0117 is approved, but not included in the current mod |  | WG3 (26) | Open
18 | WG2 (25) | AJ/SK | Consider whether to include regional demand forecast error analysis in the CBA |  | WG3 (26) | Open
19 | WG2 (25) | MT | Advise that the connection data analysis be refreshed after the connections reform queue is updated, due to expected significant changes |  | WG3 (26) | Open
20 | WG2 (25) | AJ | Review and, if necessary, update the generator CapEx and OpEx cost data (Annex 20 of the GC0117 Final Modification Report) to ensure these costs are appropriately included in the formal CBA, considering increased engagement from generators |  | WG3 (26) | Open
21 | WG3 (26) | MT/EB | Look into the possibility of including forecasts for future connections |  | TBC | Open
22 | WG3 (26) | MT/EB | Provide raw data behind forecasted embedded generation levels |  | WG4(27) | Open
23 | WG3 (26) | All | Populate the spreadsheet |  | 2026-01-09 | Open
24 | WG4 (27) | AJ | Clarify the BC 1.6 data sharing requirements, including what data is required from DNOs for operational and constraint purposes and the associated timescales. |  | WG5(28) | Open
25 | WG4 (27) | JR | Prepare and circulate a written timeline of the CBA review process flow for the Workgroup to clarify steps and sequencing. |  | WG5(28) | Open
26 | WG4 (27) | AJ | Provide a slide listing consequential code changes (e.g., compliance, data flows, SQSS, CUSC) to the Workgroup and allow members to add further items as needed. |  | WG5(28) | Open