## CUSC Prioritisation
CUSC Prioritisation Criteria |  |  |  | Prioritiy Category (Modifications are listed in numerical order within their priority category)
Section 8: 8.19.1.(e) makes the following provision for the Panel and states “Having regard to the complexity, importance and urgency of particular CUSC Modification Proposals, the CUSC Modifications Panel may determine the priority of CUSC Modification Proposals and may (subject to any objection from the Authority taking into account all those issues) adjust the priority of the relevant CUSC Modification Proposal accordingly” |  |  |  | High
Complexity | The likely implications for industry and consumers; e.g. size of process change, potential requirement for additional Authority consultation etc. Level of industry resource and intensity required to complete the governance process in a timely manner; e,g. volume of Workgroup meetings, range of industry party representation, level of uncertainty/ certainty introduced by the modification etc. |  |  | Medium to High Medium
Importance | The perceived value, criticality and risk to industry and consumers; e.g. strategic alignment and interaction/ enabling of other financial/ regulatory / licence/ compliance obligations or modification packages, changes to costs. |  |  | Medium to Low Low
Urgency | A modification which requires speedy consideration within the code governance process, both complexity and importance should be factors considered in evaluating urgency as well as the timescales for implementation within the respective code.
Priority Category | Mod Number | Title | Previous Priority Category (changes highlighted in blue) | Panel Comments on Prioritisation as of 26 July 2024 | Proposer Organisation | Outside WG stage
High | CMP414(Non-Charging) | CMP414 - CMP330/CMP374 Consequential Modification | High | October 2024 update: The Panel agreed that when rationalised against the other modifications in the stack this was a medium priority. August 2024 update- Complexity – Panel agreed the modification topic was complex and the work required ahead of resubmitting the FMR was likely to be extensive. •Importance – Panel acknowledged that more certainty is required in the connections reform space before fully evaluating CMP414 importance. Panel recognises that this modification is aiming to speed up the connections process.* •Urgency – Panel acknowledged that a quick FMR resubmission was unlikely, and the current connections reform space made it difficult to predict the required timescales. August 2025 update - The Panel agreed that CMP414 should be placed high on the prioritisation stack due to the dependences with CMP330/CMP374’s currently with the Authority for decision. *Updated from July 2024 | NESO
High | CMP417(Non-Charging) | Extending principles of CUSC Section 15 to all Users | High | March 2025 Update: The Panel placed CMP417 within the High Priority category, given the impacts it has. The Panel agreed that this modification should be progress together with the other high priority and urgent modifications. October 2024 Update: The Panel placed within the medium priority category, given the complexity and analysis required. April 2024 Update: The Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. Special April 2024 Panel: Due to the complexity, importance and the required timescales of the other modifications in the stack the Panel reprioritised the modification from ‘Medium - High’ to ‘Medium’ Panel agreed to place within the 'Medium to High' priority category due to being part of the Connections reform package and the potential benefits to demand customers. | NESO
High | CMP423 (Charging) | Generation Weighted Reference Node | High | February 2025 Update - On the 14 February Special Panel the Panel agreed that CMP423 should be High Priority and progressed alongside the current urgent modifications. October Update 2024 - The Panel acknowledged the complexity of this modification and the contributions from the Task Force to the development of the solution and agreed this should be placed within the medium priority criteria. April 2024 Update :The Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. December 2023: The Panel agreed that whilst the modification was complex, when rationalised against the other modifications in the stack this should be placed as 'Medium' Due to the complexity and technical aspects of the defect, alongside the amount of time the TNUoS Task Force had already contributed to the development of the solution, the Panel considered modification should be prioritised as ‘Medium to High’ | SSE
High | CMP440 (Charging) | Re-Introduction of Demand TNUoS Locational Signals by removal of the zero-price floor | High | February 2025 Update - On the 14 February Special Panel the Panel agreed that CMP440 should be High Priority and progressed alongside the current urgent modifications. October 2024 update: The Panel agreed that when rationalised against the other modifications in the stack this was a high priority. September 2024: The Panel agreed to discuss the prioritisation of the new modifications at the October 2024 Panel | RWE
High | CMP445 (Charging) | Pro-rating first year TNUoS for Generators | High | March 2025 Update: The Panel placed CMP445 within the High Priority category, given the impacts it has. The Panel agreed that this modification should be progress together with the other high priority and urgent modifications. November 2024 Update: Panel decided to defer the discussions on CMP445 priority to the December 2024 Panel, once the Authority has made a decision on the urgency request. December 2024 Update : Panel agreed that when rationalised against other modifications in the stack this was a high priority. | Ocean Winds
High | CMP460 (Charging) | Improving Transmission Connection Asset Charging | High | September 2025 Update: Panel decided to place CMP460 as High in the Prioritisation Stack with an expedite timeline. | Innova
Medium | CMP457 (Charging) | Revision of the Obligatory Reactive Power Service (ORPS) | Medium | October 2025 Update: Panel decided to place CMP457 as Medium priority and advised that key publications should be out before the Workgroups starts. | NESO
Medium | CMP442 (Charging) | Introducing the option to fix Generator TNUoS | Medium | February 2025 update : At the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification be placed as medium on the prioritsation stack. October 2024 update: The Panel agreed high priority for this due to its complexity and potential interactions with CMP444. | RWE
Medium | CMP426 (Charging) | TNUoS charges for transmission circuits identified for the HND as onshore transmission | Medium | February 2025 update: At the Special CUSC Panel the Panel discussed, at length and in detail, the prioritisation of CUSC Modifications. The CUSC Panel agreed this modification be placed as "Medium to High" in the prioritisation stack. October Update 2024: The Panel agreed this should be placed within the high priority category given its interactions with CMP419. April 2024 Update: There were no Workgroup meetings planned when the Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. Panel agreed that given the profile and required timescales of the modification it should be placed as High | NESO
High | CMP315 and CMP375 | TNUoS: Review of the expansion constant and the elements of the transmission system charged for (CMP315) Enduring Expansion Constant & Expansion Factor Review (CMP375) | High | • Panel recognised there is a material impact here; however, argued that need to understand the TCR outcome before progressing further This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. November 2020 Panel agreed to move CMP315 from “Low to Medium” to “High” in light of recent developments re: the Expansion Constant. ESO's modification re: the wider solution on the Expansion Constant (CMP375) was presented to the June 2021 Panel. Panel agreed that CMP315 will be progressed in parallel with CMP375 (rather than be formally amalgamated) with Workgroups on the same day. Panel noted that CMP375 is a complex change and agreed that it is better to commence this as soon as possible and provide clarity for stakeholders on the future of the Expansion Constant and placed this “High” in the prioritisation stack. Given the interaction with CMP315, CMP315 will remain high in the prioritisation stack. Workgroups recommenced on 10 August 2021. | PeakGen (CMP315) ESO (CMP375)
Medium | CMP393 | Using Imports and Exports to Calculate Annual Load Factor for Electricity Storage | Medium | Panel agreed that CMP393 will be placed as “Medium” in the prioritisation stack as although there could be a high materiality and complexity (given the analysis required), some Panel Members noted it may be prudent to wait for the TNUoS Taskforce to meet and agree high-level principles. On balance, Panel agreed a "Medium" priority. | Zenobe | x
Medium | CMP402 | Introduction of Anticipatory Investment (AI) principles within the User Commitment Arrangements | Medium | October 2024 Update: The Panel placed within the medium priority criteria due to the further development required for the solution. April 2024 Update: There were no Workgroup meetings planned when the Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. Given the high materiality and that this is the first of a number of changes in this area, this was placed as “Medium to High” in the prioritisation stack | NESO | x
Medium | CMP433 (Charging) | Optimised Transmission Investment Cost model (OpTIC) | Medium | October 2024 Panel: The Panel agreed medium priority for this modification, acknowledging the REMA outcome and the implementation timescales. Panel agreed that the due to the complexity of the defect the modification should be placed in 'Medium' below the Task Force modifications. Acknowledging that Workgroups were not proposed to start until September 2024. | SPEN
Low | CMP288 (Charging) | CMP288 - Explicit charging arrangements for customer delays and backfeeds | Low | October 2024 Update: Panel agreed that this modification should be placed within the low priority criteria, acknowledging that the charging arrangements aspect of this proposal will be covered under the TO charging arrangements, it is the back feeds aspect that still needs to be addressed. April 2024 Update: The Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. December 2023: The Panel agreed that when rationalised against the other modifications in the stack this should be placed as 'Medium to Low' Due to the consideration required by the Ofgem send back letter of 14 September 2023, the September 2023 CUSC Panel agreed to return the modification to the same priority it was given prior to the initial submission of the FMR. | NESO
Low | CMP304 (Non-Charging) | Improving the Enhanced Reactive Power Service by making it fit for purpose | Low | October 2024 Update: The Panel agreed that when rationalised against the other modifications in the stack this was a low priority. April 2024 Update: There were no Workgroup meetings planned when the Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. Special April 2024 Panel: Due to there being no Workgroup scheduled the Panel reprioritised the modification from ‘Medium – Low’ to ‘Low’ December 2023: The Panel agreed that when rationalised against the other modifications in the stack this should be placed as 'Medium to Low' July 2023 - Proposer and ESO Panel Rep to review the output of Phase 1 of the ESO's feasibility studies ahead of reconvening the Workgroup. • Modification seeks to apply a different timescale to the provision on reactive power – Panel divided though on whether this is a simple change as solution still needs to be clarified • Ofgem cannot make a final decision on CMP305 until CMP304 is completed • Decreased cost to consumers if more competition This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. Workgroups recommenced on 8 November 2021. Prioritisation was discussed at October 2022 Panel and priority was not changed, as there remains a need for reactive services. However, the Panel (and Proposer) agreed that work on CMP304 is paused until such time that the ESO team, who are leading on the Reactive Reform (Market Design), have completed their Feasibility studies, which in turn will help to inform the Proposer's solution. | SSE Generation
Low | CMP328 (Non-Charging) | Connections Triggering Distribution Impact Assessment | Low | October 2024 Update: Panel determined that the priority of this was low but will revisit this priority status following the outcome of the Connections Reform. April 2024 Update: There were no Workgroup meetings planned when the Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. Special April 2024 Panel: Due to there being no Workgroup scheduled the Panel reprioritised the modification from ‘Medium – Low’ to ‘Low’ December 2023: The Panel agreed that until there is further Proposer engagement, and, when rationalised against the other modifications in the stack this should be placed as 'Medium to Low' Although this was prioritised as "High" when originally progressed, there was challenge that the materiality is not as high as when originally progressed. However, as the Workgroup are reconvening following an Authority send-back, Panel on balance was felt that this should have a Medium to High priority. | Scottish and Southern Energy Power Distribution Limited
Low | CMP341 (Non-Charging) | CUSC Sandbox: enabling derogation from certain obligations to support small-scale trials of innovative propositions | Low | October 2024 update: The Panel agreed that when rationalised against the other modifications in the stack this was a low priority. April 2024 Update: There were no Workgroup meetings planned when the Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. • Complex • Although a CACOP and Ofgem driven initiative, there does not appear to be any current industry appetite to progress This was de-prioritised by Panel whilst the Modifications to address Ofgem's Targeted Charging Review decision were being progressed. At June 2020 Panel, Panel determined that the priority of this was Low. At the last quarterly prioritisation deep-dive (October 2022 Panel), no case was presented to change the priority. | NESO
Low | CMP405 (Non- Charging) | TNUoS Locational Demand Signals for Storage | Low | March 2025 Update: The Panel placed CMP405 within the Medium - High category, given the impacts it has. October 2024 Update: The Panel agreed that when rationalised against the other modifications in the stack this was a low priority. April 2024 Update: There were no Workgroup meetings planned when the Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. Special April 2024 Panel: Due to there being no Workgroup scheduled as the modification is being paused until the outcome of the Storage Subgroup the Panel reprioritised the modification from ‘Medium’ to ‘Low’. As this is being developed in parallel with CMP393, Panel placed CMP405 at the same “Medium” priority as CMP393 August 2025 Panel: The Panel agreed that this modification should be placed as low on the stack due to the ongoing work by the storage sub- group. | SSE Generation
Low | CMP419 (Charging) | Generation Zoning Methodology Review | Low | October 2024 Update: The Panel agreed that when rationalised against the other modifications in the stack this was a high priority. April 2024 Update: The Panel agreed that based on the volume of industry resource being utilised by the existing and 2 new proposed Urgent modifications (30 planned Workgroups meetings between 07 May- 07 August, represented below) that all other modification Workgroup meetings should take a hiatus. Given the complexity of the defect, the potential for several alternative solutions and the advantage of an early decision on re-zoning for investors, this was placed as “Medium to High” in the prioritisation stack. August 2025 Update: The Panel agreed this modification should be moved to a low priority on the stack. | NESO
Low | CMP441 - SendBack ( Non- Charging) | Reducing the credit risk of supplying non-embedded hydrogen Electrolysers​ | Low | August Update: On 28 July the Authority sent back this modification for Panel to consider its next steps. In the postponed 03 September Panel, the Panel moved this modification prioity to low. | Statkraft