## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | JSC | Share the slides presented at Workgroup 1 with Workgroup members | Slides shared on 12 November | 2025-11-28 | Complete | WG2
2 | WG1 | FK and JSC | investigate reporting practices in other countries (Europe, US, etc.). | Presented at WG2 | 2025-11-28 | Complete | WG2
3 | WG1 | FK and AU | Review STC sections and Energy Data Task Force requirements for data sharing. | Electricity licensing (from October 2025) - Publications - Ofgem Public Register | 2025-11-28 | Complete | WG2
4 | WG1 | GW | Assess cost and workload implications for Transmission Owners (TOs) providing additional data. |  | 2025-11-28 | Open
5 | WG1 | FK and JSC | Check NESO data triage process against Energy Data Taskforce guidelines. | Presented at WG2 | 2025-11-28 | Complete | WG2
6 | WG1 | FK and GN | FK & JSC to provide ballpark estimate resource costs for weekly vs. monthly reporting and consider the Iberian blackout impact. GN to draft and share a benefits case | Presented at WG2 | 2025-11-28 | Complete | WG2
7 | WG1 | MB | Suggest thresholds for publishing larger incidents weekly and smaller ones monthly; NESO to consider if this mitigates workload concerns. |  | 2025-11-28 | Open
8 | WG1 | FK | Clarify what improvements are possible now, what would require more time, and how much better future data could be. | Presented at WG2 | 2025-11-28 | Complete | WG2
9 | WG2 | MD | Provide sources or a public version of the NESO data classification guidelines. |  | WG3
10 | WG2 | GW | Investigate whether TO data is published and where it can be accessed. |  | WG3
11 | WG2 | AL | Prepare a short presentation on phase jumps. |  | WG3
12 | WG2 | JR and LT | Review the GC0181 defect description to determine if phase jump data can be included. |  | WG3
13 | WG2 | JSC | Confirm the timing for when 73 PMUs (or at least 5) will be operational and consider regional coverage. |  | WG3