## Sheet1
Action number | Workgroup Raised | Owner | Action | Comment | Due by | Status | Workgroup Closed
1 | WG1 | JSC | Share the slides presented at Workgroup 1 with Workgroup members | Slides shared on 12 November | WG2 | Complete | WG2
2 | WG1 | FK and JSC | investigate reporting practices in other countries (Europe, US, etc.). | Presented at WG2 | WG2 | Complete | WG2
3 | WG1 | FK and AU | Review STC sections and Energy Data Task Force requirements for data sharing. | Electricity licensing (from October 2025) - Publications - Ofgem Public Register | WG2 | Complete | WG2
4 | WG1 | GW | Assess cost and workload implications for Transmission Owners (TOs) providing additional data. |  | WG2 | Open
5 | WG1 | FK and JSC | Check NESO data triage process against Energy Data Taskforce guidelines. | Presented at WG2 | WG2 | Complete | WG2
6 | WG1 | FK and GN | FK & JSC to provide ballpark estimate resource costs for weekly vs. monthly reporting and consider the Iberian blackout impact. GN to draft and share a benefits case | Presented at WG2 | WG2 | Complete | WG2
7 | WG1 | MB | Suggest thresholds for publishing larger incidents weekly and smaller ones monthly; NESO to consider if this mitigates workload concerns. |  | WG2 | Open
8 | WG1 | FK | Clarify what improvements are possible now, what would require more time, and how much better future data could be. | Presented at WG2 | WG2 | Complete | WG2
9 | WG2 | MD | Provide sources or a public version of the NESO data classification guidelines. | The NESO SME confirmed that there is no public source for their internal data guidelines, but they are available upon request and will share the presentation with the Workgroup. | WG3 | Complete
10 | WG2 | GW | Investigate whether TO data is published and where it can be accessed. | The NESO SME provided an update on whether Transmission Owner (TO) data can be published and where it could best be accessed. Noting practicality and constraints around sharing PMU (Phasor Measurement Unit) data more widely and in real time. | WG3 | Complete
11 | WG2 | AL | Prepare a short presentation on phase jumps. |  | WG3 | Open
12 | WG2 | JR and LT | Review the GC0181 defect description to determine if phase jump data can be included. |  | WG3 | Open
13 | WG2 | JSC | Confirm the timing for when 73 PMUs (or at least 5) will be operational and consider regional coverage. | The NESO SME advised the Workgroup that NGET are considering timelines for the full PMU rollout, noting that Scotland's rollout is complete, and other regions are expected to follow, with significant progress anticipated by March 2026 and completion targeted by the end of 2027. They also mentioned that the same timeline applies to frequency, inertia and system resolution data and by December 2027, there should be sufficient rollout to access the necessary data. | WG3 | Complete
14 | WG2 | FK | Propose amended draft Legal text for the solution. | Legal text presented in WG3. | WG3 | Complete
15 | WG2 | FK and JSC | Confirm GB alignment with the European standard of 0.5 seconds for frequency recording. | GB currently aligns with European requirements for frequency data resolution, which is set at one second for frequency quality analysis, referencing Article 131.1A; the one-second resolution is used for frequency quality checks and event analysis, while frequency control in Europe uses lower resolutions (one minute and fifteen minutes); there is no ROCOF (rate of change of frequency) reporting requirement in the referenced European standards. | WG3 | Complete
16 | WG3 | MD | Provide the data guidelines and check if the direct policy documents can be shared with the Workgroup. |  | WG4 | Open
17 | WG3 | FK | Provide more information regarding confidentiality, costs, and data sharing with the TOs. |  | WG4 | Open
18 | WG3 | JAK | Provide information on PMUs being installed are of the same technology or specification and to clarify their technical capabilities. |  | WG4 | Open
19 | WG3 | GN | Review and improve the framing of the cost-benefit analysis for blackout prevention, specifically by comparing the expected probability of a blackout event to the calculated benefit of enhanced reporting. |  | WG4 | Open
20 | WG3 | MC | Provide specific information on the system incident report spreadsheet such as format changes. |  | WG4 | Open
21 | WG3 | ALL | Review legal text when circulated with updated wording. |  | WG4 | Open