## Sheet1
Action number | Workgroup Raised | Owner | Action | Comments | Due by | Status | Workgroup Closed
1 | WG 1 | MPS | Clarify with NGET how Grid Park assets are classified (Connection vs Infrastructure Assets). |  | WG 2 | Closed | WG 4
2 | WG 1 | JC | Create worked examples showing how Assets could be charged, requesting contributions from Workgroup members. |  | WG 2 | Closed | WG 2
3 | WG 1 | JC / JR | Seek clarification from NESO Charging Team on how Infrastructure Assets are charged. |  | WG 2 | Closed | WG 2
4 | WG 1 | CP | Confirm Ofgem’s position on the TNUoS Review and the possibility of changing Connection / Infrastructure Asset definitions. |  | WG 2 | Closed | WG 2
5 | WG 1 | AH | Contact NESO Legal to discuss the practicalities of changing Asset definitions and retrospectivity. |  | WG 2 | Closed | WG 2
6 | WG 1 | JC | Formalise the data collection requirements for Impact Assessment. |  | WG 2 | Closed | WG 3
7 | WG 1 | MPS | Update and share the spreadsheet for the Proposer’s fourth option, after correcting the net asset value column. |  | WG 2 | Closed | WG 2
8 | WG 1 | JR | Amend Terms of Reference b) and f) and take back to CUSC Panel. |  | WG 6 | Open
9 | WG 1 | JC | Consider retrospectivity issue. |  | WG 2 | Closed | WG 3
10 | WG 2 | JC | Review DCP 464 for relevance and report back to the next Workgroup. |  | WG 3 | Closed | WG 4
11 | WG 2 | BH | Provide an update on DCP 461 and report back to the next Workgroup. Provide an update to the Workgroup in January on the options being taken forward by DCP 461 |  | WG 3 | Closed | WG 4
12 | WG 2 | JC | Update the worked example slides, including colour adjustments and clarifications, and circulate them for review. |  | WG 3 | Closed | WG 4
13 | WG 2 | JR | Email OFGEM’s open letter to all . |  | WG 3 | Closed | WG 3
14 | WG 2 | JC/AH | Review potential changes to Legal Text with legal team (possibly Section 3 or 11). |  | WG 6 | Open
15 | WG 2 | JC | Prepare a workbook for options 1, 2, and 3 against the baseline for the next meeting. |  | WG 3 | Closed | WG 3
16 | WG 2 | JC | Review DCP392. |  | WG 3 | Closed | WG 4
17 | WG 2 | All | Comment on the retrospectivity slide before the next meeting. |  | WG 3 | Closed | WG 4
18 | WG 3 | JR | Circulate the response to Action 1 to all Workgroup members. |  | WG 4 | Closed | WG 4
19 | WG 3 | JC | Review CMP417 for the introduction of a tech equivalent for final demand and report findings to the Workgroup. |  | WG 4 | Closed | WG 5
20 | WG 3 | JC | Update the worked example slides with additional labels, glossary entries, numbering, and a content page, and circulate the revised slides to the group. |  | WG 4 | Closed | WG 4
21 | WG 4 | NZ | Review DNO offers and provide a brief consumer impact analysis. |  | WG 6 | Open
22 | WG 4 | LS | Check the status of transmission charging reform work. |  | WG 5 | Closed | WG 5
23 | WG 4 | JC | Provide data for an impact assessment of Option 1 and seek feedback on assumptions. |  | WG 6 | Closed | WG 6
24 | WG 5 | JC | Update worked examples. |  | WG 5 | Closed | WG 5
25 | WG 5 | KH | Share example slides showing baseline vs Option 1 diagrams side-by-side. |  | WG 6 | Closed | WG 6
26 | WG 5 | PM / AH | Work with Revenue and provide analysis of the expected increase in TDR if Option 1 moves connection costs into TNUoS. |  | WG 6 | Closed | WG 6
27 | WG 5 | JC / AH | Produce first draft of Legal Text, to be reviewed by NESO Commercial Codes and Legal. |  | WG 6 | Open
28 | WG 5 | JR | Add several new headings to the Workgroup Consultation and share with Workgroup members. |  | WG 6 | Closed | WG 6
29 | WG 5 | All | Provide comments and content in Workgroup Consultation. |  | WG 6 | Closed | WG 6
30 | WG 6 | AH | Confirm queries regarding directly connected demand data and SGT discrepancies. |  | WG 7 | Open
31 | WG 6 | MH | Provide Scottish TO data. |  | WG 7 | Open
32 | WG 6 | JC | Incorporate the NESO data into an updated impact assessment. |  | WG 7 | Open
33 | WG 6 | JC | Update Workgroup Consultation text on ‘Applicability’ and application to all User types. |  | WG 7 | Open
34 | WG 6 | MPS | Add baseline explanation regarding proportional capital contributions. |  | WG 7 | Open
35 | WG 6 | RS | Add text to the ‘Applicability’ section on potential delay incentives for 2026 – 2027 projects. |  | WG 7 | Open
36
37
38
39
40